## Data
Oracle Project Number | Operating Group | Project Number | check | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
15110003-159 | FCG Operations | 15110003-159 | 1 | McCarthy/Mortenson JV-NBAF 3 | 2015-05-28 | 2021-10-31 | 0 | 0 | 0 | 740779583 | 0
15110008-159 | FCG Operations | 15110008-159 | 1 | McC/Mort JV NBAF 3 Site Log | 2015-05-28 | 2021-10-31 | 0 | 0 | 0 | 13020699 | 0
15110003 | FCG Operations | 15110003 | 1 | McCarthy/Mortenson NBAF 3 | 2015-05-28 | 2021-10-31 | 707000 | 0 | 0 | 33149706.6 | 37745807.93 | 0 | 187731 | 83.5% | 16.49% | 0.007457%
15110006 | FCG Operations | 15110006 | 1 | McC/M NBAF Cup O&M | 2015-11-09 | 2020-12-08 | 0 | 0 | 0 | 101600 | 133927.83
15110006-159 | FCG Operations | 15110006-159 | 1 | McC/M JV NBAF CUP O&M | 2015-11-09 | 2020-12-08 | 0 | 0 | 0 | 18168338 | 0
15060046 | Denver Operations | 15060046 | 1 | Denver Water-OCR WP#6 | 2017-11-01 | 2020-03-31 | 385893 | 1688836.69 | 1420078 | 75260387.2774 | 74193000.8 | 129379.75 | 163559.5 | 89.91% | 10.09% | 0%
15060041 | Denver Operations | 15060041 | 1 | Denver Water-OCR WP#1 | 2015-11-01 | 2020-03-31 | 1481040 | 994089.5 | 737024 | 40568083.0639 | 41677507.58 | 94919 | 101669.05 | 87.35% | 12.65% | 0%
15060026 | Denver Operations | 15060026 | 1 | Park Creek-Stapleton Maint | 2015-08-01 | 2019-12-31 | 0 | 10474.2 | 28 | 7059715.2 | 7208953.28 | 15774.3 | 39457 | 94.49% | 5.514% | 0%
15050003 | Seattle Operations | 15050003 | 1 | Northgate Station-(N160)Precon |  | 2019-09-30 | 0 | 289 | 0 | 1411225 | 1661995.62 | 125 | 155.5 | 97.75% | 2.251% | 0%
15030055 | Minneapolis Operations | 15030055 | 1 | Cornell - Russell Science Ctr | 2017-04-04 | 2019-08-02 | 96000 | 866958.23 | 553745 | 27499372.37 | 25723848.91 | 29385.4 | 27109.71 | 87.62% | 12.33% | 0.0498%
15000007-040, 15030048 | Minneapolis Operations | 15030048 | 15 | Mort Dev - 333 Hennepin | 2017-11-15 | 2019-08-01 | 414000 | 3717330.1 | 1285621 | 78220221.47 | 77212796.51 | 112107.21 | 114891.44 | 90.12% | 9.782% | 0.09531%
15080020-063 | Mortenson Infrastructure Milw Operations | 15080020-063 | 1 | WI DOT-Zoo I Change Phase 2 PC | 2016-01-01 | 2019-06-30 | 0 | 1 | 0 | 1857664 | 1783744.19
15000004-040, 15050008 | Portland Operations | 15050008 | 15 | OCC Hotel Parking Garage | 2018-03-01 | 2019-06-25 | 302000 | 16758.14 | 29757 | 27328257.9 | 29220571.93 | 3159.93 | 8829 | 92.32% | 7.64% | 0.04531%
15110005 | FCG Operations | 15110005 | 1 | DON-Dahlgren P287MissileSptFac | 2016-02-25 | 2019-06-01 | 63269 | 1638 | 0 | 28612520.64 | 28471217.62 | 0 | 463.5 | 97.3% | 2.697% | 0%
15060028 | Denver Operations | 15060028 | 1 | UAL-Pilot Training | 2016-02-01 | 2019-05-31 | 0 | 65586 | 84813 | 129969808.115 | 128031238.15 | 89439 | 155455.5 | 89.72% | 10.28% | 0%
15145026 | Solar and Emerging Renewables Operations | 15145026 | 1 | Bongards CSG - Sunshare | 2015-10-30 | 2019-05-31 | 6855030 | 379223 | 378177 | 10537206.09 | 11692645.9 | 32044 | 32370 | 79.93% | 13.26% | 6.802%
15080020 | Milwaukee Operations | 15080020 | 1 | WI DOT-Zoo I Change Phase 2 PC | 2016-01-01 | 2018-12-31 | 0 | 0 | 0 | 0.01 | -0.01
15050005 | Seattle Operations | 15050005 | 1 | The Dalles Wastewater Plant | 2017-05-01 | 2018-12-21 | 0 | 123542 | 68088 | 13440489.662 | 13813539.49 | 20868 | 21393.56 | 94.14% | 5.796% | 0.06077%
15050016 | Seattle Operations | 15050016 | 1 | UW Computer Science Eng II | 2016-12-26 | 2018-12-17 | 130000 | 798255.1 | 704033 | 78567291.0207 | 79875911.32 | 66496.25 | 69453.03 | 92.96% | 6.764% | 0.2728%
15060014-162 | Denver Operations | 15060014-162 | 1 | ACCH - Gaylord Rockies Resort | 2015-06-22 | 2018-12-14 | 0 | 212048 | 0 | 541963907.59 | 541146657.73 | 187120.5 | 303887.89 | 91.26% | 8.74% | 0%
15060014 | Denver Operations | 15060014 | 1 | MAM/Welbro-Gaylord Rockies Hot | 2015-04-20 | 2018-12-14 | 1900000 | 1422234.2 | 1534288 | 64242516.8133 | 66447466.15 | 292018.61 | 441675.88 | 89.89% | 10.11% | 0%
15110002-151, 15110002, 20110002-151, 20110002 | FCG Operations | 15110002-151 | 1 | DOA-ECB Marine Corps | 2016-01-01 | 2018-11-15 | 158106 | 0 | 0 | 88447803.897 | 96752656.66
15090011 | Chicago Operations | 15090011 | 1 | Univ of Chicago Keller Center | 2015-05-01 | 2018-11-05 | 125000 | 290917.5 | 89640 | 57600046.379 | 56861634.62 | 32713.7 | 32013.93 | 91.64% | 6.653% | 1.706%
15050010 | Portland Operations | 15050010 | 1 | Nike IHM Expansion | 2016-04-25 | 2018-08-30 | 200000 | 23015 | 43148 | 59184515.22 | 59087861.45 | 12808 | 16885.09 | 91.39% | 8.584% | 0.02369%
15060032-162 | Denver Operations | 15060032-162 | 1 | Aurora CCH-Gaylord Offsite | 2015-11-01 | 2018-08-18 | 0 | 0 | 0 | 23168718.44 | 23492823.84 | 2080 | 1729.02 | 99.68% | 0.3181% | 0%
15060032 | Denver Operations | 15060032 | 1 | MAM/Welbro-Gaylord Offsite | 2015-11-01 | 2018-08-16 | 0 | 241257.75 | 263049 | 10827564.7154 | 11714685.68 | 47856.55 | 61341 | 86.47% | 13.53% | 0%
15060009 | Denver Operations | 15060009 | 1 | Park Creek-District IV Outfall | 2015-04-15 | 2018-07-31 | 0 | 0 | 0 | 791075 | 846500.25 | 0 | 955 | 94.55% | 5.445% | 0%
15040011 | Phoenix Operations | 15040011 | 1 | SRP-PAB Capital Improvements | 2015-09-30 | 2018-07-31 | 431000 | 0 | 0 | 900968.29 | 908796.13
15040012 | Phoenix Operations | 15040012 | 1 | SRP-PAB Exp Repair Improve | 2015-09-30 | 2018-07-31 | 431000 | 0 | 0 | 68219.38 | 66408.74
15060020 | Denver Operations | 15060020 | 1 | Park Creek-Filing 49 | 2015-10-15 | 2018-06-30 | 0 | 0 | 47 | 5541985 | 6078662.05 | 1600 | 12527 | 97.77% | 2.227% | 0%
15000006-040, 15050011 | Portland Operations | 15050011 | 15 | 12th and Market Apartments | 2016-11-22 | 2018-06-30 | 89480 | 792923 | 673928 | 30253384.5637 | 36635553.75 | 21741 | 39088.39 | 77.56% | 21.63% | 0.8097%
15145008 | Solar and Emerging Renewables Operations | 15145008 | 1 | Glazier CSG-SunShare | 2015-08-01 | 2018-06-30 | 4037040 | 332730 | 328567 | 6376636.4936 | 6769043.63 | 16743 | 19177 | 80.64% | 14.09% | 5.264%
15060002 | Denver Operations | 15060002 | 1 | Exempla-St Joe's Facility Agrt | 2015-06-01 | 2018-06-29 | 0 | 2013.17 | 0 | 741235.4 | 729903.99 | 959.5 | 5459.5 | 91.26% | 8.737% | 0%
15060005 | Denver Operations | 15060005 | 1 | MDI-Sterling Ranch Civic Ctr | 2017-07-28 | 2018-06-04 | 30787 | 336607 | 238207 | 8338253.01 | 7553087.89 | 16556 | 13617 | 92.3% | 7.704% | 0%
15060024 | Denver Operations | 15060024 | 1 | Park Creek-Forest CIty | 2015-08-01 | 2018-04-30 | 0 | 0 | 0 | 2525949.61 | 2388906.11 | 0 | 3583 | 89.05% | 10.95% | 0%
15080006 | Milwaukee Operations | 15080006 | 1 | St.Camillus-Phase 1 Campus Exp | 2015-03-09 | 2018-01-16 | 195000 | 1772702.6 | 1054606 | 47252867.17 | 45730092.36 | 46939.5 | 44274.6 | 95.11% | 4.867% | 0.02033%
15030021 | Minneapolis Operations | 15030021 | 1 | UMN-Athletes Village | 2016-02-15 | 2018-01-08 | 339000 | 529807.78 | 459874 | 87326032.767 | 87054781.16 | 82434.7 | 95920.18 | 92.54% | 7.367% | 0.09279%
15080021 | Milwaukee Operations | 15080021 | 1 | HellermannTyton-Misc. Alteratn | 2015-12-18 | 2017-12-31 | 500 | 28 | 0 | 37508 | 36746.89 | 128 | 299.5 | 99.17% | 0.8347% | 0%
15146008 | Power Delivery Solutions Operations | 15146008 | 1 | Grande Prairie Wind - HVT | 2015-08-17 | 2017-12-31 | 0 | 752438 | 757427 | 36224647.4863 | 33776665.57 | 108779 | 51258 | 79.61% | 20.39% | 0%
15145023 | Solar and Emerging Renewables Operations | 15145023 | 1 | Theis CSG - Sunshare | 2015-10-30 | 2017-12-31 | 6441120 | 25 | 0 | 283118.84 | 289231.43
15145009 | Solar and Emerging Renewables Operations | 15145009 | 1 | Becker CSG-SunShare | 2017-08-01 | 2017-12-31 | 6581250 | 77 | 0 | 276678.25 | 367137.28
15145024 | Solar and Emerging Renewables Operations | 15145024 | 1 | Kane CSG - Sunshare | 2015-10-30 | 2017-12-31 | 6640200 | 460 | 0 | 169797 | 82609.94
15145007 | Solar and Emerging Renewables Operations | 15145007 | 1 | Bartlett CSG-SunShare | 2015-05-01 | 2017-12-31 | 7059150 | 12 | 0 | 261796.84 | 246064.71 | 0 | 0 | 0% | 0% | 0%
15145027 | Solar and Emerging Renewables Operations | 15145027 | 1 | Gregor CSG - Sunshare | 2015-10-30 | 2017-12-31 | 7142850 | 100 | 0 | 233683 | 241816.76
15145006 | Solar and Emerging Renewables Operations | 15145006 | 1 | Murphy CSG-SunShare | 2015-05-01 | 2017-12-31 | 7379775 | 0 | 0 | 243462.84 | 270760.07 | 0 | 0 | 0% | 0% | 0%
15110002-151, 15110002, 20110002-151, 20110002 | FCG Operations | 15110002 | 1 | DOA-ECB Marine Corps JV-Int | 2016-01-01 | 2017-11-30 | 158106 | 0 | 0 | 2470470 | 5970530.74 | 0 | 16729.5 | 74.44% | 25.32% | 0.2391%
15050014 | Seattle Operations | 15050014 | 1 | AMLI/MDI Residential Tower | 2015-10-02 | 2017-11-16 | 424994 | 1958079.37 | 1479535 | 112996953.4075 | 112560314.66 | 96452.09 | 99949.17 | 81.72% | 15.92% | 2.358%
15090014 | Chicago Operations | 15090014 | 1 | College of Lake County GMP2 | 2015-11-01 | 2017-10-31 | 190000 | 175965.2 | 168521 | 29253836.6357 | 28455478.63 | 15175.5 | 14673.21 | 95.52% | 3.857% | 0.6202%
15060042, 15060043, 14060010, 15060045, 15060044 | Denver Operations | 15060045 | 31 | Denver Water-OCR WP#5 | 2017-05-01 | 2017-10-31 | 103442 | 0 | 0 | 0.01 | 0
16148001, 16146001, 15145028 | Solar and Emerging Renewables Operations | 15145028 | 21 | Pearl Solar Project - OCI | 2016-03-22 | 2017-10-31 | 66339000 | 5530356 | 4830684 | 30878316.0466 | 31145780.16 | 274223 | 291200.25 | 94.36% | 5.639% | 0%
15148021, 15110004 | FCG Operations | 15110004 | 11 | DON-Kings Bay Land Water Inter | 2015-11-23 | 2017-10-22 | 0 | 116266.25 | 123005 | 16284510.984 | 13705272.04 | 68368 | 35379.75 | 87.88% | 12.12% | 0%
15148007 | Civil Group Operations | 15148007 | 1 | I-70 Havana Civil | 2015-06-13 | 2017-09-30 | 0 | 36846 | 17260 | 283774.2136 | 229742.69 | 1123 | 1255 | 87.05% | 12.95% | 0%
15060013 | Denver Operations | 15060013 | 1 | Park Creek-Aurora Filing 1 & 2 | 2015-11-01 | 2017-09-30 | 0 | 1 | 0 | 1427511 | 1539511.1 | 600 | 1286 | 92.46% | 7.543% | 0%
15050020 | Portland Operations | 15050020 | 1 | Marriott Portland City Ctnr |  | 2017-09-30 | 0 | 0 | 0 | 38840 | 51421.52
15050021 | Seattle Operations | 15050021 | 1 | Marriott Residence Inn Seattle | 2016-03-01 | 2017-09-22 | 245375 | 1636350.55 | 1561021 | 58554466.81 | 61764713.08 | 64874 | 81111.96 | 86.3% | 12.86% | 0.8359%
15090001 | Chicago Operations | 15090001 | 1 | SAIC HVAC Improvements | 2015-05-01 | 2017-08-31 | 3500 | 18461 | 0 | 3347909.61 | 2961160.92 | 2247 | 3336.08 | 97.96% | 2.038% | 0%
15150003 | Sports + Entertainment Group Operations | 15150003 | 1 | PSU-IM Bldg-Phase 3 Exp | 2016-05-23 | 2017-08-31 | 60676 | 0 | 0 | 22475764.633 | 22122083.74 | 0 | 946 | 82.51% | 15.38% | 2.114%
15090013 | Chicago Operations | 15090013 | 1 | Advocate GS Life Safety | 2015-08-01 | 2017-08-30 | 25000 | 27257 | 5662 | 2909361.69 | 2852826.89 | 16828 | 4223.26 | 88.42% | 10.04% | 1.539%
15060025 | Denver Operations | 15060025 | 1 | MAM/Welbro - Gaylord Concrete | 2017-02-15 | 2017-08-15 | 1164217 | 10713481.1 | 6305087 | 50372795.2618 | 45035323.82 | 333350 | 312432.47 | 87.48% | 12.52% | 0%
15060042, 15060043, 14060010, 15060045, 15060044 | Denver Operations | 15060044 | 41 | Denver Water-OCR WP#4 | 2016-05-01 | 2017-08-01 | 129744 | 859521.09 | 883127 | 44082938.9074 | 43472482.1 | 64592 | 67784.5 | 90.58% | 9.423% | 0%
15050012 | Seattle Operations | 15050012 | 1 | Salmon Bay - Lot R | 2016-06-01 | 2017-07-31 | 125000 | -1 | 0 | 357534.14 | 354998.16 | 48 | 413.97 | 100% | 0% | 0%
15060004 | Denver Operations | 15060004 | 1 | Exempla-Lutheran Med Ctr. | 2015-01-26 | 2017-07-28 | 0 | 13329.5 | 20 | 8520566.573 | 8584916.49 | 17322 | 14237.5 | 91.78% | 8.225% | 0%
15060047 | Denver Operations | 15060047 | 1 | Larimer Humane Society | 2016-04-01 | 2017-07-01 | 38000 | 12991 | 0 | 14232064.7717 | 14633211.97 | 746 | 5256 | 97.88% | 2.121% | 0%
15060039 | Denver Operations | 15060039 | 1 | SCL - St. Francis Hosp. Renov | 2015-11-15 | 2017-06-30 | 0 | 0 | 0 | 12946672.37 | 13030229.42
15060018 | Denver Operations | 15060018 | 1 | MCV Capital-Boulder Commons | 2015-12-11 | 2017-06-30 | 105000 | 609898 | 70234 | 23060983.72 | 24816233.86 | 26798 | 38478.5 | 90.27% | 9.731% | 0%
15145029 | Solar and Emerging Renewables Operations | 15145029 | 1 | Byron CSG - Sunshare | 2015-01-01 | 2017-06-30 | 0 | 113 | 0 | 37107 | 30465.34
15141007 | Wind Energy I Operations | 15141007 | 1 | Sunflower Wind | 2015-07-27 | 2017-06-30 | 0 | 245441 | 243735 | 37405744.61 | 37170835.47 | 60104 | 58130.25 | 69.46% | 28.53% | 2.014%
15080005 | Milwaukee Operations | 15080005 | 1 | Kohler Co. - Lodge Kohler | 2016-04-04 | 2017-06-20 | 111228 | 646142 | 473107 | 40478342.43 | 39113702.74 | 27324 | 26252 | 92.98% | 7.024% | 0%
15030034 | Minneapolis Operations | 15030034 | 1 | Dickinson Pub Schl - Mid Schl | 2015-07-01 | 2017-05-31 | 212000 | 11588 | 4633 | 55908124.9438 | 50559168.56 | 11051 | 9350.84 | 87.51% | 12.46% | 0.02139%
15146003 | Power Delivery Solutions Operations | 15146003 | 1 | Alamo 7 Solar -HVT | 2015-10-12 | 2017-05-26 | 0 | 105214 | 104853 | 3994818.27 | 3567963.53 | 8157.18 | 6366.25 | 91.53% | 8.47% | 0%
15050004 | Seattle Operations | 15050004 | 1 | Tilt49 Podium | 2015-03-23 | 2017-05-25 | 212615 | 726099.5 | 553190 | 26097715.9645 | 26265950.55 | 44266.5 | 46273 | 86.76% | 12.68% | 0.5619%
15080019 | Milwaukee Operations | 15080019 | 1 | Guardian IG-Feasibility Study |  | 2017-04-30 | 0 | 0 | 0 | 47548 | 37638.24
15141004 | Wind Energy I Operations | 15141004 | 1 | Grande Prairie Wind | 2015-08-01 | 2017-04-30 | 0 | 1228610 | 1025366 | 115399840.146 | 107296719 | 205334 | 168863.5 | 76.14% | 23.86% | 0%
15080017 | Milwaukee Operations | 15080017 | 1 | Froedtert-West Clinic Vert Exp | 2016-03-15 | 2017-03-31 | 33116 | 168407 | 105013 | 10702657.22 | 10574302.55 | 9047.5 | 9420 | 91.72% | 7.415% | 0.8652%
15080015-064 | Mortenson Direct Operations | 15080015-064 | 1 | Froedtert-Direct MR LinAc | 2015-10-05 | 2017-03-31 | 1910 | 0 | 0 | 15601 | 15601
15146012 | Power Delivery Solutions Operations | 15146012 | 1 | Broadview-Energy JN Substation | 2016-01-04 | 2017-03-31 | 0 | 464613 | 463442 | 13718744.0325 | 15246553.59 | 22963 | 27237.25 | 71.67% | 28.33% | 0%
15146013 | Power Delivery Solutions Operations | 15146013 | 1 | Broadview Energy KW Substation | 2016-01-04 | 2017-03-31 | 0 | 121077 | 120396 | 4943196.68 | 4741585.58 | 7631 | 7372 | 77.75% | 22.25% | 0%
14000002-040, 15050002 | Portland Operations | 15050002 | 17 | AC Hotel Portland | 2015-09-01 | 2017-02-01 | 119790 | 933650.76 | 933137 | 37740392.1058 | 41683714.41 | 25775 | 24745.15 | 83.29% | 16.03% | 0.687%
15050019, 15000008-040, 16050011 | Portland Operations | 15050019 | 1 | United Way Hotel-Portland |  | 2017-01-31 | 0 | 0 | 0 | 53417.06 | 55033.14
15145022 | Solar and Emerging Renewables Operations | 15145022 | 1 | Terning CSG - Sunshare | 2015-10-30 | 2017-01-31 | 7081425 | 65 | 0 | 233108.84 | 231583.93
15150001 | Sports + Entertainment Group Operations | 15150001 | 1 | PSU-Lasch Bldg-Phase 2 | 2016-01-04 | 2017-01-31 | 12380 | 0 | 0 | 10612573.87 | 10595060.75
15080015 | Milwaukee Operations | 15080015 | 1 | Froedtert-MR LinAc | 2015-10-01 | 2017-01-27 | 1910 | 18364 | 6459 | 2004110.54 | 1918186.03 | 2655 | 3821 | 88.5% | 9.474% | 2.028%
15090992 | Chicago Operations | 15090992 | 1 | Chicago Laser Scanning | 2015-01-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | -154263.56 | 0 | 1767 | 82.29% | 11.74% | 5.971%
15090006 | Chicago Operations | 15090006 | 1 | Lucas Museum of Narrative Art | 2015-01-01 | 2016-12-31 | 512000 | 844.69 | 0 | 1331562 | 1010039.02 | 14 | 1093.32 | 80.38% | 15.18% | 4.436%
15148008 | Civil Group Operations | 15148008 | 1 | Solar-Alamo VII Civil | 2015-06-15 | 2016-12-31 | 0 | 259299 | 259255 | 2596856.25 | 2063790.17 | 8772 | 7519 | 89% | 11% | 0%
15060023 | Denver Operations | 15060023 | 1 | CoorsTek-WTM Highway | 2015-10-01 | 2016-12-31 | 0 | 276 | 0 | 16922761.3 | 16666939.23 | 997 | 9256 | 93.32% | 6.682% | 0%
15030043 | Minneapolis Operations | 15030043 | 1 | UHG - NT Data Coil Failure War | 2015-06-30 | 2016-12-31 | 0 | 0 | 0 | 0 | 71873.89
15030031 | Minneapolis Operations | 15030031 | 1 | Brd of Regnts IA - Schindler | 2015-08-17 | 2016-12-31 | 143812 | 852 | 0 | 28260897.77 | 27754469.42 | 3530 | 5461 | 88.77% | 11.23% | 0%
15146015 | Power Delivery Solutions Operations | 15146015 | 1 | Rocksprings HVT | 2015-11-16 | 2016-12-31 | 0 | 123 | 0 | 5269935 | 5035246.62 | 0 | 1101 | 77.75% | 22.25% | 0%
15146016 | Power Delivery Solutions Operations | 15146016 | 1 | Mariah Del Norte HVT |  | 2016-12-31 | 0 | 265203 | 254484 | 6313551.22 | 6123386.77 | 9965 | 7355 | 73.29% | 26.71% | 0%
15146014 | Power Delivery Solutions Operations | 15146014 | 1 | Broadview-Western Interconnect | 2016-01-04 | 2016-12-30 | 0 | 5867.92 | 5528 | 21380287.8784 | 22586444.69 | 60535 | 63371 | 74.69% | 25.31% | 0%
15145030 | Solar and Emerging Renewables Operations | 15145030 | 1 | Target 8 | 2015-12-01 | 2016-12-30 | 0 | 195812 | 195637 | 3580687.9915 | 5245426.24 | 18989.85 | 27847.75 | 95.54% | 4.113% | 0.3501%
15148014 | Civil Group Operations | 15148014 | 1 | South Plains II Civil | 2015-07-06 | 2016-12-17 | 0 | 832101.91 | 654137 | 7492984.2911 | 7241548.1 | 88388.4 | 31317 | 84.1% | 15.9% | 0%
15030018 | Minneapolis Operations | 15030018 | 1 | MN Sculpture Garden | 2015-10-01 | 2016-12-01 | 0 | 2023 | 0 | 436992 | 425591.72 | 1520 | 2335.5 | 99.61% | 0.3854% | 0%
15060017 | Denver Operations | 15060017 | 1 | PESCO-Operations & Tech Ctr | 2015-10-15 | 2016-11-30 | 112500 | 815313.65 | 498313 | 13044088.2435 | 13013704.12 | 18135.78 | 16435.5 | 85.98% | 14.02% | 0%
15030039 | Minneapolis Operations | 15030039 | 1 | Walker - Vineland Entry | 2015-08-03 | 2016-11-11 | 6292 | 319164.8 | 168865 | 12370086.9088 | 12118482.9 | 22524 | 24970.96 | 94.21% | 5.613% | 0.1762%
15148003, 15146007, 15145004 | Solar and Emerging Renewables Operations | 15145004 | 21 | Alamo VI - OCI SP LLC | 2015-04-01 | 2016-11-01 | 140313600 | 12369036 | 12306980 | 78610967.479 | 70326560.99 | 704916.35 | 702114.34 | 89.9% | 10.1% | 0.002421%
15090016 | Chicago Operations | 15090016 | 1 | Allstate Jacksonville PH5 | 2016-02-01 | 2016-10-31 | 30000 | 0 | 0 | 6035069.07 | 5915120.74 | 854 | 712 | 100% | 0% | 0%
15148005 | Civil Group Operations | 15148005 | 1 | Solar-Henrietta Civil | 2015-05-26 | 2016-10-31 | 0 | 170643 | 170492 | 3427321.055 | 2592040.92 | 11702 | 9308 | 79.86% | 20.12% | 0.02686%
15148019 | Civil Group Operations | 15148019 | 1 | Sunflower Civil | 2015-09-08 | 2016-10-31 | 0 | 600485 | 600451 | 7492780.85 | 7224498.76 | 21121 | 23670 | 76.81% | 22.7% | 0.4901%
15060035 | Denver Operations | 15060035 | 1 | DHHA-Pavilion I Renovate | 2015-10-08 | 2016-10-31 | 8300 | 30 | 0 | 3793657.74 | 3681990.37 | 0 | 8829.25 | 90.14% | 9.862% | 0%
15145010 | Solar and Emerging Renewables Operations | 15145010 | 1 | Alamo VII-OCI | 2015-07-01 | 2016-10-31 | 132300000 | 12981805 | 12715372 | 79722860.9454 | 66660655.16 | 707310.26 | 688722.07 | 85.24% | 14.75% | 0.0009438%
15040016 | Phoenix Operations | 15040016 | 1 | AlaskaUSA-Arcadia Branch | 2016-09-12 | 2016-10-20 | 500 | 0 | 0 | 194800.82 | 214580.23 | 0 | 18 | 100% | 0% | 0%
15060038 | Denver Operations | 15060038 | 1 | MillerCoors-East Gate Mod | 2015-10-01 | 2016-10-13 | 0 | 22831 | 117692 | 1482393.6 | 1514389.3 | 2706 | 6032 | 87.18% | 12.82% | 0%
15060006 | Denver Operations | 15060006 | 1 | PVH-NICU Renovation | 2015-03-23 | 2016-10-13 | 24080 | 10.5 | 0 | 9064220.92 | 8997642.64 | 4243.5 | 8523.5 | 92.78% | 7.221% | 0%
15060019 | Denver Operations | 15060019 | 1 | Park Creek-Filing 48 | 2015-09-01 | 2016-09-30 | 0 | 100 | 0 | 89843 | 109597.49 | 60 | 270 | 92.22% | 7.778% | 0%
15030023 | Minneapolis Operations | 15030023 | 1 | NS II-Northern Stacks II | 2016-03-14 | 2016-09-30 | 135000 | 359322 | 0 | 11134923.69 | 9656275.5 | 12338 | 10417.46 | 89.53% | 10.47% | 0%
15030054 | Minneapolis Operations | 15030054 | 1 | UIA-Kinnick Stadium-Renovate | 2016-12-01 | 2016-09-30 | 156678 | 2480 | 0 | 174783.01 | 111109.02
15145017 | Solar and Emerging Renewables Operations | 15145017 | 1 | Granite Mtn E Solar-Sun Edison | 2015-08-03 | 2016-09-30 | 100012200 | 6730922 | 6726311 | 37100086.625 | 35468376.16 | 246750 | 228532.45 | 81.32% | 18.67% | 0.006126%
15040014 | Phoenix Operations | 15040014 | 1 | Project Tilden | 2015-12-11 | 2016-09-16 | 1300000 | 50024 | 0 | 174011883.18 | 172822962.77 | 8883 | 18687.5 | 76.73% | 21.29% | 1.977%
15030041 | Minneapolis Operations | 15030041 | 1 | CH Robinson - Data Center | 2015-09-24 | 2016-09-14 | 25000 | 995.61 | 31206 | 17879305.41 | 17684765.84 | 16163 | 18513.6 | 94.88% | 4.848% | 0.2755%
15145018 | Solar and Emerging Renewables Operations | 15145018 | 1 | Granite Mtn W Solar-Sun Edison | 2015-08-03 | 2016-09-09 | 62521440 | 3833137 | 3813439 | 21814267.727 | 18641392.38 | 138271 | 115812.81 | 85.48% | 14.51% | 0.01209%
15145019 | Solar and Emerging Renewables Operations | 15145019 | 1 | Iron Springs Solar-Sun Edison | 2015-08-03 | 2016-09-09 | 100012200 | 5662194 | 5661743 | 30398366.7454 | 26886156.96 | 253794 | 226617.3 | 82.3% | 17.7% | 0%
15030058 | Minneapolis Operations | 15030058 | 1 | RMC Surgery Remodel Proj | 2016-01-11 | 2016-09-03 | 7727 | 10441 | 25511 | 1828737.86 | 1814696.92 | 4919 | 6916 | 92.45% | 7.418% | 0.1301%
15148002 | Civil Group Operations | 15148002 | 1 | REG I-South Plains I Civil | 2015-02-23 | 2016-09-01 | 0 | 806831.01 | 737823 | 6438732.1225 | 5892269.66 | 88500 | 30348 | 80.59% | 19.41% | 0%
15030047 | Minneapolis Operations | 15030047 | 1 | Temple Israel-Edu & Lobby Exp. | 2015-09-01 | 2016-09-01 | 34800 | 279065 | 248506 | 10229665.33 | 9493672.09 | 26617 | 31384.31 | 94.79% | 4.478% | 0.7329%
15148010 | Civil Group Operations | 15148010 | 1 | Solar-Enterprise Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1838377.39 | 1836874.94
15148011 | Civil Group Operations | 15148011 | 1 | Solar-Escalante I Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1899629.9 | 1904241.18
15148012 | Civil Group Operations | 15148012 | 1 | Solar-Escalante II Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1676584.3 | 1675196.16
15148013 | Civil Group Operations | 15148013 | 1 | Solar-Escalante III Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1987630.53 | 1984145.94
15148015 | Civil Group Operations | 15148015 | 1 | Solar-Iron Springs Civil | 2015-08-03 | 2016-08-31 | 0 | 0 | 0 | 4119673.87 | 4116681.24
15148016 | Civil Group Operations | 15148016 | 1 | Solar Granite Mtn East Civil | 2015-08-03 | 2016-08-31 | 0 | 0 | 0 | 6936740.02 | 6936932.71
15148017 | Civil Group Operations | 15148017 | 1 | Solar Granite Mtn West Civil | 2015-08-03 | 2016-08-31 | 0 | 0 | 0 | 3564025.56 | 3541533.52
15146005 | Power Delivery Solutions Operations | 15146005 | 1 | Solar-Enterprise HVT | 2015-09-01 | 2016-08-31 | 0 | 0 | 0 | 5108162.86 | 5110237.21
15146006 | Power Delivery Solutions Operations | 15146006 | 1 | Solar-Escalante II HVT | 2015-09-01 | 2016-08-31 | 0 | 0 | 0 | 11283024.99 | 11277938.87
15146010 | Power Delivery Solutions Operations | 15146010 | 1 | Solar Escalante I HVT | 2015-12-01 | 2016-08-31 | 0 | 0 | 0 | 1121378 | 1120372.63
15146011 | Power Delivery Solutions Operations | 15146011 | 1 | Solar - Escalante III HVT | 2015-12-01 | 2016-08-31 | 0 | 0 | 0 | 810916 | 809843.43
15145012 | Solar and Emerging Renewables Operations | 15145012 | 1 | Enterprise Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104889120 | 6732794 | 6731343 | 37537724.5694 | 34388770.82 | 257363 | 237108.12 | 84.19% | 15.49% | 0.3239%
15145013 | Solar and Emerging Renewables Operations | 15145013 | 1 | Escalante 1 Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104889120 | 6304312 | 5982240 | 29040537.5367 | 26229989.53 | 248887.5 | 184195.27 | 85.31% | 14.69% | 0%
15145014 | Solar and Emerging Renewables Operations | 15145014 | 1 | Escalante 2 Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104889120 | 6257551 | 6180253 | 41603658.075 | 38152896.43 | 237009 | 212717.5 | 83.02% | 16.98% | 0.005641%
15145015 | Solar and Emerging Renewables Operations | 15145015 | 1 | Escalante 3 Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104896360 | 7241418 | 7169047 | 31090428.9693 | 27705033.94 | 258258.55 | 273616.5 | 83.39% | 16.61% | 0%
15141005 | Wind Energy I Operations | 15141005 | 1 | Rocksprings Wind | 2015-09-01 | 2016-08-31 | 0 | 1631 | 168 | 20759426 | 20807148.5 | 13393 | 5560.25 | 78.33% | 21.67% | 0%
15040013 | Phoenix Operations | 15040013 | 1 | SRP-PAB MRI AV Systems | 2016-02-01 | 2016-08-30 | 0 | 0 | 0 | 244229.45 | 243843.42
15080002 | Milwaukee Operations | 15080002 | 1 | Uline - Conference Center | 2015-06-01 | 2016-08-12 | 18700 | 465991 | 291474 | 12503791 | 12685245.73 | 18774 | 23565 | 89.79% | 9.62% | 0.5941%
15030049 | Minneapolis Operations | 15030049 | 1 | UofMN-Mech Eng Lab Renovation |  | 2016-08-01 | 31600 | 17065 | 11729 | 3727348.93 | 3608301.12 | 3902.5 | 4344.84 | 96.23% | 3.775% | 0%
15148023 | Civil Group Operations | 15148023 | 1 | Rocksprings Civil | 2015-11-09 | 2016-07-31 | 0 | 342228 | 444225 | 4690149 | 4647148.82 | 4923 | 12701.25 | 80.55% | 19.45% | 0%
15150004-155 | Sports + Entertainment Group Operations | 15150004-155 | 1 | KSU - NorthEast Connector | 2016-01-05 | 2016-07-30 | 17000 | 2873 | 0 | 13484912.9 | 12312362.75 | 5444 | 2518.5 | 87.35% | 12.65% | 0%
15080007 | Milwaukee Operations | 15080007 | 1 | Kohl's-Data Center Renov & Add | 2015-10-19 | 2016-07-07 | 70000 | 0 | 0 | 4615563 | 4215315.13 | 103 | 592.5 | 99.83% | 0.1688% | 0%
15148022 | Civil Group Operations | 15148022 | 1 | First Creek Restoration Civil | 2015-10-26 | 2016-07-01 | 0 | 335389 | 345249 | 1185604.7504 | 1034870.69 | 4158 | 5888.25 | 82.78% | 17.22% | 0%
15030012 | Minneapolis Operations | 15030012 | 1 | PNHS - Meth E Tower Vert Exp | 2015-05-01 | 2016-07-01 | 38334 | 294398 | 117936 | 14235788.76 | 14150037 | 28775 | 30980 | 93.35% | 6.583% | 0.07101%
15090009 | Chicago Operations | 15090009 | 1 | Silver Cross Master Plan | 2015-01-31 | 2016-06-30 | 22800 | 15730 | 0 | 544366 | 564078.17 | 1591 | 1830.73 | 99.95% | 0.05462% | 0%
15060042, 15060043, 14060010, 15060045, 15060044 | Denver Operations | 15060043 | 11 | Denver Water-OCR WP#3 | 2016-01-01 | 2016-06-30 | 160814 | 5444 | 6709 | 1420596.74 | 1410378.68 | 1122 | 1210 | 85.12% | 14.88% | 0%
15030008 | Minneapolis Operations | 15030008 | 1 | RPB - Vertical Expansion | 2015-05-15 | 2016-06-15 | 41600 | 234541 | 249112 | 8026043.6 | 8472899.03 | 12870 | 15404.21 | 92.32% | 7.306% | 0.3765%
15060036 | Denver Operations | 15060036 | 1 | SCL-Data Center | 2015-08-10 | 2016-06-01 | 0 | 0 | 0 | 81706.09 | 82362.77
15090017 | Chicago Operations | 15090017 | 1 | Faegre Baker Daniels 45th FL | 2016-01-04 | 2016-05-31 | 0 | 0 | 0 | 950058 | 969173.94 | 546 | 614 | 98.05% | 1.954% | 0%
15090015 | Chicago Operations | 15090015 | 1 | Allstate Largo FL | 2015-10-01 | 2016-05-31 | 140000 | 0 | 0 | 10904487.06 | 10814707.07 | 0 | 674 | 100% | 0% | 0%
15080004 | Milwaukee Operations | 15080004 | 1 | Froedtert-7 & 8 Inpatient BO's | 2015-09-21 | 2016-05-31 | 66808 | 194133 | 210018 | 12548203.4 | 11869930.31 | 13937 | 15169.5 | 93.71% | 6.269% | 0.01978%
15080004-064 | Mortenson Direct Operations | 15080004-064 | 1 | Froedtert-Direct Levels 7&8 BO | 2015-10-01 | 2016-05-31 | 0 | 0 | 0 | 3889347.44 | 3889347.63
15030032 | Minneapolis Operations | 15030032 | 1 | Stream - DH2 Fitup (1200kw) | 2015-07-01 | 2016-05-16 | 3000 | 3 | 0 | 7087922.37 | 7028194.33 | 1656 | 1351.01 | 96.54% | 3.46% | 0%
15146004 | Power Delivery Solutions Operations | 15146004 | 1 | REG I-Marshall HVT |  | 2016-05-13 | 0 | 258090 | 255247 | 4051230.19 | 3734991.51 | 4618 | 4828 | 84.55% | 15.45% | 0%
15050001 | Seattle Operations | 15050001 | 1 | Swedish Cherry Hill Projects | 2015-02-01 | 2016-04-30 | 19575 | 51415.0903 | 0 | 12725713.2396 | 12643140.03 | 12042 | 13831.94 | 92.55% | 6.499% | 0.9507%
15080014 | Milwaukee Operations | 15080014 | 1 | WEC Energy Group-Facility Asmt |  | 2016-04-29 | 0 | 0 | 0 | 213790 | 169568.2
15050022 | Seattle Operations | 15050022 | 1 | 1111 Third Ave Plaza Reno | 2016-01-04 | 2016-04-15 | 8143 | 0 | 0 | 0 | 114186.6
15090004 | Chicago Operations | 15090004 | 1 | Loyola Univ MC Misc. Projects | 2015-02-01 | 2016-03-31 | 0 | 0 | 0 | 0 | 891.35
15148004 | Civil Group Operations | 15148004 | 1 | REG I - Sendero Civil | 2015-05-18 | 2016-03-31 | 0 | 433394 | 412769 | 4486700.01 | 3803669.23 | 18499 | 17758 | 75.33% | 24.67% | 0%
15148018 | Civil Group Operations | 15148018 | 1 | Wind-Marshall Civil | 2015-08-31 | 2016-03-31 | 0 | 371661 | 354395 | 3791825.8611 | 3153890.16 | 13922.48 | 9855 | 79.07% | 20.93% | 0%
15060012 | Denver Operations | 15060012 | 1 | SCL-Exempla Luth-EP Lab Precon | 2015-11-30 | 2016-03-31 | 0 | 1385 | 0 | 515532.04 | 516786.06 | 2481 | 1786.5 | 92.86% | 7.137% | 0%
15030052 | Minneapolis Operations | 15030052 | 1 | MN Twins - 2016 Improvements | 2015-10-28 | 2016-03-31 | 9000 | 45654 | 0 | 4499965.94 | 4291872.51 | 5917 | 8183.71 | 95.28% | 4.717% | 0%
15148003, 15146007, 15145004 | Power Delivery Solutions Operations | 15146007 | 11 | Alamo VI Solar -HVT | 2015-11-09 | 2016-03-31 | 0 | 86847 | 87648 | 3026575.194 | 2629838.26 | 5245 | 3892.5 | 90.15% | 9.852% | 0%
15050017 | Seattle Operations | 15050017 | 1 | City of Bend WWTF Exp | 2015-09-15 | 2016-03-31 | 0 | 0 | 0 | 733243.92 | 1162814.59 | 380 | 691 | 100% | 0% | 0%
15145005 | Solar and Emerging Renewables Operations | 15145005 | 1 | Henrietta Solar-SunPower | 2015-06-09 | 2016-03-18 | 127785600 | 834756.53 | 819212 | 12152451.4648 | 9673435.14 | 68994.5 | 55735.5 | 98.03% | 1.969% | 0.002691%
15030057 | Minneapolis Operations | 15030057 | 1 | U of MN - Siebert Field | 2015-12-11 | 2016-03-16 | 4695 | 26691 | 29591 | 1044779.13 | 1082414.5 | 4360 | 4201.65 | 99.69% | 0.3094% | 0%
15030044 | Minneapolis Operations | 15030044 | 1 | MOA - Group Sales Banquet Hall | 2015-08-01 | 2016-03-04 | 8321 | 37891.35 | 0 | 2843347.8782 | 2679475.84 | 5804 | 4123.5 | 76.2% | 23.41% | 0.388%
15148003, 15146007, 15145004 | Civil Group Operations | 15148003 | 1 | Alamo VI Solar -Civil | 2015-03-30 | 2016-03-01 | 0 | 261960 | 241300 | 2079343.09 | 1953440.82 | 5146 | 4839.5 | 76.24% | 23.76% | 0%
15080016 | Milwaukee Operations | 15080016 | 1 | Froedtert-MRI 4 E.R.R. | 2015-11-01 | 2016-03-01 | 2850 | 36674 | 4804 | 1032808 | 952192.57 | 901 | 1326.5 | 75.12% | 16.77% | 8.104%
15080018 | Milwaukee Operations | 15080018 | 1 | Froedtert-MRI 5 MRgFUS | 2015-11-01 | 2016-03-01 | 2850 | 0 | 120 | 40775 | 35602.43 | 0 | 4 | 100% | 0% | 0%
15080016-064 | Mortenson Direct Operations | 15080016-064 | 1 | Froedtert-Direct MRI 4 E.R.R. | 2015-11-01 | 2016-03-01 | 0 | 0 | 0 | 24970 | 24970
15040009 | Phoenix Operations | 15040009 | 1 | CU Boulder-Solar Array | 2015-08-24 | 2016-03-01 | 0 | 0 | 0 | 873780.79 | 1307401.75
15060029 | Denver Operations | 15060029 | 1 | Vestas-Windsor Phase X | 2015-08-24 | 2016-02-29 | 35000 | 291956 | 100569 | 7696194.99 | 8058902.09 | 12180 | 19223 | 82.31% | 17.69% | 0%
15030016 | Minneapolis Operations | 15030016 | 1 | FlyOver America | 2015-03-23 | 2016-02-29 | 14584 | 9220.8 | 4 | 6100970.464 | 6072672.02 | 8129.4 | 7760.5 | 76.67% | 22.27% | 1.057%
15090012 | Chicago Operations | 15090012 | 1 | United ORD T1 Club Renovations | 2015-08-01 | 2016-02-28 | 8368 | 30194.23 | 19901 | 4015501.355 | 3878322 | 2935.5 | 3865.17 | 91.54% | 6.352% | 2.109%
15060040 | Denver Operations | 15060040 | 1 | SCL-EONS Level 4 Package | 2016-01-01 | 2016-02-26 | 225 | 98 | 0 | 77195.02 | 76458.61 | 28 | 383.5 | 98.83% | 1.173% | 0%
15050013 | Seattle Operations | 15050013 | 1 | 2015 Providence Everett Small | 2015-08-03 | 2016-02-19 | 1347 | 3507 | 0 | 674049.68 | 723182.8 | 799.5 | 2230.89 | 85.36% | 13.18% | 1.457%
15040015 | Phoenix Operations | 15040015 | 1 | AlaskaUSA-Tempe Bank Branch | 2016-09-06 | 2016-02-08 | 500 | 0 | 0 | 175714.83 | 198862.63 | 0 | 3 | 100% | 0% | 0%
15060034 | Denver Operations | 15060034 | 1 | Co Rockies-Coors Field Winter | 2015-10-01 | 2016-02-01 | 0 | 5646 | 8 | 1013717 | 1022168.48 | 1527 | 2067 | 95.79% | 4.209% | 0%
15080008 | Milwaukee Operations | 15080008 | 1 | Marquette-N.Campus Bldg. Demo | 2015-06-01 | 2016-02-01 | 0 | 0 | 0 | 2004673 | 1968218.02 | 0 | 97 | 96.91% | 3.093% | 0%
15060033 | Denver Operations | 15060033 | 1 | CU-VAC-Replace Faulty Humid | 2015-11-15 | 2016-01-31 | 9800 | 0 | 0 | 88593 | 119888.02
15040010 | Phoenix Operations | 15040010 | 1 | Globe-PRV Replacement | 2015-11-01 | 2016-01-31 | 0 | 0 | 0 | 605826.6 | 586997.87
15060042, 15060043, 14060010, 15060045, 15060044 | Denver Operations | 15060042 | 1 | Denver Water-Materials Lab | 2015-11-16 | 2016-01-29 | 2694 | 2721 | 0 | 273555.5 | 243015.29 | 1180 | 506.5 | 97.04% | 2.962% | 0%
15145011 | Solar and Emerging Renewables Operations | 15145011 | 1 | Blue Lake-SunEdison | 2015-06-08 | 2016-01-22 | 1567800 | 158513.08 | 157082 | 1932901.97 | 1886941.86 | 9924 | 11609.75 | 83.52% | 16.48% | 0%
15050018 | Seattle Operations | 15050018 | 1 | Swedish Ballard Small Projects | 2015-11-02 | 2016-01-15 | 1347 | 513 | 2 | 782390.77 | 799381.69 | 664 | 1082.15 | 93.95% | 6.053% | 0%
15080009 | Milwaukee Operations | 15080009 | 1 | Columbia St.Mary's-Oz.3rd Flr. | 2015-07-31 | 2016-01-11 | 2786 | 17012 | 3682 | 401899.15 | 363856.41 | 1785.5 | 1566.5 | 86.12% | 13.88% | 0%
15030001 | Minneapolis Operations | 15030001 | 1 | FUMC-Annual Contract 2015 | 2015-01-01 | 2016-01-01 | 0 | 75994.589 | 0 | 4586721.64 | 4535466.89 | 9222.5 | 11145.36 | 98.15% | 1.763% | 0.08524%
15145016 | Solar and Emerging Renewables Operations | 15145016 | 1 | CU Boulder Solar Array | 2015-08-24 | 2016-01-01 | 0 | 0 | 0 | 0.01 | 0
15090008 | Chicago Operations | 15090008 | 1 | Kliment-Neubauer Collegium | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 26520 | 2075.44
15090991 | Chicago Operations | 15090991 | 1 | Chicago Prefab Shop | 2015-01-01 | 2015-12-31 | 0 | 187159 | 96390 | 0 | -59011.56 | 5716.25 | 10212.9 | 98.43% | 1.464% | 0.1028%
15090997 | Chicago Operations | 15090997 | 1 | Chicago Equip Facility 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -1998874.12
15090999 | Chicago Operations | 15090999 | 1 | Chicago Closed Projects 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 5000.01 | 8545.84 | 0 | 70.88 | 100% | 0% | 0%
15148997 | Civil Group Operations | 15148997 | 1 | Civil-Equipment Facility '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -1463123.08
15148999 | Civil Group Operations | 15148999 | 1 | Civil-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -19577.67
15060015 | Denver Operations | 15060015 | 1 | CU-Athletics Branding Impl. | 2015-06-01 | 2015-12-31 | 200000 | 1462 | 0 | 1739594 | 1680716.8
15110997 | FCG Operations | 15110997 | 1 | FCG 2015 Equipment Facility | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0 | -16161.5
15110999 | FCG Operations | 15110999 | 1 | FCG 2015 Closed Projects | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0 | -150836.91
15080999 | Milwaukee Operations | 15080999 | 1 | Milwaukee Closed Job Costs '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 14524.9 | 0 | 55 | 96.36% | 3.636% | 0%
15080003 | Milwaukee Operations | 15080003 | 1 | Acuity Ins-Lvl 1 Flrg Warranty | 2015-03-04 | 2015-12-31 | 38052 | 0 | 0 | 0.01 | 0
15030015 | Minneapolis Operations | 15030015 | 1 | MOA-Small Projects 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 88168 | 84048.9 | 0 | 1090 | 69.08% | 30.92% | 0%
15030028 | Minneapolis Operations | 15030028 | 1 | U of MN - 2015 Small Projects | 2015-05-18 | 2015-12-31 | 0 | 512 | 0 | 567509.89 | 496792.97 | 741 | 566.5 | 93.56% | 6.443% | 0%
15030997 | Minneapolis Operations | 15030997 | 1 | 2015 Mpls Equip Facility Recog | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -4728635
15030999 | Minneapolis Operations | 15030999 | 1 | MAM - 2015 Closed Projects | 2013-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -125838.08 | 0 | 222 | 100% | 0% | 0%
15030014 | Minneapolis Operations | 15030014 | 1 | UMN ASVM 3rd Floor Renovation |  | 2015-12-31 | 3000 | 2551 | 0 | 717908.32 | 718245.01 | 1116 | 993.5 | 99.4% | 0.6039% | 0%
15030045 | Minneapolis Operations | 15030045 | 1 | 4150 LLC - 3rd Fl Corridor | 2015-08-05 | 2015-12-31 | 3087 | 12277 | 0 | 1083507.172 | 1027032.58 | 1524 | 1559.5 | 97.31% | 2.693% | 0%
15030056 | Minneapolis Operations | 15030056 | 1 | 4150 LLC. - NW Assoc. Cons. | 2015-11-18 | 2015-12-31 | 3150 | 9010 | 0 | 197672.13 | 172590.73 | 233 | 200 | 98% | 2% | 0%
15030053 | Minneapolis Operations | 15030053 | 1 | 4150 LLC-LifeScience Alley | 2015-10-19 | 2015-12-31 | 26000 | 9259 | 0 | 274952.5 | 225995.83 | 640 | 478.5 | 98.12% | 1.881% | 0%
15040003 | Phoenix Operations | 15040003 | 1 | Mortenson-Phx Office 2015 TI | 2015-09-01 | 2015-12-31 | 0 | 0 | 0 | 180000 | -134.29 | 0 | 16.5 | 96.97% | 3.03% | 0%
15146001 | Power Delivery Solutions Operations | 15146001 | 1 | Slate Creek HVT | 2015-03-30 | 2015-12-31 | 0 | 748131 | 747909 | 9286049 | 8920778.41 | 15434 | 21066.5 | 77.72% | 22.28% | 0%
15146002 | Power Delivery Solutions Operations | 15146002 | 1 | REG I-Amazon HVT | 2015-05-15 | 2015-12-31 | 0 | 141 | 0 | 3961175 | 3911326.41
15146997 | Power Delivery Solutions Operations | 15146997 | 1 | HVT-Equipment Facility '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -112854.89
15146999 | Power Delivery Solutions Operations | 15146999 | 1 | HVT-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -81128.47
15050997 | Seattle Operations | 15050997 | 1 | 2015 Seattle Equip Facility | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -1315981.5
15050999 | Seattle Operations | 15050999 | 1 | 2015 Seattle Closed Projects | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 14818.1 | 0 | 16 | 100% | 0% | 0%
15145999 | Solar and Emerging Renewables Operations | 15145999 | 1 | Solar-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 59689.94
15141001 | Wind Energy I Operations | 15141001 | 1 | Fowler Ridge IV LLC-Amazon | 2015-05-04 | 2015-12-31 | 0 | 7768 | 7457 | 45492782.0635 | 44537488.92 | 67838 | 60931.75 | 67.42% | 23.74% | 8.838%
15141002 | Wind Energy I Operations | 15141002 | 1 | Sendero Wind Energy LLC-Sender | 2015-06-01 | 2015-12-31 | 0 | 3164 | 2084 | 17759387.55 | 18147771.67 | 31995 | 46677.25 | 74.11% | 25.89% | 0%
15141008 | Wind Energy I Operations | 15141008 | 1 | SunEdison Antelope Hills Wind | 2015-07-27 | 2015-12-31 | 0 | 0 | 0 | 561720.5 | 565082.3
15141997 | Wind Energy I Operations | 15141997 | 1 | Wind Equipment Facility '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -6197627.41
15141999 | Wind Energy I Operations | 15141999 | 1 | Wind-Closed Projects 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 361360.57 | 0 | 1927.14 | 94.5% | 5.5% | 0%
15141999-110 | Wind Energy I Operations | 15141999-110 | 1 | Wind-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 11133.39
15060027 | Denver Operations | 15060027 | 1 | Kroenke-Pepsi Ctr Ext Lighting | 2015-08-03 | 2015-12-21 | 10000 | -1 | 0 | 1738599.7 | 1705878.78 | 2389 | 1876 | 93.47% | 6.53% | 0%
15080013 | Milwaukee Operations | 15080013 | 1 | Columbia St.Mary's-Oz.MRI Repl | 2015-09-18 | 2015-12-18 | 1870 | 14747 | 0 | 588822.48 | 582882.81 | 1820 | 1780 | 97.58% | 2.416% | 0%
15146009 | Power Delivery Solutions Operations | 15146009 | 1 | AEP-Uvalde Substation HVT | 2015-08-17 | 2015-12-18 | 0 | 23551 | 23550 | 249056 | 218948.18 | 1829 | 2022 | 92.73% | 7.27% | 0%
15145020 | Solar and Emerging Renewables Operations | 15145020 | 1 | OCI-AlamoV SCADA Retrofit | 2015-09-28 | 2015-12-18 | 120279600 | 35263 | 35235 | 432047.49 | 295537.34 | 4966 | 5238.75 | 89.37% | 10.63% | 0%
15030051 | Minneapolis Operations | 15030051 | 1 | MOA - Crayola Demolition | 2015-09-15 | 2015-12-11 | 8321 | 22 | 0 | 146857 | 120408.79 | 1896 | 1357 | 79.96% | 20.04% | 0%
15060003 | Denver Operations | 15060003 | 1 | Charles Schwab-Train Station | 2015-06-01 | 2015-12-01 | 5200 | 0 | 0 | 85352 | 89707.66 | 0 | 15.01 | 100% | 0% | 0%
15030036 | Minneapolis Operations | 15030036 | 1 | TC United Way - 1st Floor | 2015-06-22 | 2015-12-01 | 13898 | 10 | 0 | 403378.5 | 408495.59 | 340 | 657 | 96.5% | 3.501% | 0%
15030006 | Minneapolis Operations | 15030006 | 1 | Basilica Renovation and HVAC | 2015-03-15 | 2015-12-01 | 22000 | 38229 | 41055 | 1382228.08 | 1331666.66 | 2689 | 4177.91 | 97.16% | 2.836% | 0%
15050007 | Seattle Operations | 15050007 | 1 | Providence Everett Hospice | 2015-06-01 | 2015-12-01 | 14330 | 15256.8263 | 0 | 3479928.04 | 3643962.69 | 2408 | 6104.68 | 90.14% | 7.642% | 2.22%
15030050 | Minneapolis Operations | 15030050 | 1 | Basilica Annual Contract Work | 2015-09-08 | 2015-11-30 | 0 | 0 | 0 | 198753.76 | 198104.6 | 1302 | 1228.51 | 87.99% | 12.01% | 0%
15148006 | Civil Group Operations | 15148006 | 1 | REG I-Alexander Civil | 2015-06-03 | 2015-11-27 | 0 | 155494 | 152435 | 2771108.79 | 2272562.42 | 11803 | 8518 | 71.61% | 27.32% | 1.068%
15060007 | Denver Operations | 15060007 | 1 | CCP/MS-US Bank Tower | 2015-03-02 | 2015-11-27 | 13500 | 3 | 208 | 1325133.05 | 1377531.17 | 0 | 4202.5 | 86.86% | 13.14% | 0%
15148001 | Civil Group Operations | 15148001 | 1 | REG I-Amazon Civil | 2015-05-04 | 2015-11-16 | 0 | 541707 | 518102 | 8147753.2504 | 7992158.22 | 29744.67 | 30429.5 | 67.7% | 30.11% | 2.189%
15030022 | Minneapolis Operations | 15030022 | 1 | HCMC-Helistop and Elevator | 2015-07-01 | 2015-11-16 | 9900 | 11018 | 0 | 2226398.69 | 1999036.38 | 3475 | 4646.5 | 93.34% | 6.317% | 0.3443%
15080001 | Milwaukee Operations | 15080001 | 1 | Guardian IG-Sun Prairie Remodl | 2015-04-06 | 2015-11-02 | 226106 | 0 | 0 | 3672060.02 | 3624753.24 | 901 | 849.5 | 99.06% | 0.9417% | 0%
15030011 | Minneapolis Operations | 15030011 | 1 | PNHS - MSE Core & Shell | 2015-04-20 | 2015-11-01 | 22944 | 119470 | 90487 | 3654453.06 | 3654442.2 | 11739 | 12516.75 | 94.46% | 5.537% | 0%
15090010 | Chicago Operations | 15090010 | 1 | Allstate Jcksnvl Restack IV | 2015-03-31 | 2015-10-31 | 19138 | 0 | 0 | 1705777.69 | 1691925.63 | 252 | 920 | 100% | 0% | 0%
15080010 | Milwaukee Operations | 15080010 | 1 | AHC-SLMC Starbucks | 2015-08-26 | 2015-10-30 | 2547 | 7804 | 0 | 406715.82 | 356574.74 | 1114 | 1281 | 82.16% | 17.84% | 0%
15030033 | Minneapolis Operations | 15030033 | 1 | 4150 LLC - Best Vendors 2nd Fl | 2015-05-04 | 2015-10-30 | 26000 | 101636 | 0 | 1076107.36 | 978892.57 | 912 | 1199 | 95.54% | 4.462% | 0%
15030038 | Minneapolis Operations | 15030038 | 1 | RMC - Cherry St. Parking Lot | 2015-05-15 | 2015-10-30 | 70000 | 0 | 0 | 736263 | 753624.05 | 320 | 446.5 | 97.31% | 2.688% | 0%
15060011 | Denver Operations | 15060011 | 1 | Sterling Ranch-Roxbrough | 2015-07-01 | 2015-10-15 | 0 | 0 | 0 | 0.01 | 0
15060021 | Denver Operations | 15060021 | 1 | Vestas-Windsor Phase IX | 2015-06-22 | 2015-10-12 | 63000 | 298606 | 2967 | 4045272.35 | 3825824.11 | 9888 | 8550.5 | 86.8% | 13.2% | 0%
15060031 | Denver Operations | 15060031 | 1 | CCP-US Bank Phase 2 | 2015-08-11 | 2015-10-11 | 0 | 0 | 0 | 364652 | 369282.31 | 0 | 16 | 100% | 0% | 0%
15050015 | Seattle Operations | 15050015 | 1 | Jars Juice Retail TI | 2015-08-17 | 2015-10-01 | 1055 | 0 | 0 | 192839.12 | 193595.38 | 0 | 2.5 | 80% | 20% | 0%
15145003 | Solar and Emerging Renewables Operations | 15145003 | 1 | UC Davis - SunPower | 2015-02-18 | 2015-10-01 | 16286400 | 43051 | 35843 | 1798685.28 | 1561869.54 | 9482.82 | 7532 | 84.63% | 15.37% | 0%
15090007 | Chicago Operations | 15090007 | 1 | Northwestern Athletic Field | 2015-03-01 | 2015-09-30 | 0 | 3509 | 0 | 2753770.16 | 2644246.17 | 1227 | 1090.4 | 78.86% | 16.97% | 4.173%
15060010 | Denver Operations | 15060010 | 1 | Univ. Of Co-Athletic Audio/V | 2015-04-01 | 2015-08-31 | 0 | 320 | 0 | 0 | 0
15050006 | Seattle Operations | 15050006 | 1 | Freshy's Tenant Improvement | 2015-03-16 | 2015-08-31 | 1301 | 2 | 8 | 142613.87 | 142763.72 | 68 | 32 | 100% | 0% | 0%
15030027 | Minneapolis Operations | 15030027 | 1 | U of MN - Weaver Dens 2nd Flr | 2015-05-18 | 2015-08-21 | 5500 | 18148 | 0 | 515801 | 506296.1 | 983 | 1115 | 98.92% | 1.076% | 0%
15030013 | Minneapolis Operations | 15030013 | 1 | UMN Scholars Walk Canopy | 2015-05-18 | 2015-08-14 | 9000 | 2332.2 | 0 | 1660557.4 | 1557745.52 | 2548 | 2494 | 95.31% | 4.491% | 0.2005%
15030020 | Minneapolis Operations | 15030020 | 1 | Cornell-Dows & Tarr Hall Reno | 2015-03-14 | 2015-08-14 | 38208 | 2055 | 0 | 3934287.89 | 3865657.17 | 3331 | 2256 | 85.42% | 14.58% | 0%
15050009 | Seattle Operations | 15050009 | 1 | Elemental Pizza | 2015-05-04 | 2015-08-14 | 4740 | 1142.15 | 4607 | 608186.37 | 579035.01 | 1309 | 1219.5 | 94.3% | 5.699% | 0%
15060001 | Denver Operations | 15060001 | 1 | CSU-PERC New Facility | 2015-03-01 | 2015-08-01 | 27608 | 0 | 0 | 0.01 | 0
15090003 | Chicago Operations | 15090003 | 1 | Chicago Theater Bathroom Ren. | 2014-12-01 | 2015-07-31 | 220 | 0 | 0 | 76101 | 52046.53 | 475 | 134 | 100% | 0% | 0%
15090005 | Chicago Operations | 15090005 | 1 | 111 S Wacker Column Retro | 2015-01-28 | 2015-07-31 | 8125 | 4896 | 0 | 5861817.98 | 5026432.95 | 3649 | 4155.9 | 66.87% | 23.44% | 9.697%
15060022 | Denver Operations | 15060022 | 1 | Ft Collins DDA-Old Towne Sq | 2015-01-01 | 2015-07-31 | 0 | 0 | 0 | 34343 | 37406.8
15040005 | Phoenix Operations | 15040005 | 1 | AlaskaUSA-Mesa Bank Branch | 2015-06-10 | 2015-07-22 | 1490 | 871.4565 | 0 | 235351.49 | 233910.61
15030024 | Minneapolis Operations | 15030024 | 1 | Deer District-Bucks Precon |  | 2015-07-15 | 694000 | 0 | 0 | 0.01 | 0
15150002 | Sports + Entertainment Group Operations | 15150002 | 1 | Deer District- Bucks Precon |  | 2015-07-15 | 694000 | 0 | 0 | 99213.45 | 115464.28
15030030 | Minneapolis Operations | 15030030 | 1 | Stream - MNPDC DH1 Office | 2015-05-11 | 2015-07-09 | 3000 | 55.22 | 0 | 215977.22 | 234452.82 | 151 | 462.5 | 100% | 0% | 0%
15040006 | Phoenix Operations | 15040006 | 1 | AlaskaUSA-Phoenix Branch | 2015-06-08 | 2015-07-04 | 1490 | 881.5661 | 0 | 227957.56 | 233333.69
15090002 | Chicago Operations | 15090002 | 1 | Advocate GS Cooling Tower Upg. | 2015-02-01 | 2015-06-30 | 0 | 0 | 0 | 1017732.5 | 1017155.94 | 0 | 288.69 | 100% | 0% | 0%
15120001 | Discontinued Groups | 15120001 | 1 | Yahoo! BF2 Day 1 Phase 2 | 2014-12-31 | 2015-06-30 | 30000 | 22 | 0 | 14303752 | 13911537.6 | 0 | 7 | 100% | 0% | 0%
15030025 | Minneapolis Operations | 15030025 | 1 | HCMC - Mock-Ups | 2015-05-04 | 2015-06-30 | 12000 | 0 | 0 | 121267 | 116506.67 | 754 | 733.92 | 93.53% | 6.472% | 0%
15030019 | Minneapolis Operations | 15030019 | 1 | Northern Stacks-Kaufman TI | 2015-04-01 | 2015-06-20 | 48207 | 523 | 0 | 726745 | 733889.11 | 1078 | 751 | 87.62% | 12.38% | 0%
15030017 | Minneapolis Operations | 15030017 | 1 | MOA-SE Court Duct Relocation | 2015-04-06 | 2015-06-17 | 0 | 7 | 0 | 446197.99 | 421381.69 | 406 | 284 | 80.28% | 19.72% | 0%
15040002 | Phoenix Operations | 15040002 | 1 | SunPower Corp Systems-Stanford | 2015-09-10 | 2015-05-30 | 0 | 0 | 0 | 129411.5 | 71391.98
15030002 | Minneapolis Operations | 15030002 | 1 | UMMC-Fairview - Repro/MMC | 2014-12-17 | 2015-05-01 | 12000 | 26 | 0 | 1359521.38 | 1117046.94 | 2334 | 1105 | 93.39% | 5.701% | 0.905%
15060008 | Denver Operations | 15060008 | 1 | Denver Water-Conduit | 2015-04-01 | 2015-04-30 | 0 | 0 | 0 | 0.01 | 0
15030007 | Minneapolis Operations | 15030007 | 1 | BAE Systems Data Center | 2015-02-02 | 2015-04-01 | 1500 | 3357 | 0 | 501973 | 432006.87 | 622 | 303.99 | 98.68% | 1.316% | 0%
15030004 | Minneapolis Operations | 15030004 | 1 | RMC - Wound Care Clinic | 2015-01-05 | 2015-03-31 | 3200 | 3529.2 | 0 | 738382.19 | 716634.85 | 2137 | 2603 | 96.64% | 3.362% | 0%
15030005 | Minneapolis Operations | 15030005 | 1 | UMN Physics Nano Lab 353 | 2015-02-16 | 2015-03-15 | 1400 | 410 | 0 | 354605 | 342361.35 | 280 | 224 | 100% | 0% | 0%
15040001 | Phoenix Operations | 15040001 | 1 | PCH-Rosenburg Sterilizer | 2015-02-11 | 2015-03-11 | 289 | 378 | 0 | 106193 | 113593.66
15080997 | Milwaukee Operations | 15080997 | 1 | Milwaukee - Equip Facility '15 | 2015-01-01 | 2015-01-31 | 0 | 0 | 0 | -739966 | -1381419.87
15030003 | Minneapolis Operations | 15030003 | 1 | 4150, LLC - ZIVIX | 2014-12-22 | 2015-01-30 | 6750 | 85.59 | 0 | 197325.36 | 195273.78 | 247 | 255 | 99.22% | 0.7843% | 0%
15040997 | Phoenix Operations | 15040997 | 1 | Phoenix-Equipment Facility '15 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 85691.18
15040999 | Phoenix Operations | 15040999 | 1 | Phoenix-Closed Projects 2015 | 2013-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -8414.84
15145997 | Solar and Emerging Renewables Operations | 15145997 | 1 | Solar-Equipment Facility '15 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -2308021.62
15060997 | Denver Operations | 15060997 | 1 | Denver-EF 2015 | 2013-01-01 | 2013-12-31 | 0 | 0 | 0 | 0.01 | -2457024.28
15060999 | Denver Operations | 15060999 | 1 | Denver-Closed Project 2015 | 2012-01-01 | 2012-12-31 | 0 | 2 | 0 | 0.01 | -466.91 | 0 | 9.5 | 84.21% | 15.79% | 0%
15148009 | Civil Group Operations | 15148009 | 1 | Solar - Blue Lake Center Civil | 2015-05-26 |  | 0 | 5918 | 5916 | 177132 | 156308.76 | 866 | 788 | 74.24% | 25.76% | 0%
15120999 | Data Center Operations | 15120999 | 1 | MCG 2015 Closed Project | 2015-01-01 |  | 0 | 0 | 0 | 0 | 2135.41
15400999 | Discontinued Groups | 15400999 | 1 | Discontinued-15 Closed |  |  | 0 | 0 | 0 | 0 | 98084.67
15110007-159 | FCG Operations | 15110007-159 | 1 | McC/Mort JV NBAF 3 Concrete | 2015-05-28 |  | 0 | 0 | 0 | 47618831 | 0
15110001 | FCG Operations | 15110001 | 1 | JBLM Entertainment Center |  |  | 74000 | 0 | 0 | 784711.03 | 782682.54
15001 | FCG Operations | 15001 | 1 | DON-AIRCRAFT MAINT.HANGAR P-5 | 2002-11-23 |  | 123000 | 69284 | 0 | 20749086 | 20750359 | 0 | 5621 | 100% | 0% | 0%
15030009 | Minneapolis Operations | 15030009 | 1 | RMC - 2015 Annual Contract | 2015-01-01 |  | 0 | 9597 | 8 | 211213.36 | 199760.62 | 1385 | 924 | 96.65% | 3.355% | 0%
15030026 | Minneapolis Operations | 15030026 | 1 | ANW Facilities Contract - 2015 | 2015-01-01 |  | 0 | 0 | 0 | 0.01 | 3984926.2 | 0 | 33824.3 | 90.94% | 7.69% | 1.373%
15030029 | Minneapolis Operations | 15030029 | 1 | UHG - NTC2 Coil Replacement | 2015-07-01 |  | 0 | 0 | 0 | 2633880.95 | 2387003.54 | 797 | 1223.57 | 66.35% | 33.65% | 0%
15030040 | Minneapolis Operations | 15030040 | 1 | Do not use |  |  | 0 | 0 | 0 | 0.01 | 0
15030042 | Minneapolis Operations | 15030042 | 1 | MN Twins - MMA Warranty | 2015-06-30 |  | 0 | 0 | 0 | 0 | 442572.19 | 0 | 698 | 71.63% | 28.37% | 0%
15030035 | Minneapolis Operations | 15030035 | 1 | Landry's - Rainforest Cafe | 2015-06-01 |  | 10913 | 29714 | 0 | 2156761.09 | 2119485.48 | 2103 | 1453.5 | 83.8% | 14% | 2.202%
15030046 | Minneapolis Operations | 15030046 | 1 | MAM - Campus Office Space Reno | 2015-08-24 |  | 40120 | 0 | 0 | 4857701 | 3587238.78 | 3109 | 3698 | 97.89% | 2.109% | 0%
15030037 | Minneapolis Operations | 15030037 | 1 | Northern Stacks I - OnTrac TI | 2015-06-15 |  | 52724 | 4981 | 0 | 1218320 | 1033680.25 | 1614 | 1230 | 87.85% | 10.85% | 1.301%
15030010 | Minneapolis Operations | 15030010 | 1 | Mort Dev-Museum of Art | 2016-06-01 |  | 60000 | 1 | 0 | 2088931 | 1897920.1
15040007 | Phoenix Operations | 15040007 | 1 | SRP PAB Balance of Reno |  |  | 431000 | 0 | 0 | 0.01 | 0
15145001 | Solar and Emerging Renewables Operations | 15145001 | 1 | MN Solar Gardens - SunShare |  |  | 0 | 0 | 0 | 0.01 | 661090.41 | 0 | 18.5 | 100% | 0% | 0%
15145021 | Solar and Emerging Renewables Operations | 15145021 | 1 | Traxler CSG - Sunshare | 2015-10-31 |  | 0 | 63 | 0 | 18739 | 22125.78
15145025 | Solar and Emerging Renewables Operations | 15145025 | 1 | Kroll CSG - Sunshare |  |  | 0 | 98 | 0 | 18938 | 25494.95
15150004 | Sports + Entertainment Group Operations | 15150004 | 1 | KSU - NorthEast Connector | 2016-01-05 |  | 17000 | 2812 | 0 | 1171316.63 | 1170794.85 | 5444 | 2518.5 | 87.35% | 12.65% | 0%
15141003 | Wind Energy I Operations | 15141003 | 1 | Minnesota Power-Taconite Ridge | 2015-06-08 |  | 0 | 380749 | 0 | 459310.5404 | 489319.43 | 1360 | 1451 | 60.92% | 24.47% | 14.61%
15141006 | Wind Energy I Operations | 15141006 | 1 | Siemens-Ocotillo Turbine 110 | 2015-08-03 |  | 0 | 1017307 | 0 | 1197557 | 1013487.49 | 2474 | 2075.5 | 72.18% | 21.97% | 5.854%
14060010 | Denver Operations | 14060010 | 1 | Denver Water-Campus | 2014-04-28 | 2020-03-01 | 325000 | 0 | 0 | 532951 | 496849.89 | 0 | 15 | 100% | 0% | 0%
14050005 | Portland Operations | 14050005 | 1 | Hyatt Regency Hotel (OCC) | 2017-08-09 | 2019-11-04 | 634000 | 1962295.55 | 1576116 | 174850901.1072 | 175728472.35 | 78390.2 | 94370.89 | 85.48% | 14.4% | 0.1197%
14150006 | Sports + Entertainment Group Operations | 14150006 | 1 | Mortenson Clark - Golden State | 2017-01-09 | 2019-08-01 | 0 | 0 | 0 | 29134095 | 29426155.55 | 1992 | 1454 | 100% | 0% | 0%
14050001 | Seattle Operations | 14050001 | 1 | Coos Bay Wastewater Treatment | 2016-09-01 | 2019-07-22 | 4800 | 324516 | 329454 | 20581708.33 | 22610150.74 | 27093 | 36060.5 | 95.81% | 4.072% | 0.1165%
14110001 | FCG Operations | 14110001 | 1 | DHS-Rpr Rbld USCG Academy | 2015-04-06 | 2018-12-31 | 0 | 2421 | 0 | 23715115.26 | 24236022.1
14030033 | Minneapolis Operations | 14030033 | 1 | City of Mpls-Target Center Ren | 2016-05-06 | 2018-09-07 | 0 | 1102439.46 | 760040 | 115862113.7914 | 114968520.37 | 95564.53 | 77651.48 | 88.87% | 10.43% | 0.7057%
14030054 | Minneapolis Operations | 14030054 | 1 | HCMC - AOSC | 2015-11-02 | 2018-09-04 | 320000 | 3459675 | 2432594 | 107026144.0185 | 100531025.81 | 217683.1 | 152716.22 | 90.96% | 8.941% | 0.09495%
14060023 | Denver Operations | 14060023 | 1 | RTD-Central Park Station | 2014-08-14 | 2018-07-01 | 0 | 32789 | 13363 | 10701134.13 | 11056173.64 | 7389 | 15741 | 93.09% | 6.906% | 0%
14135001 | HVDC Group Operations | 14135001 | 1 | MCC-Bipole III Converter HVDC | 2015-11-01 | 2018-06-30 | 248000 | 0 | 0 | 34220629 | 34220628.88 | 0 | -140765.96 | 102.1% | -1.583% | -0.4792%
14135001-110 | HVDC Group Operations | 14135001-110 | 1 | Manitoba Hydro-Bipole III | 2015-11-01 | 2018-06-30 | 248000 | 185290.74 | 104874 | 438371573.2709 | 459645057.76 | 94719.5 | 37157.65 | -112.1% | 116.4% | 95.69%
16148011, 14060015 | Denver Operations | 14060015 | 11 | Sterling Ranch-Development | 2014-06-01 | 2018-06-29 | 0 | 184172.5 | 365079 | 84033394.92 | 89304254.52 | 25862.14 | 97079.68 | 87.08% | 12.92% | 0%
14030054-900 | Minneapolis Operations | 14030054-900 | 1 | HCMC - AOSC Tax Exempt | 2015-11-02 | 2018-02-16 | 320000 | 4 | 0 | 42449253.28 | 42453385.88
14090001 | Chicago Operations | 14090001 | 1 | College of Lake County A&B | 2013-10-01 | 2017-12-31 | 475000 | 151342.5 | 132527 | 19967389.7552 | 19672885.96 | 14791 | 15301.89 | 91.14% | 8.473% | 0.3856%
14080007 | Milwaukee Operations | 14080007 | 1 | Harley-Davidson-Misc.Projects | 2014-05-22 | 2017-12-31 | 0 | 2 | 0 | 182059 | 157733.88 | 582 | 577 | 96.45% | 3.553% | 0%
14040005 | Phoenix Operations | 14040005 | 1 | SRP-Full Renovation, Expansion | 2014-09-02 | 2017-12-31 | 431000 | 490.72 | 0 | 80027668.2387 | 79801586.92 | 26226.77 | 32210 | 86.48% | 13.52% | 0%
14060006 | Denver Operations | 14060006 | 1 | Park Creek-P-10 | 2015-06-01 | 2017-12-04 | 0 | 757 | 0 | 1751415 | 1801957.39 | 1230 | 6850 | 96.23% | 3.766% | 0%
14050006 | Seattle Operations | 14050006 | 1 | Tilt49 Office | 2015-02-02 | 2017-09-30 | 530000 | 1468654 | 1535590 | 50870539.9097 | 50470832.9 | 69436 | 71825.3 | 84.77% | 13.94% | 1.29%
14060011 | Denver Operations | 14060011 | 1 | Exempla-St Joseph-Campus | 2014-12-13 | 2017-09-07 | 12000 | 133704.05 | 65672 | 24986657.9226 | 25296024.25 | 27943.85 | 64224.5 | 91.22% | 8.782% | 0%
14060009 | Denver Operations | 14060009 | 1 | Park Creek-Westerly Creek Ph3 | 2015-01-07 | 2017-06-01 | 0 | 743 | 0 | 1245565 | 1232569.59 | 1036 | 7429.5 | 95.65% | 4.348% | 0%
14050012 | Seattle Operations | 14050012 | 1 | UWT-Urban Solutions Center | 2014-12-01 | 2017-05-18 | 40000 | 306391.5 | 213317 | 18694153.2515 | 18044259.8 | 20557.5 | 17681.43 | 96.32% | 3.603% | 0.07352%
14110002 | FCG Operations | 14110002 | 1 | DHS-USCG Recapitalize Fac NJ | 2014-09-05 | 2017-05-04 | 35000 | -3 | 0 | 26292883.77 | 28663615.84 | 4000 | 4232 | 100% | 0% | 0%
14110003 | FCG Operations | 14110003 | 1 | DOJ-Bldg 7 Washingtn Dorm Reno | 2015-04-06 | 2017-04-14 | 81723 | 355362 | 0 | 31107486.802 | 31737579.7 | 0 | 3867.5 | 98.85% | 1.151% | 0%
14060027 | Denver Operations | 14060027 | 1 | Park Creek-Section 10 | 2015-03-14 | 2017-03-31 | 0 | 100 | 0 | 468553 | 491718.11 | 380 | 154 | 77.92% | 22.08% | 0%
14080003 | Milwaukee Operations | 14080003 | 1 | Acuity Ins-Corporate HQ Expnsn | 2014-03-15 | 2017-02-10 | 873000 | 11215391.36 | 2416842 | 171798194.9892 | 174500254.73 | 217323.21 | 272124 | 85.85% | 13.89% | 0.2604%
14030045 | Minneapolis Operations | 14030045 | 1 | SW Healthcare Serv. - Hospital | 2015-03-01 | 2017-02-06 | 75095 | 227472 | 169515 | 27905214.331 | 25960744.96 | 12526.44 | 11988.5 | 66.58% | 29.44% | 3.975%
14090003 | Chicago Operations | 14090003 | 1 | Advocate Dreyer Clinic | 2013-10-01 | 2016-12-31 | 60000 | 0 | 0 | 33833.86 | 39631.21
14060005 | Denver Operations | 14060005 | 1 | Park Creek-P-9 | 2014-05-01 | 2016-12-31 | 0 | 686 | 0 | 194843.01 | 194900.34 | 5 | 83 | 98.19% | 1.807% | 0%
14030002 | Minneapolis Operations | 14030002 | 1 | Thrivent Lutheran-Annual Cont | 2014-01-01 | 2016-12-31 | 0 | 0 | 0 | 504204.92 | 504007.8 | 1583.5 | 1922.5 | 98.47% | 1.534% | 0%
14040009 | Phoenix Operations | 14040009 | 1 | SunPower Target 49 | 2015-03-02 | 2016-12-31 | 0 | 1355184 | 652914 | 12322266.2675 | 17331690.58 | 56587.21 | 114109.25 | 95.73% | 3.896% | 0.3762%
14146006 | Power Delivery Solutions Operations | 14146006 | 1 | REG I-Shannon HVT | 2015-02-01 | 2016-12-31 | 0 | 181380 | 197549 | 15186884.37 | 14832501.27 | 28997 | 32736.25 | 84.26% | 15.69% | 0.0504%
14080012 | Milwaukee Operations | 14080012 | 1 | Columbia St.Mary's-Misc2014-16 | 2014-01-01 | 2016-12-30 | 0 | 4462.26 | 0 | 238653.26 | 241801.15 | 686 | 786 | 83.08% | 16.92% | 0%
14060028 | Denver Operations | 14060028 | 1 | Park Creek-Filing 47 | 2014-11-05 | 2016-12-16 | 0 | 100 | 0 | 1530678 | 1694726.14 | 1355 | 2751 | 97.2% | 2.799% | 0%
14060017 | Denver Operations | 14060017 | 1 | Dominion Water-Water/Waste | 2015-11-01 | 2016-11-30 | 0 | 0 | 0 | 0.01 | 0
14050008 | Seattle Operations | 14050008 | 1 | UW West Campus Utility Plant | 2015-08-05 | 2016-11-30 | 20000 | 138901.65 | 99862 | 34622485.4418 | 34992924.42 | 15910.5 | 14827.31 | 90.71% | 9.155% | 0.1315%
14090015 | Chicago Operations | 14090015 | 1 | Five Star ORD Baggage Handling | 2015-04-07 | 2016-10-27 | 8102 | 16833.53 | 3490 | 2573817.6408 | 2525159.76 | 2052.12 | 3737.44 | 88.8% | 8.495% | 2.702%
14030047 | Minneapolis Operations | 14030047 | 1 | AC Marriott - 4th & Hennepin | 2015-04-01 | 2016-10-14 | 131039 | 1204930 | 718558 | 39303768.5716 | 37517067.95 | 39525 | 46939.5 | 92.5% | 7.502% | 0%
14140020 | Wind Energy I Operations | 14140020 | 1 | Mariah del Norte Wind | 2014-12-16 | 2016-09-30 | 0 | 571595 | 572144 | 53196896.0826 | 52296993.5 | 74316 | 80956.5 | 82.51% | 17.49% | 0%
14080004 | Milwaukee Operations | 14080004 | 1 | AHC-St.Luke's Main Lobby Renov | 2015-07-10 | 2016-09-01 | 7675 | 125958 | 92117 | 3875608.44 | 3475400.47 | 7997.5 | 7947.78 | 91.98% | 7.908% | 0.1132%
14030046 | Minneapolis Operations | 14030046 | 1 | City of Mankato-Civic Ctr Exp | 2015-04-01 | 2016-07-20 | 112000 | 380084 | 295430 | 28593981.61 | 26469012.17 | 28703.5 | 30819 | 94.89% | 4.864% | 0.2434%
14030023 | Minneapolis Operations | 14030023 | 1 | Iowa State - Marston Hall Ren. | 2014-07-07 | 2016-07-15 | 64534 | 14799.7365 | 0 | 1641215.604 | 2002780.01 | 2706 | 2917 | 81.28% | 18.51% | 0.2057%
14090014 | Chicago Operations | 14090014 | 1 | QTS Chicago Data Center | 2016-12-23 | 2016-06-30 | 80000 | 795780 | 602113 | 76192992.47 | 75573181.03 | 23011 | 18939.51 | 94.23% | 5.401% | 0.3722%
14148021 | Civil Group Operations | 14148021 | 1 | Slate Creek Civil | 2015-03-30 | 2016-06-30 | 0 | 460911 | 461851 | 5725521.6097 | 5218679.61 | 24401.19 | 23759 | 80.75% | 19.25% | 0%
14140015 | Wind Energy I Operations | 14140015 | 1 | South Plains II Wind | 2015-03-23 | 2016-06-30 | 0 | 17268 | 10536 | 72077363.8203 | 71914299.07 | 185355 | 188738 | 83.17% | 16.83% | 0%
14060022 | Denver Operations | 14060022 | 1 | BMC Investments-245 Columbine | 2015-01-26 | 2016-06-17 | 0 | 426862 | 362465 | 40952456.74 | 41969495.15 | 33797 | 65599.5 | 92.78% | 7.222% | 0%
14080011 | Milwaukee Operations | 14080011 | 1 | Uline - Distribution Center W2 | 2014-09-11 | 2016-06-17 | 1128150 | 2333785.3 | 235783 | 85118914.28 | 84417290.61 | 21282 | 30962.5 | 89.81% | 10.15% | 0.03876%
14080017 | Milwaukee Operations | 14080017 | 1 | Froedtert-ISIP Make Ready | 2016-01-04 | 2016-06-15 | 150000 | 887531 | 1080795 | 3536193.32 | 3515905.68 | 14488 | 15294.38 | 91.79% | 7.741% | 0.4675%
14140024 | Wind Energy I Operations | 14140024 | 1 | Slate Creek Wind | 2015-03-30 | 2016-06-01 | 0 | 5291 | 5267 | 36950914.8 | 37241113.19 | 75492.5 | 98770.5 | 75.13% | 24.87% | 0%
14050004 | Seattle Operations | 14050004 | 1 | Pacific Tower Improvements | 2014-05-15 | 2016-05-31 | 205368 | 43633.07 | 9423 | 11415903.4229 | 10376482.4 | 16305.25 | 13132.63 | 96.68% | 2.947% | 0.3769%
14090010 | Chicago Operations | 14090010 | 1 | AGSH AHU Refurbishment | 2015-06-01 | 2016-05-01 | 1000 | 7 | 0 | 3055595.27 | 3051169.82 | 420 | 1014 | 90.93% | 8.531% | 0.5424%
14090017 | Chicago Operations | 14090017 | 1 | Harper College Direct | 2014-12-01 | 2016-05-01 | 3000 | 97969 | 0 | 3898963.68 | 3667092.59 | 2307 | 2354.25 | 88.68% | 10.13% | 1.189%
14060013 | Denver Operations | 14060013 | 1 | City of Aurora-Iliff Station | 2015-03-15 | 2016-04-30 | 206000 | 1865980.9 | 1233265 | 9872095.6637 | 10565115.94 | 21430 | 48232 | 89.99% | 10.01% | 0%
14110004 | FCG Operations | 14110004 | 1 | DHS-USCG Training Ctr Pier 4 | 2015-03-06 | 2016-04-08 | 10652 | 18 | 0 | 15937763.36 | 16621138.07 | 0 | 756.5 | 81.89% | 18.11% | 0%
14030009 | Minneapolis Operations | 14030009 | 1 | Westminster Church - Open Door | 2014-01-29 | 2016-03-17 | 0 | 372 | 0 | 78225.7 | 139584.12 | 8 | 383 | 96.74% | 3.264% | 0%
14050009 | Portland Operations | 14050009 | 1 | Nike TV Highway Warehouse | 2015-11-02 | 2016-03-04 | 210000 | 569 | 0 | 1950357 | 1767233.36 | 31 | 344.73 | 100% | 0% | 0%
14060029 | Denver Operations | 14060029 | 1 | Ft Collins DDA-Old Town | 2015-03-26 | 2016-02-29 | 0 | 168689.07 | 97836 | 2730418.2183 | 3553654.43 | 9625.87 | 21406.05 | 82.75% | 17.25% | 0%
14050013 | Seattle Operations | 14050013 | 1 | UWT McDonald Renovations | 2014-11-10 | 2016-02-28 | 53773 | 84789 | 54501 | 8877598.555 | 7417648.03 | 12663.5 | 11143.99 | 89.87% | 10% | 0.1256%
14145004 | Solar and Emerging Renewables Operations | 14145004 | 1 | OCI-Alamo Solar V | 2014-08-11 | 2016-02-27 | 120279600 | 47031316.95 | 22012894 | 76015715.9754 | 75086381.88 | 675943.91 | 717246.14 | 87.18% | 12.82% | 0.001046%
14148007 | Civil Group Operations | 14148007 | 1 | REG I-Shannon Civil | 2014-09-01 | 2016-01-31 | 0 | 668895 | 611106 | 8553587.261 | 7437448.95 | 37402 | 23568.5 | 83.25% | 16.75% | 0%
14060025 | Denver Operations | 14060025 | 1 | CU-Folsom Parking Garage | 2014-10-01 | 2016-01-29 | 210000 | 1344065 | 793825 | 21449173 | 21236483.74 | 56250.24 | 53613 | 81.43% | 18.55% | 0.01492%
14030048 | Minneapolis Operations | 14030048 | 1 | MOA - North Garden Renovation | 2015-01-01 | 2016-01-15 | 111835 | 81384.0041 | 0 | 13950491.26 | 13502534.68 | 14821 | 14004.5 | 80.53% | 19.38% | 0.08569%
14060024 | Denver Operations | 14060024 | 1 | Woodward-Headquarters | 2014-11-06 | 2016-01-14 | 60000 | 6692232 | 120003 | 20346127.95 | 19023429.7 | 11339 | 26567 | 91.55% | 8.447% | 0%
14148001 | Civil Group Operations | 14148001 | 1 | Sanford Medical (Mpls) - Civil | 2014-03-10 | 2015-12-31 | 0 | 1132671 | 1132034 | 11024511.04 | 11142179.68 | 31740 | 48241.5 | 71.46% | 27.92% | 0.6193%
14148006 | Civil Group Operations | 14148006 | 1 | Solar-Alamo V Civil | 2014-09-01 | 2015-12-31 | 0 | 161069 | 160952 | 2975017.83 | 2874952.79 | 10299.5 | 7306.5 | 82.77% | 17.23% | 0%
14060018 | Denver Operations | 14060018 | 1 | Dominion Water-Sanitation | 2014-11-30 | 2015-12-31 | 0 | 22 | 0 | 0 | 0
14080018 | Milwaukee Operations | 14080018 | 1 | AHC-Aurora Summit Data Center | 2015-06-11 | 2015-12-31 | 17915 | 269537 | 104649 | 9397426.151 | 8523966.49 | 7012 | 5429 | 94.57% | 4.9% | 0.5342%
14146003 | Power Delivery Solutions Operations | 14146003 | 1 | MCC-Clarington HVT | 2014-05-01 | 2015-12-31 | 0 | 0 | 0 | 9640 | 9640.66
14146003-110 | Power Delivery Solutions Operations | 14146003-110 | 1 | REG Canada-Clarington HVT | 2014-05-01 | 2015-12-31 | 0 | 8 | 0 | 77355 | 67162.17
14146004 | Power Delivery Solutions Operations | 14146004 | 1 | MCC-Majestic & Meyer HVT | 2014-06-01 | 2015-12-31 | 0 | 0 | 0 | 5640 | 5640.43
14146004-110 | Power Delivery Solutions Operations | 14146004-110 | 1 | REG Canada-Majestic HVT | 2014-06-01 | 2015-12-31 | 0 | 8 | 0 | 70861 | 53003.72
14146005 | Power Delivery Solutions Operations | 14146005 | 1 | MCC-Trout Creek HVT | 2014-06-01 | 2015-12-31 | 0 | 0 | 0 | 3902 | 3902.11
14146005-110 | Power Delivery Solutions Operations | 14146005-110 | 1 | REG Canada-Trout Creek HVT | 2014-06-01 | 2015-12-31 | 0 | 8 | 0 | 68161 | 48524.49
14050002 | Seattle Operations | 14050002 | 1 | Providence-Small Projects | 2014-04-03 | 2015-12-31 | 1347 | 47115.8 | 0 | 5116514.51 | 4985761.65 | 6302 | 8267.34 | 90.8% | 8.667% | 0.5322%
14050010 | Seattle Operations | 14050010 | 1 | UWT Tioga & MDS Bldg Renovatio | 2015-08-30 | 2015-12-31 | 55000 | 11 | 0 | 163699.16 | 156102.99
14140010 | Wind Energy I Operations | 14140010 | 1 | Relight-Meridien Wind | 2015-03-15 | 2015-12-31 | 0 | 2 | 0 | 12154 | 34586.45
14140012 | Wind Energy I Operations | 14140012 | 1 | GE Power & Water-GE Wind | 2014-10-08 | 2015-12-31 | 0 | 801 | 193 | 3381492 | 2946513.76 | 163935 | 40054.5 | 82.39% | 17.56% | 0.04993%
14080001 | Milwaukee Operations | 14080001 | 1 | MDI - Hotel Commonwealth Exp. | 2014-07-21 | 2015-12-15 | 152082 | 2 | 0 | 49608546.81 | 50156415.61 | 0 | 4069.84 | 92.81% | 7.089% | 0.09828%
14140016 | Wind Energy I Operations | 14140016 | 1 | Sunwind Energy - Doyle Wind | 2015-04-01 | 2015-12-01 | 0 | 0 | 0 | 20660 | 22919.08
14030042 | Minneapolis Operations | 14030042 | 1 | North Pad Office - MOA Office | 2014-10-30 | 2015-11-30 | 181831 | 6 | 584567 | 24240248.84 | 23787912.72 | 21540 | 22114.14 | 81.13% | 18.43% | 0.4432%
14147004-110 | Wind Energy I Operations | 14147004-110 | 1 | Grand Valley LTD-Grand Valley | 2014-06-27 | 2015-11-30 | 0 | 0 | 0 | 13766 | 1206.97
14030018 | Minneapolis Operations | 14030018 | 1 | Agribank FCB - Tenant Improve | 2014-03-17 | 2015-11-20 | 7400 | 16993 | 0 | 878562.8116 | 719504.38 | 1969 | 1590.5 | 92.8% | 7.199% | 0%
14150008 | Sports + Entertainment Group Operations | 14150008 | 1 | PSU-Lasch Bldg-Phase I | 2015-03-01 | 2015-11-12 | 6300 | 0 | 0 | 2419307.7 | 2360474
14060001 | Denver Operations | 14060001 | 1 | Charles Schwab-Denver Campus | 2014-01-09 | 2015-11-05 | 670685 | 1830920.82 | 687059 | 78381470.81 | 75609518.15 | 110742.67 | 111081.99 | 86.21% | 13.79% | 0%
14140007 | Wind Energy I Operations | 14140007 | 1 | South Plains Wind | 2015-04-01 | 2015-11-01 | 0 | 10971 | 7895 | 55185356.37 | 54058585.87 | 105339 | 102009.25 | 75.33% | 24.67% | 0%
14090016 | Chicago Operations | 14090016 | 1 | Advocate GS Firemain Repl. | 2014-09-15 | 2015-10-31 | 0 | 0 | 0 | 402894 | 403086.33
14140013 | Wind Energy I Operations | 14140013 | 1 | NJR-Alexander Wind | 2015-06-01 | 2015-10-31 | 0 | 1613 | 1231 | 17636914 | 17750774.43 | 23835 | 25296 | 63.65% | 28.36% | 7.989%
14060014 | Denver Operations | 14060014 | 1 | Mortenson-Denv Office Remodel | 2015-02-16 | 2015-10-09 | 25052 | 391.03 | 0 | 3270199.08 | 32386.8 | 1866 | 1084 | 95.94% | 4.059% | 0%
14120003 | Discontinued Groups | 14120003 | 1 | Hayward Data Center LBA Realty | 2014-11-05 | 2015-10-09 | 147000 | 3 | 0 | 17755226.3 | 16667306.01
14150007 | Sports + Entertainment Group Operations | 14150007 | 1 | Tampa Bay Lightning - Amalie | 2015-06-15 | 2015-10-08 | 73495 | 1573 | 0 | 17478044.2744 | 17520071.53 | 0 | 4328.5 | 67.17% | 26.44% | 6.388%
14040011 | Phoenix Operations | 14040011 | 1 | DFS-Carpet Replacement | 2014-11-01 | 2015-10-01 | 0 | 0 | 0 | 1049055.79 | 1047980.81
14150002 | Sports + Entertainment Group Operations | 14150002 | 1 | Mort/GE J - Stadium N End Zone | 2014-12-01 | 2015-09-30 | 0 | 0 | 0 | 3487890 | 3551673.49 | 0 | 8979.55 | 78.15% | 21.4% | 0.4455%
14150002-155 | Sports + Entertainment Group Operations | 14150002-155 | 1 | KSU - North End Zone | 2014-05-01 | 2015-09-30 | 0 | 22459 | 0 | 55897335.68 | 53142179.97 | 26240 | 10628.11 | 77.74% | 22.26% | 0%
14147003 | Wind Energy I Operations | 14147003 | 1 | MCC-Trout Creek Wind PSC | 2014-01-14 | 2015-09-30 | 0 | 0 | 0 | 28321 | 28321.07
14147003-110 | Wind Energy I Operations | 14147003-110 | 1 | Leader Resources-Trout Creek | 2014-01-14 | 2015-09-30 | 0 | 1 | 0 | 175743 | 164168.72
14120002 | Data Center Operations | 14120002 | 1 | PTC UPS Rplcmt & Elec Upgr | 2014-09-15 | 2015-09-25 | 0 | 32931 | 0 | 15098948.29 | 14213825.27 | 7292.07 | 6037.49 | 97.83% | 2.17% | 0%
14030029 | Minneapolis Operations | 14030029 | 1 | BCBS -DC Stabilization Phase 2 | 2014-06-09 | 2015-09-11 | 6300 | 1494 | 0 | 3518068.54 | 3391267.86 | 2680 | 2649.8 | 94.4% | 4.963% | 0.6416%
14146007 | Power Delivery Solutions Operations | 14146007 | 1 | Solar-Alamo V HVT | 2015-02-14 | 2015-08-21 | 0 | 205392 | 33987 | 3019372.55 | 2712718.8 | 7946 | 5174.5 | 87.18% | 12.82% | 0%
14030052 | Minneapolis Operations | 14030052 | 1 | MCTC - Workforce Prog Renovat | 2015-05-11 | 2015-08-14 | 0 | 37587 | 32898 | 2687423.72 | 2433258.61 | 6251 | 4868.18 | 97.68% | 1.982% | 0.3389%
14030051 | Minneapolis Operations | 14030051 | 1 | U of MN - Centennial Hall HVAC | 2015-01-15 | 2015-08-14 | 235525 | 236268 | 0 | 9557549.57 | 9602781.27 | 13923 | 10727.45 | 88.02% | 11.98% | 0%
14060004 | Denver Operations | 14060004 | 1 | CU-Boulder Athletics Complex | 2014-05-01 | 2015-08-01 | 0 | 4590269.82 | 902045 | 145444737.15 | 161385313.74 | 216768.74 | 393937.25 | 81.21% | 18.79% | 0%
14146002-110 | Power Delivery Solutions Operations | 14146002-110 | 1 | REG Canada-St. Columban HVT | 2014-01-10 | 2015-07-31 | 0 | 212097 | 0 | 15797292 | 16487613.56
14140001 | Wind Energy I Operations | 14140001 | 1 | Balko Wind LLC- Balko Wind | 2014-10-01 | 2015-07-31 | 0 | 11034.85 | 8501 | 45992204.8588 | 45040394.78 | 103787 | 114018 | 82.39% | 17.61% | 0%
14140005 | Wind Energy I Operations | 14140005 | 1 | EDF-Pilot Hill Wind | 2014-07-01 | 2015-07-03 | 0 | 7887 | 5128 | 77129390.78 | 87618710.89 | 83836 | 115109.98 | 65.52% | 21.85% | 12.63%
14148003 | Civil Group Operations | 14148003 | 1 | REG I-Balko Civil | 2014-08-15 | 2015-07-01 | 0 | 1254760 | 961981 | 9339893.4449 | 7404607.2 | 43088.35 | 39067.5 | 77.02% | 22.98% | 0%
14080014 | Milwaukee Operations | 14080014 | 1 | Froedtert-1st Floor Pharmacy | 2015-01-19 | 2015-07-01 | 1000 | 32949 | 0 | 1252211 | 1235910.12 | 1967 | 1686 | 93.77% | 5.931% | 0.2966%
14080015 | Milwaukee Operations | 14080015 | 1 | Froedtert-3rd Cath Lab 1&2 Ren | 2015-01-19 | 2015-07-01 | 1000 | 6045 | 0 | 237759 | 239268.34 | 503 | 338.5 | 70.75% | 29.25% | 0%
14080014-064 | Mortenson Direct Operations | 14080014-064 | 1 | Froedtert-Direct 1st Flr Phrmc | 2015-01-19 | 2015-07-01 | 0 | 0 | 0 | 87016.35 | 87016.35
14080015-064 | Mortenson Direct Operations | 14080015-064 | 1 | Froedtert-Direct 3rd Cath Lab | 2015-01-19 | 2015-07-01 | 1000 | 0 | 0 | 7236 | 7236
14090005 | Chicago Operations | 14090005 | 1 | Lakefront Athletic Complex | 2013-10-01 | 2015-06-30 | 553000 | 0 | 0 | 278453 | 256549.54
14060016 | Denver Operations | 14060016 | 1 | Park Creek-Filing 44 | 2014-07-28 | 2015-06-30 | 0 | 545 | 0 | 55059 | 56021.94 | 175 | 187.5 | 98.93% | 1.067% | 0%
14030043 | Minneapolis Operations | 14030043 | 1 | Allina Health-2014 Annual Cont | 2014-01-01 | 2015-06-30 | 0 | 0 | 0 | 0.01 | 29257404.55 | 0 | 127551.54 | 88.76% | 10.09% | 1.151%
14145006 | Solar and Emerging Renewables Operations | 14145006 | 1 | Sunpower-Quinto Solar | 2014-07-25 | 2015-06-09 | 135590400 | 544354.12 | 271265 | 21525316.005 | 21328272.18 | 125455.13 | 139011 | 89.87% | 9.696% | 0.4356%
14148010 | Civil Group Operations | 14148010 | 1 | REG I-Macksburg Civil Add'l 3 | 2014-10-01 | 2015-06-01 | 0 | 12 | 12 | 760158.27 | 801039.3 | 721 | 1703 | 68.09% | 30.5% | 1.409%
14080013 | Milwaukee Operations | 14080013 | 1 | S.C.Johnson-Courtyrd Restoratn | 2014-09-02 | 2015-06-01 | 41358 | 73073.0875 | 0 | 1632135.6375 | 1609306.05 | 2458 | 3551.5 | 88.69% | 11.08% | 0.2253%
14140014 | Wind Energy I Operations | 14140014 | 1 | MidAmerican-Macksburg Add'l 3 | 2013-10-21 | 2015-06-01 | 0 | 211969 | 0 | 4097047.19 | 3592241.34 | 0 | 4109.5 | 63.2% | 26.04% | 10.77%
14050003 | Seattle Operations | 14050003 | 1 | Yahoo GQ Pond and Lift Station | 2014-07-10 | 2015-05-31 | 2100 | 561.47 | 0 | 3720998.4396 | 3711947.44 | 1330.47 | 1328.04 | 100% | 0% | 0%
14030016 | Minneapolis Operations | 14030016 | 1 | Mayo Clinic Square-Base Build | 2014-03-07 | 2015-05-29 | 146519 | 341111.9 | 253478 | 22250346.23 | 21966534.48 | 39423.5 | 39313.07 | 96.44% | 3.332% | 0.2264%
14030036 | Minneapolis Operations | 14030036 | 1 | Allina -ANW East Tower Upgrade | 2014-11-19 | 2015-05-15 | 17215 | 18123 | 0 | 3559698.84 | 3597117.94 | 10041 | 10794.6 | 92.84% | 6.624% | 0.5373%
14030049 | Minneapolis Operations | 14030049 | 1 | Park Nicollet - Methodist Hosp | 2015-04-01 | 2015-05-08 | 55000 | 0 | 0 | 90701 | 92464.66 | 0 | 24 | 100% | 0% | 0%
14080019-064 | Mortenson Direct Operations | 14080019-064 | 1 | Froedtert-Direct 1st Fl WC EVS | 2015-01-15 | 2015-05-08 | 1000 | 0 | 0 | 13088 | 13088
14145014 | Solar and Emerging Renewables Operations | 14145014 | 1 | SunPower-Hooper Solar | 2014-12-01 | 2015-04-30 | 58046400 | 148469.1361 | 100956 | 2678804.9691 | 2120392.34 | 13718.8 | 10643.5 | 86.24% | 13.76% | 0%
14030055 | Minneapolis Operations | 14030055 | 1 | Twins Ballpark - 2015 Improve | 2014-12-15 | 2015-04-10 | 4500 | 31581 | 0 | 1739078 | 1701226.8 | 3022 | 4091.5 | 92.66% | 7.344% | 0%
14080019 | Milwaukee Operations | 14080019 | 1 | Froedtert-1st Flr. W.C. EVS Rm | 2015-01-15 | 2015-04-01 | 1000 | 8965 | 0 | 196288 | 189644.4 | 638 | 559 | 92.58% | 7.424% | 0%
14090004 | Chicago Operations | 14090004 | 1 | Residential/Life Safety | 2014-05-12 | 2015-03-31 | 0 | 144262.34 | 24978 | 5190573.37 | 4377438.56 | 10325.5 | 8431.86 | 98.91% | 0.9666% | 0.1186%
14090006 | Chicago Operations | 14090006 | 1 | Hudson ATS Replacement | 2014-03-01 | 2015-03-31 | 20000 | 16 | 0 | 989973 | 905451.25
14060026 | Denver Operations | 14060026 | 1 | Leprino-Food Hangar | 2014-10-06 | 2015-03-31 | 34525 | 408443 | 18746 | 4509248.35 | 4519427.74 | 11009.1 | 12807 | 82.84% | 17.16% | 0%
14080006 | Milwaukee Operations | 14080006 | 1 | AHC-St. Luke's IR BiPlane Rm 1 | 2015-01-05 | 2015-03-27 | 862 | 2079.27 | 0 | 632186.27 | 582744.18 | 764 | 775 | 89.1% | 10.9% | 0%
14030039 | Minneapolis Operations | 14030039 | 1 | TRIA ASC Renovation | 2014-09-10 | 2015-03-15 | 8400 | 1154.34 | 0 | 1739058.14 | 1674264.72 | 2163 | 2097 | 92.89% | 5.961% | 1.144%
14148009 | Civil Group Operations | 14148009 | 1 | REG I-Route 66 Civil | 2014-08-15 | 2015-02-28 | 0 | 834292 | 710523 | 5355935.9152 | 4689174.19 | 25177.3 | 25582.5 | 79.11% | 20.89% | 0%
14030022 | Minneapolis Operations | 14030022 | 1 | U of MN - Dwan Imaging Center | 2014-06-16 | 2015-02-28 | 7000 | 8722.36 | 0 | 2213713.79 | 2264764.52 | 2426 | 3195.5 | 99.77% | 0.2347% | 0%
14145011 | Solar and Emerging Renewables Operations | 14145011 | 1 | Fulton Mill Solar Farm, LLC-Fu | 2014-10-27 | 2015-02-28 | 2996460 | 9862 | 0 | 4758195 | 4817923.41
14050007 | Seattle Operations | 14050007 | 1 | Apple Inc-Castle Rock | 2014-06-06 | 2015-02-26 | 129200 | 20 | 0 | 56855870.24 | 56184031.96 | 0 | 527.5 | 72.04% | 27.39% | 0.5687%
14145001 | Solar and Emerging Renewables Operations | 14145001 | 1 | OCI-Alamo Solar III | 2014-01-27 | 2015-02-07 | 6747300 | 830161.26 | 1029926 | 6349063 | 6459588.96 | 42955 | 53357.25 | 92.09% | 7.899% | 0.01499%
14030050 | Minneapolis Operations | 14030050 | 1 | UMN - Physics Lab 481 Comp | 2014-12-01 | 2015-02-06 | 1400 | 249 | 0 | 205963 | 196998.28 | 213 | 181.5 | 100% | 0% | 0%
14040012 | Phoenix Operations | 14040012 | 1 | SRP-CUB Roof Replacement | 2014-10-31 | 2015-01-31 | 20000 | 0 | 0 | 169280.32 | 164699.55
14040013 | Phoenix Operations | 14040013 | 1 | SRP-CUB Mechanical Improve. | 2014-11-07 | 2015-01-31 | 20000 | 4 | 0 | 769491.89 | 764710.3 | 32 | 0 | 0% | 0% | 0%
14145010 | Solar and Emerging Renewables Operations | 14145010 | 1 | Dooley Solar Farm LLC, Dooley | 2014-09-16 | 2015-01-31 | 998820 | 3400 | 0 | 1749371 | 1794380.73
14145012 | Solar and Emerging Renewables Operations | 14145012 | 1 | Plum Solar Farm, LLC-Plum Sola | 2014-10-21 | 2015-01-28 | 1997640 | 6591 | 0 | 3193547 | 3259634.01
14145013 | Solar and Emerging Renewables Operations | 14145013 | 1 | Stillmore Solar Farm, LLC-Stil | 2014-10-21 | 2015-01-27 | 998820 | 3379 | 0 | 1679915 | 1753617.32
14080020 | Milwaukee Operations | 14080020 | 1 | WHEDA - Door Installation | 2014-12-29 | 2015-01-08 | 40 | 0 | 0 | 3490 | 2601.25 | 0 | 21 | 100% | 0% | 0%
14030032 | Minneapolis Operations | 14030032 | 1 | Fridley Land - Northern Stacks | 2014-07-14 | 2015-01-02 | 213000 | 823397 | 311899 | 10825927.23 | 10658924.79 | 13210 | 15752.7 | 88.71% | 11.14% | 0.1524%
14090007 | Chicago Operations | 14090007 | 1 | Blue Sky Professional Services | 2014-03-01 | 2014-12-31 | 0 | 0 | 0 | 19250 | 17536.86
14090008 | Chicago Operations | 14090008 | 1 | Guestroom Renovation PH2 | 2014-03-01 | 2014-12-31 | 0 | 200 | 0 | 73170 | 64614.18 | 0 | 115 | 93.91% | 5.652% | 0.4348%
14090009 | Chicago Operations | 14090009 | 1 | SAIC Interior Renovation | 2013-10-01 | 2014-12-31 | 0 | 18975 | 1880 | 1056665 | 1091220.98 | 492 | 1493.79 | 92.94% | 6.795% | 0.2678%
14090997 | Chicago Operations | 14090997 | 1 | Chicago Equip Facility 2014 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -991469.06
14090999 | Chicago Operations | 14090999 | 1 | Chicago Closed Projects 2014 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -1830.7 | 0 | 166 | 100% | 0% | 0%
14090013 | Chicago Operations | 14090013 | 1 | Advocate Collaboration Space | 2014-07-01 | 2014-12-31 | 5000 | 0 | 0 | 89784 | 74194.55 | 274 | 273.74 | 93.42% | 4.749% | 1.827%
14148002 | Civil Group Operations | 14148002 | 1 | REG I-Windthorst II Civil | 2014-04-01 | 2014-12-31 | 0 | 271542.15 | 176834 | 2119876.443 | 2453695.94 | 11905.5 | 10638.5 | 90.09% | 9.912% | 0%
14148011 | Civil Group Operations | 14148011 | 1 | Solar-Hooper Civil (Close) |  | 2014-12-31 | 0 | 38877 | 32051 | 506191 | 0 | 3190 | 0 | 0% | 0% | 0%
14148014 | Civil Group Operations | 14148014 | 1 | REG I-Mariah Del Norte 2 | 2014-12-19 | 2014-12-31 | 0 | 13 | 4 | 35758 | 37362.85 | 120 | 87.5 | 100% | 0% | 0%
14148015 | Civil Group Operations | 14148015 | 1 | REG I-Mariah South 3 Civil | 2014-12-01 | 2014-12-31 | 0 | 12 | 4 | 38400 | 52068.25 | 120 | 100 | 100% | 0% | 0%
14148019 | Civil Group Operations | 14148019 | 1 | Solar-Hooper Civil |  | 2014-12-31 | 0 | 38881 | 6800 | 517250.74 | 257594.37 | 3222 | 840 | 76.9% | 22.38% | 0.7143%
14148020 | Civil Group Operations | 14148020 | 1 | REG I-Mariah NW Phase 1 Civil | 2014-12-18 | 2014-12-31 | 0 | 13 | 4 | 36480 | 46597.91 | 120 | 165 | 100% | 0% | 0%
14148997 | Civil Group Operations | 14148997 | 1 | Civil-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -509053.82
14148999 | Civil Group Operations | 14148999 | 1 | Civil-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 8471.04
14060002 | Denver Operations | 14060002 | 1 | Sterling Ranch Dev-Consulting | 2014-01-13 | 2014-12-31 | 0 | 0 | 0 | 347024 | 338194.27 | 28 | 21.5 | 65.12% | 34.88% | 0%
14110997 | FCG Operations | 14110997 | 1 | FCG 2014 Equipment Facility | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0 | -30018.99
14110999 | FCG Operations | 14110999 | 1 | FCG 2014 Closed Projects | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0 | -452756.88
14080010 | Milwaukee Operations | 14080010 | 1 | AHC-Data Center Assessmnt (PS) | 2014-04-01 | 2014-12-31 | 0 | 0 | 0 | 63283.64 | 63283.64
14080997 | Milwaukee Operations | 14080997 | 1 | Milwaukee - Equip Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | -433968 | -526112
14080999 | Milwaukee Operations | 14080999 | 1 | Milwaukee Closed Job Costs '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -110108.4 | 0 | 137.5 | 95.27% | 4.727% | 0%
14080016 | Milwaukee Operations | 14080016 | 1 | Guardian IG-New Facility Precn |  | 2014-12-31 | 240000 | 0 | 0 | 38000 | 43416.44
14030001 | Minneapolis Operations | 14030001 | 1 | FUMC-Annual Contract 2014 |  | 2014-12-31 | 0 | 35645.86 | 0 | 1857782.61 | 1841238.89 | 8880 | 10100 | 95.98% | 2.733% | 1.292%
14030035 | Minneapolis Operations | 14030035 | 1 | MOA-West Parking Ramp Repairs | 2014-06-03 | 2014-12-31 | 0 | 63 | 0 | 216725 | 230249.3 | 1877 | 901 | 73.58% | 26.42% | 0%
14030997 | Minneapolis Operations | 14030997 | 1 | 2014 Mpls Equip Facility Recog | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -2279740.5
14030999 | Minneapolis Operations | 14030999 | 1 | MAM - 2014 Closed Projects | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 26496.22 | 0 | 2617 | 93.73% | 6.267% | 0%
14030044 | Minneapolis Operations | 14030044 | 1 | HCMC Generator Addition | 2014-11-03 | 2014-12-31 | 400 | 6279.17 | 0 | 735678.57 | 711527.87 | 1863 | 1795.5 | 98.33% | 1.671% | 0%
14030020 | Minneapolis Operations | 14030020 | 1 | RMC - Nuclear Medicine Equip. | 2014-03-17 | 2014-12-31 | 800 | 370 | 0 | 120471.94 | 121670.3 | 394 | 448 | 96.99% | 3.013% | 0%
14030008 | Minneapolis Operations | 14030008 | 1 | Mortenson HQ Projects | 2014-01-22 | 2014-12-31 | 2400 | 513.65 | 0 | 1954997.4 | 0.42 | 1996 | 2291 | 77.28% | 21.8% | 0.9166%
14030015 | Minneapolis Operations | 14030015 | 1 | Mall of America - West Market | 2014-02-23 | 2014-12-31 | 107215 | 360034.572 | 0 | 10208750 | 9801370.77 | 9756.14 | 9084.5 | 82.11% | 17.89% | 0%
14040008 | Phoenix Operations | 14040008 | 1 | PCH at MGMC Discharge Canopy |  | 2014-12-31 | 0 | 0 | 0 | 0.01 | 0 | 0 | -800 | 100% | 0% | 0%
14040997 | Phoenix Operations | 14040997 | 1 | Phoenix-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 30220.23
14040999 | Phoenix Operations | 14040999 | 1 | Phoenix-Closed Projects 2014 | 2013-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 177.56
14050011 | Portland Operations | 14050011 | 1 | Nike Small Projects | 2014-12-01 | 2014-12-31 | 0 | 1 | 0 | 15630 | 17268.93 | 27 | 0 | 0% | 0% | 0%
14146001 | Power Delivery Solutions Operations | 14146001 | 1 | REG I-Windthorst II HVT | 2014-04-14 | 2014-12-31 | 0 | 1516582 | 221293 | 5451800.3 | 5933595.82 | 7615 | 22211.5 | 78.09% | 21.91% | 0%
14146997 | Power Delivery Solutions Operations | 14146997 | 1 | HVT-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -1027453.41
14146999 | Power Delivery Solutions Operations | 14146999 | 1 | HVT-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 47761.54 | 0 | 88.5 | 93.79% | 6.215% | 0%
14050997 | Seattle Operations | 14050997 | 1 | Seattle Equip Facility 2014 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -2391119.27
14050999 | Seattle Operations | 14050999 | 1 | Seattle 2014 Closed Projects | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -6098.86
14145997 | Solar and Emerging Renewables Operations | 14145997 | 1 | Solar-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -284987.62
14145999 | Solar and Emerging Renewables Operations | 14145999 | 1 | Solar-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 8277.52 | 0 | 1786.74 | 100% | 0% | 0%
14145007 | Solar and Emerging Renewables Operations | 14145007 | 1 | Granby Road Solar LLC-Granby | 2014-08-18 | 2014-12-31 | 1015560 | 202 | 0 | 4147182 | 4285136.62 | 0 | 15.5 | 96.77% | 3.226% | 0%
14140017 | Wind Energy I Operations | 14140017 | 1 | Pattern Panhandle 3-Panhandle | 2014-12-12 | 2014-12-31 | 0 | 18 | 3 | 257671 | 238666.3 | 36 | 19.5 | 0% | 100% | 0%
14140997 | Wind Energy I Operations | 14140997 | 1 | US Wind-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -3142190.97
14140999 | Wind Energy I Operations | 14140999 | 1 | US Wind-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 144852.24
14147001 | Wind Energy I Operations | 14147001 | 1 | MCC-Clarington Wind PSC | 2014-01-14 | 2014-12-31 | 0 | 0 | 0 | 32909 | 32909.43
14147001-110 | Wind Energy I Operations | 14147001-110 | 1 | Leader Resources-Clarington | 2014-01-14 | 2014-12-31 | 0 | 1 | 0 | 230282 | 231362.03
14147002 | Wind Energy I Operations | 14147002 | 1 | MCC-Majestic & Meyer Wind PSC | 2014-01-14 | 2014-12-31 | 0 | 0 | 0 | 13827 | 13826.74
14147002-110 | Wind Energy I Operations | 14147002-110 | 1 | Leader Resources-Majestic | 2014-01-14 | 2014-12-31 | 0 | 1 | 0 | 193887 | 187878.49
14147997 | Wind Energy I Operations | 14147997 | 1 | REG Canada-Equip Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 0
14147999 | Wind Energy I Operations | 14147999 | 1 | Wind I Can-Closed Proj '14 US | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0 | -75.45
14147999-110 | Wind Energy I Operations | 14147999-110 | 1 | REG Canada-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 437098.79
14030026 | Minneapolis Operations | 14030026 | 1 | Fairview Ridges - Master Agree | 2014-04-01 | 2014-12-30 | 0 | 2120.14 | 0 | 480673.23 | 461781.3 | 1079 | 1250.64 | 96% | 3.998% | 0%
14030038 | Minneapolis Operations | 14030038 | 1 | Hudson MRI Replacement | 2014-08-04 | 2014-12-26 | 512 | 228.2 | 0 | 173186.2 | 158497.6 | 290 | 311 | 96.95% | 3.055% | 0%
14145008 | Solar and Emerging Renewables Operations | 14145008 | 1 | Twiss Street Solar, LLC-Twiss | 2014-08-18 | 2014-12-15 | 1953000 | 202 | 0 | 4072941 | 4272243.45 | 0 | 245.5 | 80.04% | 19.55% | 0.4073%
14148004 | Civil Group Operations | 14148004 | 1 | FCG-Galena Park Civil |  | 2014-12-10 | 0 | 2102 | 9 | 436057 | 313232.02 | 1716 | 836 | 76.5% | 23.5% | 0%
14140008 | Wind Energy I Operations | 14140008 | 1 | Sherbino Mesa II-Sherbino Foun | 2014-07-07 | 2014-11-30 | 0 | 1545 | 1112 | 768439 | 617102.78 | 2058 | 1591 | 84.99% | 15.01% | 0%
14040007 | Phoenix Operations | 14040007 | 1 | SRP Board Conference Room | 2014-10-06 | 2014-11-26 | 431000 | 7171.54 | 0 | 428606.4 | 423236.57 | 0 | 0 | 0% | 0% | 0%
14146002 | Power Delivery Solutions Operations | 14146002 | 1 | MCC-St. Columban HVT | 2014-01-10 | 2014-11-10 | 0 | 0 | 0 | 765552 | 765552.68
14140003 | Wind Energy I Operations | 14140003 | 1 | Broadview Energy KW-Broadview | 2014-11-01 | 2014-11-01 | 0 | 0 | 0 | 15250 | 15233.02
14060021 | Denver Operations | 14060021 | 1 | City of Boulder-Airport | 2014-08-04 | 2014-10-31 | 0 | 1780 | 0 | 1132451.03 | 1020246.82 | 1138 | 821.5 | 75.35% | 24.65% | 0%
14030013 | Minneapolis Operations | 14030013 | 1 | Mayo Sports Clinic | 2014-04-07 | 2014-10-31 | 20000 | -823.43 | 4188 | 2995389 | 2931318.74 | 6411 | 5822.33 | 89.82% | 10.18% | 0%
14145017 | Solar and Emerging Renewables Operations | 14145017 | 1 | SunPower-Antelope Valley 2 | 2013-02-08 | 2014-10-31 | 0 | 69475.7021 | 22994 | 1264203.0109 | 1021839.76 | 17916.8 | 19876.25 | 89.54% | 8.599% | 1.864%
14140006 | Wind Energy I Operations | 14140006 | 1 | Trinity Hills Wind LLC-Trinity | 2014-07-07 | 2014-10-31 | 0 | 5839 | 3641 | 1804555.81 | 1949760.74 | 6438 | 7660 | 80.91% | 19.09% | 0%
14040010 | Phoenix Operations | 14040010 | 1 | AlaskaUSA-Branch Bank TI | 2014-10-01 | 2014-10-25 | 910 | 112 | 0 | 151229 | 141892.97
14030040 | Minneapolis Operations | 14030040 | 1 | Ridgeview Med Ctr-Hospice Rep. | 2014-09-08 | 2014-10-20 | 0 | 4 | 0 | 121226 | 120937.28 | 336 | 312 | 87.82% | 12.18% | 0%
14150001 | Sports + Entertainment Group Operations | 14150001 | 1 | Rushmore Plaza Civic Center | 2014-02-01 | 2014-10-20 | 0 | 0 | 0 | 78690 | 70688.08
14030021 | Minneapolis Operations | 14030021 | 1 | U of MN - Williams Arena Roof | 2014-06-05 | 2014-10-16 | 134388 | 6055.15 | 0 | 6325678.76 | 6318759.26 | 4155 | 3873.46 | 83.5% | 16.5% | 0%
14120001 | Data Center Operations | 14120001 | 1 | Eden Prairie Data Ctr Ph 3 & | 2014-01-14 | 2014-10-01 | 18885 | 28475.82 | 0 | 1868784 | 1795772.14 | 4035 | 3696.5 | 98.5% | 1.501% | 0%
14060003 | Denver Operations | 14060003 | 1 | UCCS-Stanton Round About | 2014-04-28 | 2014-10-01 | 0 | 49517 | 9525 | 905308 | 1136603.92 | 3384 | 7499 | 79.58% | 20.42% | 0%
14090012 | Chicago Operations | 14090012 | 1 | United Customer Service Center | 2014-07-15 | 2014-09-30 | 3000 | 216 | 0 | 1167544.43 | 1157540.43 | 867 | 1087.35 | 94.16% | 5.38% | 0.4598%
14080002 | Milwaukee Operations | 14080002 | 1 | ATC-Project Badger:Phase 0 | 2014-03-15 | 2014-09-30 | 500 | 36659 | 25832 | 4672991.71 | 4862204.23 | 3239 | 3454 | 93.82% | 6.181% | 0%
14030031 | Minneapolis Operations | 14030031 | 1 | CHC - Woodbury Clinic TI | 2014-05-22 | 2014-09-17 | 17661 | 39799.33 | 0 | 783344.25 | 795923.74 | 2784 | 2475 | 93.27% | 6.727% | 0%
14145005 | Solar and Emerging Renewables Operations | 14145005 | 1 | SunPower-Castaic Lake Solar | 2014-06-23 | 2014-09-15 | 4384800 | 85253.4702 | 80256 | 2472661.0002 | 2587785.18 | 12378 | 8117 | 99.66% | 0.3388% | 0%
14040006 | Phoenix Operations | 14040006 | 1 | PCH-East Valley Lab Remodel | 2014-08-25 | 2014-09-09 | 0 | 949 | 0 | 54117 | 51415.47
14090002 | Chicago Operations | 14090002 | 1 | Allstate Jacksonvl Restack 3 | 2013-10-01 | 2014-08-31 | 25000 | 10 | 0 | 3529426 | 3540577.01 | 1440 | 2259 | 73.75% | 26.25% | 0%
14040002 | Phoenix Operations | 14040002 | 1 | PCH-Mercy Gilbert Med Ctr | 2014-06-22 | 2014-08-31 | 809 | 4612.6 | 0 | 355140.92 | 352906.35 | 0 | 832 | 100% | 0% | 0%
14080009 | Milwaukee Operations | 14080009 | 1 | Historic Courteen Seed - Vault | 2014-07-02 | 2014-08-29 | 105 | 1 | 0 | 54813 | 47591.47 | 0 | 239 | 93.93% | 6.067% | 0%
14140009 | Wind Energy I Operations | 14140009 | 1 | General Electric-Schenectady | 2014-07-21 | 2014-08-25 | 0 | 98 | 78 | 581473.74 | 516170.51 | 2552 | 2789.5 | 72.88% | 27.12% | 0%
14030010 | Minneapolis Operations | 14030010 | 1 | Fairview Ridges-Ambulatory Sur | 2014-03-31 | 2014-08-15 | 14250 | 7999 | 0 | 3339471.29 | 3274408.71 | 3129 | 2698.36 | 95.11% | 4.892% | 0%
14040003 | Phoenix Operations | 14040003 | 1 | PCH-Signage Improvements | 2015-01-12 | 2014-08-15 | 0 | -300.44 | 0 | 38859.56 | 37180.73
14030007 | Minneapolis Operations | 14030007 | 1 | U of MN - Akerman Hall Impr | 2014-02-03 | 2014-07-31 | 120000 | 1082.33 | 0 | 1114412 | 1067357.14 | 1799 | 1807 | 98.67% | 1.328% | 0%
14140011 | Wind Energy I Operations | 14140011 | 1 | PPM Technical-Penescal Blade | 2014-07-22 | 2014-07-26 | 0 | 2 | 1 | 26756 | 23738.63 | 16 | 30 | 0% | 100% | 0%
14030014 | Minneapolis Operations | 14030014 | 1 | Cornell College-Residence Hall | 2014-05-14 | 2014-07-22 | 80561 | 51 | 0 | 4770945.14 | 4752109.78 | 2438 | 3507.6 | 95.62% | 4.376% | 0%
14030017 | Minneapolis Operations | 14030017 | 1 | AT&T - DAS Head-End Room - TCF | 2014-03-17 | 2014-06-30 | 850 | 2066 | 0 | 909466 | 865637.05 | 361 | 217 | 88.94% | 11.06% | 0%
14145003 | Solar and Emerging Renewables Operations | 14145003 | 1 | SunPower-China Secondment | 2014-04-10 | 2014-06-30 | 0 | 207 | 0 | 60278.66 | 33495.09 | 88 | 440 | 65.45% | 20.68% | 13.86%
14060008 | Denver Operations | 14060008 | 1 | Town of Lyons-Meadow Park | 2014-04-21 | 2014-06-17 | 0 | 12578 | 0 | 671013.28 | 742881.68 | 8 | 1433 | 80.46% | 19.54% | 0%
14080005 | Milwaukee Operations | 14080005 | 1 | Levy R&H LP-Chrome Tent @H-D | 2014-04-23 | 2014-05-30 | 15000 | 2305.09 | 0 | 93221 | 78662.22 | 250 | 195.5 | 90.79% | 9.207% | 0%
14030005 | Minneapolis Operations | 14030005 | 1 | U of MN - Hasselmo Hall | 2014-01-13 | 2014-05-30 | 5150 | 1153.05 | 0 | 543068 | 530849.89 | 752 | 864.56 | 99.07% | 0.9253% | 0%
14060007 | Denver Operations | 14060007 | 1 | Shawmut-MLBAM Instant Replay | 2014-04-11 | 2014-05-23 | 308 | 32 | 0 | 228824 | 204396.38 | 16 | 666 | 87.46% | 12.54% | 0%
14030012 | Minneapolis Operations | 14030012 | 1 | U of MN - Hasselmo - Robotics | 2014-03-03 | 2014-05-23 | 4300 | 5828.45 | 0 | 507966 | 505986.91 | 845 | 881.8 | 99.77% | 0.2268% | 0%
14140002 | Wind Energy I Operations | 14140002 | 1 | Milw-Acuity Flagpole Erection | 2014-04-24 | 2014-05-20 | 0 | 1 | 0 | 353171 | 482478.35 | 0 | 105.5 | 54.5% | 25.59% | 19.91%
14060012 | Denver Operations | 14060012 | 1 | Town of Lyons-NRCS | 2014-04-28 | 2014-05-14 | 0 | 0 | 0 | 61440 | 65206.44 | 0 | 84.5 | 73.37% | 26.63% | 0%
14030019 | Minneapolis Operations | 14030019 | 1 | Fairview Ridges - NICU Refresh | 2014-03-13 | 2014-05-13 | 4000 | 120.63 | 0 | 194879.38 | 191242.14 | 275 | 468.5 | 99.79% | 0.2134% | 0%
14030027 | Minneapolis Operations | 14030027 | 1 | Silliker Lab Remodel | 2014-02-27 | 2014-05-01 | 4900 | 190.29 | 0 | 128647 | 104556.5 | 424 | 123 | 100% | 0% | 0%
14140004 | Wind Energy I Operations | 14140004 | 1 | Iberdrola Renewables-Locust | 2014-04-17 | 2014-04-28 | 0 | 7 | 0 | 447930 | 396159.61 | 300 | 508.5 | 75.02% | 24.98% | 0%
14030004 | Minneapolis Operations | 14030004 | 1 | RMC TTMC 1st Fl Clinic 3rd Fl | 2014-01-06 | 2014-04-01 | 16338 | 5098.2 | 0 | 863056.44 | 864560.95 | 1867 | 1394.5 | 97.71% | 2.295% | 0%
14040001 | Phoenix Operations | 14040001 | 1 | Banner-Telemetry Monitoring | 2014-03-31 | 2014-03-25 | 350 | 0 | 0 | 38088 | 30180.97
14145002 | Solar and Emerging Renewables Operations | 14145002 | 1 | SunPower-Churchill Reno Solar | 2014-02-05 | 2014-03-05 | 0 | 160.58 | 0 | 187808.99 | 187967.2 | 802 | 872.5 | 86.88% | 13.12% | 0%
14030006 | Minneapolis Operations | 14030006 | 1 | UMPhysicians Park Plaza 4th | 2014-01-24 | 2014-01-29 | 1000 | -9.64 | 0 | 22247 | 20860.42 | 98.5 | 99.5 | 72.36% | 19.1% | 8.543%
14030003 | Minneapolis Operations | 14030003 | 1 | U of MN-Physicians Lower Lev | 2014-01-02 | 2014-01-24 | 3200 | 249.06 | 0 | 39182 | 39440.93 | 129.5 | 133.01 | 100% | 0% | 0%
14060997 | Denver Operations | 14060997 | 1 | Denver-EF-2014 | 2013-01-01 | 2013-12-31 | 0 | 0 | 0 | 0.01 | -2899870.78
14060999 | Denver Operations | 14060999 | 1 | Denver-Closed Projects 2014 | 2012-01-01 | 2012-12-31 | 0 | 0 | 0 | 0.01 | 110900.99 | 0 | 103.5 | 88.89% | 11.11% | 0%
14148005 | Civil Group Operations | 14148005 | 1 | Solar-Alamo III Civil | 2014-07-11 |  | 0 | 288416 | 158983 | 377520 | 291749.71 | 1977 | 1421 | 84.41% | 15.59% | 0%
14148008 | Civil Group Operations | 14148008 | 1 | Solar-Quinto Civil |  |  | 0 | 0 | 0 | 6662612 | 6664410.7
14148012 | Civil Group Operations | 14148012 | 1 | REG I-Panhandle 3 Civil | 2014-12-13 |  | 0 | 32488 | 18341 | 186000 | 111097.99 | 650 | 313.5 | 54.7% | 45.3% | 0%
14148013 | Civil Group Operations | 14148013 | 1 | REG I-Panhandle 4 Civil | 2014-12-15 |  | 0 | 32490 | 17422 | 135232 | 87030.27 | 580 | 277 | 61.73% | 38.27% | 0%
14148017 | Civil Group Operations | 14148017 | 1 | REG I-Route 66 II Civil | 2014-12-17 |  | 0 | 13 | 5 | 41760 | 22075.26 | 500 | 186.5 | 68.9% | 31.1% | 0%
14148018 | Civil Group Operations | 14148018 | 1 | REG I-Castro County Civil | 2014-12-17 |  | 0 | 14 | 8 | 31520 | 23298.4 | 200 | 70 | 7.143% | 92.86% | 0%
14400999 | Discontinued Groups | 14400999 | 1 | Discontinued-14 Closed |  |  | 0 | 0 | 0 | 0 | 2417990.83 | 0 | 20 | 40% | 60% | 0%
14030024 | Minneapolis Operations | 14030024 | 1 | Timberwolves/MCS - GC's | 2014-03-07 |  | 0 | 0 | 0 | 0.01 | -0.07 | 0 | 8530 | 89.7% | 10.19% | 0.1172%
14030025 | Minneapolis Operations | 14030025 | 1 | Abbott Hospital-Facilites Supp | 2014-04-03 |  | 0 | 0 | 0 | 70802 | 73591.79
14030034 | Minneapolis Operations | 14030034 | 1 | MOAC LLC - Small Projects 2014 | 2014-05-19 |  | 0 | 0 | 0 | 75720 | 74361.46 | 0 | 378.5 | 90.22% | 9.775% | 0%
14030011 | Minneapolis Operations | 14030011 | 1 | Betacom - AT&T Head End Room | 2014-02-25 |  | 700 | 16 | 0 | 573522 | 390754.9 | 962 | 666 | 91.74% | 8.258% | 0%
14030041 | Minneapolis Operations | 14030041 | 1 | TC United Way - Restroom Rem | 2014-10-13 |  | 958 | 9 | 0 | 336744.39 | 353638 | 1212 | 1127.5 | 94.46% | 5.543% | 0%
14030037 | Minneapolis Operations | 14030037 | 1 | MOA - SE Court Slab Infill | 2014-07-13 |  | 5000 | 20888.61 | 0 | 1251482.38 | 1181878.33 | 1115 | 737 | 79.78% | 20.22% | 0%
14030028 | Minneapolis Operations | 14030028 | 1 | Allina Health - West Health | 2014-03-10 |  | 10000 | 34 | 0 | 962410 | 985866.6 | 2542 | 2682.09 | 88.29% | 11.71% | 0%
14030030 | Minneapolis Operations | 14030030 | 1 | Kilbourne Group - Block 9 | 2014-03-01 |  | 445682 | 0 | 0 | 11574 | 17679.67
14030053 | Minneapolis Operations | 14030053 | 1 | Fridley Land-North. Stacks BAE | 2015-01-26 |  | 479000 | 143339 | 36627 | 12737225.38 | 12104260.5 | 6988 | 12616.18 | 95.78% | 4.134% | 0.08719%
14040004 | Phoenix Operations | 14040004 | 1 | Concourse-UofA Boingo Phase II |  |  | 0 | 0 | 0 | 0.01 | 0
14145016 | Solar and Emerging Renewables Operations | 14145016 | 1 | Northwirth-Mortenson HQ RooftC |  |  | 0 | 1713 | 0 | 111158 | 0 | 246 | 0 | 0% | 0% | 0%
14145018 | Solar and Emerging Renewables Operations | 14145018 | 1 | Northwirth-Mortenson HQ Roofto |  |  | 0 | 0 | 0 | 111158 | 0
14145009 | Solar and Emerging Renewables Operations | 14145009 | 1 | Chicopee River Solar, LLC-Chic |  |  | 2611080 | 202 | 0 | 5358475 | 5429033.24 | 0 | 113.5 | 81.94% | 15.86% | 2.203%
14150005 | Sports + Entertainment Group Operations | 14150005 | 1 | Boingo Wireless - KSU DAS | 2014-07-07 |  | 7500 | 0 | 0 | 0.01 | 78965.21
14150004 | Sports + Entertainment Group Operations | 14150004 | 1 | American Builders - Atl Braves | 2014-09-16 |  | 1100000 | 3 | 0 | 11667010.01 | 12940093.92 | 0 | 4261 | 76.41% | 21.3% | 2.288%
14150004-141 | Sports + Entertainment Group Operations | 14150004-141 | 1 | Cobb County - Atlanta Braves | 2014-09-16 |  | 1100000 | 0 | 0 | 600600984 | 0
14140018 | Wind Energy I Operations | 14140018 | 1 | Pattern Panhandle 4-Panhandle | 2014-12-12 |  | 0 | 16 | 3 | 190162 | 185795.55 | 36 | 10 | 0% | 100% | 0%
14140019 | Wind Energy I Operations | 14140019 | 1 | Orion Wind Resources-Castro | 2015-04-01 |  | 0 | 0 | 0 | 54300 | 53860.33
14140021 | Wind Energy I Operations | 14140021 | 1 | Mariah South LLC-Mariah South | 2014-12-18 |  | 0 | 0 | 0 | 63100 | 62400.79
14140022 | Wind Energy I Operations | 14140022 | 1 | Mariah North West LLC-Mariah 1 | 2014-12-18 |  | 0 | 0 | 0 | 63250 | 60274.16
14140023 | Wind Energy I Operations | 14140023 | 1 | Route 66 Wind II-Route 66 Wind | 2014-12-17 |  | 0 | 0 | 0 | 58628 | 58848.42
17110009 | FCG Operations | 17110009 | 1 | USDA SE Poultry Research Lab | 2017-10-15 | 2023-04-12 | 243000 | 95951.5 | 0 | 141118520.89 | 115443924.9 | 0 | 7368 | 80.45% | 19.29% | 0.2647%
17030050 | Minneapolis Operations | 17030050 | 1 | Genesis Silvis MCP Precon | 2018-12-01 | 2022-03-31 | 60000 | 0 | 0 | 33242.73 | 28417.61
17080026 | Milwaukee Operations | 17080026 | 1 | Kohler Kitchen & Bath HQ | 2019-05-01 | 2021-06-01 | 396000 | 2086 | 0 | 300000 | 421118.13
17146022 | Power Delivery Solutions Operations | 17146022 | 1 | Alice to Falfurrias | 2017-06-18 | 2021-04-30 | 0 | 2881634 | 571604 | 49114524.541 | 53858765.99 | 150638.05 | 180730.8 | 76.23% | 23.77% | 0%
17110002 | FCG Operations | 17110002 | 1 | Ft Knox Medical Clinic Rplc | 2017-09-08 | 2021-04-26 | 101606 | 0 | 0 | 58698852.92 | 58428861.07 | 0 | 794.5 | 91.13% | 8.874% | 0%
17080024 | Milwaukee Operations | 17080024 | 1 | Froedtert - Ambulatory | 2018-03-19 | 2021-03-22 | 193000 | 1754786.06 | 539804 | 46283943.32 | 46061599.78 | 67628.12 | 81031.11 | 84.74% | 13.65% | 1.607%
17060024 | Denver Operations | 17060024 | 1 | Evergreen Dev-Clear Creek Cro | 2017-09-01 | 2020-12-31 | 0 | 224 | 0 | 362995.7 | 261181.33 | 0 | 0 | 0% | 0% | 0%
17080007 | Milwaukee Operations | 17080007 | 1 | AHC-AMC Sheboygan County | 2018-09-01 | 2020-12-31 | 462185 | 6549485.06 | 2867375 | 241401451.2122 | 241661661.04 | 149269.78 | 189431.34 | 92.9% | 6.961% | 0.1346%
17110010 | FCG Operations | 17110010 | 1 | UPH-BEQ Bldg 3606 Renovation | 2018-03-12 | 2020-12-22 | 94778 | 0 | 0 | 26558987.1168 | 25716489.37 | 0 | 505 | 80.1% | 19.9% | 0%
17050019 | Seattle Operations | 17050019 | 1 | AC Marriott - Cascade Station | 2017-11-01 | 2020-12-01 | 0 | 0 | 0 | 0 | 35771.88
17030040 | Minneapolis Operations | 17030040 | 1 | Blake-Hopkins Infrastructure | 2018-03-01 | 2020-10-01 | 0 | 12899 | 11742 | 3166193.52 | 3150811.33 | 3266 | 4903 | 95.39% | 4.609% | 0%
17141026, 18146020, 19148025 | Wind Energy I Operations | 17141026 | 1 | Blazing Star 2 Wind | 2019-06-03 | 2020-09-08 | 0 | 11066.54 | 9299 | 103916276.1272 | 95589229.23 | 152753.1 | 108977 | 79.49% | 19.58% | 0.9208%
17030005 | Minneapolis Operations | 17030005 | 1 | Coralville-IRL Hockey Arena | 2018-08-13 | 2020-08-25 | 261000 | 1557459.88 | 808432 | 54867481.3374 | 56197100.97 | 78303.15 | 68507.63 | 88.25% | 11.62% | 0.1328%
17150004 | Sports + Entertainment Group Operations | 17150004 | 1 | Las Vegas Raiders | 2017-03-01 | 2020-07-31 | 0 | 0 | 239800 | 65046496.35 | 64507956.33 | 0 | 256237.99 | 81.94% | 14.1% | 3.962%
17150004-163 | Sports + Entertainment Group Operations | 17150004-163 | 1 | LV Stadium Company-LV Stadium | 2017-11-01 | 2020-07-20 | 0 | 18438 | 0 | 1474028005.2644 | 1480541033.34 | 0 | 0 | 0% | 0% | 0%
17060013 | Denver Operations | 17060013 | 1 | WelArm-EGOS Hotel Remodel | 2018-06-01 | 2020-06-19 | 135000 | 394046.4 | 34320.5 | 37437703.0225 | 42339900.54 | 5844.5 | 38515.8 | 91.66% | 8.337% | 0%
17050007 | Portland Operations | 17050007 | 1 | Nike World Headquarters Bldg 6 | 2017-08-15 | 2020-06-05 | 692087 | 163806.52 | 29567 | 272790290.9213 | 286795512.57 | 39365.5 | 92320.49 | 91.03% | 8.684% | 0.286%
17050021, 17050008 | Seattle Operations | 17050008 | 11 | South Lake Union Hotel | 2018-02-14 | 2020-05-29 | 0 | 674335.89 | 535843 | 83475021.6041 | 106648790.45 | 72508.24 | 104488.45 | 87.81% | 11.38% | 0.8135%
17110013 | FCG Operations | 17110013 | 1 | P966 Special Ops Forces Fac | 2018-04-16 | 2020-04-19 | 81540 | 619 | 0 | 42828727.28 | 42816711.58
17150011 | Sports + Entertainment Group Operations | 17150011 | 1 | LCFC Preconstruction | 2017-10-01 | 2020-03-31 | 0 | 0 | 0 | 48550 | 8615.56
17145002 | Mortenson Energy Services-Operations | 17145002 | 1 | Alamo 6 O&M Solar | 2017-02-17 | 2020-01-17 | 140313600 | 36729 | 10254 | 4261806.004 | 4243034.52 | 41007 | 34780.75 | 91.97% | 8.029% | 0%
17145016 | Mortenson Energy Services-Operations | 17145016 | 1 | Pearl O&M - MES | 2017-08-21 | 2020-01-01 | 0 | 5594 | 608 | 1347265 | 860825.9 | 8518 | 7125 | 91.67% | 8.33% | 0%
17050017 | Seattle Operations | 17050017 | 1 | Tualatin Interceptor No 6493 | 2018-04-15 | 2019-12-31 | 0 | 47 | 0 | 30383569.916 | 30324183.95 | 46 | 480 | 100% | 0% | 0%
17110019 | FCG Operations | 17110019 | 1 | USACE Site R Substat 3N1 Rplc | 2018-07-25 | 2019-12-26 | 0 | 9001 | 0 | 7032852.9051 | 6891871
17146021 | Power Delivery Solutions Operations | 17146021 | 1 | Ross-Highland 69kV | 2017-07-17 | 2019-12-13 | 0 | 2903 | 0 | 21803082.61 | 22585965.82
17060034, 20060007 | Denver Operations | 17060034 | 1 | Rocky Mtn Public - Buell Media | 2016-08-01 | 2019-11-22 | 85000 | 935081.5 | 576071 | 28016986.3533 | 29331224.12 | 39691.7 | 49833.5 | 90.9% | 9.096% | 0%
17141025 | Wind Energy I Operations | 17141025 | 1 | Blazing Star 1 Wind | 2018-08-06 | 2019-11-18 | 0 | 6498 | 6181 | 65929837.473 | 69859197.64 | 95662 | 118013.3 | 67.46% | 30.23% | 2.308%
17060022 | Denver Operations | 17060022 | 1 | Charles Schwab-Phase 3 | 2018-04-16 | 2019-11-04 | 430036 | 1862475.26 | 1430007 | 45224270.6383 | 45653872.6 | 72521.98 | 85419.97 | 87.08% | 12.92% | 0%
17030051 | Minneapolis Operations | 17030051 | 1 | MA-Upper Campus Re-Build | 2018-06-01 | 2019-10-31 | 0 | 1183431.42 | 947717 | 25615420.6819 | 25699242.21 | 57716.14 | 51552.98 | 92.26% | 7.713% | 0.02328%
17141012 | Wind Energy I Operations | 17141012 | 1 | Fenner Repower Wind | 2017-08-01 | 2019-10-31 | 0 | 45 | 0 | 1113916.12 | 851297.48 | 466 | 691 | 84.37% | 15.63% | 0%
17080023 | Milwaukee Operations | 17080023 | 1 | MarquetteUniv-12th&Wells Demo | 2017-11-20 | 2019-09-02 | 4120 | 853 | 0 | 912885.05 | 854662.5 | 694 | 201.5 | 90.07% | 3.97% | 5.955%
17110007 | FCG Operations | 17110007 | 1 | DON-Repair Explosive Hndlg Wha | 2017-06-29 | 2019-08-31 | 104942 | 0 | 0 | 22648672.73 | 21725521.74 | 4600 | 7034.85 | 99.88% | 0.1208% | 0%
17080017 | Milwaukee Operations | 17080017 | 1 | AHC-Pharmacy Upgrades | 2018-01-18 | 2019-08-31 | 1500 | 27651.91 | 0 | 4302381.99 | 4223022.26 | 5248.9 | 4644.5 | 90.39% | 9.28% | 0.3337%
17030028 | Minneapolis Operations | 17030028 | 1 | Surmodics-Contract Coating | 2017-10-02 | 2019-08-31 | 6500 | 11677 | 0 | 1453130.4 | 1322736.16 | 746 | 730 | 96.99% | 3.014% | 0%
17060036 | Denver Operations | 17060036 | 1 | Chatfield Reservoir - Modifica | 2017-12-01 | 2019-08-30 | 0 | 391798.02 | 312439 | 43023104.4323 | 46346253.91 | 48099.8 | 61946 | 82.38% | 17.62% | 0.004843%
17040010 | Phoenix Operations | 17040010 | 1 | Great Wolf Lodge Scottsdale | 2018-01-15 | 2019-08-30 | 394500 | 0 | 0 | 83335656.12 | 92532681.45 | 8775 | 13640 | 83.01% | 16.99% | 0%
17080009 | Milwaukee Operations | 17080009 | 1 | JMKAC - Art Preserve | 2018-04-10 | 2019-08-02 | 60000 | 570456.02 | 468835 | 23927573.102 | 24314034.65 | 26819.38 | 30756.12 | 94.58% | 5.384% | 0.03089%
17110016 | FCG Operations | 17110016 | 1 | USACE 902nd OSC Ft Riley | 2019-05-06 | 2019-07-31 | 1500 | 0 | 0 | 101787.85 | 89483.74
17030048 | Minneapolis Operations | 17030048 | 1 | Skogman Companies | 2017-08-01 | 2019-07-31 | 40000 | 25881.75 | 5997 | 9325170.1805 | 9491293.93 | 3298.1 | 9597.5 | 80.14% | 18.66% | 1.203%
17110011 | FCG Operations | 17110011 | 1 | USACE Portal A Security Upgr | 2018-08-01 | 2019-07-09 | 2000 | 1799 | 0 | 1807963 | 1693342.11
17141016, 17146018, 17148014 | Wind Energy I Operations | 17141016 | 1 | Rio Bravo Wind-Longroad Energy | 2018-05-15 | 2019-06-30 | 0 | 4703 | 4619 | 57503194.1889 | 66070214.57 | 102415 | 143465.98 | 80.61% | 19.39% | 0%
17030023 | Minneapolis Operations | 17030023 | 1 | Blake Dining Hall Addition | 2018-04-16 | 2019-06-28 | 32200 | 254254.04 | 22893 | 6934502.4 | 6994483.88 | 15750.4 | 21796.12 | 95.32% | 4.368% | 0.312%
17050006 | Seattle Operations | 17050006 | 1 | Clover Park Technical College | 2018-04-23 | 2019-06-27 | 63000 | 657223.51 | 256496 | 30764763.4727 | 29575694.05 | 20562.5 | 15450.26 | 97.01% | 2.964% | 0.02589%
18060010, 17060007, 17060006, 16060029 | Denver Operations | 17060006 | 21 | Westfield-AEG Venue | 2017-11-01 | 2019-06-21 | 0 | 1145833.8 | 612493 | 35768818.0459 | 33837030.44 | 71821.5 | 82327 | 88.39% | 11.61% | 0%
17141016, 17146018, 17148014 | Civil Group Operations | 17148014 | 21 | Rio Bravo Civil | 2017-08-21 | 2019-05-31 | 0 | 1402736 | 1328140 | 7072957 | 9471318.67 | 27678.5 | 47620 | 78.22% | 21.78% | 0%
17110008 | FCG Operations | 17110008 | 1 | CyberComm Pershing Hall | 2017-11-27 | 2019-05-31 | 5000 | 0 | 0 | 2583972.57 | 2452676.45 | 0 | 933.1 | 98.93% | 1.072% | 0%
17141016, 17146018, 17148014 | Power Delivery Solutions Operations | 17146018 | 11 | Rio Bravo Wind - HVT | 2018-03-16 | 2019-05-18 | 0 | 706664 | 425865 | 15465617.89 | 15415980.17 | 34607.5 | 31716.25 | 83.79% | 16.18% | 0.03153%
17080015 | Milwaukee Operations | 17080015 | 1 | AHC-Misc. Projects 2017-2018 | 2017-08-14 | 2019-05-17 | 0 | 626 | 66 | 1099720.0008 | 838790.86 | 4759 | 3495 | 88.43% | 9.928% | 1.645%
17110012 | FCG Operations | 17110012 | 1 | USACE INSCOM Scalable Mod Data | 2018-08-20 | 2019-05-10 | 8000 | 0 | 0 | 466058.67 | 515349.16
17110020 | FCG Operations | 17110020 | 1 | USACE Site C HEMP UPS Rplmt | 2018-03-08 | 2019-05-09 | 2000 | 3870 | 0 | 1821106.93 | 1690794.99
17080028, 16080027 | Milwaukee Operations | 17080028 | 1 | Marquette University - AHPRC | 2018-02-26 | 2019-05-01 | 46950 | 519363.48 | 306082 | 16315798.448 | 17295196.68 | 17085.7 | 24091.81 | 91.73% | 7.587% | 0.6787%
17110014 | FCG Operations | 17110014 | 1 | USACE Herndon II Office Reno | 2018-05-29 | 2019-04-30 | 2117 | 0 | 0 | 366211.58 | 353856.87
17040009 | Phoenix Operations | 17040009 | 1 | Polk & Central Apartment Tower | 2017-11-06 | 2019-04-30 | 250999 | 0 | 0 | 0.01 | 33832.98
17150003 | Sports + Entertainment Group Operations | 17150003 | 1 | Mizzou Memorial Stadium Expan | 2018-03-01 | 2019-04-23 | 207000 | 334920.86 | 0 | 81630437.0862 | 88649756.3 | 54729.7 | 76952.5 | 98.09% | 1.791% | 0.1202%
17030038 | Minneapolis Operations | 17030038 | 1 | CentraCare-LP Wellness | 2018-08-06 | 2019-04-05 | 13500 | 28450 | 0 | 2978153.24 | 2915690.29 | 5089 | 6121.49 | 93.2% | 6.6% | 0.196%
17090010 | Chicago Operations | 17090010 | 1 | QTS Chicago - Hogan | 2017-08-01 | 2019-03-31 | 0 | 0 | 1008 | 5537108 | 5452614.02 | 0 | 2154.36 | 96.33% | 3.667% | 0%
17080029 | Milwaukee Operations | 17080029 | 1 | AHC - Summit VLCC Pharmacy | 2018-07-09 | 2019-03-31 | 475 | 14468.5 | 8314 | 1429425.97 | 1349994.59 | 1306.8 | 1728 | 80.38% | 18.17% | 1.447%
17000003-040, 17060025, 17060014, 18060057, 20060016 | Denver Operations | 17060014 | 25 | MDI-BioSciences 3 | 2017-12-01 | 2019-03-29 | 90000 | 1154392.59 | 600720 | 24030314.2057 | 24759643.17 | 35895.4 | 56072.97 | 89.44% | 10.56% | 0%
17080021 | Milwaukee Operations | 17080021 | 1 | AHC - Kenosha 22nd Ave Clinic | 2018-03-23 | 2019-03-28 | 6000 | 43572 | 32317 | 1522340.17 | 1464477.56 | 2434.4 | 2020.5 | 89.63% | 10.02% | 0.3464%
17110015 | FCG Operations | 17110015 | 1 | USACE 21st BDE Shielding - MD | 2017-11-01 | 2019-03-15 | 0 | 0 | 0 | 183502 | 175022.48
17110023 | FCG Operations | 17110023 | 1 | USACE 21st DBE Shielding VA | 2017-11-01 | 2019-03-15 | 0 | 0 | 0 | 800918 | 783567.66
17110024 | FCG Operations | 17110024 | 1 | USACE 21st BDE Shielding PA | 2017-11-01 | 2019-03-15 | 0 | 0 | 0 | 212752 | 198766.43
17050021, 17050008 | Seattle Operations | 17050021 | 1 | SLU Hotal Mockup Rooms & Cor | 2018-01-02 | 2019-03-04 | 0 | 406 | 2 | 293973.72 | 258745.6 | 445 | 295 | 94.41% | 5.593% | 0%
17145018, 18148014 | Solar and Emerging Renewables Operations | 17145018 | 1 | Montross Solar | 2018-06-25 | 2019-03-01 | 27973000 | 1848190 | 1791627 | 16073374.99 | 18949456.36 | 61802 | 108984.33 | 81.49% | 18.48% | 0.0367%
17080020 | Milwaukee Operations | 17080020 | 1 | AHC - Grafton VLCC Pharmacy | 2018-05-15 | 2019-02-28 | 455 | 13509.5 | 9227 | 947724.37 | 937306.13 | 1179.6 | 1035 | 77.1% | 20.19% | 2.705%
17030011 | Minneapolis Operations | 17030011 | 1 | MAM-HQ Campus-W Bldg Tenant | 2017-01-09 | 2019-02-28 | 15000 | 60 | 17030091 | 4087637 | 26751162.63 | 4987 | 33347.67 | 91.95% | 7.617% | 0.4348%
17040018 | Phoenix Operations | 17040018 | 1 | UofA-ICA Indoor Sports Center | 2018-04-13 | 2019-02-20 | 67000 | 174 | 0 | 13800934.81 | 14265999.35 | 0 | 1682.5 | 57.06% | 35.93% | 7.013%
17030043 | Minneapolis Operations | 17030043 | 1 | Swervo-N Loop Office Bldg | 2017-10-16 | 2019-02-15 | 461299 | 2649148 | 2162379 | 23671121.047 | 23571685.92 | 90428.28 | 92794.93 | 89.22% | 10.71% | 0.0625%
17030031 | Minneapolis Operations | 17030031 | 1 | Faegre Baker Daniels-TI | 2017-08-21 | 2019-02-05 | 220000 | 217 | 0 | 7748785.69 | 7320761.19 | 3177 | 5525 | 78.93% | 18.39% | 2.679%
17030020 | Minneapolis Operations | 17030020 | 1 | MHS-Fort Snelling Visitor Ctr | 2018-10-01 | 2019-02-01 | 50000 | 214898.69 | 174957 | 19051693.75 | 19133459.78 | 30302 | 31030.5 | 98.57% | 1.413% | 0.01289%
17080019 | Milwaukee Operations | 17080019 | 1 | AHC - Grafton MainPharmReno | 2018-07-20 | 2019-01-31 | 465 | 8810 | 5101 | 507584.64 | 495820.1 | 531 | 488 | 89.86% | 10.14% | 0%
17080014 | Milwaukee Operations | 17080014 | 1 | AHC - Mukwonago | 2018-07-11 | 2019-01-24 | 15000 | 130289.41 | 67909 | 5597012.67 | 5513608.14 | 7618.6 | 7416.84 | 95.74% | 4.247% | 0.01348%
17040020 | Phoenix Operations | 17040020 | 1 | Brewers-Maryvale Renovation | 2018-03-26 | 2019-01-15 | 106800 | 2 | 21 | 43605607.35 | 45195701.11 | 6964 | 6945.5 | 71.47% | 28.53% | 0%
17050005 | Seattle Operations | 17050005 | 1 | citizenM Hotel - San Francisco | 2017-09-01 | 2019-01-11 | 92240 | 56 | 0 | 380965.43 | 386027.12 | 56 | 48 | 100% | 0% | 0%
17030029 | Minneapolis Operations | 17030029 | 1 | UMP-DB Master Agreement | 2017-06-05 | 2019-01-01 | 0 | 1 | 0 | 468723.9474 | 479363.59 | 1378.66 | 826 | 89.29% | 7.446% | 3.269%
17145007, 17148005 | Civil Group Operations | 17148005 | 11 | Upton II Solar - Civil | 2017-04-10 | 2018-12-31 | 0 | 337362 | 339443 | 5534210.6 | 5479461.06 | 18001 | 24963 | 80.82% | 19.18% | 0%
18060010, 17060007, 17060006, 16060029 | Denver Operations | 17060007 | 11 | Westfield-4120 Parcel B&C | 2017-09-01 | 2018-12-31 | 0 | 0 | 0 | 92087.86 | 99904.42
17060029 | Denver Operations | 17060029 | 1 | 76 Commerce Bldg 5 | 2017-11-15 | 2018-12-31 | 265000 | 357943 | 1549204 | 29316324.93 | 27199304.53 | 27406.5 | 39561.5 | 83.21% | 16.79% | 0%
17030001 | Minneapolis Operations | 17030001 | 1 | FUMC-Annual Contract 2017 | 2017-01-01 | 2018-12-31 | 0 | 0 | 0 | 6063010.79 | 6063010.78 | 0 | 14662.72 | 95.08% | 3.881% | 1.043%
17030042 | Minneapolis Operations | 17030042 | 1 | CentraCare Health-Master Ag | 2017-10-09 | 2018-12-31 | 25000 | 707 | 3469 | 1123006.03 | 1096332.67 | 2954 | 2509.71 | 90.46% | 9.304% | 0.2391%
17030030 | Minneapolis Operations | 17030030 | 1 | BSE-Branch Support Center | 2017-08-24 | 2018-12-31 | 119618 | 129574.5 | 96843 | 30057198.2108 | 30079162.36 | 22444.5 | 15859.38 | 91.99% | 8.011% | 0%
17050012 | Portland Operations | 17050012 | 1 | Nike M73 | 2017-06-12 | 2018-12-31 | 0 | 2933 | 0 | 17813236.295 | 17598440.14 | 0 | 161.5 | 97.52% | 2.477% | 0%
17141023, 17146028, 17148018 | Power Delivery Solutions Operations | 17146028 | 11 | Rattlesnake Creek Wind - HVT | 2018-04-04 | 2018-12-31 | 0 | 1872351 | 523223 | 17500658.2 | 17177126.48 | 56340 | 29543 | 76.31% | 23.55% | 0.1354%
17145003 | Solar and Emerging Renewables Operations | 17145003 | 1 | Mt Signal 3 - 93LF 8ME,LLC | 2017-07-24 | 2018-12-31 | 328080450 | 22506190 | 22312567 | 318586500.35 | 306242313.05 | 646353 | 731176.86 | 91.45% | 8.177% | 0.378%
17141023, 17146028, 17148018 | Wind Energy I Operations | 17141023 | 1 | Rattlesnake Creek Wind | 2017-11-06 | 2018-12-31 | 0 | 14424 | 13827 | 96229956.4413 | 99998588.22 | 146201 | 198476.7 | 74.24% | 24.81% | 0.9561%
17110017 | FCG Operations | 17110017 | 1 | USACE FILS Phase II | 2017-11-01 | 2018-12-21 | 0 | 564 | 0 | 11902679.69 | 11110589.59 | 0 | 982.5 | 74.91% | 25.09% | 0%
17050009 | Portland Operations | 17050009 | 1 | Kaiser Small Works Facilities | 2017-12-04 | 2018-12-18 | 0 | 174 | 0 | 31958 | 19298.35 | 102 | 40 | 100% | 0% | 0%
18148011, 17141024, 18146004 | Wind Energy I Operations | 17141024 | 11 | Solomon Fork 345kV Wind | 2018-04-10 | 2018-12-17 | 0 | 20035 | 179964 | 85008674.135 | 88120482.34 | 109294 | 160791.25 | 78.22% | 21.78% | 0%
17040008 | Phoenix Operations | 17040008 | 1 | Scottsdale Booster 56 & 116 | 2017-04-03 | 2018-12-10 | 0 | 153 | 88 | 1435592.992 | 1698806.37 | 3754 | 5149 | 96.11% | 3.894% | 0%
17141013, 18148024, 19146004 | Wind Energy I Operations | 17141013 | 1 | Palo Alto Wind | 2017-09-05 | 2018-12-09 | 0 | 9191 | 7214 | 125124809.31 | 118830478.12 | 204505 | 186473.5 | 65.66% | 31.45% | 2.891%
17146019 | Power Delivery Solutions Operations | 17146019 | 1 | Pearl MPT MES - HVT | 2017-12-01 | 2018-12-01 | 0 | 12876 | 350 | 178650 | 171418.78 | 406 | 130 | 79.62% | 20.38% | 0%
17141022, 17148020 | Wind Energy I Operations | 17141022 | 1 | Green River Wind | 2017-11-11 | 2018-12-01 | 0 | 49410 | 5503 | 85493225.35 | 89731638.19 | 118415 | 152201.13 | 69.76% | 29.16% | 1.083%
17030010 | Minneapolis Operations | 17030010 | 1 | NWA-HQ Campus-W Bldg Link | 2018-05-21 | 2018-11-30 | 15000 | 65757.03 | 8 | 1932396.62 | 1980370.65 | 3986.7 | 4080 | 85.5% | 14.5% | 0%
17060041 | Denver Operations | 17060041 | 1 | SCL-OBGYN Stapleton | 2018-01-22 | 2018-11-26 | 0 | 808 | 35 | 846011.4 | 844825.06 | 1714 | 1926.5 | 90.11% | 9.888% | 0%
17030027 | Minneapolis Operations | 17030027 | 1 | JAUM-University Park Center | 2017-10-01 | 2018-11-09 | 47155 | 194407.16 | 118019 | 6353637.43 | 6313936.3 | 16013.9 | 14623.26 | 98.65% | 1.354% | 0%
18090005, 17090008 | Chicago Operations | 17090008 | 11 | United North Airfield | 2017-05-01 | 2018-11-06 | 250000 | 310383 | 5550359 | 104949161.44 | 106542645.1 | 17538 | 28524.61 | 82.19% | 14.27% | 3.548%
17150012 | Sports + Entertainment Group Operations | 17150012 | 1 | PSU Lasch Position Room | 2017-12-06 | 2018-11-03 | 9300 | 209 | 0 | 2173848.71 | 2168599.59
16090007, 17090001 | Chicago Operations | 17090001 | 11 | NU Welsh Ryan Arena Ren. | 2017-02-03 | 2018-11-01 | 210647 | 160406.6 | 115018 | 94689601.2146 | 97633214.79 | 25928 | 21925.89 | 87.74% | 10.83% | 1.428%
17060011 | Denver Operations | 17060011 | 1 | Park Creek-Filing 53 | 2017-04-06 | 2018-10-31 | 0 | 0 | 0 | 340814 | 339949.79 | 80 | 895.5 | 92.35% | 7.649% | 0%
17060020 | Denver Operations | 17060020 | 1 | SCL-LMC Infrastructure 2017 | 2017-09-01 | 2018-10-31 | 0 | 11648 | 8106 | 4919691.4432 | 4915113.49 | 3656.18 | 4018.5 | 88.52% | 11.48% | 0%
17060033 | Denver Operations | 17060033 | 1 | Park Creek-Aurora 3 | 2017-09-12 | 2018-10-31 | 0 | 0 | 0 | 599735 | 661639.15 | 450 | 2217 | 98.24% | 1.759% | 0%
17146010 | Power Delivery Solutions Operations | 17146010 | 1 | Mount Signal 3 Solar - HVT | 2017-09-21 | 2018-10-31 | 0 | 181 | 0 | 9512455.01 | 9490404.92
16000009-040, 17060008 | Denver Operations | 17060008 | 15 | BCSP RINO-HUB RiNo Station | 2017-04-10 | 2018-10-19 | 437879 | 2766319.19 | 1144389 | 57020133.4078 | 59525490.03 | 82733.7 | 121654.65 | 87.04% | 12.96% | 0%
17030041 | Minneapolis Operations | 17030041 | 1 | SCCR-Sign Reloc & Sidewalk | 2017-10-02 | 2018-10-12 | 750 | 69 | 0 | 232323.76 | 215315.06 | 484 | 711.5 | 52.28% | 39.28% | 8.433%
17080022 | Milwaukee Operations | 17080022 | 1 | Froedtert - Inpatient Imaging | 2017-11-10 | 2018-10-01 | 14000 | 79773.53 | 53992 | 5049230.26 | 5044588.59 | 7048.6 | 7162.5 | 87.89% | 10.51% | 1.599%
17030052 | Minneapolis Operations | 17030052 | 1 | NS VII-Office Whse | 2018-04-01 | 2018-10-01 | 200000 | 602386.26 | 18496 | 14732632.3405 | 12130890.29 | 24615.59 | 13373.13 | 93.74% | 6.263% | 0%
17150009 | Sports + Entertainment Group Operations | 17150009 | 1 | PSU - Lasch Auditorium Reno | 2017-07-20 | 2018-09-30 | 0 | 0 | 0 | 851400.04 | 845422.35 | 16 | 0 | 0% | 0% | 0%
17040011 | Phoenix Operations | 17040011 | 1 | SRP PAB Phase 3 West Wing | 2017-12-18 | 2018-09-28 | 100000 | 6 | 0 | 21292082.7548 | 21390597.89 | 6244 | 7551 | 94.6% | 5.395% | 0%
17040003 | Phoenix Operations | 17040003 | 1 | Airport WRF Grit Removal | 2017-03-06 | 2018-09-24 | 0 | 92263 | 31313 | 5669268.7612 | 6752075.79 | 13826 | 20034.5 | 95.86% | 4.143% | 0%
17141032 | Wind Energy I Operations | 17141032 | 1 | Beaver Creek Wind Phase 2 | 2018-04-23 | 2018-09-15 | 0 | 7457 | 5068 | 56860227.4705 | 55416142.29 | 83945 | 89715.5 | 59% | 36.62% | 4.381%
17080013 | Milwaukee Operations | 17080013 | 1 | WEC - PSB/PSA Renovations | 2018-01-08 | 2018-09-14 | 38915 | 100643.5 | 66461 | 6376561.645 | 6188127.07 | 5637.9 | 6887.67 | 88.6% | 10.59% | 0.813%
17145014 | Solar and Emerging Renewables Operations | 17145014 | 1 | Legislative Office Building | 2017-12-04 | 2018-09-14 | 132480 | 86 | 0 | 210326 | 177251.6
17030036 | Minneapolis Operations | 17030036 | 1 | Dunwoody College Reno | 2017-11-15 | 2018-08-31 | 10000 | 172451.74 | 47794 | 6094922.4815 | 5353880.02 | 12293.5 | 10179.09 | 96.74% | 3.262% | 0%
17030009 | Minneapolis Operations | 17030009 | 1 | NWA-HQ Campus-Parking | 2017-01-09 | 2018-08-31 | 80000 | 0 | 0 | 743095.48 | 735554.86 | 1032 | 686.76 | 87.4% | 12.6% | 0%
17050011 | Portland Operations | 17050011 | 1 | Newberg ASC | 2017-12-06 | 2018-08-31 | 0 | 84774.69 | 54699 | 9051667.335 | 9184177.34 | 6261.13 | 4753.41 | 91.69% | 8.142% | 0.1683%
17150002 | Sports + Entertainment Group Operations | 17150002 | 1 | Gaylord Rockies DAS | 2017-04-01 | 2018-08-31 | 0 | 0 | 0 | 3443624.02 | 2679276.15
17150005 | Sports + Entertainment Group Operations | 17150005 | 1 | Milwaukee Bucks DAS | 2017-05-15 | 2018-08-31 | 0 | 0 | 0 | 5742710.52 | 5065832.36 | 0 | 312.83 | 100% | 0% | 0%
17080025 | Milwaukee Operations | 17080025 | 1 | HGA-Great Lakes Office Reno | 2017-11-15 | 2018-08-10 | 41020 | 217833.65 | 201024 | 3564198.26 | 3514323.95 | 7886 | 7568.5 | 89.39% | 10.52% | 0.09249%
17110018 | FCG Operations | 17110018 | 1 | USACE Fort Sill Building 2703 | 2018-01-02 | 2018-07-31 | 2000 | 734 | 0 | 234567.92 | 225289.88
17030008 | Minneapolis Operations | 17030008 | 1 | NWA-HQ Campus-W Bldg Imp | 2017-01-09 | 2018-07-31 | 55000 | 0 | 0 | 1758479 | 1646192.66 | 48 | 526 | 96.39% | 3.612% | 0%
17040004 | Phoenix Operations | 17040004 | 1 | Deer Valley WTP Rehab | 2017-05-01 | 2018-07-31 | 0 | 2378 | 0 | 3476635.54 | 3562675.9 | 2297 | 5381.5 | 88.87% | 11.13% | 0%
17146013 | Power Delivery Solutions Operations | 17146013 | 1 | Opossum Creek Synchro Cond | 2017-10-30 | 2018-07-31 | 0 | 169030 | 195431 | 5655358.4398 | 6148084.5 | 26106.6 | 20294.15 | 77.9% | 22.1% | 0%
17000003-040, 17060025, 17060014, 18060057, 20060016 | Denver Operations | 17060025 | 15 | FRA-Bioscience 3 Offsites | 2018-05-21 | 2018-07-27 | 90000 | 4306 | 6812 | 286133.5984 | 268493.97 | 852.97 | 1153.5 | 83.09% | 16.91% | 0%
17110022 | FCG Operations | 17110022 | 1 | USACE FANX 2 Sidewalk Improv | 2018-04-23 | 2018-07-11 | 500 | 0 | 0 | 112323 | 113191.03
17080012 | Milwaukee Operations | 17080012 | 1 | AHC-ED Remodel Kenosha | 2017-10-23 | 2018-07-06 | 2779 | 18652 | 32 | 1257497.7 | 1175250.6 | 2533.9 | 2794 | 89.96% | 9.789% | 0.2505%
17030016 | Minneapolis Operations | 17030016 | 1 | Scouting - N Star Coun Ld Cen | 2017-05-01 | 2018-07-02 | 42000 | 255522.61 | 270918 | 8271368.075 | 8680897.73 | 17421.1 | 19421.32 | 97.6% | 2.397% | 0%
17060030 | Denver Operations | 17060030 | 1 | Park Creek-Filing 55 | 2017-08-25 | 2018-06-30 | 0 | 0 | 0 | 199651 | 189148.97 | 60 | 127.5 | 96.86% | 3.137% | 0%
17040013 | Phoenix Operations | 17040013 | 1 | Gilbert Rd Water Rehab | 2017-09-15 | 2018-06-30 | 0 | 1837 | 0 | 2167697 | 2405792.25 | 2029 | 3457 | 83.22% | 16.78% | 0%
17145011, 17148008 | Solar and Emerging Renewables Operations | 17145011 | 1 | Terning CSG - MONTSUN LLC | 2017-06-05 | 2018-06-30 | 7081425 | 208860 | 205188 | 9664442.76 | 9142075.88 | 27903 | 25284 | 80.9% | 13.99% | 5.108%
17145010 | Solar and Emerging Renewables Operations | 17145010 | 1 | Murphy CSG - WAVESUN LLC | 2017-05-30 | 2018-06-30 | 7379775 | 254951 | 231028 | 9789051.82 | 10252761.72 | 29352 | 27673 | 80.3% | 15.47% | 4.233%
17050010 | Portland Operations | 17050010 | 1 | Kaiser SMC QR Heads Install | 2017-12-26 | 2018-06-18 | 0 | 23047 | 2658 | 787369.07 | 578702.43 | 3320 | 1625 | 92.74% | 0% | 7.262%
17148004 | Civil Group Operations | 17148004 | 1 | Beaver Creek Civil | 2017-05-05 | 2018-06-01 | 0 | 311279 | 308174 | 7818748.4666 | 7791228.25 | 33704 | 27730 | 76.53% | 23.05% | 0.4219%
17060026 | Denver Operations | 17060026 | 1 | Lendlease Horizon LLC-Horizon | 2017-10-01 | 2018-06-01 | 0 | 58 | 0 | 11655.89 | 1506.83
17030044 | Minneapolis Operations | 17030044 | 1 | Int Paper-Roof Repalcement | 2017-10-16 | 2018-06-01 | 9000 | 19 | 0 | 2076805.84 | 2032027.9 | 1035 | 4104.5 | 94.54% | 4.921% | 0.536%
17145007, 17148005 | Solar and Emerging Renewables Operations | 17145007 | 1 | Upton County 2 Solar-ConEdison | 2017-03-27 | 2018-06-01 | 233985760 | 15039320.4 | 14756842 | 118865693.7669 | 107914341.73 | 530443.12 | 499113.56 | 87.45% | 12.55% | 0%
17090003 | Chicago Operations | 17090003 | 1 | Lurie Children's Inpatient Exp | 2017-07-01 | 2018-05-31 | 60000 | 51191 | 35754 | 27277150.6249 | 25548485.96 | 28381.5 | 30751.59 | 82.84% | 12.97% | 4.193%
17060043 | Denver Operations | 17060043 | 1 | SCL-LMC IR Equipment Rep | 2018-01-03 | 2018-05-31 | 0 | 1415 | 1395 | 429157.57 | 435117.87 | 1295 | 1398.5 | 92.53% | 7.472% | 0%
17110021 | FCG Operations | 17110021 | 1 | FANX 1 Sidewalk Improv & Rpr | 2018-04-23 | 2018-05-31 | 200 | 0 | 0 | 76964 | 77991.45
17030026 | Minneapolis Operations | 17030026 | 1 | Northern Stacks VI | 2017-08-15 | 2018-05-31 | 120600 | 341124 | 0 | 8634316.87 | 6990954.09 | 14634 | 7843.06 | 92.43% | 7.567% | 0%
17080010 | Milwaukee Operations | 17080010 | 1 | AHC-MRI South Shore @S.L. | 2018-01-02 | 2018-05-15 | 1642 | 13976.5 | 1762 | 793960.14 | 747115.26 | 1253 | 321 | 74.3% | 20.72% | 4.984%
17080016 | Milwaukee Operations | 17080016 | 1 | AHC-IR South Shore @S.L. | 2018-01-02 | 2018-05-09 | 1150 | 8705.51 | 1822 | 777546.71 | 760430.07 | 549.2 | 1272.5 | 90.77% | 9.234% | 0%
17040001 | Phoenix Operations | 17040001 | 1 | MDI-Hampton Inn FF&E | 2017-02-06 | 2018-05-09 | 0 | 0 | 0 | 3396481.91 | 2941843.15
17060028 | Denver Operations | 17060028 | 1 | CCD-Glenbrook Detention Basin | 2017-10-01 | 2018-05-04 | 0 | 292021 | 41578 | 3515173.11 | 4004416.3 | 7295 | 13327 | 85.12% | 14.88% | 0%
17060002 | Denver Operations | 17060002 | 1 | City & County of Denver-Mt H | 2017-03-01 | 2018-05-01 | 0 | 38947.5 | 25101 | 1356034.17 | 1694826.44 | 4334 | 7509.5 | 84.77% | 15.23% | 0%
17060005 | Denver Operations | 17060005 | 1 | City & Cty of Denver-Mt Mass | 2017-05-01 | 2018-05-01 | 0 | 52698 | 28088 | 3413327.1 | 3506399.11 | 9465 | 12317.5 | 85.34% | 14.66% | 0%
17060039 | Denver Operations | 17060039 | 1 | Ardent Hills-Colton CA PV | 2017-11-29 | 2018-05-01 | 0 | 0 | 0 | 19675 | 18187.67
17060040 | Denver Operations | 17060040 | 1 | SCL-LMC MOB II | 2018-01-03 | 2018-05-01 | 0 | 0 | 0 | 0.01 | 2602.59
17060042 | Denver Operations | 17060042 | 1 | SCL-NJH Ctr of Outpatient | 2017-12-01 | 2018-05-01 | 0 | 0 | 0 | 83581 | 61105.78
17030032 | Minneapolis Operations | 17030032 | 1 | HCMC-AOSC Connectors | 2017-08-01 | 2018-04-30 | 22300 | 37408 | 4572 | 1735854.67 | 1674300.2 | 3660.5 | 3804 | 92.03% | 7.965% | 0%
17040019 | Phoenix Operations | 17040019 | 1 | SRP PAB 2018 Cap Improve | 2017-09-01 | 2018-04-30 | 80000 | 0 | 0 | 28617.38 | 28426.27
17146020 | Power Delivery Solutions Operations | 17146020 | 1 | East Valley BESS | 2018-01-08 | 2018-04-30 | 0 | 18928 | 1464 | 3866155.2 | 4782840.15 | 3640 | 5300 | 83.12% | 16.88% | 0%
17040002 | Phoenix Operations | 17040002 | 1 | 24th St WT Res No. 3 Rehab | 2017-03-13 | 2018-04-06 | 155000 | 0 | 42 | 3090170.05 | 3503185.72 | 4786 | 4610 | 83.86% | 16.14% | 0%
17141027 | Mortenson Energy Services-Operations | 17141027 | 1 | Auwahi Turbine 4 Rebuild | 2017-11-27 | 2018-04-02 | 0 | 2191561 | 0 | 5211524 | 5518573.47 | 3040 | 6739 | 66.79% | 27.16% | 6.047%
17060015 | Denver Operations | 17060015 | 1 | Co Rockies-Coors Field 2017 | 2017-10-01 | 2018-04-01 | 5000 | 99029 | 18875 | 8805198.39 | 8665635.04 | 16054.97 | 21893.5 | 85.71% | 14.29% | 0%
17145013, 17146026, 17148015 | Power Delivery Solutions Operations | 17146026 | 11 | Eleven Mile Substation HVT | 2017-12-18 | 2018-04-01 | 0 | 65417 | 66765 | 2053254.27 | 2230976.97 | 13454 | 11266 | 76.92% | 23.08% | 0%
17146029 | Power Delivery Solutions Operations | 17146029 | 1 | Maxwell Stabilization | 2018-01-08 | 2018-03-31 | 0 | 60 | 0 | 311817.55 | 283966.68 | 1168 | 607 | 98.85% | 1.153% | 0%
17030045 | Minneapolis Operations | 17030045 | 1 | Twins-Target Field 2018 Impr | 2017-10-16 | 2018-03-30 | 2500 | 311413.32 | 0 | 9658188.66 | 9411237.91 | 18216.2 | 18310.5 | 79.84% | 17.73% | 2.43%
17050020 | Seattle Operations | 17050020 | 1 | UW WCUP TSO | 2017-07-01 | 2018-03-30 | 0 | 0 | 0 | 140264.98 | 138830.13
17050001 | Seattle Operations | 17050001 | 1 | Alternate Utility Facility | 2017-07-24 | 2018-03-28 | 0 | 44164 | 35652 | 25591819.42 | 26304413.1 | 2130 | 4267.14 | 96.86% | 3.14% | 0%
17030034 | Minneapolis Operations | 17030034 | 1 | UMN-CMRR Suite, Lab & CCRB | 2017-08-21 | 2018-03-09 | 3362 | 7060 | 350 | 750331.6 | 687431.66 | 774 | 353.43 | 98.59% | 1.415% | 0%
17090011 | Chicago Operations | 17090011 | 1 | Mercyhealth Hospital & Clinic | 2017-09-01 | 2018-03-01 | 149200 | 608 | 0 | 632863 | 649803.75 | 40 | 15.04 | 100% | 0% | 0%
17060003 | Denver Operations | 17060003 | 1 | Par Equities-Aurora Crossing | 2017-03-01 | 2018-03-01 | 0 | 163444 | 6701 | 2331461.9 | 2507170.48 | 6808 | 7819.5 | 85.3% | 14.7% | 0%
17060027 | Denver Operations | 17060027 | 1 | SCL-LMC Hail Damage | 2017-07-10 | 2018-03-01 | 18000 | 2769 | 4472 | 9852749.97 | 9405410.79 | 6981 | 7434 | 87.15% | 12.85% | 0%
17030025 | Minneapolis Operations | 17030025 | 1 | St David's Center at WPC | 2017-06-19 | 2018-03-01 | 5682 | 4417 | 242 | 1338658.3 | 1263157.6 | 1520.7 | 1582.28 | 93.17% | 6.826% | 0%
17141003 | Wind Energy I Operations | 17141003 | 1 | Milligan 3 Wind | 2017-08-01 | 2018-03-01 | 0 | 40 | 0 | 5170240.5 | 5143794.66
17141030 | Wind Energy I Operations | 17141030 | 1 | Century 3 Repower Wind | 2018-01-02 | 2018-02-26 | 0 | 599 | 503 | 2010911.34 | 1968628.08 | 7774 | 7833.5 | 60.52% | 23.02% | 16.46%
17050013 | Seattle Operations | 17050013 | 1 | Prov Med Ctr Evrt - AWing | 2017-07-19 | 2018-02-15 | 0 | 4223.2 | 1417 | 352411.54 | 346977.54 | 847 | 613.76 | 97.39% | 2.607% | 0%
17145015 | Solar and Emerging Renewables Operations | 17145015 | 1 | Alamo 4 Retrofit Mockup - CED | 2017-09-25 | 2018-02-09 | 0 | 203 | 196 | 23227 | 29086.31 | 194 | 105.5 | 98.58% | 1.422% | 0%
17040015 | Phoenix Operations | 17040015 | 1 | CBR 1st Baseline Shade | 2017-11-17 | 2018-02-02 | 10150 | 800 | 0 | 734371.76 | 709437.88 | 71 | 0 | 0% | 0% | 0%
17090006 | Chicago Operations | 17090006 | 1 | Allstate Ireland Consulting | 2017-02-03 | 2018-02-01 | 0 | 0 | 0 | 182129 | 213128.79
17060038 | Denver Operations | 17060038 | 1 | SCL-LMC Fire Main Repair | 2017-12-04 | 2018-02-01 | 0 | 0 | 0 | 218879 | 220519.76
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 | Power Delivery Solutions Operations | 17146003 | 41 | Jasper Solar I HVT | 2017-04-01 | 2018-01-31 | 0 | 15345 | 15105 | 4255850.61 | 3989816.9 | 8147.86 | 2973.5 | 94.05% | 5.946% | 0%
17040016 | Phoenix Operations | 17040016 | 1 | Rockies Ceiling Replacement | 2017-12-18 | 2018-01-29 | 0 | 0 | 0 | 88313.98 | 84091.23
17030035 | Minneapolis Operations | 17030035 | 1 | HSRE-West Health MOB-Reno | 2017-09-18 | 2018-01-21 | 1500 | 0 | 0 | 616278.71 | 574943.33 | 1870 | 2082.66 | 98.99% | 1.008% | 0%
17040017 | Phoenix Operations | 17040017 | 1 | Industrious-Scottsdale Lincoln | 2018-02-02 | 2018-01-19 | 20062 | 0 | 0 | 2058322.57 | 2383570.35 | 0 | 526 | 97.34% | 2.662% | 0%
17040014 | Phoenix Operations | 17040014 | 1 | Rio de Flag-Emergency Aeration | 2017-11-13 | 2018-01-18 | 0 | 1361 | 0 | 254522 | 244096.26 | 964 | 393 | 96.82% | 3.181% | 0%
17110006 | FCG Operations | 17110006 | 1 | UDC HVAC Large | 2017-08-02 | 2018-01-17 | 2500 | 0 | 0 | 649034.24 | 538470.08
17110005 | FCG Operations | 17110005 | 1 | ECB-1 INCR Inst RF Window | 2017-06-26 | 2018-01-16 | 150000 | 0 | 0 | 1052065.83 | 995051.83 | 0 | 140.23 | 100% | 0% | 0%
17145017 | Solar and Emerging Renewables Operations | 17145017 | 1 | Alamo 5 Module Replacement CED | 2017-10-23 | 2018-01-14 | 0 | 33182 | 32334 | 930847 | 815545.92 | 15156 | 10175.5 | 92.04% | 7.96% | 0%
17060023 | Denver Operations | 17060023 | 1 | Children's Hosp-18th & Marion | 2017-09-20 | 2018-01-12 | 0 | 146 | 0 | 113778 | 100812.97 | 0 | 8.5 | 94.12% | 5.882% | 0%
17030046 | Minneapolis Operations | 17030046 | 1 | Swervo-Brickhouse Link | 2017-10-02 | 2018-01-02 | 8000 | 0 | 0 | 467061.39 | 506388.43 | 4492 | 5189.46 | 91.99% | 8.006% | 0%
17148016 | Civil Group Operations | 17148016 | 1 | Intrepid Foundations Civil | 2017-09-01 | 2017-12-31 | 0 | 431 | 424 | 1231687.02 | 1179806.66 | 7516 | 7484 | 66.76% | 31.45% | 1.79%
17148017 | Civil Group Operations | 17148017 | 1 | Century Fdn Upg Civil | 2017-09-01 | 2017-12-31 | 0 | 409 | 135 | 1051656.8638 | 1051171.21 | 7011 | 7360 | 67.47% | 32.07% | 0.462%
17060044 | Denver Operations | 17060044 | 1 | Mort Dev-Cottrell Redevelop | 2017-01-01 | 2017-12-31 | 0 | 0 | 0 | 0.01 | 58942.32
17080011 | Milwaukee Operations | 17080011 | 1 | Marquette - Misc. Projects | 2017-07-17 | 2017-12-31 | 0 | 0 | 0 | 131004 | 105510.4 | 80 | 123 | 97.56% | 2.439% | 0%
17030002 | Minneapolis Operations | 17030002 | 1 | Allina-Annual Contract 2017 | 2017-01-01 | 2017-12-31 | 0 | 0 | 0 | 8369804.12 | 8369645.2 | 0 | 39071.34 | 83.59% | 15.3% | 1.107%
17030037 | Minneapolis Operations | 17030037 | 1 | Basilica of St Mary-2017 | 2017-08-28 | 2017-12-31 | 0 | 2 | 0 | 175625.16 | 188814.5 | 826 | 1004.5 | 99.35% | 0.6471% | 0%
17030004 | Minneapolis Operations | 17030004 | 1 | AccessAbililty-Hoover Street | 2017-04-01 | 2017-12-31 | 9244 | 33270.82 | 0 | 1570806.76 | 1631445.49 | 3043.9 | 3210.5 | 99.3% | 0.7008% | 0%
17030019 | Minneapolis Operations | 17030019 | 1 | Mayo Clinic Square Phase 2 | 2017-04-27 | 2017-12-31 | 18880 | 46704 | 21313 | 3201903.95 | 3076052.17 | 5969 | 6372.5 | 95.97% | 3.288% | 0.7375%
17141001 | Mortenson Energy Services-Operations | 17141001 | 1 | MSA 2017 Wind | 2017-01-01 | 2017-12-31 | 0 | 64775 | 0 | 12789482.5303 | 12789482.53 | 393279 | 170418 | 74.77% | 25.04% | 0.1878%
17141007 | Mortenson Energy Services-Operations | 17141007 | 1 | GE Gen Aligns 2017 | 2017-04-26 | 2017-12-31 | 0 | 8614 | 0 | 2498397.585 | 3581367.63 | 68017 | 59086.25 | 75.79% | 23.89% | 0.3241%
17040005 | Phoenix Operations | 17040005 | 1 | Mortenson Office-Rebuild |  | 2017-12-31 | 0 | 0 | 0 | 0 | 54.59
17146001 | Power Delivery Solutions Operations | 17146001 | 1 | Firewheel Transmission OK HVT | 2017-03-01 | 2017-12-31 | 0 | 18 | 0 | 595408 | 472771.67
17146002 | Power Delivery Solutions Operations | 17146002 | 1 | Firewheel Transmission TX HVT | 2017-03-01 | 2017-12-31 | 0 | 8 | 0 | 35910 | 23856.02
17146023 | Power Delivery Solutions Operations | 17146023 | 1 | Broadview Energy JN - T01 | 2017-12-11 | 2017-12-31 | 0 | 3504 | 0 | 21447.98 | 18470.26 | 97 | 0 | 0% | 0% | 0%
17146024 | Power Delivery Solutions Operations | 17146024 | 1 | Broadview Energy KW - T01 | 2017-12-11 | 2017-12-31 | 0 | 3202 | 0 | 18270.5 | 14995.47 | 103 | 0 | 0% | 0% | 0%
17050018 | Seattle Operations | 17050018 | 1 | Surface Water Intake Gen | 2017-10-31 | 2017-12-31 | 0 | 9 | 4 | 41675.46 | 41756.89 | 136 | 134 | 85.07% | 14.93% | 0%
17145009 | Solar and Emerging Renewables Operations | 17145009 | 1 | SAT Slew Drive Replacement | 2017-05-15 | 2017-12-31 | 0 | 2 | 0 | 18591 | 6708.63 | 90 | 34.5 | 100% | 0% | 0%
17145006 | Solar and Emerging Renewables Operations | 17145006 | 1 | Quincy II CSG - SunShare | 2017-07-17 | 2017-12-31 | 2000000 | 0 | 0 | 2200 | 1124.25
17141005 | Wind Energy I Operations | 17141005 | 1 | Moventas MSA 2017 | 2017-02-20 | 2017-12-31 | 0 | 55 | 0 | 255994.7105 | 164851.3 | 4799 | 2383.49 | 67.67% | 32.33% | 0%
17090002 | Chicago Operations | 17090002 | 1 | Lurie Children's Hosp Bridge | 2017-06-01 | 2017-12-29 | 3200 | 12732 | 3783 | 4867732 | 4798247.36 | 5430 | 6966.74 | 72.26% | 17.15% | 10.59%
17080004 | Milwaukee Operations | 17080004 | 1 | EUA - WEC Energy Precon Servcs | 2016-11-18 | 2017-12-29 | 0 | 0 | 0 | 5608 | 6403.48
17080006 | Milwaukee Operations | 17080006 | 1 | AHC-Summit Data Center Expansn | 2017-06-13 | 2017-12-29 | 5000 | 26293.45 | 6181 | 7774982.49 | 7558018.92 | 1481.6 | 874.75 | 98.74% | 1.258% | 0%
17030006 | Minneapolis Operations | 17030006 | 1 | UMN-PWB 8th Fl-Health Info | 2017-10-16 | 2017-12-29 | 8500 | 34377 | 25426 | 1368584 | 1335392.14 | 1879 | 2055.67 | 99.81% | 0.1946% | 0%
17030012 | Minneapolis Operations | 17030012 | 1 | Vibra LTAC Hospital of Fargo | 2017-02-06 | 2017-12-29 | 27605 | 6697 | 4905 | 7795922.3458 | 7488659.85 | 10299 | 6210 | 96.09% | 3.913% | 0%
17141031 | Mortenson Energy Services-Operations | 17141031 | 1 | Taconite Ridge | 2017-12-04 | 2017-12-18 | 0 | 0 | 0 | 34137 | 38376.54 | 40 | 250.5 | 99.8% | 0.1996% | 0%
17141008 | Wind Energy I Operations | 17141008 | 1 | Intrepid Repower Wind | 2017-08-01 | 2017-12-15 | 0 | 4204 | 3058 | 17107134.704 | 16832383.57 | 52852 | 64773 | 47.08% | 43.33% | 9.592%
17141009 | Wind Energy I Operations | 17141009 | 1 | Century Repower Wind | 2017-07-15 | 2017-12-15 | 0 | 3670 | 2435 | 19839711.12 | 19556942.57 | 48942 | 78415.53 | 58.73% | 17.59% | 23.67%
17141010 | Wind Energy I Operations | 17141010 | 1 | Victory Repower Wind | 2017-08-01 | 2017-12-15 | 0 | 5045 | 4903 | 14583988.79 | 15486697.22 | 48200 | 62179.5 | 51.3% | 38.89% | 9.81%
17141011 | Wind Energy I Operations | 17141011 | 1 | Fenton Repower Wind | 2017-08-01 | 2017-12-15 | 0 | 143 | 37 | 92457.07 | 86070.15 | 0 | 268 | 92.16% | 7.836% | 0%
17141014 | Wind Energy I Operations | 17141014 | 1 | Intrepid Wind Fnd Upgrades | 2017-08-14 | 2017-12-15 | 0 | 1663 | 1555 | 12352771.7 | 11208031.16 | 37070 | 32994.5 | 68.95% | 27.95% | 3.096%
17141015 | Wind Energy I Operations | 17141015 | 1 | Century Wind Fnd Upgrades | 2017-08-14 | 2017-12-15 | 0 | 1620 | 1609 | 12196024.4308 | 11249979.08 | 33649.7 | 34346.25 | 71.82% | 21.52% | 6.662%
17110004 | FCG Operations | 17110004 | 1 | UDC DCM 4 Technical Library | 2017-07-10 | 2017-12-13 | 2500 | 0 | 0 | 595354.65 | 521932.61
17141028 | Wind Energy I Operations | 17141028 | 1 | Palo Alto Substation Pad Wind | 2017-11-27 | 2017-12-13 | 0 | 14 | 0 | 1532577.9 | 1386754.76
17141004 | Wind Energy I Operations | 17141004 | 1 | Beaver Creek Wind | 2017-06-01 | 2017-12-09 | 0 | 7277 | 5391 | 47417413.2216 | 46700711.81 | 88280 | 87065.3 | 57.9% | 29.8% | 12.3%
17050014 | Seattle Operations | 17050014 | 1 | Prov Med Ctr D Wing OR 312 | 2017-07-01 | 2017-12-04 | 0 | 3376.2 | 2615 | 685239.8364 | 640240.57 | 1052.72 | 983.83 | 90.75% | 9.25% | 0%
17141029 | Mortenson Energy Services-Operations | 17141029 | 1 | High Lonesome Mesa Gearbox | 2017-11-27 | 2017-12-02 | 0 | 24530 | 0 | 271963.28 | 350050.03 | 446 | 782 | 76.66% | 23.34% | 0%
17030022 | Minneapolis Operations | 17030022 | 1 | CGA Mpls Office Remodel | 2017-06-01 | 2017-12-01 | 18000 | 2 | 0 | 2688070.44 | 2711832.11 | 1296 | 1610.97 | 98.42% | 1.583% | 0%
17141019 | Mortenson Energy Services-Operations | 17141019 | 1 | Victory Gen. Refurbishment | 2017-09-11 | 2017-12-01 | 0 | 1 | 0 | 323265.64 | 264390.67
17060017 | Denver Operations | 17060017 | 1 | Woodward-2017 Capital Imp | 2017-06-01 | 2017-11-30 | 0 | 5 | 0 | 583597 | 522296.9 | 0 | 749 | 58.48% | 41.52% | 0%
17060021 | Denver Operations | 17060021 | 1 | SCL-LMC Cardia Nuclear Camera | 2017-07-24 | 2017-11-30 | 0 | 415 | 0 | 80358 | 83552.78 | 415 | 25 | 100% | 0% | 0%
17030003 | Minneapolis Operations | 17030003 | 1 | Fridley Land-NS IV | 2017-03-15 | 2017-11-30 | 177600 | 6671 | 13251 | 13702488.7825 | 11063274.13 | 21585 | 8851.97 | 88.87% | 11.02% | 0.113%
17146015 | Power Delivery Solutions Operations | 17146015 | 1 | Maxwell Cut-In HVT | 2017-09-05 | 2017-11-30 | 0 | 73 | 0 | 436224.3199 | 322071.92 | 966 | 1132 | 65.95% | 34.05% | 0%
17146016 | Power Delivery Solutions Operations | 17146016 | 1 | Maxwell Demo HVT | 2017-09-05 | 2017-11-30 | 0 | 8 | 0 | 23903 | 11833.41 | 240 | 0 | 0% | 0% | 0%
17060018 | Denver Operations | 17060018 | 1 | SCL-LMC Outpatient Pharmacy | 2017-07-12 | 2017-11-29 | 0 | 682 | 0 | 329597.85 | 333351.97 | 744 | 723 | 87.34% | 12.66% | 0%
17060019 | Denver Operations | 17060019 | 1 | SCL-LMC TSN Offices | 2017-06-26 | 2017-11-29 | 0 | 2915 | 2410 | 1747162.44 | 1748968.11 | 2936 | 2768.5 | 93.08% | 6.917% | 0%
17146027 | Power Delivery Solutions Operations | 17146027 | 1 | Alliance Pipeline Feisabil HVT | 2017-11-27 | 2017-11-27 | 0 | 0 | 0 | 15170 | 106.88
17060037 | Denver Operations | 17060037 | 1 | SCL-St Joe's Wall of Hope | 2017-11-06 | 2017-11-24 | 0 | 52 | 0 | 10100.64 | 5854.69 | 32 | 40 | 100% | 0% | 0%
17146011 | Power Delivery Solutions Operations | 17146011 | 1 | Stillwater 2 | 2017-08-01 | 2017-11-23 | 0 | 75918 | 65701 | 6351397.106 | 6055482.02 | 10358 | 9177.5 | 70.7% | 29.3% | 0%
17146006 | Power Delivery Solutions Operations | 17146006 | 1 | Beaver Creek HVT | 2017-06-19 | 2017-11-21 | 0 | 369321 | 295812 | 10313594.63 | 10023056.17 | 11431 | 12597 | 84.84% | 15.16% | 0%
17060031 | Denver Operations | 17060031 | 1 | SCL-St Joe's Pharmacy Retail | 2017-08-21 | 2017-11-17 | 0 | 9 | 0 | 371509.62 | 382518.93 | 1008 | 1189 | 93.27% | 6.728% | 0%
17141020 | Wind Energy I Operations | 17141020 | 1 | Flat Ridge II Bolt Tensioning | 2017-09-18 | 2017-11-17 | 0 | 1357 | 0 | 147108.21 | 133858.48 | 1440 | 1519.5 | 89.21% | 10.79% | 0%
17030033 | Minneapolis Operations | 17030033 | 1 | Minnehaha Academy-Reno | 2017-08-16 | 2017-11-15 | 28000 | 0 | 0 | 1126827.85 | 1119691.88 | 2214 | 2212.86 | 56.35% | 30.8% | 12.86%
17030018 | Minneapolis Operations | 17030018 | 1 | CHS Renovations FY2017 | 2017-04-17 | 2017-11-13 | 330000 | 44188 | 11500 | 1974408.18 | 2007369.27 | 2914.7 | 3504.63 | 87.76% | 10.64% | 1.598%
17090007 | Chicago Operations | 17090007 | 1 | Lurie Childrns Resident Lnge | 2017-06-01 | 2017-11-07 | 1020 | 1897 | 2576 | 617838.6051 | 540028.92 | 2776 | 1285.84 | 79.2% | 14.19% | 6.61%
17030047 | Minneapolis Operations | 17030047 | 1 | UMN-Gibson Repairs for NFL Use | 2017-09-11 | 2017-11-06 | 88000 | 0 | 0 | 545613.15 | 536838.85 | 64 | 65 | 98.46% | 1.538% | 0%
17141002 | Wind Energy I Operations | 17141002 | 1 | Firewheel Transmission Texas | 2017-04-15 | 2017-11-03 | 0 | 0 | 0 | 37914 | 38159.03
17080003 | Milwaukee Operations | 17080003 | 1 | AHC-Grafton Nuclear Medicine | 2017-08-01 | 2017-11-02 | 1315 | 6944 | 0 | 371207.98 | 337520.3 | 479 | 124 | 100% | 0% | 0%
17030017 | Minneapolis Operations | 17030017 | 1 | Blake Ice | 2017-03-27 | 2017-11-01 | 44113 | 75779 | 0 | 2590193.92 | 2525646.5 | 7463 | 7181 | 90.62% | 9.156% | 0.2228%
17030015 | Minneapolis Operations | 17030015 | 1 | Allina-Hastings Clinic TI | 2017-02-27 | 2017-11-01 | 50095 | 21484 | 12870 | 5764205.52 | 5756056.09 | 6937 | 6308.62 | 90.51% | 9.257% | 0.2378%
17050015 | Seattle Operations | 17050015 | 1 | Black Butte WWTP upgrades | 2017-08-24 | 2017-10-31 | 0 | 96.9 | 8 | 58773.83 | 49943.19 | 150.3 | 136 | 86.76% | 13.24% | 0%
17141017 | Wind Energy I Operations | 17141017 | 1 | Muscatine Blade Reload | 2017-09-05 | 2017-10-31 | 0 | 1349.5 | 0 | 206994.1405 | 214381.32 | 0 | 1350.5 | 75.86% | 15.85% | 8.293%
17040007 | Phoenix Operations | 17040007 | 1 | SRP PAB AV Systems Ph2 | 2017-04-03 | 2017-10-30 | 0 | 0 | 0 | 737765.67 | 737019.1
17141021 | Mortenson Energy Services-Operations | 17141021 | 1 | King Mtn. M-03 Demolition | 2017-10-06 | 2017-10-20 | 0 | 554 | 0 | 140954 | 152499.51 | 0 | 867.5 | 71.3% | 28.7% | 0%
17145004, 17146012, 17148006 | Power Delivery Solutions Operations | 17146012 | 11 | Stuttgart Substation HVT | 2017-07-24 | 2017-10-19 | 0 | 70461 | 68709 | 983232.13 | 782102.62 | 6309 | 4485.49 | 81.96% | 18.04% | 0%
17148009 | Civil Group Operations | 17148009 | 1 | Redstone Arsenal Civil | 2017-07-01 | 2017-10-18 | 0 | 38676.02 | 28663 | 681251.973 | 574225.68 | 2608 | 2067 | 83.12% | 16.88% | 0%
17080005 | Milwaukee Operations | 17080005 | 1 | AHC-Healing Garden Railing @SL | 2017-06-20 | 2017-10-13 | 1056 | 3510.5 | 0 | 716124.55 | 679732.48 | 204.5 | 337 | 96.74% | 3.264% | 0%
17146017 | Power Delivery Solutions Operations | 17146017 | 1 | Alamo 5 & 7 PRC 005 HVT | 2017-09-20 | 2017-10-06 | 0 | 0 | 0 | 8122.18 | 7106.81
17060035 | Denver Operations | 17060035 | 1 | SCL-Good Sam Fire Line Repair | 2017-09-01 | 2017-09-30 | 0 | 0 | 0 | 129011 | 129370.08
17030039 | Minneapolis Operations | 17030039 | 1 | TCO-WH MOB-Level 2 Reno | 2017-07-03 | 2017-09-30 | 1200 | 0 | 0 | 374478.04 | 358477.34 | 1148 | 1185.82 | 93.89% | 6.114% | 0%
17141018 | Mortenson Energy Services-Operations | 17141018 | 1 | Shannon Turbine 3 Demo | 2017-09-06 | 2017-09-18 | 0 | 208360 | 0 | 232105.62 | 194083.89 | 0 | 964.5 | 66.56% | 33.44% | 0%
17080002 | Milwaukee Operations | 17080002 | 1 | Johnson Controls - Pond Renvtn | 2017-04-10 | 2017-09-08 | 0 | 8969.69 | 840 | 554416.18 | 521171.36 | 1982.9 | 1957 | 99.74% | 0.2555% | 0%
17150007 | Sports + Entertainment Group Operations | 17150007 | 1 | PSU - Energy Savings Program | 2017-06-19 | 2017-09-02 | 0 | 688 | 0 | 602981.7 | 583161.3 | 388 | 241.5 | 89.03% | 9.524% | 1.449%
17090004 | Chicago Operations | 17090004 | 1 | Allstate Jcksnvl 2017 Misc. | 2017-02-03 | 2017-09-01 | 0 | 0 | 0 | 1250222.79 | 1207397.71 | 0 | 0 | 0% | 0% | 0%
17090005 | Chicago Operations | 17090005 | 1 | QTS Chicago Phase 2 | 2017-02-03 | 2017-09-01 | 0 | 50104 | 237 | 3658782.77 | 3514129.89 | 3212 | 2656.25 | 90.97% | 8.536% | 0.4894%
18090991, 18090001, 17090009 | Chicago Operations | 17090009 | 21 | Halas Hall Consulting | 2017-05-01 | 2017-09-01 | 0 | 0 | 0 | 445945 | 310212.1 | 0 | 53.33 | 100% | 0% | 0%
17060004 | Denver Operations | 17060004 | 1 | Woodward-IS Equipment | 2017-02-22 | 2017-09-01 | 100000 | 0 | 0 | 1807556 | 1586099.72 | 0 | 1357 | 82.65% | 17.35% | 0%
17060032 | Denver Operations | 17060032 | 1 | SCL-St Joe's CT3 Power | 2017-08-21 | 2017-08-31 | 0 | 0 | 0 | 15117.01 | 15064.7 | 0 | 12 | 100% | 0% | 0%
17110001 | FCG Operations | 17110001 | 1 | UDC Silver Galaxy ATD | 2017-05-17 | 2017-08-21 | 12500 | 0 | 0 | 272987 | 287161.73
17050002 | Seattle Operations | 17050002 | 1 | Yahoo! GQ2 Office TI | 2017-02-06 | 2017-08-18 | 21156 | 25 | 0 | 2140362.97 | 2134965.8 | 82 | 0 | 0% | 0% | 0%
17030013 | Minneapolis Operations | 17030013 | 1 | UMN-Frontier Hall HVAC | 2017-05-15 | 2017-08-15 | 175510 | 317203 | 8948 | 6475452.81 | 6561681.67 | 5991.35 | 6534.98 | 88.65% | 10.58% | 0.7651%
17060016 | Denver Operations | 17060016 | 1 | SCL-LMC Parking Lot Security | 2017-07-10 | 2017-08-01 | 0 | 16 | 0 | 15224 | 15363.18 | 16 | 20 | 82.5% | 17.5% | 0%
17080008 | Milwaukee Operations | 17080008 | 1 | Johnson Controls - Bld.4,Flr 1 | 2017-05-12 | 2017-07-31 | 4847 | 6343 | 6245 | 166363 | 159899.78 | 524 | 510 | 98.24% | 1.765% | 0%
17146014 | Power Delivery Solutions Operations | 17146014 | 1 | Clearwater Trans Line HVT | 2017-06-01 | 2017-07-28 | 0 | 0 | 0 | 11718 | 7160.62
17145011, 17148008 | Civil Group Operations | 17148008 | 11 | Terning CSG Solar - Civil | 2017-06-01 | 2017-07-17 | 0 | 35 | 0 | 555082 | 471386.08 | 960 | 1913 | 80.97% | 19.03% | 0%
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 | Civil Group Operations | 17148002 | 51 | Jasper Civil | 2017-02-01 | 2017-07-01 | 0 | 234599 | 147405 | 5226993.46 | 5401867.11 | 16942 | 19761.5 | 80.67% | 19.33% | 0%
17145004, 17146012, 17148006 | Civil Group Operations | 17148006 | 21 | Stuttgart Civil | 2017-05-01 | 2017-07-01 | 0 | 68688 | 17001 | 1598236.99 | 1484688.81 | 5130 | 2945 | 75.3% | 24.7% | 0%
17148007 | Civil Group Operations | 17148007 | 1 | Murphy CSG Civil | 2017-05-01 | 2017-07-01 | 0 | 30 | 0 | 493820 | 435546.13 | 960 | 1104.5 | 75.69% | 24.31% | 0%
17060009 | Denver Operations | 17060009 | 1 | Woodward-RMTIC | 2017-04-03 | 2017-07-01 | 0 | 0 | 0 | 468817 | 422704.68 | 0 | 692 | 69.8% | 30.2% | 0%
17060012 | Denver Operations | 17060012 | 1 | Stadium Mgmt-Broncos 2017 | 2017-04-17 | 2017-07-01 | 0 | 20 | 304 | 595466.25 | 753556.83 | 0 | 4055.5 | 87.18% | 12.82% | 0%
17050016 | Portland Operations | 17050016 | 1 | OHSU Vollum Preconstruction | 2017-01-01 | 2017-07-01 | 0 | 127 | 0 | 12466.31 | 79007.45 | 64 | 86 | 100% | 0% | 0%
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 | Civil Group Operations | 17148001 | 61 | Ridgeland Civil | 2017-01-09 | 2017-06-30 | 0 | 756963 | 39188 | 1481167.69 | 1410215.1 | 4280 | 4945 | 79.94% | 20.06% | 0%
17060010 | Denver Operations | 17060010 | 1 | SCL-LMC Integration System | 2017-04-01 | 2017-06-30 | 0 | 0 | 0 | 35269 | 35436.71 | 0 | 329 | 60.49% | 39.51% | 0%
17141006 | Wind Energy I Operations | 17141006 | 1 | Ocotillo WTG 126 | 2017-01-23 | 2017-06-30 | 0 | 734418 | 0 | 1288473.986 | 1316111.51 | 5734 | 3278.51 | 82% | 17.13% | 0.8693%
17146007 | Power Delivery Solutions Operations | 17146007 | 1 | Alamo 6 - HVT - MPT FND | 2017-05-15 | 2017-06-15 | 0 | 617 | 0 | 257225.17 | 255375.18 | 867 | 694 | 92.07% | 3.89% | 4.035%
17040006 | Phoenix Operations | 17040006 | 1 | AlaskaUSA-Glendale Financial | 2017-02-20 | 2017-06-12 | 5257 | 0 | 0 | 1308220.42 | 1377272.96 | 0 | 25 | 100% | 0% | 0%
17146005 | Power Delivery Solutions Operations | 17146005 | 1 | AEP Paint Creek | 2017-03-13 | 2017-05-31 | 0 | 104 | 0 | 38478 | 37359.2 | 360 | 320.5 | 74.88% | 25.12% | 0%
17145005 | Solar and Emerging Renewables Operations | 17145005 | 1 | Midway - Hanwha Q Cell | 2017-04-10 | 2017-05-31 | 229100000 | 13 | 0 | 76056.42 | 43879.51 | 0 | 190.5 | 78.35% | 21.65% | 0%
17110003 | FCG Operations | 17110003 | 1 | Westway Suite Renovation | 2017-05-01 | 2017-05-15 | 1750 | 0 | 0 | 81456.33 | 82331.01
17080001 | Milwaukee Operations | 17080001 | 1 | Johnson Controls - Bld.3,Flr 4 | 2017-03-01 | 2017-05-05 | 9950 | 24355 | 22692 | 298648.6 | 284944.27 | 628.5 | 574 | 100% | 0% | 0%
17146004 | Power Delivery Solutions Operations | 17146004 | 1 | AEP -Fermi Metering | 2017-02-10 | 2017-05-01 | 0 | 9316 | 0 | 47966.53 | 35389.06 | 480 | 623.41 | 63.35% | 36.65% | 0%
17146008 | Power Delivery Solutions Operations | 17146008 | 1 | Sweetwater 3 Repower Analysis | 2017-02-27 | 2017-05-01 | 0 | 4 | 0 | 21739 | 17948.96
17146009 | Power Delivery Solutions Operations | 17146009 | 1 | Cedar Creek Repower Analysis | 2017-03-01 | 2017-05-01 | 0 | 5 | 0 | 21739 | 18142.77
17060001 | Denver Operations | 17060001 | 1 | Co Rockies-Coors Fld Concessio | 2017-01-26 | 2017-03-31 | 2800 | 3 | 0 | 763619.33 | 749702.06 | 0 | 1552.5 | 78.26% | 21.74% | 0%
17030007 | Minneapolis Operations | 17030007 | 1 | Twins-Target Field 2017 Imp | 2017-01-23 | 2017-03-17 | 2500 | 8 | 0 | 502925.98 | 490091.26 | 1094 | 693 | 100% | 0% | 0%
17148003 | Civil Group Operations | 17148003 | 1 | Griffin Trail Wind Civil | 2016-12-22 | 2016-12-31 | 0 | 387 | 0 | 94203 | 32203.18 | 692 | 0 | 0% | 0% | 0%
17013 | Seattle Operations | 17013 | 1 | St of WA-Leg Bldg Rehab & Add | 2006-12-31 | 2004-12-29 | 267000 | 19484 | 39660 | 82983531 | 83033622 | 0 | 79805 | 100% | 0% | 0%
17010 | Seattle Operations | 17010 | 1 | CH2M HILL-CEDAR TREATMENT FAC | 2004-06-01 | 2004-06-01 | 0 | 16110 | 0 | 1177457 | 1258963 | 0 | 3511 | 100% | 0% | 0%
17016 | Seattle Operations | 17016 | 1 | AK AIR-HANGAR MAINTN FACILITY | 2004-01-31 | 2004-03-19 | 0 | 20654 | 7192 | 11136325 | 11148445 | 0 | 20095 | 100% | 0% | 0%
17001 | Seattle Operations | 17001 | 1 | TULALIP TRIBES-NEW TULALIP CA |  | 2003-06-30 | 245000 | 383493 | 569152 | 4596846 | 4650460 | 0 | 47734 | 100% | 0% | 0%
17018 | Seattle Operations | 17018 | 1 | MICROSOFT-CRITICAL ENVIRONMEN | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 0 | 698606 | 0 | 31 | 100% | 0% | 0%
17015 | Seattle Operations | 17015 | 1 | UC BERKELEY-INSECTRY& GRNHOUS | 2001-10-31 | 2001-12-06 | 8000 | 443 | 0 | 2438794 | 2448940 | 0 | 2428 | 100% | 0% | 0%
17012 | Seattle Operations | 17012 | 1 | UNIV BOOKSTORE-BOTHELL CAMPUS | 2001-06-25 | 2001-06-25 | 10510 | 109 | 0 | 471049 | 478884 | 0 | 821 | 100% | 0% | 0%
17003 | Seattle Operations | 17003 | 1 | AK AIR-FLGHT ASI 55IMPROVEMEN | 2001-04-02 | 2001-04-02 | 4038 | 0 | 0 | 279955 | 280461 | 0 | 734 | 100% | 0% | 0%
17004 | Seattle Operations | 17004 | 1 | AK AIR-FLGHT MISC FINISH IMPR | 2001-04-02 | 2001-04-02 | 4500 | 0 | 0 | 43029 | 42860 | 0 | 65 | 100% | 0% | 0%
17148010 | Civil Group Operations | 17148010 | 1 | Mount Signal 3 - Civil | 2017-08-15 |  | 0 | 502733 | 445098 | 5902497.66 | 6386036.31 | 18424 | 24742.5 | 80.55% | 19.05% | 0.4082%
17148011 | Civil Group Operations | 17148011 | 1 | Intrepid RePowering Civi | 2017-08-14 |  | 0 | 54010 | 144 | 2587332.3734 | 2624003.42 | 9657.12 | 10408.5 | 71.71% | 28.08% | 0.2162%
17148012 | Civil Group Operations | 17148012 | 1 | Century RePowering Civil | 2017-08-14 |  | 0 | 117661 | 126681 | 3689986.9932 | 3425349.66 | 13198.5 | 11978.5 | 72.89% | 26.91% | 0.2004%
17148013 | Civil Group Operations | 17148013 | 1 | Victory RePowering Civil | 2017-08-14 |  | 0 | 13396 | 7113 | 1896627.2971 | 1900596.08 | 6540.24 | 8832.5 | 71.11% | 28.26% | 0.6284%
17145013, 17146026, 17148015 | Civil Group Operations | 17148015 | 21 | Pinal Solar - Civil | 2017-10-13 |  | 0 | 16260 | 68144 | 1110128.8 | 1157039.71 | 4736 | 5843 | 81.48% | 18.52% | 0%
17141023, 17146028, 17148018 | Civil Group Operations | 17148018 | 21 | Rattlesnake Creek Wind - Civil | 2017-11-06 |  | 0 | 4439850 | 7882813 | 29768503.52 | 29040610.36 | 100562 | 98382.95 | 76.56% | 23.44% | 0%
17148019 | Civil Group Operations | 17148019 | 1 | Palo Alto Substation - Civil | 2017-11-28 |  | 0 | 11 | 0 | 1245174.8 | 1225205.93 | 3470 | 2443.5 | 54.08% | 38.14% | 7.776%
17141022, 17148020 | Civil Group Operations | 17148020 | 11 | Green River Wind - Civil | 2017-11-28 |  | 0 | 1 | 800 | 517868 | 581461 | 1305 | 1004.5 | 83.92% | 15.93% | 0.1493%
17030021 | Minneapolis Operations | 17030021 | 1 | TCF Bank Stadium Wall Rpr |  |  | 0 | 0 | 0 | 0.01 | 186868.16 | 0 | 604.5 | 86.52% | 13.48% | 0%
17030024 | Minneapolis Operations | 17030024 | 1 | Mortenson Misc |  |  | 0 | 0 | 0 | 0.01 | 9667.82 | 0 | 55 | 100% | 0% | 0%
17030049 | Minneapolis Operations | 17030049 | 1 | MDI-Discovery Square Phase 2 |  |  | 0 | 597235.4 | 110394 | 25703038.2293 | 24111745.03 | 25034.9 | 22052 | 96.21% | 3.752% | 0.03628%
17030014 | Minneapolis Operations | 17030014 | 1 | UMP-Shingle Creek Pkwy TI | 2017-01-25 |  | 2000 | 0 | 0 | 29735.19 | 30542.83 | 102 | 102 | 92.16% | 7.843% | 0%
17040012 | Phoenix Operations | 17040012 | 1 | Phx Rising Precon & Consult | 2017-07-21 |  | 0 | 0 | 0 | 10393 | 12240.53
17050004 | Portland Operations | 17050004 | 1 | Kaiser IDIQ Precon | 2017-06-01 |  | 0 | 46 | 0 | 202677.04 | 232785.87 | 0 | 80 | 100% | 0% | 0%
17050003 | Portland Operations | 17050003 | 1 | Mortenson Portland Office | 2017-02-15 |  | 8107 | 0 | 0 | 551509 | 563224.15 | 184 | 100 | 100% | 0% | 0%
17002 | Seattle Operations | 17002 | 1 | MICROSOFT-DUSC 2001 | 2001-12-31 |  | 0 | 0 | 0 | 142909 | 257347 | 0 | 0 | 0% | 0% | 0%
17014 | Seattle Operations | 17014 | 1 | ST OF WA-EMERGENCY REPAIRS | 2001-05-31 |  | 0 | 55 | 0 | 0 | 785443 | 0 | 1477 | 100% | 0% | 0%
17021 | Seattle Operations | 17021 | 1 | BELLEVUE TECH TOWER | 2001-12-14 |  | 0 | 624 | 0 | 36144 | 36874 | 0 | 252 | 100% | 0% | 0%
17999 | Seattle Operations | 17999 | 1 | MORTENSON-CLOSED JOBSEATTLE O | 2001-12-31 |  | 0 | 0 | 0 | 0 | 21805
17005 | Seattle Operations | 17005 | 1 | QUILEUTE TRIBAL SCHOOL-GYMNAS | 2002-01-31 |  | 16476 | 60943 | 27583 | 3665785 | 3692195 | 0 | 9405 | 100% | 0% | 0%
17017 | Seattle Operations | 17017 | 1 | AK AIR FTC PHASE IV EXPANSION |  |  | 26037 | 0 | 0 | 5043 | 5209
17020 | Seattle Operations | 17020 | 1 | EVERETT FACILITIES-EVENTS CTR |  |  | 200000 | 0 | 0 | 0 | 7708
17145008 | Solar and Emerging Renewables Operations | 17145008 | 1 | AlamoVII Demo & 1 MW Add - CED | 2017-04-20 |  | 11811366 | 26 | 12 | 31884.91 | 42940.26 | 350 | 331 | 84.59% | 15.41% | 0%
17145012 | Solar and Emerging Renewables Operations | 17145012 | 1 | Redstone Arsenal - SunPower | 2017-06-14 |  | 12528000 | 953224 | 1051926 | 5372105.7717 | 5800616.31 | 44691.76 | 53504.59 | 82.28% | 17.72% | 0%
17145013, 17146026, 17148015 | Solar and Emerging Renewables Operations | 17145013 | 1 | Pinal Solar Project | 2017-11-13 |  | 30960000 | 2241585 | 2013138 | 19638993.95 | 18802722.61 | 76291 | 73368 | 87.14% | 12.86% | 0%
17145004, 17146012, 17148006 | Solar and Emerging Renewables Operations | 17145004 | 1 | Stuttgart Solar Project | 2017-06-30 |  | 125553090 | 7998711 | 7320181 | 33571940.57 | 35482435.73 | 280083 | 328477.83 | 82.97% | 17.03% | 0%
17150006 | Sports + Entertainment Group Operations | 17150006 | 1 | Raiders Las Vegas Stadium |  |  | 0 | 0 | 0 | 0 | 1678.22
17150010 | Sports + Entertainment Group Operations | 17150010 | 1 | Mobilitie - MN United MLS DAS |  |  | 0 | 91 | 0 | 1857012.49 | 1828959.81 | 90 | 210 | 95.24% | 4.762% | 0%
18146012, 16080015 |  | 16080015 | 11 | S.C. Johnson-West Side Campus | 2017-03-06 | 2020-09-01 | 150517 | 2634439.85 | 1097477 | 72706913.9812 | 70618759.47 | 89972.41 | 89000.09 | 92.47% | 7.347% | 0.1848%
16060001 |  | 16060001 | 1 | Park Creek-Filing M-L MLK | 2018-10-08 | 2020-01-31 | 0 | 0 | 0 | 1476316 | 1855900.54 | 2173 | 3861 | 97.58% | 2.422% | 0%
16060023 |  | 16060023 | 1 | MDI-2250 Blake St Hotel | 2018-08-20 | 2020-01-31 | 110000 | 0 | 0 | 250039 | 258024.05
16080026 |  | 16080026 | 1 | Froedtert-CFAC Vertical Expans | 2017-05-19 | 2020-01-31 | 166420 | 1196779.05 | 536257 | 75240433.055 | 74851368.74 | 83061.89 | 86720.12 | 89.21% | 10.16% | 0.6336%
16060016 |  | 16060016 | 1 | Six Continents Hotel-2250 Bl | 2017-03-01 | 2019-12-31 | 110000 | 0 | 0 | 0.01 | 0
16080021 |  | 16080021 | 1 | AHC-Misc. Projects 2016-2017 | 2016-08-22 | 2019-12-31 | 0 | 1246 | 0 | 387503 | 331944.92 | 1372 | 1172.5 | 86.52% | 13.48% | 0%
16060033 |  | 16060033 | 1 | Park Creek-Filing PB | 2016-11-15 | 2019-12-30 | 0 | 0 | 0 | 1826462 | 1846967.24 | 2760 | 6720.5 | 99.06% | 0.9449% | 0%
16060003 |  | 16060003 | 1 | CoorsTek WTM AMP | 2017-02-20 | 2019-11-30 | 160000 | 12273.8 | 33956 | 61534552.9329 | 62295973.58 | 22937.3 | 57187 | 89.7% | 10.3% | 0%
16110003 |  | 16110003 | 1 | GSA-FASTC Contract 02 | 2016-10-06 | 2019-11-29 | 210034 | 5688028.93 | 4519432 | 145573512.6038 | 174830864.43 | 175163.4 | 407973.46 | 78% | 21.96% | 0.04522%
15050019, 15000008-040, 16050011 |  | 16050011 | 25 | HE Portland HC LLC Hyatt | 2018-02-19 | 2019-11-26 | 0 | 1616633.9 | 564596 | 48996318.8752 | 50320439.53 | 40404.08 | 52049.66 | 82.23% | 16.99% | 0.7877%
16050010 |  | 16050010 | 1 | citizenM Hotel-Seattle | 2017-03-21 | 2019-10-17 | 96285 | 374550.72 | 333480 | 51418397.2634 | 52748582.05 | 37391.58 | 83540.99 | 81.1% | 17.09% | 1.813%
16060031 |  | 16060031 | 1 | Park Creek-Filing 54 | 2017-11-01 | 2019-08-31 | 0 | 4661 | 43 | 5178630.9044 | 5656846.1 | 7439 | 16187.5 | 95.21% | 4.788% | 0%
16141018 |  | 16141018 | 1 | Walnut Ridge Wind | 2017-08-14 | 2019-08-01 | 0 | 24653 | 21934 | 104805158.5076 | 103427753.63 | 106726 | 142205.5 | 67.38% | 28.5% | 4.114%
17080028, 16080027 |  | 16080027 | 11 | Marquette - APRC | 2017-10-01 | 2019-07-01 | 305500 | 0 | 0 | 167868.63 | 54340.42 | 0 | 3 | 0% | 100% | 0%
16110004 |  | 16110004 | 1 | DON-Cherry Pt P-194 UAS Fac | 2017-06-06 | 2019-06-28 | 79973 | 946 | 0 | 25326570.7 | 28493768.52 | 2600 | 6707 | 89.6% | 10.18% | 0.2236%
16060020 |  | 16060020 | 1 | UCHealth-HR Hospital | 2016-10-01 | 2019-06-01 | 397320 | 5307203.02 | 3762020.33 | 239503448.8864 | 243788120.19 | 287855.59 | 397342.99 | 82.72% | 17.28% | 0%
16110001 |  | 16110001 | 1 | DON-P611 Crab Island Secu. Enc | 2016-06-28 | 2019-04-30 | 2180 | 688048 | 486944 | 47489397.34 | 45065788.02 | 127576 | 142849.57 | 85.45% | 14.55% | 0%
17000001-040, 16030046 |  | 16030046 | 15 | MDI- Discovery Sq | 2017-10-30 | 2019-03-31 | 80000 | 713621.27 | 325261 | 22743842.4 | 21994416.08 | 24487.5 | 18930.36 | 92.37% | 7.625% | 0%
16030010 |  | 16030010 | 1 | MN United-MN Soccer Stadium | 2017-06-14 | 2019-02-22 | 350000 | 3299819.69 | 2659885 | 178582065.541 | 177512793.97 | 156265.79 | 178624.82 | 88.2% | 11.34% | 0.461%
16090003 |  | 16090003 | 1 | Rockford Memorial Hospital | 2016-07-01 | 2019-02-01 | 530000 | 602837.85 | 340051 | 316186531.0793 | 310912710.02 | 108559.5 | 95323.07 | 83.64% | 13.02% | 3.343%
16000004-040, 16090004 |  | 16090004 | 15 | 110 West Huron | 2017-09-05 | 2019-01-07 | 121722 | 3659 | 1093 | 45532958.9401 | 43952392.6 | 3311.5 | 8870.11 | 86.09% | 10.46% | 3.45%
16060025 |  | 16060025 | 1 | Woodward-Drake Renovation | 2017-01-03 | 2018-12-31 | 0 | 133427.33 | 305 | 27717200.65 | 26085463.78 | 9322.7 | 18633 | 92.01% | 7.994% | 0%
16141016, 16146021, 16148021 |  | 16146021 | 11 | Rush Creek Wind - HVT | 2016-04-29 | 2018-12-31 | 0 | 835963 | 1096382 | 53200972.6867 | 51913960.16 | 77844 | 88447.99 | 78.31% | 21.69% | 0%
16080022 |  | 16080022 | 1 | Froedtert-IPP Phase 2 | 2017-04-01 | 2018-12-01 | 40300 | 341762.76 | 230061 | 23050441.0008 | 22931598.6 | 25363.38 | 29076.25 | 89.66% | 9.407% | 0.9286%
16080023 |  | 16080023 | 1 | Froedtert-IPP Central Sterile | 2017-01-09 | 2018-11-21 | 31000 | 492480 | 267094 | 15791605.099 | 15769263.23 | 17589.1 | 21567.25 | 92.5% | 6.37% | 1.131%
16060012 |  | 16060012 | 1 | Park Creek-Central Park Bridge | 2017-02-01 | 2018-10-31 | 0 | 0 | 0 | 827980 | 893155.25 | 100 | 9 | 100% | 0% | 0%
16141016, 16146021, 16148021 |  | 16148021 | 21 | Rush Creek Civil | 2017-06-03 | 2018-10-12 | 0 | 1591045 | 1009403 | 26694294.14 | 30584264.05 | 126660 | 148639.55 | 78.13% | 21.87% | 0%
16141016, 16146021, 16148021 |  | 16141016 | 1 | Rush Creek Wind | 2016-06-03 | 2018-10-12 | 0 | 88359 | 16124 | 173967484.58 | 169456153.36 | 240639 | 245250.55 | 82.86% | 17.14% | 0%
16080028 |  | 16080028 | 1 | Johnson Controls - Misc. Jobs | 2016-12-28 | 2018-10-01 | 0 | 24 | 0 | 56100 | 40366.37 | 383 | 259.37 | 91.13% | 8.868% | 0%
16090009 |  | 16090009 | 1 | Harper College Building M | 2017-03-01 | 2018-08-31 | 132000 | 372.6 | 47 | 34818630.35 | 34781108.81 | 4264 | 4938.98 | 87.64% | 11.39% | 0.9719%
16110002 |  | 16110002 | 1 | DOA-Comm Conc Encased DuctBank | 2017-04-22 | 2018-08-06 | 4500 | 0 | 0 | 867733.17 | 899063.25
16080003 |  | 16080003 | 1 | Ministry HC - St. Clare's Exp. | 2016-07-05 | 2018-07-27 | 44219 | 508644.5 | 303217 | 18996538.8878 | 18482550.07 | 30209.5 | 32819 | 90.52% | 9.312% | 0.1676%
16080012 |  | 16080012 | 1 | Milwaukee Bucks New Arena | 2016-06-01 | 2018-07-24 | 730000 | 3259426.51 | 1896968 | 337490358.9682 | 339038734.98 | 168629.49 | 192033.67 | 86.98% | 12.81% | 0.2106%
16060030 |  | 16060030 | 1 | Park Creek-Filing 52 | 2016-12-15 | 2018-06-30 | 0 | 0 | 7 | 780635 | 835305.35 | 312 | 1842 | 97.88% | 2.117% | 0%
16145010 |  | 16145010 | 1 | Big Lake Solar Garden - NRG | 2016-10-17 | 2018-06-30 | 6912000 | 420018 | 419110 | 5616591.4316 | 5872798.51 | 33072 | 33581.45 | 85.63% | 10.45% | 3.914%
18060010, 17060007, 17060006, 16060029 |  | 16060029 | 31 | Westfield-4120 Infrastructure | 2017-03-01 | 2018-05-31 | 0 | 554 | 1506 | 9832872.47 | 9629111.95 | 1635 | 6166.5 | 94.28% | 5.716% | 0%
16030038 |  | 16030038 | 1 | Jack Links-HQ Improvement | 2016-12-15 | 2018-05-31 | 77267 | 284692.71 | 80926 | 22653399.6324 | 22533633.5 | 14953.7 | 15532.12 | 94.96% | 4.822% | 0.2189%
16030030 |  | 16030030 | 1 | Block 9 Redevelopment | 2016-10-31 | 2018-05-31 | 273600 | 0 | 0 | 781502.18 | 733023.11 | 0 | 260 | 100% | 0% | 0%
16040007 |  | 16040007 | 1 | MDI-Downtown Hampton Inn | 2017-02-08 | 2018-05-09 | 123970 | 0 | 0 | 28214146.5753 | 25871948.68 | 7834.7 | 9685 | 90.33% | 9.67% | 0%
16060014 |  | 16060014 | 1 | Park Creek-Filing MD | 2016-08-01 | 2018-04-30 | 0 | 500 | 0 | 544409 | 547379.68 | 310 | 2151 | 96.61% | 3.394% | 0%
16148020 |  | 16148020 | 1 | Big Lake Solar -Civil | 2016-10-26 | 2018-03-31 | 0 | 1808 | 722 | 345409.91 | 182785.62 | 900 | 360.5 | 88.9% | 11.1% | 0%
16030035 |  | 16030035 | 1 | Theodore Roosevelt Library |  | 2018-03-31 | 60000 | 0 | 0 | 711691.33 | 703033.52
16030023 |  | 16030023 | 1 | Northern Stack V | 2016-08-15 | 2018-03-31 | 118400 | 295 | 58 | 12459968.2763 | 10856227.25 | 15681 | 12054.62 | 92.82% | 7.176% | 0%
16030042 |  | 16030042 | 1 | Westminster-Main Kitchen Rmdl | 2016-11-01 | 2018-03-30 | 1232 | 24 | 0 | 406529.97 | 400533.07 | 297 | 398 | 99.5% | 0.5025% | 0%
16060021 |  | 16060021 | 1 | UCH-Inverness Health Ctr | 2017-01-01 | 2018-02-01 | 0 | 1308 | 0 | 90391.39 | 160757.2
16040006 |  | 16040006 | 1 | SRP History Center | 2017-04-03 | 2018-02-01 | 3171 | 0 | 0 | 325903.3 | 318994.8
16030034 |  | 16030034 | 1 | Douglas Cty Hos-Surgery Exp | 2016-09-09 | 2018-01-31 | 32121 | 111011 | 20288 | 6908161.83 | 6529652.74 | 13371 | 12900 | 87.28% | 11.79% | 0.9225%
16030013 |  | 16030013 | 1 | Westminster-ODOF | 2016-04-18 | 2018-01-19 | 165000 | 1496570 | 945050 | 39555182.6296 | 41077926.77 | 88282.5 | 126131.37 | 91.61% | 8.371% | 0.02299%
16148019 |  | 16148019 | 1 | Upton I Solar -Civil | 2016-10-10 | 2017-12-31 | 0 | 343688 | 334272 | 4932535.5755 | 4602463.03 | 14878 | 16538.5 | 82.14% | 17.86% | 0%
16060013 |  | 16060013 | 1 | Park Creek-Eastridge Dev. | 2016-08-01 | 2017-12-31 | 0 | 0 | 0 | 2336 | 2352.54
16040009 |  | 16040009 | 1 | SRP-PAB Cap Improve FY17 |  | 2017-12-31 | 80000 | 1 | 0 | 447093.14 | 439278.92 | 0 | 0 | 0% | 0% | 0%
16145003 |  | 16145003 | 1 | Hudson Solar Garden - SunShare | 2016-06-06 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 6385.19
16145004 |  | 16145004 | 1 | Quincy Solar Garden - SunShare | 2017-06-01 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 7850.28
16145005 |  | 16145005 | 1 | Imboden II Solar - SunShare | 2017-06-01 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 8923.74
16145006 |  | 16145006 | 1 | Imboden III Solar - SunShare | 2017-06-01 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 9440.62
16145024 |  | 16145024 | 1 | McHattie CSG - SunShare | 2017-07-04 | 2017-12-31 | 5530000 | 9 | 0 | 170483 | -151900.64
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 |  | 16145018 | 21 | Jasper Solar I-JasperSlrFrmLLC | 2017-03-08 | 2017-12-31 | 93377830 | 6572286 | 4069496 | 100643640.086 | 97307869.05 | 177920 | 199123.97 | 89.47% | 10.53% | 0%
16141026 |  | 16141026 | 1 | 2016 TX Sales Tax Audit | 2015-01-01 | 2017-12-31 | 0 | 0 | 0 | 0.01 | 956378.56
16030045 |  | 16030045 | 1 | UMN-VFW/Masonic Relocation | 2017-02-01 | 2017-12-29 | 39000 | 345391.25 | 71633 | 8697971.27 | 8786377.25 | 11074 | 11457.04 | 93.45% | 6.001% | 0.5499%
16150002 |  | 16150002 | 1 | B&G - Omni Hotel at SunTrust | 2016-03-02 | 2017-12-28 | 264000 | 0 | 0 | 417149 | 419450.63
16080024 |  | 16080024 | 1 | Aurora Kenosha MOB Suite Remdl | 2016-12-01 | 2017-12-22 | 11601 | 85568 | 48280 | 2600068.97 | 2591332.67 | 4285 | 3294.5 | 91.43% | 8.545% | 0.03035%
16080007 |  | 16080007 | 1 | Kohler Co. - Inn on Woodlake E | 2016-11-01 | 2017-11-30 | 59000 | 46669 | 40046 | 11495498.22 | 11302855.23 | 6151 | 6265.5 | 95.34% | 4.621% | 0.0399%
16141014 |  | 16141014 | 1 | Rocksprings Akuo Wind | 2016-12-12 | 2017-11-30 | 0 | 29178 | 15968 | 57332461.42 | 55445035.53 | 70996 | 73508 | 84.62% | 15.38% | 0%
16141021 |  | 16141021 | 1 | Firewheel Transmission OK | 2017-04-15 | 2017-11-03 | 0 | 0 | 0 | 632977 | 631573.26
16060032 |  | 16060032 | 1 | Town of Castle Rock-Festival | 2016-11-07 | 2017-11-01 | 0 | 13628 | 1198 | 5435805.1018 | 5540790.68 | 8273 | 10436.5 | 77.32% | 22.68% | 0%
16060010 |  | 16060010 | 1 | RTD-Civic Center Project | 2016-07-05 | 2017-10-27 | 0 | 1056537 | 435694 | 25527777.27 | 26271805.6 | 36854 | 61831.5 | 84.57% | 15.43% | 0%
16040010 |  | 16040010 | 1 | Rio de Flag Aeration | 2017-03-01 | 2017-10-27 | 0 | 52 | 0 | 1044655.08 | 1054455 | 697 | 614 | 97.39% | 2.606% | 0%
16030031 |  | 16030031 | 1 | City of Mpls-Target Center Ice | 2017-05-15 | 2017-10-13 | 20000 | 0 | 0 | 72951 | 8607.79 | 48 | 62.78 | 88.85% | 11.15% | 0%
16060035 |  | 16060035 | 1 | SCL-Par Excellence | 2016-12-12 | 2017-10-06 | 0 | 0 | 0 | 72125 | 50430.63 | 0 | 687 | 97.23% | 2.766% | 0%
16090002 |  | 16090002 | 1 | SAIC HVAC PH2 | 2016-01-25 | 2017-10-01 | 50000 | 3455.9 | 227 | 6765903.5 | 5688334.75 | 8573 | 5354.06 | 86.06% | 13.71% | 0.2335%
16030014 |  | 16030014 | 1 | CentraCare - Long Prairie MC | 2016-05-09 | 2017-10-01 | 65000 | 39241 | 202232 | 13295555.43 | 13029898.86 | 17833.5 | 16814.5 | 94.42% | 5.516% | 0.05947%
16090001 |  | 16090001 | 1 | Wheaton College SOM | 2016-09-01 | 2017-09-30 | 51000 | 76316.04 | 38790 | 18431689.8905 | 18179479.37 | 12882 | 14045.2 | 90.89% | 8.031% | 1.082%
16148018 |  | 16148018 | 1 | Meadow Lake V Civil | 2016-10-17 | 2017-09-30 | 0 | 694736 | 510577 | 9179639.2741 | 8998860.86 | 26888 | 26345.5 | 72.14% | 26.87% | 0.9869%
16145016 |  | 16145016 | 1 | Upton County Solar-ConEdison | 2016-11-04 | 2017-09-30 | 212589000 | 13112484 | 12893396 | 116539897.0871 | 106216177.88 | 555607.2 | 521262.75 | 83.78% | 16.22% | 0%
16141015 |  | 16141015 | 1 | Meadow Lake V Wind | 2016-10-21 | 2017-09-27 | 0 | 13622 | 10837 | 33028756.74 | 33818729.15 | 58278 | 75645.5 | 68.36% | 20.94% | 10.7%
16080011 |  | 16080011 | 1 | Ministry HC - St. Clare's MOB | 2016-08-01 | 2017-09-25 | 0 | 202612 | 87243 | 6471936.29 | 6394402.55 | 10244 | 11110 | 90.97% | 8.857% | 0.171%
16080010 |  | 16080010 | 1 | Ministry HC - Hyperbaric Oxygn | 2016-08-01 | 2017-09-25 | 10400 | 67426 | 21780 | 3062490.215 | 2991715.2 | 5151 | 5298.5 | 85.68% | 13.98% | 0.3397%
16148017 |  | 16148017 | 1 | Rocksprings Akuo Civil | 2016-11-30 | 2017-09-15 | 0 | 1014795 | 571396 | 8400143.4809 | 7743996.73 | 27380 | 30233 | 80.85% | 19.15% | 0%
16090010 |  | 16090010 | 1 | School of Art Inst. Auditorium | 2016-08-01 | 2017-08-31 | 9760 | 109802.47 | 11954 | 6620797.6938 | 5670611.25 | 7575 | 8666.22 | 81.49% | 17.14% | 1.373%
16090006 |  | 16090006 | 1 | QTS CHI Phase 4 Addition | 2016-06-01 | 2017-08-31 | 248000 | 736924.32 | 527236 | 51972399.9988 | 52407320.19 | 30215.55 | 35859.99 | 90.97% | 7.951% | 1.078%
16080025 |  | 16080025 | 1 | AHC-St. Luke's IR#2 | 2017-05-01 | 2017-08-31 | 0 | 21660.46 | 0 | 897243.59 | 850302.57 | 1117.3 | 1175.5 | 88.9% | 11.1% | 0%
16030033 |  | 16030033 | 1 | WFPS - Hockey Facility | 2016-09-08 | 2017-08-21 | 67143 | 1065 | 809 | 14194159.18 | 14293755.16 | 5761 | 6627.5 | 85.44% | 14.29% | 0.2716%
16030041 |  | 16030041 | 1 | Vibra-Parking Lot-SFMC | 2016-11-14 | 2017-08-20 | 32711 | 0 | 0 | 247389 | 245308.86
16080017 |  | 16080017 | 1 | AHC-Oak Creek Clinic | 2016-12-17 | 2017-08-18 | 51683 | 208080.08 | 191583 | 10517273.979 | 10612993.59 | 11644.6 | 10836.5 | 89.79% | 10.09% | 0.12%
16040008 |  | 16040008 | 1 | Pecos SWTP Rehab Project | 2016-07-11 | 2017-07-28 | 0 | 105295.02 | 104049 | 2445792.3994 | 2507305.65 | 6920 | 7477.5 | 93.41% | 6.593% | 0%
16141010 |  | 16141010 | 1 | Ringer Hill Wind | 2016-05-16 | 2017-07-28 | 0 | 68363 | 64792 | 22644837.47 | 20139349.12 | 29024 | 32103.75 | 64.06% | 30% | 5.941%
16030028 |  | 16030028 | 1 | MDI-Allina Hastings PCC | 2016-10-04 | 2017-07-25 | 50000 | 286232 | 253050 | 7536730.12 | 7075629.51 | 13748 | 13194.91 | 94.12% | 5.639% | 0.2425%
16030040 |  | 16030040 | 1 | MDI-Hastings Clinic Street | 2017-04-03 | 2017-07-24 | 0 | 1 | 0 | 887968 | 873865.59 | 830 | 897.5 | 83.57% | 16.43% | 0%
16030020 |  | 16030020 | 1 | NDSU - Churchill Hall Reno | 2016-05-31 | 2017-07-24 | 44496 | 233049 | 147178 | 9416271.4301 | 8902475.85 | 17527.3 | 12197.39 | 89.16% | 10.84% | 0%
16060022 |  | 16060022 | 1 | Columbine Dev-Quality Italian | 2016-09-20 | 2017-07-20 | 0 | 161 | 0 | 1955989 | 1820592.12 | 673 | 1116.5 | 72.15% | 27.85% | 0%
16030024 |  | 16030024 | 1 | Westminster Masonry Restor | 2016-07-11 | 2017-07-07 | 7900 | 22783 | 21332 | 880211.16 | 928503.23 | 4813 | 6149 | 90.65% | 9.351% | 0%
16060019 |  | 16060019 | 1 | Larimer Humane Society Precon | 2016-04-01 | 2017-07-01 | 38000 | 0 | 0 | 59999 | 58263.8
16030037 |  | 16030037 | 1 | UMN-Wilson Library Minitex | 2017-02-01 | 2017-07-01 | 13500 | 6417 | 0 | 1899265.15 | 1901489.34 | 2338 | 2622.83 | 91.38% | 7.473% | 1.144%
16090007, 17090001 |  | 16090007 | 1 | Northwestern Welsh Ryan Precon | 2016-06-01 | 2017-06-30 | 200000 | 0 | 0 | 233750 | 253070.51 | 0 | 11 | 90.91% | 9.091% | 0%
16148022 |  | 16148022 | 1 | Vibra Healthcare Parking Lot | 2016-11-16 | 2017-06-30 | 0 | 0 | 0 | 64253 | 37462.03
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 |  | 16145026 | 1 | Ridgeland Grubbing - Adger | 2017-01-02 | 2017-06-30 | 0 | 2936 | 2936 | 47045 | 43305.1 | 729 | 729 | 98.63% | 1.372% | 0%
16145001 |  | 16145001 | 1 | NSA Crane Solar - Duke Energy | 2016-04-21 | 2017-06-30 | 24304800 | 3190267 | 3227395 | 15211282.8289 | 15481159.19 | 80042.42 | 89841.5 | 80.34% | 19.66% | 0%
16145021 |  | 16145021 | 1 | Alamo V Fndtn Upgrade Ph II | 2016-10-01 | 2017-06-30 | 120279600 | 256787 | 220426 | 9486369.75 | 9500967.48 | 94962.7 | 95832.5 | 87.78% | 12.22% | 0%
16141008 |  | 16141008 | 1 | Firewheel Phase A1 | 2016-03-07 | 2017-06-30 | 0 | 38 | 0 | 2208726 | 2110505.68
16146018 |  | 16146018 | 1 | Rocksprings Akuo Wind - HVT | 2017-01-02 | 2017-06-29 | 0 | 111250 | 109538 | 18778545.77 | 17650402.5 | 34161.85 | 52206.49 | 82% | 18% | 0%
16150001 |  | 16150001 | 1 | One Ballpark Ctr Office Bldg | 2015-12-04 | 2017-06-07 | 255278 | 0 | 0 | 288480.0944 | 311342.16
16141011 |  | 16141011 | 1 | MSA Maintenance Wind | 2016-06-06 | 2017-06-06 | 0 | 9 | 0 | 694068.3061 | 554446.96 | 8929 | 7406.5 | 92.38% | 7.622% | 0%
16060009 |  | 16060009 | 1 | Hub-Mixed Use Development | 2016-08-01 | 2017-06-05 | 507000 | 0 | 0 | 0.01 | 576833.02 | 0 | 497 | 68.11% | 31.89% | 0%
16148011, 14060015 |  | 16148011 | 1 | Sterling Ranch Filing 1 Civil | 2016-06-01 | 2017-06-01 | 0 | 427771 | 188018 | 3593264.6088 | 4568600.52 | 11645.5 | 4676.5 | 74.44% | 25.56% | 0%
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 |  | 16145017 | 31 | RidgelandSolarI-RdglndSolarLLC | 2016-11-22 | 2017-06-01 | 12240000 | 1596994 | 693002 | 15229815.894 | 14586436.67 | 28152 | 33436.74 | 90.88% | 9.116% | 0%
16141006 |  | 16141006 | 1 | Ida Grove - Wind | 2016-04-01 | 2017-06-01 | 0 | 543218 | 482892 | 95322247.8416 | 95219367.11 | 126182.5 | 117183 | 59.99% | 35.41% | 4.598%
16141007 |  | 16141007 | 1 | O'Brien County - Wind | 2016-04-16 | 2017-06-01 | 0 | 217306 | 174032 | 66091490.1826 | 60678982.74 | 105189.5 | 84195 | 60.98% | 36.48% | 2.545%
16148003 |  | 16148003 | 1 | Ida Grove - Civil | 2016-04-11 | 2017-05-31 | 0 | 3012503 | 2301029 | 21569928.41 | 19887440.41 | 143672 | 66259.25 | 70.52% | 28.98% | 0.5014%
16148014 |  | 16148014 | 1 | Bongards Solar -Civil | 2016-08-03 | 2017-05-31 | 0 | 43 | 0 | 576441.45 | 428025.37 | 1360 | 1183 | 80.73% | 19.27% | 0%
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 |  | 16145027 | 11 | Jasper Grubbing - Adger | 2017-01-24 | 2017-05-31 | 0 | 36043.4 | 36016 | 900450.69 | 1252344.69 | 5278 | 6350.08 | 73.37% | 26.63% | 0%
17000004-040, 16050004 |  | 16050004 | 15 | Smokey Pt Behavioral Hospital | 2016-06-01 | 2017-05-29 | 70257 | 311396.25 | 291276 | 18810983.9003 | 18242213.85 | 9998.21 | 8738.03 | 88.58% | 11.24% | 0.1717%
16030043 |  | 16030043 | 1 | Trinity Health Medical Center | 2016-11-23 | 2017-05-15 | 840000 | 3 | 0 | 805115.84 | 805115.84 | 370 | 240 | 100% | 0% | 0%
16145008 |  | 16145008 | 1 | Alamo V Fnd Upgrade | 2016-05-15 | 2017-05-01 | 120279600 | 85883.5 | 83447 | 5120665.15 | 5031238.77 | 49127 | 57721.5 | 93.28% | 6.722% | 0%
16145022 |  | 16145022 | 1 | Alamo 5: 1 MW Expansion - CED | 2016-10-01 | 2017-04-30 | 1333800 | 43208 | 2 | 1058501.11 | 1060860.61 | 3331 | 5226 | 91.01% | 8.993% | 0%
16080019 |  | 16080019 | 1 | AHC-Grafton MRI #2 / Alcove BO | 2017-01-03 | 2017-04-14 | 687 | 10505 | 17174 | 593187 | 556409.12 | 593 | 900 | 82.33% | 17.67% | 0%
16080005 |  | 16080005 | 1 | Froedtert-ISIP | 2016-01-04 | 2017-03-31 | 77595 | 437233 | 249079 | 34630159.0083 | 34282844.6 | 9538.51 | 11279.62 | 82.44% | 13.61% | 3.95%
16146020 |  | 16146020 | 1 | Bronco Battery Storage HVT | 2016-10-25 | 2017-03-31 | 0 | 5566 | 6288 | 173432 | 169616.46 | 745 | 1174 | 91.52% | 8.475% | 0%
16050006 |  | 16050006 | 1 | 2016 PEMC Small Projects | 2016-07-18 | 2017-03-31 | 780 | 1152.63 | 0 | 747923.1051 | 741557.79 | 1391.38 | 1536.14 | 96.65% | 2.376% | 0.9765%
16145011 |  | 16145011 | 1 | Wabasha Solar Garden - NRG | 2016-08-22 | 2017-03-31 | 4078080 | 211740 | 209685 | 3426586.46 | 3496380.36 | 32347 | 21418.25 | 81.41% | 18.41% | 0.1809%
16145025 |  | 16145025 | 1 | Steinkraus CSG - Sunshare | 2016-10-25 | 2017-03-31 | 4147000 | 11 | 0 | 35239 | 32271.64
16141013 |  | 16141013 | 1 | Tenaska MSA | 2016-07-14 | 2017-03-31 | 0 | 0 | 0 | 48776 | 38098.65
16146010 |  | 16146010 | 1 | Welsh Upgrade HVT | 2016-07-25 | 2017-03-29 | 0 | 283776 | 262812 | 2441530.344 | 2346312.35 | 19263 | 14500 | 88.21% | 11.79% | 0%
16030022 |  | 16030022 | 1 | Allina-Unity Mental Health | 2016-05-16 | 2017-03-10 | 0 | 2481 | 0 | 5969131.47 | 6457355.52 | 15975 | 24733.37 | 93.3% | 6.216% | 0.4852%
16030016 |  | 16030016 | 1 | RMC Small Projects 2016 | 2016-03-01 | 2017-03-01 | 8500 | 1775.8 | 0 | 66121.88 | 67197.91 | 382 | 266 | 88.35% | 11.65% | 0%
16030027 |  | 16030027 | 1 | Fairview Ridges - 2016 Annual | 2016-07-11 | 2017-02-19 | 0 | 5442.1 | 0 | 161158.8 | 167911.51 | 895 | 851.5 | 89.67% | 10.33% | 0%
16148024 |  | 16148024 | 1 | Firewheel Phase A1 Civil | 2016-12-07 | 2017-02-15 | 0 | 101334 | 0 | 419600 | 386580.99 | 3806 | 1258 | 75.24% | 24.76% | 0%
16040005 |  | 16040005 | 1 | AlaskaUSA-Scottsdale Branch | 2017-01-03 | 2017-02-03 | 405 | 0 | 0 | 229682 | 222981.28 | 0 | 2 | 100% | 0% | 0%
16135002 |  | 16135002 | 1 | SCT Geotech-LA | 2016-11-28 | 2017-01-31 | 0 | 115 | 0 | 97300 | 89966.44 | 80 | 0 | 0% | 0% | 0%
16135003 |  | 16135003 | 1 | SCT Geotech-MS | 2016-11-28 | 2017-01-31 | 0 | 30 | 0 | 103545 | 87045.88
16135004 |  | 16135004 | 1 | SCT Geotech TX | 2016-11-28 | 2017-01-31 | 0 | 23 | 0 | 24800 | 21118.58 | 10 | 0 | 0% | 0% | 0%
16146003 |  | 16146003 | 1 | Wind - Western Plains HVT | 2016-04-18 | 2017-01-31 | 0 | 212 | 0 | 10589663 | 10207785.16 | 0 | 0 | 0% | 0% | 0%
16141023 |  | 16141023 | 1 | Muscatine Blade Unload - Wind | 2016-12-12 | 2017-01-20 | 0 | 46 | 0 | 373948.66 | 271400.4 | 1820 | 1468.5 | 91.79% | 8.206% | 0%
16141024 |  | 16141024 | 1 | Siemens Blade Repair MSA Wind | 2016-12-17 | 2017-01-15 | 0 | 80 | 0 | 646118.445 | 724939.81 | 19238 | 9633.75 | 72.99% | 25.79% | 1.22%
16141020 |  | 16141020 | 1 | Ocotillo T126 Turbine Removal | 2016-12-19 | 2017-01-13 | 0 | 150 | 0 | 396256 | 317260.27 | 1507 | 1435.5 | 84.64% | 15.01% | 0.3483%
16030036 |  | 16030036 | 1 | SCCR-Office Rmdl & Sterlizer E | 2016-10-07 | 2017-01-06 | 750 | 12 | 0 | 83573.08 | 78758.91 | 0 | 10 | 50% | 50% | 0%
16060026 |  | 16060026 | 1 | SCL-Lutheran Med Ctr-CT 6 | 2016-09-15 | 2017-01-01 | 0 | 0 | 0 | 168060 | 168881.81 | 340 | 473 | 95.45% | 4.545% | 0%
16030001 |  | 16030001 | 1 | FUMC-Annual Contract 2016 | 2016-01-01 | 2017-01-01 | 0 | 100 | 0 | 3853531.9956 | 3853500.88 | 7062.33 | 10421.5 | 97.33% | 2.346% | 0.3262%
16090008 |  | 16090008 | 1 | Sky Landing Sculpture | 2016-08-01 | 2016-12-31 | 0 | 0 | 0 | 25000 | 142575.98 | 0 | 593.79 | 93.6% | 6.4% | 0%
16090005 |  | 16090005 | 1 | Chicago Office Buildout | 2016-04-01 | 2016-12-31 | 20255 | 0 | 172 | 2674880 | 2986355.57 | 690 | 1591.75 | 88.41% | 10.81% | 0.7853%
16148001, 16146001, 15145028 |  | 16148001 | 1 | Pearl Solar -Civil | 2016-01-01 | 2016-12-31 | 0 | 107964 | 75983 | 1231300 | 946913.55 | 3615 | 2196 | 78.16% | 21.84% | 0%
16148002 |  | 16148002 | 1 | Wind - Hidalgo Civil | 2016-02-08 | 2016-12-31 | 0 | 2216133 | 2170317 | 10895789.8448 | 8474914.34 | 49441.27 | 38591.5 | 77.9% | 22.1% | 0%
16148004 |  | 16148004 | 1 | O'Brien County - Civil | 2016-04-04 | 2016-12-31 | 0 | 771343 | 639291 | 12024906.8682 | 11035012.73 | 34382.5 | 35695.5 | 70.8% | 28.93% | 0.2787%
16148006 |  | 16148006 | 1 | Mariah del Norte Civil | 2016-03-07 | 2016-12-31 | 0 | 1045701 | 1045484 | 6451066.69 | 5227795.43 | 27300 | 26176.5 | 78.13% | 21.87% | 0%
16148007 |  | 16148007 | 1 | Western Plains Civil | 2016-04-11 | 2016-12-31 | 0 | 1303317 | 1319789 | 13751361.59 | 11642058.6 | 51579 | 37365 | 78.56% | 21.44% | 0%
16148008 |  | 16148008 | 1 | NSA Crane Civil | 2016-05-16 | 2016-12-31 | 0 | 34332 | 10290 | 1806968.62 | 1585096.75 | 3150 | 1470 | 89.56% | 10.44% | 0%
16148010 |  | 16148010 | 1 | Ringer Hill - Civil |  | 2016-12-31 | 0 | 3 | 0 | 94483 | 94282.33 | 700 | 0 | 0% | 0% | 0%
16148015 |  | 16148015 | 1 | Glazier Solar -Civil | 2016-09-06 | 2016-12-31 | 0 | 12 | 0 | 255184 | 206271.85 | 850 | 897.5 | 85.24% | 14.76% | 0%
16148016 |  | 16148016 | 1 | Wabasha Solar -Civil | 2016-09-26 | 2016-12-31 | 0 | 12 | 0 | 316106 | 293348.38 | 850 | 1189.5 | 84.03% | 15.97% | 0%
16148023 |  | 16148023 | 1 | Plum Creek Civil PTC Work | 2016-12-05 | 2016-12-31 | 0 | 15101 | 7429 | 269700 | 218858.36 | 2298 | 575.5 | 76.46% | 23.54% | 0%
16148025 |  | 16148025 | 1 | Foard City 2016 PTC Civil | 2016-12-01 | 2016-12-31 | 0 | 42623 | 35844 | 479793.8 | 392459.6 | 1845 | 1478 | 68.03% | 31.97% | 0%
16060024 |  | 16060024 | 1 | NJH-Misc. Projects | 2016-09-26 | 2016-12-31 | 0 | 0 | 0 | 32733.38 | 53366.93 | 0 | 260 | 78.85% | 21.15% | 0%
16060027 |  | 16060027 | 1 | HNTB-Sports Auth Field Site | 2016-09-16 | 2016-12-31 | 0 | 0 | 0 | 26431 | -1412
16060028 |  | 16060028 | 1 | MDI-Block 173 Hotel | 2016-07-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | 67849.53
16080016 |  | 16080016 | 1 | AHC-Summit MRI | 2016-09-27 | 2016-12-31 | 687 | 3996 | 3081 | 593876 | 531248.75 | 675 | 329.5 | 96.81% | 3.187% | 0%
16030997 |  | 16030997 | 1 | 2016 Mpls Equip Facility Recog | 2016-01-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | 0
16145019 |  | 16145019 | 1 | Pena Station - SunPower | 2016-10-03 | 2016-12-31 | 1678000 | 6516 | 7017 | 710622.61 | 612547.1 | 5214.5 | 3841.5 | 88.3% | 11.7% | 0%
16150999 |  | 16150999 | 1 | NPG 2016 Closed Projects | 2016-01-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | 0
16141001 |  | 16141001 | 1 | MSA 2016 Wind |  | 2016-12-31 | 0 | 32450 | 0 | 10245305.2479 | 8259778.66 | 98776 | 119983.25 | 74.44% | 25.14% | 0.4176%
16141004 |  | 16141004 | 1 | MES 2016 Misc. Wind | 2016-01-01 | 2016-12-31 | 0 | 506 | 0 | 82123.9991 | 64712.19 | 1058 | 643.5 | 79.49% | 20.51% | 0%
16141005 |  | 16141005 | 1 | Westar Energy-Western Plains W | 2016-04-18 | 2016-12-31 | 0 | 740703.27 | 702365 | 83805299.0135 | 81624439.68 | 97120 | 115917 | 77.06% | 22.94% | 0%
16141017 |  | 16141017 | 1 | A&D PMT Wind | 2016-11-10 | 2016-12-31 | 0 | 211 | 0 | 3178940 | 3316099.01 | 7446 | 9494.5 | 74.3% | 25.7% | 0%
16141019 |  | 16141019 | 1 | Foard City 2016 PTC | 2016-12-07 | 2016-12-31 | 0 | 0 | 0 | 566809.82 | 556686.17
16141022 |  | 16141022 | 1 | Alstom Decom. Wind | 2016-11-10 | 2016-12-31 | 0 | 3 | 0 | 574224.25 | 513762.02 | 3641 | 1376.5 | 84.78% | 15.22% | 0%
16080008 |  | 16080008 | 1 | Engberg Anderson-GMIA Skywalk | 2016-09-01 | 2016-12-30 | 10000 | 0 | 0 | 3495 | 822.53
16060005 |  | 16060005 | 1 | MillerCoors-Kiln 9 Fan | 2016-02-26 | 2016-12-28 | 21000 | 77652.75 | 32172 | 8025697.885 | 7737192.92 | 8373.95 | 7827.5 | 88.06% | 11.94% | 0%
16060034 |  | 16060034 | 1 | Co Rockies-Coors Fld Sales | 2016-11-23 | 2016-12-23 | 0 | 10 | 0 | 216760.13 | 205038.56 | 364 | 1118.5 | 93.56% | 6.437% | 0%
16060011 |  | 16060011 | 1 | Park Creek-PA Trunk Open Space | 2016-05-09 | 2016-12-17 | 0 | 293273 | 128605 | 6071858.592 | 6047598.31 | 7640 | 36195 | 93.6% | 6.404% | 0%
16050008 |  | 16050008 | 1 | Nike Flight Operations Center | 2016-09-26 | 2016-12-12 | 40000 | 17 | 0 | 633024.02 | 598653.98 | 0 | 0 | 0% | 0% | 0%
16080006 |  | 16080006 | 1 | AHC-St. Luke's CT#1 & #3 Renov | 2016-07-25 | 2016-12-09 | 1824 | 2409 | 0 | 1448603.43 | 1258599.11 | 1733 | 976.15 | 93.55% | 6.454% | 0%
16080004 |  | 16080004 | 1 | Froedtert-Simulation Learn Ctr | 2016-06-01 | 2016-12-02 | 11330 | 27765 | 51554 | 3084197 | 3064864.54 | 9357 | 9961 | 90.29% | 9.477% | 0.2359%
16146006 |  | 16146006 | 1 | Ida Grove - HVT |  | 2016-12-02 | 0 | 1252188 | 1370 | 27687902.2 | 26741839.29 | 33080 | 31866 | 73.54% | 26.46% | 0%
16146005 |  | 16146005 | 1 | O'Brien County - HVT | 2016-04-04 | 2016-12-01 | 0 | 627748 | 627927 | 16886575.13 | 16525295.01 | 23986 | 28501.75 | 77.69% | 22.31% | 0%
16146013 |  | 16146013 | 1 | Siemens Industry,Inc-Lk Er ECS | 2016-08-01 | 2016-11-30 | 0 | 0 | 0 | 62150 | 58223.02
16146014 |  | 16146014 | 1 | MCC-Lake Erie Con. HCS Geo | 2016-08-15 | 2016-11-30 | 0 | 0 | 0 | 3366 | 3367.36
16146014-110 |  | 16146014-110 | 1 | Siemens CAD Ltd-Lk Er HCS | 2016-08-15 | 2016-11-30 | 0 | 0 | 0 | 75737 | 71751.44
16080009 |  | 16080009 | 1 | Froedtert-Interim Gen. Solutn | 2016-04-18 | 2016-11-22 | 0 | 1782 | 1412 | 6884643 | 6889957.19 | 1397 | 2626.5 | 85.49% | 13.27% | 1.237%
16146019 |  | 16146019 | 1 | NSA Crane HVT | 2016-10-01 | 2016-11-22 | 0 | 41078 | 41108 | 409972.1 | 411796.73 | 1434 | 2349.25 | 88.09% | 11.91% | 0%
16050001 |  | 16050001 | 1 | Arauco NA Flakeboard Plant Imp | 2016-05-02 | 2016-11-18 | 0 | 1025 | 0 | 5536318.96 | 5143952.51 | 16 | 0 | 0% | 0% | 0%
16141012 |  | 16141012 | 1 | MES Western Plains IR Wind | 2016-07-11 | 2016-11-06 | 0 | 983 | 0 | 87220 | 73496.47 | 304 | 200 | 68% | 32% | 0%
16060002 |  | 16060002 | 1 | CoorsTek-WTM TI & Remodel | 2016-04-22 | 2016-11-01 | 31625 | 0 | 0 | 2763415.25 | 2731424.32 | 0 | 1443.5 | 89.85% | 10.15% | 0%
16146015 |  | 16146015 | 1 | DO NOT USE RockspringsHVT-Akuo | 2017-01-02 | 2016-11-01 | 0 | 0 | 0 | 10914 | 0
16080020 |  | 16080020 | 1 | MRIC - Capital Plan Study | 2016-08-01 | 2016-10-31 | 0 | 0 | 0 | 25000 | 13362.56
16060017 |  | 16060017 | 1 | SCL-Lutheran Med Ctr CT | 2016-07-25 | 2016-10-28 | 0 | 280 | 0 | 505698.38 | 504198.62 | 569 | 1836.5 | 91.29% | 8.712% | 0%
16050009 |  | 16050009 | 1 | Loews Regency Seattle Model RM | 2016-09-21 | 2016-10-25 | 823 | 12 | 0 | 58723 | 56955.72
16146017 |  | 16146017 | 1 | MES 2016 Misc. A&D HVT | 2016-10-03 | 2016-10-24 | 0 | 0 | 0 | 17300 | 18273.06
16040002 |  | 16040002 | 1 | Corona de Tucson Water | 2016-03-21 | 2016-10-21 | 0 | 16297 | 0 | 1292883.03 | 1404865.37 | 3517 | 3720 | 98.25% | 1.747% | 0%
16146012 |  | 16146012 | 1 | IHI-Tuscon Elec. Power 2 HVT | 2016-08-26 | 2016-10-19 | 0 | 403 | 0 | 63764.79 | 61348.41 | 388 | 313.5 | 79.74% | 20.26% | 0%
16141002 |  | 16141002 | 1 | Hidalgo Wind | 2016-02-01 | 2016-10-15 | 0 | 634000 | 628983 | 56257968.06 | 54666744.32 | 122711 | 123061 | 73.57% | 26.42% | 0.005282%
16080014 |  | 16080014 | 1 | Kohl's-EFC 5 | 2016-01-01 | 2016-10-03 | 0 | 0 | 0 | 791023 | 759175.14 | 0 | 20.15 | 100% | 0% | 0%
16060018 |  | 16060018 | 1 | Woodward-Coy Plaza | 2016-07-15 | 2016-09-30 | 0 | 0 | 0 | 1139979 | 991341.87 | 0 | 1697.5 | 84.27% | 15.73% | 0%
16030004 |  | 16030004 | 1 | Blake School-Athletic Triangle | 2016-03-21 | 2016-09-30 | 500 | 349 | 0 | 2030563.86 | 2081252.84 | 2513 | 2113.2 | 99.31% | 0.6862% | 0%
16030009 |  | 16030009 | 1 | U of MN-2016 Small Projects | 2016-05-09 | 2016-09-30 | 3500 | 29 | 0 | 440085.95 | 418755.47 | 369 | 314.63 | 89.51% | 10.49% | 0%
16148001, 16146001, 15145028 |  | 16146001 | 11 | Pearl Solar -HVT | 2016-04-11 | 2016-09-30 | 0 | 91805 | 91972 | 2590991.64 | 2128439.58 | 4148 | 1829 | 89.91% | 10.09% | 0%
16150005 |  | 16150005 | 1 | PSU - Lasch Bldg Maintenance |  | 2016-09-29 | 3500 | 0 | 0 | 108167.84 | 108354.48
16080013 |  | 16080013 | 1 | Marquette-Wisc Ave Demo Prjcts | 2016-04-26 | 2016-09-16 | 61000 | 1 | 0 | 1224512.93 | 1148436.2 | 0 | 210.5 | 92.87% | 3.8% | 3.325%
16030011 |  | 16030011 | 1 | Blake-MPAC Phase 1 Reno | 2016-06-13 | 2016-09-14 | 5627 | 3848 | 0 | 973530.06 | 951277.71 | 1425 | 1300.8 | 99.38% | 0.615% | 0%
16060004 |  | 16060004 | 1 | SCL-St Joseph's-NICU | 2016-05-09 | 2016-09-13 | 1414 | 0 | 0 | 643114.32 | 643459.48 | 0 | 1344.5 | 96.36% | 3.644% | 0%
16080018 |  | 16080018 | 1 | Johnson Controls - DES Lab | 2016-08-08 | 2016-09-09 | 7583 | 67 | 0 | 288352.82 | 275511.77 | 283 | 389.5 | 99.1% | 0.8986% | 0%
16030002 |  | 16030002 | 1 | US Bank - St. Anthony Falls | 2016-04-01 | 2016-09-01 | 3400 | 753 | 0 | 1587277.24 | 1666560.71 | 0 | 1038 | 88.54% | 11.46% | 0%
16030007 |  | 16030007 | 1 | IP Stream - Data Hall 3 | 2016-03-07 | 2016-09-01 | 9000 | 37088 | 11169 | 7546618 | 7509412.39 | 6978 | 6830.87 | 88.85% | 10.77% | 0.3733%
16060006 |  | 16060006 | 1 | Stadium Mgmt-Denver Broncos | 2016-04-01 | 2016-08-31 | 2304 | 13 | 0 | 2308038.57 | 2292704.34 | 1606.5 | 3262.5 | 87.85% | 12.15% | 0%
16030044 |  | 16030044 | 1 | UMN-Jane Sage Cowles | 2016-07-05 | 2016-08-31 | 50000 | 0 | 0 | 1086135.01 | 1089582.87
16145012 |  | 16145012 | 1 | Alamo VII Tracker - Nor-Cal | 2016-05-01 | 2016-08-30 | 132300000 | 10351 | 10223 | 427458.0049 | 222643.09 | 6818 | 4246.5 | 91.51% | 8.489% | 0%
16030003 |  | 16030003 | 1 | U of M - Mariucci Arena Locker | 2016-04-11 | 2016-08-12 | 0 | 71977 | 43324 | 3699523.19 | 3868690.51 | 4124 | 5785.62 | 90.53% | 9.195% | 0.2765%
16050007 |  | 16050007 | 1 | Loews Regency Fitness Center | 2016-08-01 | 2016-08-12 | 560 | 11 | 0 | 55490 | 54517.27
16148013 |  | 16148013 | 1 | Rockrimmon Civil | 2016-07-29 | 2016-08-06 | 0 | 1 | 0 | 25263.21 | 20370.53 | 0 | 241.5 | 53.42% | 46.58% | 0%
16040001 |  | 16040001 | 1 | Pecos Well Equipping | 2016-03-07 | 2016-08-04 | 0 | 9910 | 0 | 692205.833 | 747965.65 | 1087 | 1663 | 94.53% | 5.472% | 0%
16060015 |  | 16060015 | 1 | Murray & Stafford-Enterprise | 2016-04-01 | 2016-08-01 | 0 | 0 | 0 | 0.01 | 47422.01
16146007 |  | 16146007 | 1 | Jordan Creek HVT | 2016-04-30 | 2016-08-01 | 0 | 4 | 0 | 8181 | 8026.41 | 0 | 0 | 0% | 0% | 0%
16060008 |  | 16060008 | 1 | Dominican Friars-St Dominic's | 2016-03-01 | 2016-07-31 | 0 | 0 | 0 | 10162.5 | 15119.27
16146011 |  | 16146011 | 1 | AEP Panadero | 2016-07-18 | 2016-07-29 | 0 | 10069 | 0 | 41779.8754 | 30776.75 | 341.7 | 364.5 | 89.85% | 10.15% | 0%
16030008 |  | 16030008 | 1 | Hudson Hospital Outpatient Reg |  | 2016-07-15 | 500 | 24 | 0 | 85683.01 | 95871.32 | 304 | 618 | 100% | 0% | 0%
16040003 |  | 16040003 | 1 | AlaskaUSA-Peoria Branch | 2016-06-13 | 2016-07-15 | 438 | 0 | 0 | 223637.92 | 231779.7 | 0 | 12 | 100% | 0% | 0%
16146009 |  | 16146009 | 1 | MSA Maintenance HVT | 2016-06-15 | 2016-07-15 | 0 | 16 | 0 | 35390.45 | 22436.03 | 102 | 104 | 73.08% | 26.92% | 0%
16050002 |  | 16050002 | 1 | Boren Ave Retail | 2016-04-04 | 2016-07-05 | 1700 | 33 | 0 | 158484.02 | 142959.91 | 44 | 0 | 0% | 0% | 0%
16050003 |  | 16050003 | 1 | Metropolitan Cafe and Deli | 2016-04-04 | 2016-07-05 | 1700 | 0 | 0 | 172081.56 | 162023.46
16050005 |  | 16050005 | 1 | The Wild Building | 2016-05-27 | 2016-06-07 | 5000 | 0 | 0 | 12138 | 10422.75 | 118 | 109 | 100% | 0% | 0%
16146002 |  | 16146002 | 1 | Solara AEP Metering | 2016-02-08 | 2016-05-31 | 0 | 4692 | 0 | 15801.41 | 13978.16 | 146 | 150 | 80% | 20% | 0%
16146008 |  | 16146008 | 1 | Pyron WTG 156 HVT | 2016-05-05 | 2016-05-27 | 0 | 63 | 0 | 113864 | 41342.01 | 244 | 0 | 0% | 0% | 0%
16141009 |  | 16141009 | 1 | GE MSA - Pyron WTG 156 Repair | 2016-05-02 | 2016-05-26 | 0 | 260 | 0 | 281060.47 | 218333.55 | 0 | 245.5 | 87.37% | 12.63% | 0%
16040004 |  | 16040004 | 1 | AlaskaUSA-Avondale Branch | 2016-04-04 | 2016-05-06 | 700 | 0 | 0 | 213934.62 | 216432.71 | 0 | 17 | 100% | 0% | 0%
16080001 |  | 16080001 | 1 | Froedtert-CCC 5th Floor Renvtn | 2016-03-28 | 2016-05-03 | 1900 | 960 | 974 | 185686 | 164930.27 | 212 | 180.5 | 94.46% | 5.54% | 0%
16060007 |  | 16060007 | 1 | Oakwood Homes-GVR East | 2016-03-01 | 2016-04-15 | 0 | 0 | 0 | 21756 | 10021.18
16080002 |  | 16080002 | 1 | Froedtert-OR 17 Renovation | 2016-01-25 | 2016-04-01 | 1000 | 12566 | 7638 | 646826 | 599062.31 | 792 | 1138 | 77.55% | 21.92% | 0.5272%
16141003 |  | 16141003 | 1 | Wind - Sendero MES | 2016-01-25 | 2016-03-31 | 0 | 0 | 0 | 19806 | 10431.69 | 100 | 86 | 93.02% | 6.977% | 0%
16037 |  | 16037 | 1 | AMGEN INC.AMGEN AC 7 | 2003-01-06 | 2003-01-06 | 4500 | 0 | 0 | 2172061 | 2178762 | 0 | 8537 | 100% | 0% | 0%
16148005 |  | 16148005 | 1 | Wind - Mariah Del Norte Civil | 2016-03-07 |  | 0 | 0 | 0 | 4750 | 0
16148009 |  | 16148009 | 1 | Ringer Hill Civil | 2016-05-16 |  | 0 | 0 | 0 | 4750 | 0
16007 |  | 16007 | 1 | KROENKE-PEPSI EIFS | 2004-10-31 |  | 0 | 0 | 0 | 1490354 | 1490381 | 0 | 135 | 100% | 0% | 0%
16008 |  | 16008 | 1 | EAST/WEST PARTNERSPARK PLACE | 2001-12-31 |  | 0 | 0 | 0 | 430456 | 450504 | 0 | 6 | 100% | 0% | 0%
16009 |  | 16009 | 1 | EAST/WEST PARTNERSPARK TOWER | 2002-02-01 |  | 0 | 0 | 0 | 0 | 432545
16010 |  | 16010 | 1 | EAST/WEST PARTNERSPROMENADE B | 2002-01-01 |  | 0 | 25 | 0 | 182728 | 187429
16013 |  | 16013 | 1 | COLORADO ROCKIES COORS FIELD | 2002-01-14 |  | 0 | 0 | 0 | 0 | 7639 | 0 | 91 | 100% | 0% | 0%
16015 |  | 16015 | 1 | HASKELL CONSTRUCTORSVAN SKAT | 2001-06-30 |  | 0 | 0 | 0 | 0 | 62843 | 0 | 1026 | 100% | 0% | 0%
16017 |  | 16017 | 1 | AGILENT TECHNOLOGIESMISC FACI | 2001-12-31 |  | 0 | 0 | 0 | 0 | 15071 | 0 | 300 | 100% | 0% | 0%
16019 |  | 16019 | 1 | STATE OF COLORADOARAPAHOE CNT | 2001-12-31 |  | 0 | 0 | 0 | 0 | 22914 | 0 | 97 | 100% | 0% | 0%
16024 |  | 16024 | 1 | CITY & CNTY OF DENDENVER ART | 2006-01-29 |  | 0 | 627203 | 346691 | 0 | 56510848 | 0 | 90552 | 100% | 0% | 0%
16025 |  | 16025 | 1 | MILE HIGH DEVELOPMENCULTURAL |  |  | 0 | 1299744 | 1728924 | 0 | 13561160 | 0 | 36720 | 100% | 0% | 0%
16028 |  | 16028 | 1 | LARIMER CNTY FACILITIES - FAI |  |  | 0 | 0 | 0 | 0 | 307595 | 0 | 166 | 100% | 0% | 0%
16029 |  | 16029 | 1 | CLAYTON STREET ASSOCCHERRY CR | 2004-05-01 |  | 0 | 12178197 | 3502053 | 41732499 | 103954370 | 0 | 377444 | 100% | 0% | 0%
16032 |  | 16032 | 1 | AMGEN INC. - SITEIMPROVEMENTS | 2002-11-30 |  | 0 | 484 | 0 | 3071293 | 2994459 | 0 | 4592 | 100% | 0% | 0%
16034 |  | 16034 | 1 | CLAYTON STREET ASSOCSEARS L/D | 2002-04-20 |  | 0 | 149168 | 18636 | 0 | 1597211 | 0 | 7746 | 100% | 0% | 0%
16036 |  | 16036 | 1 | MAM-SAUNDERS-EXEMPLAHOSPITAL | 2004-11-04 |  | 0 | 1501815 | 1124998 | 20174858 | 18833608 | 0 | 144528 | 100% | 0% | 0%
16999 |  | 16999 | 1 | DENVER-CLOSED JOBS | 2001-12-31 |  | 0 | 0 | 0 | 0 | 97258 | 0 | 183 | 100% | 0% | 0%
16022 |  | 16022 | 1 | EAST/WEST PARTNERS-SALES OFFI | 2001-11-15 |  | 3100 | 1950 | 0 | 0 | 238229 | 0 | 544 | 100% | 0% | 0%
16031 |  | 16031 | 1 | EAST/WEST PARTNERSRIVERFRONT | 2002-01-15 |  | 3100 | 413 | 0 | 0 | 318252 | 0 | 742 | 100% | 0% | 0%
16020 |  | 16020 | 1 | BROADMOOR-BEE HIVE |  |  | 3184 | 8937 | 7753 | 616135 | 617953 | 0 | 2123 | 100% | 0% | 0%
16014 |  | 16014 | 1 | EAST/WEST PARTNERS-MARK SMITH | 2001-12-19 |  | 4100 | 855 | 0 | 656706 | 919469 | 0 | 2809 | 100% | 0% | 0%
16023 |  | 16023 | 1 | FOREST CITYSTAPLETON VISITOR | 2001-11-30 |  | 5144 | 0 | 32178 | 1018802 | 1022270 | 0 | 3641 | 100% | 0% | 0%
16035 |  | 16035 | 1 | AERIE NETWORKS | 2001-12-21 |  | 7400 | 0 | 0 | 0 | 58830 | 0 | 406 | 100% | 0% | 0%
16003 |  | 16003 | 1 | CSG SYSTEMS INCOFFICE ADDITIO | 2001-07-01 |  | 8000 | 317 | 0 | 280866 | 261272 | 0 | 408 | 100% | 0% | 0%
16012 |  | 16012 | 1 | BROADMOOR-NORTHEASTMOOR OFFIC | 2002-07-01 |  | 11000 | 16 | 0 | 387321 | 416658 | 0 | 2844 | 100% | 0% | 0%
16016 |  | 16016 | 1 | KROENKE SPORTS ENTER PEPSI CN | 2002-07-02 |  | 13500 | 0 | 143617 | 4347550 | 4299489 | 4903 | 5804 | 100% | 0% | 0%
16011 |  | 16011 | 1 | KROENKE SPORTS ENTER 917 AURA | 2001-07-01 |  | 15000 | 0 | 0 | 266914 | 269892 | 0 | 480 | 100% | 0% | 0%
16018 |  | 16018 | 1 | PEPSI BOTTLING |  |  | 20000 | 0 | 0 | 0 | 78562 | 0 | 549 | 100% | 0% | 0%
16021 |  | 16021 | 1 | MORTENSON-NEW OFFICETI | 2001-11-01 |  | 22200 | 21 | 0 | 0 | 230684 | 0 | 671 | 100% | 0% | 0%
16002 |  | 16002 | 1 | KROENKE SPORTS ENTERPEPSI CNT | 2002-07-01 |  | 49690 | 346875 | 12600085847 | 9342583 | 9365768 | 0 | 22178 | 100% | 0% | 0%
16004 |  | 16004 | 1 | AMGEN INC. - AC-27AC-27 | 2002-06-30 |  | 90000 | 476765 | 377732 | 17640166 | 17646132 | 0 | 32893 | 100% | 0% | 0%
16001 |  | 16001 | 1 | BROADMOOR-2001 PHASE3 | 2002-05-01 |  | 100000 | 363017 | 412611 | 28098114 | 29266457 | 0 | 167598 | 100% | 0% | 0%
16027 |  | 16027 | 1 | CLAYTON STREET ASSOCCHERRY CR | 2002-10-01 |  | 218230 | 825513 | 727146 | 1 | 14848807 | 0 | 43073 | 100% | 0% | 0%
16006 |  | 16006 | 1 | HP-HARMONY TECHNOLOGY PARK | 2002-08-30 |  | 270000 | 0 | 0 | 0 | 267942 | 0 | 0 | 0% | 0% | 0%
16033 |  | 16033 | 1 | CORUM REAL ESTATE |  |  | 387025 | 5009869 | 1316581 | 31066923 | 31499547 | 0 | 110021 | 100% | 0% | 0%
16005 |  | 16005 | 1 | 2101 MARKET ST LLCP.W. MAC MA | 2002-11-29 |  | 404000 | 0 | 0 | 0 | 62547
16135001 |  | 16135001 | 1 | Southern Cross Conv Stations |  |  | 0 | 0 | 0 | 598609 | 367678.17
16030005 |  | 16030005 | 1 | Medtronic Monument | 2016-02-29 |  | 0 | 1068 | 0 | 2497877.37 | 2497840.55 | 264 | 200 | 100% | 0% | 0%
16030006 |  | 16030006 | 1 | UMP-MRI Removals | 2016-03-06 |  | 0 | 0 | 0 | 74382.85 | 77890.25 | 240 | 464 | 78.88% | 20.69% | 0.431%
16030017 |  | 16030017 | 1 | HSRE-WestHealth Sanitary | 2016-05-09 |  | 0 | 0 | 0 | 309966.82 | 243909.8 | 212 | 87 | 100% | 0% | 0%
16030018 |  | 16030018 | 1 | Mortenson Cabins - Oheym |  |  | 0 | 0 | 0 | 0 | 350947.79 | 0 | 2225 | 91.33% | 8.674% | 0%
16030019 |  | 16030019 | 1 | BCBS Lighting Replacement | 2016-06-01 |  | 0 | 0 | 0 | 1033470.52 | 1056151.92 | 403 | 935 | 91.82% | 8.182% | 0%
16030022-900 |  | 16030022-900 | 1 | Allina-Unity MH-Exempt | 2016-05-16 |  | 0 | 0 | 0 | 3274211.2 | 3274211.2
16030025 |  | 16030025 | 1 | Mortenson Cabins - Alepho |  |  | 0 | 0 | 0 | 0 | 97595.22 | 0 | 550 | 92% | 8% | 0%
16030029 |  | 16030029 | 1 | Fridley Land-Misc Projects | 2016-07-15 |  | 0 | 0 | 0 | 287057.66 | 319017.93 | 24 | 819 | 84.98% | 15.02% | 0%
16030047 |  | 16030047 | 1 | AECOM-Vertical Exp Study |  |  | 0 | 0 | 0 | 2291.92 | 4311.88
16030048 |  | 16030048 | 1 | UMP-Mill City Water Damage | 2016-12-20 |  | 0 | 0 | 0 | 23704 | 23652.18 | 0 | 158 | 98.73% | 1.266% | 0%
16030999 |  | 16030999 | 1 | MAM - 2016 Closed Projects | 2016-01-01 |  | 0 | 0 | 0 | 0.01 | 18899.29 | 0 | 190 | 100% | 0% | 0%
16030021 |  | 16030021 | 1 | MPR - Misc. Projects | 2016-06-15 |  | 300 | 0 | 0 | 18653.13 | 17739.81 | 0 | 8 | 100% | 0% | 0%
16030039 |  | 16030039 | 1 | JW Marriott-Locker Room Rpr | 2016-08-24 |  | 2000 | 320 | 0 | 47771.78 | 47143.03 | 240 | 220 | 100% | 0% | 0%
16030012 |  | 16030012 | 1 | NS I - Lindenmeyr TI | 2016-04-19 |  | 111000 | 2694 | 0 | 1814810.36 | 1790049.8 | 1476 | 1908 | 84.43% | 15.15% | 0.4193%
16030032 |  | 16030032 | 1 | Fridley Land-NS III | 2016-09-15 |  | 118400 | 787 | 21320 | 11032640.58 | 9517627.82 | 16178 | 12967.61 | 93.52% | 6.431% | 0.04627%
16030015 |  | 16030015 | 1 | MDI - 800 Washington Ave | 2016-10-01 |  | 134001 | 0 | 0 | 0.01 | 149262.49 | 0 | 0 | 0% | 0% | 0%
16030026 |  | 16030026 | 1 | CHS Campus Projects | 2016-07-15 |  | 330000 | 5 | 0 | 276295.6 | 298301.43 | 356 | 125 | 99.2% | 0.8% | 0%
16146004 |  | 16146004 | 1 | Wind - Ida Grove HVT | 2016-04-01 |  | 0 | 0 | 0 | 11884682.4 | 0
16146016 |  | 16146016 | 1 | MES 2016 Misc. HVT | 2016-10-03 |  | 0 | 0 | 0 | 17300 | 0
16146022 |  | 16146022 | 1 | Firewheel Phase A1 HVT | 2016-10-31 |  | 0 | 31 | 0 | 828961.64 | 734786.67
16145007 |  | 16145007 | 1 | Gilcrest SolarGarden-SunShare | 2016-06-06 |  | 0 | 43 | 0 | 10314.12 | 7754.47
16145015 |  | 16145015 | 1 | MAM Solar Training Yard | 2016-09-05 |  | 0 | 0 | 0 | 0.01 | 0 | 0 | 2067.75 | 99.3% | 0.7012% | 0%
16145020 |  | 16145020 | 1 | G&K Service Pilot - Stem | 2016-10-24 |  | 0 | 14 | 14 | 10435 | 17681.6 | 56 | 97 | 75.26% | 24.74% | 0%
16145023 |  | 16145023 | 1 | Oasis 3.0 Mini-Build-SunPower | 2016-10-10 |  | 15000 | 5932 | 730 | 23325 | 22111.6 | 208 | 160 | 100% | 0% | 0%
16145014 |  | 16145014 | 1 | RadiatorSpringsRacer-SunPower | 2016-08-02 |  | 470880 | 10806 | 10806 | 307640.86 | 278096.78 | 2128 | 2612 | 92.15% | 7.848% | 0%
16145013 |  | 16145013 | 1 | Stanford Multi-Site-SunPower | 2016-07-06 |  | 1365552 | 361333 | 356645 | 3319742.68 | 5122921.51 | 18102.5 | 33967.5 | 88.72% | 10.67% | 0.6079%
16145002 |  | 16145002 | 1 | Target Helix 10 - SunPower | 2016-04-04 |  | 5838890 | 164141 | 162599 | 4324263.453 | 5541173 | 25781.6 | 34687.25 | 93.28% | 5.191% | 1.531%
22090001 |  | 22090001 | 1 | QTS - 4.5MW F Block |  |  | 0 | 13883 | 2976 | 21329649.1 | 17012983.45 | 3888 | 4497.5 | 94.7% | 5.236% | 0.0667%
22090003 |  | 22090003 | 1 | Loyola - Chicago Small Proj 22 |  |  | 0 | 240 | 0 | 520685 | 384323.79 | 0 | 162 | 93.83% | 6.173% | 0%
22090004 |  | 22090004 | 1 | Allstate-Hudson Infrastructure |  |  | 4000 | 1810 | 0 | 1694397 | 451047.34
22090005 |  | 22090005 | 1 | Lurie-9Enable/19Pharm/Biorepo |  |  | 10000 | 5212.8 | 0 | 4607608 | 1734599.4 | 4840.8 | 2448.5 | 89.01% | 7.106% | 3.88%
22090002 |  | 22090002 | 1 | Wheaton - McAlister Reno |  |  | 19200 | 54631 | 0 | 6411135 | 5073683.67 | 3095.1 | 1789.5 | 95.14% | 4.862% | 0%
22090006 |  | 22090006 | 1 | Esperanza Health Center |  |  | 45000 | 39575 | 0 | 24134498.69 | 2004434.36 | 3569.3 | 730 | 95.41% | 4.315% | 0.274%
22148001 |  | 22148001 | 1 | Chevelon Butte Wind - Civil |  |  | 0 | 10925884 | 466641.25 | 11708644.94 | 10965138.82 | 52037.93 | 35550.47 | 77.2% | 22.8% | 0%
22148002 |  | 22148002 | 1 | Appaloosa Wind - Civil |  |  | 0 | 8554749.82 | 0 | 8258988.64 | 7209975.31 | 35706.31 | 34100 | 72.18% | 27.82% | 0%
22148003 |  | 22148003 | 1 | Stampede Storage - Civil |  |  | 0 | 960581.5 | 12881.55 | 1150288.69 | 904440.73 | 3478.53 | 2547.5 | 66.05% | 33.95% | 0%
22148004 |  | 22148004 | 1 | Laurel Mtn AES Repower - Civil |  |  | 0 | 5363797.35 | 28162 | 4019733.96 | 2831285.26 | 8752.6 | 11031 | 75.61% | 20.63% | 3.758%
22148005 |  | 22148005 | 1 | Inertia Wind - Civil |  |  | 0 | 1202056.3 | 489795 | 19862193.2044 | 12032353.45 | 57462.51 | 41933.88 | 80.56% | 19.32% | 0.1192%
22148006 |  | 22148006 | 1 | King Mountain Power - Civil |  |  | 0 | 3746108.31 | 156705 | 3859565.9928 | 2169509.28 | 12198.12 | 6267 | 73.54% | 26.46% | 0%
22148007 |  | 22148007 | 1 | Wolf Hollow Power - Civil |  |  | 0 | 2855682.39 | 197706.7 | 3064918.87 | 2257403.96 | 10240.81 | 6835.32 | 71.33% | 28.67% | 0%
22148009 |  | 22148009 | 1 | Eclipse & ML Repower - Civil |  |  | 0 | 9131862.95 | 618.5 | 8826411.16 | 5934455.84 | 24750.71 | 25224 | 70.02% | 29.71% | 0.2656%
22148010 |  | 22148010 | 1 | Chokecherry Sierra Madre 2022 |  |  | 0 | 923997.36 | 612204.69 | 18172502.56 | 15125907.41 | 254316.37 | 57699.16 | 79.55% | 20% | 0.4506%
22148011 |  | 22148011 | 1 | Texas Solar Nova I - Civil |  |  | 0 | 14464146.64 | 797815.05 | 17466737.09 | 14970975.54 | 54147.3 | 49920.61 | 77.55% | 22.44% | 0.005008%
22148012 |  | 22148012 | 1 | Fort Stockton Power - Civil |  |  | 0 | 738240.5 | 57506 | 1046305.34 | 942088.45 | 3047.05 | 2103.5 | 67.13% | 32.87% | 0%
22148013 |  | 22148013 | 1 | Abilene Power - Civil |  |  | 0 | 1479576.62 | 69146 | 742050.54 | 532112.97 | 2755.21 | 2383 | 61.08% | 38.92% | 0%
22148014 |  | 22148014 | 1 | ELS UNO State Street - Civil |  |  | 0 | 159064 | 51328 | 4690117.5 | 1571032.67 | 6700 | 6773 | 77.58% | 22.42% | 0%
22148016 |  | 22148016 | 1 | White Rock Wind - Civil |  |  | 0 | 12968413 | 130199 | 20672199.9 | 2281218.27 | 68410.97 | 10189.5 | 82.02% | 17.98% | 0%
22148018 |  | 22148018 | 1 | Grand Meadow Repower - Civil |  |  | 0 | 3434963.31 | 19717 | 3911128.3 | 2577518.54 | 10897.91 | 10197.98 | 90.89% | 9.114% | 0%
22148019 |  | 22148019 | 1 | Texas Solar Nova II - Civil |  |  | 0 | 12590694.52 | 14778 | 12443508.09 | 2110933.51 | 36818.66 | 8289.02 | 82.68% | 17.32% | 0%
22148020 |  | 22148020 | 1 | Nobles ADLS Repower - Civil |  |  | 0 | 100 | 0 | 70870 | 70592.02 | 0 | 480 | 83.33% | 16.67% | 0%
22148021 |  | 22148021 | 1 | Nobles V136 Repower - Civil |  |  | 0 | 2 | 0 | 121899 | 115880.27 | 0 | 962.5 | 86.44% | 13.56% | 0%
22148022 |  | 22148022 | 1 | Pyron Repower - Civil |  |  | 0 | 8184487 | 152 | 3047468.34 | 983640.35 | 4851.12 | 3278 | 82.67% | 17.33% | 0%
22148023 |  | 22148023 | 1 | UNO1A Substation - Civil |  |  | 0 | 1000553.97 | 14594.4 | 1509149.65 | 51223.46 | 2604.84 | 636.5 | 80.75% | 19.25% | 0%
22148024 |  | 22148024 | 1 | Revolution Storage - Civil |  |  | 0 | 575238.23 | 53754.9 | 470290.29 | 195149.88 | 1491.24 | 908.5 | 71.33% | 28.67% | 0%
22120001 |  | 22120001 | 1 | Meta - 2022 Program Services |  |  | 0 | 0 | 0 | 4822591.44 | 3757541.88
22120003 |  | 22120003 | 1 | Meta - EAG Retrofits 2022 SMA |  |  | 0 | 244 | 7 | 1328394.9108 | 782160.88 | 204.9 | 411 | 91.48% | 8.516% | 0%
22120004 |  | 22120004 | 1 | Google - UNO 2 Master Planning |  |  | 0 | 0 | 0 | 78985 | 20298.06
22120005 |  | 22120005 | 1 | Meta - Retrofits PMA 2022 |  |  | 0 | 0 | 0 | 243586.8 | 185307.01
22120006 |  | 22120006 | 1 | Google EWD Campus Planning |  |  | 0 | 0 | 0 | 84583.9 | 25937.24
22120007 |  | 22120007 | 1 | Google - Bluesky Expansion |  |  | 0 | 0 | 0 | 0 | 7612.01
22120009 |  | 22120009 | 1 | Google UNO1A-Offsite Formwork |  |  | 0 | 0 | 0 | 0 | 29129.05 | 0 | 395 | 99.49% | 0.5063% | 0%
22120008 |  | 22120008 | 1 | Google - UNO Building 2 |  |  | 350000 | 0 | 0 | 0 | 52645.98
22120002 |  | 22120002 | 1 | Meta - UCO |  |  | 2500000 | 0 | 5436 | 286566941 | 30395260.75 | 0 | 8055.5 | 75.48% | 24.52% | 0%
22120010 |  | 22120010 | 1 | Google - NBF1A YAWN |  |  | 300000 | 0 | 0 | 172825 | 1257.56
22060001 |  | 22060001 | 1 | SCL-LMC Irrigation Repairs |  |  | 0 | 19 | 40 | 80534.13 | 85310.3 | 59 | 40 | 100% | 0% | 0%
22060002 |  | 22060002 | 1 | SCL-LMC W Pines Cooling |  |  | 0 | 242.5 | 0 | 131683.97 | 136279.04 | 112 | 0 | 0% | 0% | 0%
22060004 |  | 22060004 | 1 | SCL-LMC Water Heater |  |  | 0 | 71 | 0 | 33323.04 | 33286.19
22060005 |  | 22060005 | 1 | MDI-3043 Walnut |  |  | 0 | 9 | 0 | 7601951.2 | 1325501.76 | 0 | 56 | 100% | 0% | 0%
22060007 |  | 22060007 | 1 | MC Truck Dock Repairs |  |  | 0 | 179915.62 | 5789.5 | 5507171.37 | 3886211.88 | 5482.5 | 2457.75 | 91.92% | 8.076% | 0%
22060008 |  | 22060008 | 1 | NJH - MIDC Remodel |  |  | 0 | 17354 | 75.24 | 1562892.4 | 1502039.58 | 1093.8 | 2355.5 | 83.91% | 16.09% | 0%
22060010 |  | 22060010 | 1 | SCL-SJB Electrical Coord |  |  | 0 | 11.5 | 0 | 196798.87 | 177308.97
22060012 |  | 22060012 | 1 | Woodward - Small Projects 2022 |  |  | 0 | 18245 | 15733.85 | 1859237.43 | 1159721.07 | 1629 | 1460 | 96.54% | 3.459% | 0%
22060013 |  | 22060013 | 1 | SCL - SJH LinAcc Remodel |  |  | 0 | 2272 | 1864.48 | 1567136.39 | 1125245.56 | 2538.9 | 2906.5 | 86.63% | 13.37% | 0%
22060014 |  | 22060014 | 1 | PA-07 Stockpile |  |  | 0 | 7 | 0 | 205078 | 69676.82
22060018 |  | 22060018 | 1 | NJH-Morgridge Academy |  |  | 0 | 15514.5 | 0 | 1301980.76 | 1262518.72 | 290 | 1127.5 | 81.33% | 18.67% | 0%
22060019 |  | 22060019 | 1 | SCL-SJB Smoke Detector |  |  | 0 | 30 | 0 | 83050.27 | 69413.2
22060020 |  | 22060020 | 1 | SCL-SJB Life Safety Remed |  |  | 0 | 1049 | 0 | 370750.38 | 263407.19
22060021 |  | 22060021 | 1 | SCL-LMC W Pines Waste |  |  | 0 | 300 | 0 | 14282.53 | 18280.66 | 152 | 0 | 0% | 0% | 0%
22060022 |  | 22060022 | 1 | SCL-LMC W Pines Load Bank |  |  | 0 | 382 | 18.6 | 62739.21 | 60291.38 | 154 | 51 | 100% | 0% | 0%
22060025 |  | 22060025 | 1 | SCL-SJB Small Capital 2022 |  |  | 0 | 4 | 0 | 29377.01 | 19275.07
22060026 |  | 22060026 | 1 | SCL-SJB OPEX Projects |  |  | 0 | 11 | 0 | 0.01 | 1599.68
22060027 |  | 22060027 | 1 | NJH-MRI/CT Project |  |  | 0 | 10149 | 1917.5 | 715576.23 | 594887.14 | 2010.3 | 1376.5 | 81.51% | 18.49% | 0%
22060029 |  | 22060029 | 1 | MHUW Renovations |  |  | 0 | 0 | 0 | 0.01 | 5790
22060030 |  | 22060030 | 1 | SCL-SJB RMAP Lab |  |  | 0 | 13092.5 | 0 | 710017.53 | 11160.11
22060031 |  | 22060031 | 1 | Park Creek-Filing 59 "IFDA MH" |  |  | 0 | 0 | 21 | 477234 | 27727.73 | 1780 | 37 | 100% | 0% | 0%
22060032 |  | 22060032 | 1 | SCL-SJB NUC Med Exhaust |  |  | 0 | 7031 | 0 | 228040.02 | 16812.3
22060034 |  | 22060034 | 1 | Denver Broncos Scoreboard |  |  | 0 | 0 | 0 | 4388511.02 | 81298.32
22060035 |  | 22060035 | 1 | SCL-SJB Patient Lifts |  |  | 0 | 295 | 0 | 295536.8 | 84038.17
22060037 |  | 22060037 | 1 | SCL-SJB PPBR Panel Replacement |  |  | 0 | 6226 | 0 | 96315.44 | 1599.25 | 105 | 0 | 0% | 0% | 0%
22060009 |  | 22060009 | 1 | CoorsTek NT154 |  |  | 1000 | 1951.5 | 270 | 601945.29 | 598582.47 | 267.2 | 636.5 | 91.91% | 8.091% | 0%
22060023 |  | 22060023 | 1 | SCL-SJB MRI Chiller |  |  | 1000 | 7.25 | 0 | 418463.89 | 54748.94
22060033 |  | 22060033 | 1 | NJH-Level 3 Imaging Recep |  |  | 1000 | 4507 | 0 | 209913.88 | 61707.09 | 294.5 | 0 | 0% | 0% | 0%
22060036 |  | 22060036 | 1 | InterMtn - LMC - Emerg Repair |  |  | 1000 | 485.48 | 66 | 377902.2 | 313046.72 | 219.9 | 47 | 97.87% | 2.128% | 0%
22060003 |  | 22060003 | 1 | DHHA-OBGYN |  |  | 4901 | 8436 | 542.19 | 413338.74 | 394953.19 | 662.2 | 1250.11 | 91.56% | 8.439% | 0%
22060017 |  | 22060017 | 1 | SCLH MGFR Airport & Alameda |  |  | 10000 | 14319 | 0 | 2510691.78 | 490918.23 | 830.2 | 0 | 0% | 0% | 0%
22060028 |  | 22060028 | 1 | Cleo Parker Expansion |  |  | 22000 | 0 | 0 | 0.01 | 9600
22060038 |  | 22060038 | 1 | Xcel Aurora Service Center |  |  | 32500 | 0 | 0 | 0.01 | 6679.62
22060006 |  | 22060006 | 1 | Pearl East Campus |  |  | 40000 | 79570.67 | 527 | 13222136.33 | 3354010.26 | 432.6 | 548.5 | 93.53% | 6.472% | 0%
22060011 |  | 22060011 | 1 | Arista C2 Office Building |  |  | 81000 | 0 | 0 | 0.02 | 46219.01
22060015 |  | 22060015 | 1 | HighPoint-Whole Foods |  |  | 140000 | 0 | 0 | 0.01 | 217818.4
22060024 |  | 22060024 | 1 | OneFlight International |  |  | 175000 | 0 | 0 | 0.02 | 92169.86
22060040 |  | 22060040 | 1 | Highpoint Ind Bldg 3 - Grading |  |  | 213200 | 0 | 16 | 0.01 | 0 | 0 | 0 | 0% | 0% | 0%
22060016 |  | 22060016 | 1 | HighPoint Industrial Bldg 4 |  |  | 481000 | 0 | 0 | 0.01 | 387184.59
22060039 |  | 22060039 | 1 | Denargo Market - Multifamily |  |  | 527000 | 0 | 0 | 0.01 | 0
22149001 |  | 22149001 | 1 | AVEP BESS Project |  |  | 0 | 1693 | 0 | 832769 | 559055.46
22149002 |  | 22149002 | 1 | Revolution Energy Storage |  |  | 0 | 394273.14 | 0 | 22892009.16 | 2513727.83 | 37438.74 | 409 | 94.87% | 0% | 5.134%
22149003 |  | 22149003 | 1 | EMTOC Microgrid |  |  | 0 | 0 | 0 | 909640.02 | 637593.02
22149004 |  | 22149004 | 1 | Chap Springs |  |  | 0 | 305949.47 | 0 | 14312536.68 | 1256513.09 | 33663.05 | 32 | 37.5% | 62.5% | 0%
22149005 |  | 22149005 | 1 | Beaumont Energy Storage |  |  | 0 | 0 | 0 | 5280406.49 | 1908773.82
22149006 |  | 22149006 | 1 | Canyon Country Energy Storage |  |  | 0 | 0 | 0 | 4909796.15 | 1760786.31
22149007 |  | 22149007 | 1 | Nova Power |  |  | 0 | 0 | 0 | 16470081.6 | 232037.85
22149008 |  | 22149008 | 1 | Tumbleweed Energy Storage |  |  | 0 | 0 | 0 | 14978142 | 2346751.84
22110001 |  | 22110001 | 1 | AMJV MercilessMing JV-Int |  |  | 0 | 0 | 0 | 110.01 | 763.55
22110002 |  | 22110002 | 1 | AMJV BallisticBass JV-Int |  |  | 0 | 0 | 0 | 127537 | 29979.04
22110004 |  | 22110004 | 1 | EHW 2 and 3 Unilateral Mod |  |  | 0 | 0 | 0 | 3253679.8116 | 3284636.38 | 0 | 536.5 | 81.17% | 16.96% | 1.864%
22110008 |  | 22110008 | 1 | Hill AFB UT GBSD SSC |  |  | 0 | 250404 | 0 | 91448691 | 6554147.21
22110011 |  | 22110011 | 1 | USG Perimeter Fence |  |  | 0 | 306 | 0 | 18144559 | 238366.46
22110005 |  | 22110005 | 1 | Chantilly VA Loop Road |  |  | 80 | 0 | 0 | 35667 | 32105.79
22110003 |  | 22110003 | 1 | DC Office Secure Room |  |  | 325 | 0 | 0 | 259778 | 0
22110001-174 |  | 22110001-174 | 1 | UDC MercilessMing |  |  | 2000 | 0 | 0 | 31875 | 30250.14
22110002-174 |  | 22110002-174 | 1 | UDC BallisticBass |  |  | 4000 | 0 | 0 | 2002971 | 1891057.09
22110006 |  | 22110006 | 1 | Bldg 9700B Substation Install |  |  | 5000 | 163 | 0 | 9935126.08 | 119590.25
22110010 |  | 22110010 | 1 | ASH3 DC1 Dev Office |  |  | 6100 | 0 | 0 | 1923144 | 155341.61
22110007 |  | 22110007 | 1 | ASH3 Data Center |  |  | 55358 | 118 | 0 | 21447210.51 | 13340349.49 | 0 | 362 | 93.92% | 6.077% | 0%
22110009 |  | 22110009 | 1 | Offutt AFB NE Security Campus |  |  | 106372 | 139443 | 0 | 63872156.6 | 3308399.1
22080006 |  | 22080006 | 1 | MRMC Window Replacement |  |  | 0 | 40 | 0 | 327505.69 | 625 | 400 | 0 | 0% | 0% | 0%
22080008 |  | 22080008 | 1 | RockGen Firestopping Repairs |  |  | 0 | 0 | 0 | 25470 | 21165.7 | 60 | 40 | 100% | 0% | 0%
22080010 |  | 22080010 | 1 | Froedtert SW Expansion |  |  | 0 | 0 | 0 | 0.01 | 176223.32
22080013 |  | 22080013 | 1 | WisDOT I43 Year2 |  |  | 0 | 0 | 0 | 0.01 | 15074.12
22080018 |  | 22080018 | 1 | Froedtert - Cold Storage |  |  | 0 | 0 | 0 | 0.01 | 6656
22080012 |  | 22080012 | 1 | NML - Sculpture Move |  |  | 256 | 1113.1 | 650 | 281353.77 | 258340.64 | 345.4 | 137 | 97.08% | 2.92% | 0%
22080017 |  | 22080017 | 1 | ASLMC OR Lights |  |  | 650 | 0 | 0 | 0.01 | 179
22080007 |  | 22080007 | 1 | Froedtert Volunteer Services |  |  | 1700 | 14178 | 0 | 241970.96 | 253960.86 | 628.6 | 911 | 100% | 0% | 0%
22080015 |  | 22080015 | 1 | MCW Cryo Suite |  |  | 1890 | 0 | 0 | 0.01 | 3178.9 | 0 | 40 | 100% | 0% | 0%
22080011 |  | 22080011 | 1 | ASLMC Hyperbaric Upgrades |  |  | 2500 | 4 | 0 | 131195.22 | 108072.28 | 136 | 29 | 3.448% | 96.55% | 0%
22080016 |  | 22080016 | 1 | MRMC - MCW Cancer Tunnel |  |  | 2500 | 0 | 0 | 0.01 | 0
22080003 |  | 22080003 | 1 | Froedtert Inpatient Supp |  |  | 4000 | 89800 | 3186 | 2549427.61 | 1924263.74 | 5053.6 | 4730.8 | 95.14% | 4.815% | 0.04228%
22080001 |  | 22080001 | 1 | Froedtert - MF CT Reno |  |  | 5000 | 132 | 0 | 19344 | 14785.13
22080005 |  | 22080005 | 1 | MRMC Tunnel G-1 |  |  | 5000 | 69320.98 | 24799 | 5296929.77 | 4851414.88 | 5297.1 | 6685.5 | 97.02% | 2.737% | 0.2393%
22080009 |  | 22080009 | 1 | Froedtert OR Growth |  |  | 12030 | 0 | 0 | 0.01 | 104789.6
22080014 |  | 22080014 | 1 | MRMC - Childrens Lateral |  |  | 26000 | 0 | 0 | 0.01 | 13657
22080004 |  | 22080004 | 1 | JCI Glendale Build Out |  |  | 100000 | 0 | 0 | 0.01 | 3375.75
22080002 |  | 22080002 | 1 | WEAS -JCI Core & Shell |  |  | 110000 | 0 | 0 | 0.01 | 22439.95 | 0 | 8 | 100% | 0% | 0%
22030001 |  | 22030001 | 1 | Fairview - Annual 2022 |  |  | 0 | 0 | 0 | 0.01 | 3555051.24 | 0 | 11282.5 | 96.76% | 2.907% | 0.3368%
22030002 |  | 22030002 | 1 | Allina - Annual Contract 2022 |  |  | 0 | 5698.5 | 0 | 2459481.59 | 2336136.78 | 12897 | 11478.75 | 87.57% | 10.14% | 2.291%
22030003 |  | 22030003 | 1 | Fairview Small Cap Proj 2022 |  |  | 0 | 22 | 0 | 875396.9332 | 485002.47 | 1383 | 892 | 94.62% | 5.381% | 0%
22030004 |  | 22030004 | 1 | Sanford - Master Agreement |  |  | 0 | 1 | 0 | 376463.58 | 443882.57 | 207 | 871.5 | 95.3% | 4.705% | 0%
22030005 |  | 22030005 | 1 | Fairview - Southdale Nurse Cal |  |  | 0 | 0 | 0 | 1136093 | 2335.2 | 3590 | 2 | 100% | 0% | 0%
22030006 |  | 22030006 | 1 | Fairview - St Paul Comm Health |  |  | 0 | 136444.5 | 2361.5 | 3204818.67 | 3056905.43 | 7994.91 | 7208.48 | 95.72% | 4.279% | 0%
22030007 |  | 22030007 | 1 | Northern Stacks - Res Med TI |  |  | 0 | 3 | 0 | 2166235.47 | 2061933.17 | 1217 | 968.62 | 97.15% | 2.026% | 0.8259%
22030008 |  | 22030008 | 1 | Fairview - Unit J Elevator Ren |  |  | 0 | 0 | 0 | 1933517 | 896542.03 | 2871 | 1998 | 97.57% | 0.4254% | 2.002%
22030009 |  | 22030009 | 1 | Fairview - Roche Lab Analyzer |  |  | 0 | 6198.59 | 0 | 817322.3792 | 598044.02 | 1719 | 895 | 98.94% | 1.061% | 0%
22030010 |  | 22030010 | 1 | Target - '22 Remodel - Grafton |  |  | 0 | 29900.94 | 0 | 2158245.44 | 2230812.32 | 2927.6 | 4940 | 96.23% | 3.036% | 0.7287%
22030011 |  | 22030011 | 1 | Fairview - UMMC WB EmPATH |  |  | 0 | 0 | 0 | 197582.71 | 174033.59 | 549 | 330.5 | 91.68% | 8.321% | 0%
22030012 |  | 22030012 | 1 | Marvin WFN - Breakroom Reno |  |  | 0 | 64096.79 | 0 | 2329867.17 | 2070937.69 | 2822.2 | 3020 | 90.56% | 9.437% | 0%
22030013 |  | 22030013 | 1 | UMN - Williamson Hall ASR Relo |  |  | 0 | 1239.09 | 0 | 285966.55 | 273886.6 | 245 | 310.5 | 100% | 0% | 0%
22030014 |  | 22030014 | 1 | Fairview-UMMC WB Pharmacy Exp |  |  | 0 | 0 | 0 | 2274582.59 | 1624673.36 | 4686 | 4058.5 | 98.92% | 1.084% | 0%
22030015 |  | 22030015 | 1 | Target - '22 Remodel - Oshkosh |  |  | 0 | 112843.66 | 0 | 4535044.617 | 4800527.37 | 6697.68 | 8873.48 | 86.92% | 13% | 0.07889%
22030023 |  | 22030023 | 1 | US Bank - USB Edina Redevel |  |  | 0 | 98666.9 | 29751 | 4483585.31 | 4719262.69 | 5477 | 7831 | 99.6% | 0.4022% | 0%
22030024 |  | 22030024 | 1 | MDI - USB Edina Demo/Abate |  |  | 0 | 0 | 0 | 831286 | 295402.56 | 125 | 96 | 100% | 0% | 0%
22030030 |  | 22030030 | 1 | SilverLakeInv-ODS Pent & Dock |  |  | 0 | 0 | 0 | 464716 | 455921.76 | 0 | 120 | 100% | 0% | 0%
22030031 |  | 22030031 | 1 | MN United - Allianz Field -'22 |  |  | 0 | 5143 | 0 | 159638.03 | 122829.31 | 292 | 287 | 98.43% | 1.568% | 0%
22030041 |  | 22030041 | 1 | Allina - ANW - Care (Design) |  |  | 0 | 0 | 0 | 726228 | 283389.16
22030042 |  | 22030042 | 1 | North Wirth - MAM HQ Sealant |  |  | 0 | 0 | 0 | 162714 | 170081.38 | 957 | 1121.5 | 96.26% | 3.032% | 0.7133%
22030044 |  | 22030044 | 1 | BSC - Weaver Lake Lots 2&6 |  |  | 0 | 78033.7 | 0 | 3606940.03 | 3565360.83 | 858.1 | 1460.5 | 99.11% | 0.8901% | 0%
22030045 |  | 22030045 | 1 | UMN-3MAM & Ridder Reno |  |  | 0 | 134436.15 | 0 | 12872679.17 | 750872.2 | 3357.8 | 0 | 0% | 0% | 0%
22030047 |  | 22030047 | 1 | MDI-USB Redev - JDA Scope |  |  | 0 | 213 | 0 | 665328.23 | 586489.86 | 714 | 388 | 100% | 0% | 0%
22030048 |  | 22030048 | 1 | Allina - Care Pavilion(Enable) |  |  | 0 | 0 | 1 | 10000000 | 848283.84 | 0 | 3543.5 | 96.81% | 2.85% | 0.3386%
22030051 |  | 22030051 | 1 | UMN-Vet Med Ctr & Lin Acc |  |  | 0 | 5361.99 | 0 | 648804.89 | 316675.72 | 497.5 | 117.5 | 100% | 0% | 0%
22030052 |  | 22030052 | 1 | Swervo-Century Plaza Demo |  |  | 0 | 0 | 0 | 0.01 | 23308.68
22030055 |  | 22030055 | 1 | Westminster Chapel Plaster |  |  | 0 | 0 | 0 | 0.01 | 0
22030099 |  | 22030099 | 1 | MAM-HQ Campus Renovations |  |  | 0 | 0 | 0 | 0.01 | 0
22030056 |  | 22030056 | 1 | MN Twins-Target Field Ply Rep |  |  | 1000 | 0 | 0 | 0.01 | 0
22030037 |  | 22030037 | 1 | Allina - ANW CK 3&4 Seclusion |  |  | 1500 | 0 | 0 | 344101 | 276957.34 | 988 | 1102 | 96.82% | 3.176% | 0%
22030026 |  | 22030026 | 1 | Fairview-UMMC WB Histology |  |  | 1680 | 5 | 0 | 545879.64 | 457076.58 | 1033 | 811 | 96.92% | 3.083% | 0%
22030017 |  | 22030017 | 1 | Target Field - Grounds Crew |  |  | 2000 | 0 | 0 | 325825.73 | 415910.86 | 312 | 419.5 | 95.83% | 3.218% | 0.9535%
22030043 |  | 22030043 | 1 | IDT - Small Capital Projects |  |  | 2000 | 8378.85 | 0 | 163859.84 | 110593.89 | 595.1 | 419.5 | 97.26% | 2.741% | 0%
22030019 |  | 22030019 | 1 | Allina - Mercy CT1, CT2, Spin |  |  | 2500 | 0 | 0 | 718748 | 587491.58 | 2549 | 2664 | 98.91% | 1.089% | 0%
22030020 |  | 22030020 | 1 | Jackson I - Naomi 77 9th East |  |  | 2500 | 352 | 6 | 524167.0324 | 479775.53 | 2427 | 2412 | 93.41% | 6.592% | 0%
22030028 |  | 22030028 | 1 | IDT - Tank Farm |  |  | 2586 | 22579.34 | 788.3 | 3562821.64 | 2236343.49 | 2165.4 | 1997 | 94.64% | 5.358% | 0%
22030032 |  | 22030032 | 1 | Crown College - Welcome Ctr |  |  | 2800 | 30610.6 | 0 | 1345622.88 | 1237357.76 | 3030.5 | 2265 | 94.3% | 5.166% | 0.5298%
22030034 |  | 22030034 | 1 | Fairview - Dietary Expansion |  |  | 2985 | 6606 | 0 | 1127168.19 | 579261.4 | 1409.8 | 1096.5 | 96.63% | 1.186% | 2.189%
22030054 |  | 22030054 | 1 | Fairview-UMMC Unit J Cath Lab2 |  |  | 3315 | 0 | 0 | 0.01 | 0
22030040 |  | 22030040 | 1 | Rochester 2 Assoc - 2DS Lobby |  |  | 12000 | 1 | 0 | 2276702.71 | 495765.35 | 16 | 328 | 100% | 0% | 0%
22030039 |  | 22030039 | 1 | BSC - Weaver Lake 4 TI |  |  | 14500 | 21369.42 | 1221 | 1592287.55 | 1590255.41 | 637.8 | 923.5 | 99.24% | 0.758% | 0%
22030027 |  | 22030027 | 1 | Target - Stevens Point |  |  | 15000 | 20084.03 | 0 | 2294196.97 | 2247418.5 | 2977.48 | 3342 | 87.21% | 12.79% | 0%
22030025 |  | 22030025 | 1 | Target - Fond Du Lac |  |  | 18750 | 45525.72 | 0 | 4886423.884 | 4176292.2 | 5311 | 6366.5 | 92.74% | 6.346% | 0.911%
22030018 |  | 22030018 | 1 | Fairview - 10th Street Ramp |  |  | 24284 | 129097.72 | 2 | 3767880.43 | 2842408.56 | 5913.17 | 3320 | 98.01% | 1.747% | 0.241%
22030029 |  | 22030029 | 1 | IDT - 2600 Crosspark |  |  | 25992 | 119070.43 | 42306.2 | 7414425.49 | 4855530.02 | 4688.7 | 4060 | 95.52% | 4.483% | 0%
22030016 |  | 22030016 | 1 | CentraCare - Paynesville Hosp |  |  | 35000 | 299245.28 | 0 | 11724961.32 | 3953612.88 | 19972.4 | 6065 | 96.7% | 3.298% | 0%
22030022 |  | 22030022 | 1 | Warroad Real Estate - Main Ave |  |  | 38500 | 201796.92 | 0 | 7160533.01 | 5565694.89 | 12268.1 | 9486.88 | 73.33% | 26.67% | 0%
22030053 |  | 22030053 | 1 | Fairview-St Paul Wellness Ph2A |  |  | 43476 | 0 | 0 | 0.01 | 0
22030050 |  | 22030050 | 1 | Dunwoody - 712 Ontario Cond |  |  | 45000 | 1 | 0 | 9320 | 9848.75 | 0 | 16 | 100% | 0% | 0%
22030036 |  | 22030036 | 1 | Towner County - Medical Ctr |  |  | 78999 | 158720.71 | 0 | 43536549.92 | 3054250.6 | 12459.8 | 892 | 95.96% | 4.036% | 0%
22030046 |  | 22030046 | 1 | City of Coralville-Hyatt Reno |  |  | 100000 | 0 | 0 | 0.01 | 103500.41 | 0 | 520.9196 | 66.02% | 28.03% | 5.951%
22030035 |  | 22030035 | 1 | Anne Carlsen - Rplcmnt Facil |  |  | 110000 | 229241.75 | 2874 | 47045229.73 | 13827627.34 | 19203.4 | 1460.5 | 98.97% | 1.027% | 0%
22030033 |  | 22030033 | 1 | MDI - Three Discovery Square |  |  | 144000 | 0 | 0 | 0.01 | 368120.47
22030021 |  | 22030021 | 1 | MDI - Cornell - New Residence |  |  | 213000 | 0 | 0 | 136000.01 | 489683.56
22080013-063 |  | 22080013-063 | 1 | WisDOT I43 Years 2-2 |  |  | 0 | 5 | 0 | 594939.27 | 16784.89
22040001 |  | 22040001 | 1 | SCAHC - Design Phase |  |  | 0 | 7 | 0 | 3344588.58 | 2640955.3
22040017 |  | 22040017 | 1 | Alaska USA Signal Butte Rd TI |  |  | 0 | 0 | 0 | 0 | 403.78
22040012 |  | 22040012 | 1 | CBR Sox Perf Lab Reno |  |  | 200 | 20 | 0 | 38338.81 | 25819.86 | 325 | 283 | 96.11% | 3.887% | 0%
22040003 |  | 22040003 | 1 | WhiteSox Camelback Fac Reno |  |  | 500 | 12149 | 0 | 208504.11 | 84522.93 | 726 | 46 | 91.3% | 8.696% | 0%
22040013 |  | 22040013 | 1 | Reds Female Locker Room |  |  | 835 | 12952 | 2053 | 292568 | 140197.86 | 580.4 | 665.5 | 92.64% | 7.363% | 0%
22040002 |  | 22040002 | 1 | AlaskaUSA Scottsdale |  |  | 2900 | 20162 | 15868 | 392021.3 | 404231.65 | 1124 | 1111.5 | 94.24% | 5.758% | 0%
22040014 |  | 22040014 | 1 | Exact Science MRD Lab TI |  |  | 3040 | 16551 | 3152 | 396912.34 | 35622.35 | 905 | 215 | 99.53% | 0.4651% | 0%
22040007 |  | 22040007 | 1 | AlaskaUSA Glendale Op Cntr |  |  | 3200 | 7136 | 79753 | 683041.94 | 387187.47 | 1524.7 | 2644 | 93.84% | 6.165% | 0%
22040006 |  | 22040006 | 1 | Allstate Chandler One TI |  |  | 6500 | 4647 | 10 | 507165.39 | 401322.12 | 0 | 94 | 100% | 0% | 0%
22040005 |  | 22040005 | 1 | SCAHC SanCarlos Reg/Check In |  |  | 10050 | 8 | 0 | 69604.28 | 33182.6
22040004 |  | 22040004 | 1 | Dodgers Reno Camelback |  |  | 14000 | 0 | 0 | 0.02 | 47607.99
22040011 |  | 22040011 | 1 | SCAHC Warehouse Facility |  |  | 46500 | 16 | 0 | 1313676.54 | 28152.45
22040015 |  | 22040015 | 1 | MDI - The Edith Hotel - Design |  |  | 200000 | 26 | 0 | 1058843 | 5058.94
22040009 |  | 22040009 | 1 | CCG CCPAZ Petro Manu Fac |  |  | 537000 | 436.65 | 0 | 11681312.81 | 298380.52 | 866 | 0 | 0% | 0% | 0%
22055002 |  | 22055002 | 1 | OHSU CHH1 12th Flr HPL |  |  | 0 | 11829.96 | 0 | 1015726.58 | 476108.76 | 1132.3 | 889.5 | 91.96% | 8.038% | 0%
22055003 |  | 22055003 | 1 | OHSU CHH1 6th Flr |  |  | 0 | 10 | 0 | 2559 | 2270.6
22055004 |  | 22055004 | 1 | OHSU CDW Roof Repl |  |  | 0 | 9 | 0 | 2170.11 | 2404.42
22055005 |  | 22055005 | 1 | Kaiser ORD Fire Alarm Repl |  |  | 0 | 15 | 0 | 18422.35 | 18658.77
22055006 |  | 22055006 | 1 | BPA TO4 PMO |  |  | 0 | 10 | 0 | 297397.82 | 160325.98
22055007 |  | 22055007 | 1 | Kaiser SST Nurse Call Const |  |  | 0 | 24 | 0 | 128219.47 | 104320.31 | 172 | 97.33 | 100% | 0% | 0%
22055008 |  | 22055008 | 1 | Kaiser SST Air Handle Constru |  |  | 0 | 30 | 0 | 1870401.42 | 1649266.08 | 633.9 | 1074.17 | 96.97% | 3.026% | 0%
22055009 |  | 22055009 | 1 | OHSU MQ2 MMBR |  |  | 0 | 0 | 0 | 0.02 | 0
22055010 |  | 22055010 | 1 | COH Ron Tonkin Stad Impr |  |  | 0 | 25 | 0 | 2113309.38 | 1632423.41
22055012 |  | 22055012 | 1 | Pac Seafood Clack. TI |  |  | 0 | 39133.29 | 20756 | 1092547.3792 | 1157884.17 | 1603.03 | 2411.5 | 95.96% | 4.043% | 0%
22055014 |  | 22055014 | 1 | Microchip Nitrogen Plant |  |  | 0 | 41865.65 | 28653 | 4061759.05 | 3494178.18 | 3548.9 | 2910.5 | 96.43% | 3.178% | 0.3951%
22055015 |  | 22055015 | 1 | Microchip Silane Bulk System |  |  | 0 | 36043.52 | 0 | 5479419.55 | 521959.18 | 1168.7 | 0 | 0% | 0% | 0%
22055016 |  | 22055016 | 1 | Microchip Boiler Addition |  |  | 0 | 4004.71 | 1667 | 2457406.72 | 1893446.56 | 1213.4 | 625.35 | 100% | 0% | 0%
22055017 |  | 22055017 | 1 | Microchip HF Treatment |  |  | 0 | 42 | 0 | 5175037.46 | 307958.99
22055019 |  | 22055019 | 1 | OHSU RPV MCECC Reloc |  |  | 0 | 10 | 0 | 4865 | 10100.57 | 8 | 0 | 0% | 0% | 0%
22055020 |  | 22055020 | 1 | BPA TO5 CCL/Survey Garage |  |  | 0 | 17 | 0 | 798953 | 295059.66
22055024 |  | 22055024 | 1 | Kaiser SST Lighting Constr |  |  | 0 | 27 | 0 | 797478.34 | 297394.49 | 457 | 18 | 100% | 0% | 0%
22055025 |  | 22055025 | 1 | Kaiser SST Emerg lghtg Constr |  |  | 0 | 27 | 0 | 222293.97 | 77574.46 | 376 | 46 | 100% | 0% | 0%
22055026 |  | 22055026 | 1 | Kaiser ORC Fire Alarm Constr |  |  | 0 | 31 | 0 | 897386.84 | 193430.78 | 569 | 16 | 100% | 0% | 0%
22055028 |  | 22055028 | 1 | Microchip Corrosive Storage |  |  | 0 | 14 | 0 | 18435.98 | 369.14 | 88 | 3.9 | 100% | 0% | 0%
22055030 |  | 22055030 | 1 | OHSU OCB LineAc |  |  | 0 | 12 | 0 | 14792.81 | 12791.98
22055031 |  | 22055031 | 1 | Prov Reed Retail Corridor |  |  | 0 | 23 | 0 | 199080.79 | 30640.89 | 40 | 0 | 0% | 0% | 0%
22055032 |  | 22055032 | 1 | Prov Reeds Addl TIs |  |  | 0 | 12 | 0 | 58855.36 | 669.42
22055033 |  | 22055033 | 1 | Microchip PE Scrubber |  |  | 0 | 21 | 0 | 1342215.89 | 21925.71
22055035 |  | 22055035 | 1 | BPA TO6 Ampere Demo |  |  | 0 | 0 | 0 | 0.01 | 25751
22055036 |  | 22055036 | 1 | Kaiser Reg 2021 Life Safety |  |  | 0 | 15 | 0 | 41621.97 | 29246.07
22055037 |  | 22055037 | 1 | Kaiser WMC OR & MPU Light Prec |  |  | 0 | 17 | 0 | 13792.95 | 5670.32 | 4 | 0 | 0% | 0% | 0%
22055038 |  | 22055038 | 1 | Kaiser ORC Optometry Precon |  |  | 0 | 0 | 0 | 0.01 | 0
22055039 |  | 22055039 | 1 | Kaiser NSC Maintenance |  |  | 0 | 0 | 0 | 0.01 | 0
22055040 |  | 22055040 | 1 | OHSU Prkg Structure C Est Feas |  |  | 0 | 0 | 0 | 0.01 | 0
22055041 |  | 22055041 | 1 | Microchip Oxygen Tank Replace |  |  | 0 | 0 | 0 | 0.02 | 10800
22055042 |  | 22055042 | 1 | Microchip Site Security Improv |  |  | 0 | 0 | 0 | 0.01 | 0
22055022 |  | 22055022 | 1 | OHSU IPA 8A Skybridge |  |  | 1780 | 0 | 0 | 0 | -3.99
22055027 |  | 22055027 | 1 | Microchip Medium Voltage Add |  |  | 2000 | 14153.72 | 192 | 2094566.23 | 197332.31 | 854 | 0 | 0% | 0% | 0%
22055021 |  | 22055021 | 1 | OHSU MP Pharm Admin |  |  | 3650 | 13 | 0 | 16085.18 | 6585.71 | 24 | 0 | 0% | 0% | 0%
22055029 |  | 22055029 | 1 | OHSU CDRC Eugene |  |  | 10000 | 12 | 0 | 7626 | 9374.75
22055034 |  | 22055034 | 1 | OHSU RWC Rehab |  |  | 10000 | 14 | 0 | 7394.4 | 0
22055043 |  | 22055043 | 1 | Microchip Chem Storage Ware |  |  | 23000 | 0 | 0 | 0.01 | 0
22055018 |  | 22055018 | 1 | Microchip Gresham Off Reno |  |  | 33000 | 114798.23 | 14934 | 7090685.25 | 2152686.67 | 7364.7 | 2528.43 | 97.43% | 2.571% | 0%
22055001 |  | 22055001 | 1 | Clark Advanced Manu Cntr |  |  | 61000 | 43 | 0 | 3460152.24 | 1622207.54 | 166.21 | 117.37 | 100% | 0% | 0%
22055013 |  | 22055013 | 1 | MDI Seran Comm Manu Fac |  |  | 90000 | 22 | 0 | 5992451.54 | 777247.89
22146001 |  | 22146001 | 1 | White Rock Wind - Power |  |  | 0 | 484331.96 | 0 | 31796250.01 | 2514029.82 | 30362.44 | 0 | 0% | 0% | 0%
22146002 |  | 22146002 | 1 | Abilene NW |  |  | 0 | 0 | 0 | 2539540 | 283709.83
22146003 |  | 22146003 | 1 | AEP Series Cap MOV Replace |  |  | 0 | 0 | 0 | 128745.8 | 98632.6 | 0 | 901 | 78.47% | 21.53% | 0%
22146004 |  | 22146004 | 1 | Corpus Christi |  |  | 0 | 0 | 0 | 2438869.07 | 1820890.78
22146005 |  | 22146005 | 1 | Outpost Solar Interconnect |  |  | 0 | 0 | 0 | 906271 | 5992.46
22146007 |  | 22146007 | 1 | Tierra Bonita Solar - Power |  |  | 0 | 682 | 0 | 8992726 | 2000.38
22146008 |  | 22146008 | 1 | GE SC Maintenance |  |  | 0 | 21 | 0 | 222851.95 | 49588.12 | 0 | 292.5 | 77.61% | 22.39% | 0%
22146009 |  | 22146009 | 1 | 2022 MSA Maintenance Work |  |  | 0 | 0 | 0 | 496926.42 | 193550.12 | 0 | 888.5 | 78.39% | 21.61% | 0%
22065003 |  | 22065003 | 1 | MDI-Saratoga Springs MOB |  |  | 0 | 0 | 0 | 7000 | 6116.01
22065004 |  | 22065004 | 1 | Mortenson SLC Office Space |  |  | 12300 | 0 | 0 | 0.01 | 14617.89 | 0 | 94 | 94.68% | 5.319% | 0%
22065005 |  | 22065005 | 1 | West Temple Hotel |  |  | 150000 | 0 | 0 | 0.01 | 76480.84
22065002 |  | 22065002 | 1 | Pacificorp-RMP HQ |  |  | 186000 | 0 | 0 | 200000 | 389061.36
22065001 |  | 22065001 | 1 | Domain-West Temple |  |  | 380000 | 0 | 0 | 0.01 | 418885.06
22050001 |  | 22050001 | 1 | Virtual Insights 2022 |  |  | 0 | 0 | 0 | 0.09 | 239598.01
22050002 |  | 22050002 | 1 | KP Everett - Sitework |  |  | 0 | 38260.79 | 5324.07 | 14647378.66 | 8810382.16 | 4703.8 | 2514.6 | 92.7% | 7.162% | 0.1392%
22050003 |  | 22050003 | 1 | Davita Fed Way TI |  |  | 0 | 27124.29 | 28532.65 | 649810.87 | 539088.33 | 528.9 | 560.5 | 99.64% | 0.3568% | 0%
22050004 |  | 22050004 | 1 | Sidewalk Labs Facility |  |  | 0 | 2 | 24 | 302489.65 | 310349.93 | 116 | 69 | 69.57% | 30.43% | 0%
22050005 |  | 22050005 | 1 | AMLI 5L Residential Tower |  |  | 0 | 30.29 | 0 | 1079051.19 | 558791.4
22050006 |  | 22050006 | 1 | Key Bank Pavilion |  |  | 0 | 0 | 0 | 78488.18 | 58664.77
22050007 |  | 22050007 | 1 | Seatac Meet Me Room |  |  | 0 | 15625.5 | 0 | 5389879.4 | 141119.03 | 1162.7 | 0 | 0% | 0% | 0%
22145011 |  | 22145011 | 1 | NSA Crane PV Replace - Duke |  |  | 0 | 1200 | 0 | 81500 | 50135.66 | 1100 | 960 | 83.33% | 16.67% | 0%
22145013 |  | 22145013 | 1 | FPL - Monarch (NEE) |  |  | 89 | 6 | 0 | 9108967 | 69203.64
22145012 |  | 22145012 | 1 | FPL - Caloosahatchee (NEE) |  |  | 100 | 6 | 0 | 9771265 | 70262.87
22145008 |  | 22145008 | 1 | Winquepin Solar - Duke |  |  | 103 | 6 | 0 | 6572253 | 1941504.7
22145009 |  | 22145009 | 1 | Falmouth Solar - Duke |  |  | 103 | 6 | 0 | 974812 | 307202.01
22145014 |  | 22145014 | 1 | FPL - Orchard (NEE) |  |  | 108 | 6 | 0 | 10249694 | 76436.3
22145001 |  | 22145001 | 1 | Vistra - Newton |  |  | 300 | 123 | 0 | 640290.51 | 482871.55 | 104 | 0 | 0% | 0% | 0%
22145002 |  | 22145002 | 1 | Vistra - Coffeen |  |  | 300 | 123 | 0 | 610222.51 | 362202.47 | 104 | 0 | 0% | 0% | 0%
22145003 |  | 22145003 | 1 | Vistra - Baldwin |  |  | 300 | 122 | 0 | 651140.01 | 382117.22 | 104 | 0 | 0% | 0% | 0%
22145004 |  | 22145004 | 1 | Vistra - Duck Creek |  |  | 300 | 111 | 0 | 594498.51 | 401234.31 | 104 | 0 | 0% | 0% | 0%
22145005 |  | 22145005 | 1 | Vistra - Kincaid |  |  | 300 | 123 | 0 | 588526.01 | 296381.19 | 104 | 0 | 0% | 0% | 0%
22145006 |  | 22145006 | 1 | Vistra - Hennepin |  |  | 300 | 123 | 0 | 672378.51 | 286846.57 | 104 | 0 | 0% | 0% | 0%
22145007 |  | 22145007 | 1 | Greasewood II - Tierra Bonita |  |  | 398 | 20 | 0 | 12359081 | 6730219.02 | 479 | 555 | 84.95% | 15.05% | 0%
22145010 |  | 22145010 | 1 | Tierra Blanco - CIG DS1, LLC |  |  | 507 | 0 | 0 | 71566.01 | 34644.48 | 0 | 0 | 0% | 0% | 0%
22150001 |  | 22150001 | 1 | CNS - ASU Multipurpose Arena |  |  | 0 | 0 | 0 | 710589.4 | 608821.26
22150002 |  | 22150002 | 1 | DIG - Vikrell West Manufac |  |  | 0 | 0 | 0 | 2814652 | 862767.68 | 0 | 0 | 0% | 0% | 0%
22150003 |  | 22150003 | 1 | PSU Lasch 6 Phase 2 |  |  | 0 | 0 | 0 | 143206 | 50950.99
22150004 |  | 22150004 | 1 | Hotel Mort/McCarthy Gaylord |  |  | 0 | 0 | 0 | 32105600 | 15060799.55
22150004-143 |  | 22150004-143 | 1 | Gaylord Pacific HOTEL Resort |  |  | 0 | 121150 | 0 | 511828604.38 | 81102500.87 | 32581 | 10685.5 | 88.03% | 11.13% | 0.8376%
22150005 |  | 22150005 | 1 | Convention Ctr Mort/McCarthy |  |  | 0 | 0 | 0 | 0.01 | 0
22150005-143 |  | 22150005-143 | 1 | Gaylord Pacific CONVENTION CTR |  |  | 0 | 96230 | 0 | 294383075.14 | 46127129.39 | 85557.66 | 0 | 0% | 0% | 0%
22150006 |  | 22150006 | 1 | 1A Gaylord Pacific Resort |  |  | 0 | 0 | 0 | 0.01 | 4495.7
22150006-143 |  | 22150006-143 | 1 | Gaylord Pacific 1A INFRAST |  |  | 0 | 1 | 0 | 27170957 | 8775414.03 | 0 | 3813.5 | 89.08% | 9.86% | 1.062%
22150007 |  | 22150007 | 1 | Garage Mort/McCarthy Gaylord |  |  | 0 | 0 | 0 | 0.01 | 0
22150007-143 |  | 22150007-143 | 1 | Gaylord Pacific GARAGE Resort |  |  | 0 | 495187 | 0 | 24711782 | 1100156.66 | 3937 | 0 | 0% | 0% | 0%
22150008 |  | 22150008 | 1 | Cleveland Browns NFL Precon |  |  | 0 | 0 | 0 | 0.02 | 150377.88
22150009 |  | 22150009 | 1 | MLB Cleveland Guardians |  |  | 0 | 0 | 0 | 0.01 | 340835.89
22150010 |  | 22150010 | 1 | MLB Angels Feasibility Study |  |  | 0 | 0 | 0 | 130000 | 126333.25
22141001 |  | 22141001 | 1 | Hawkeye Repower |  |  | 0 | 0 | 0 | 660250 | 350328.7
22141003 |  | 22141003 | 1 | Comm Wind South (CWS) Repower |  |  | 0 | 0 | 0 | 14569082.28 | 116219.63 | 0 | 30 | 66.67% | 33.33% | 0%
22141004 |  | 22141004 | 1 | Bishop Hill Repower |  |  | 0 | 0 | 0 | 256765 | 143284.96
22141005 |  | 22141005 | 1 | Bishop Hill II Repower |  |  | 0 | 0 | 0 | 194750 | 163194.11
22141006 |  | 22141006 | 1 | Delta Wind |  |  | 0 | 0 | 0 | 800634 | 691492.54
22141007 |  | 22141007 | 1 | Grand Meadow Repower |  |  | 0 | 2714.45 | 488 | 19925561.34 | 12654275.5 | 49401 | 37552.7 | 74.31% | 16.66% | 9.03%
22141009 |  | 22141009 | 1 | California Ridge Repower |  |  | 0 | 0 | 0 | 271700 | 25275
22141010 |  | 22141010 | 1 | Nobles ADLS Repower |  |  | 0 | 0 | 0 | 1156420 | 670998.17
22141011 |  | 22141011 | 1 | Nobles V136 Repower |  |  | 0 | 661.33 | 0 | 1208764.5 | 825723.4 | 1620 | 195 | 70.51% | 29.49% | 0%
22141012 |  | 22141012 | 1 | Fowler Ridge Repower |  |  | 0 | 0 | 0 | 24479678.59 | 84418.37
22141013 |  | 22141013 | 1 | Boswell Springs Wind |  |  | 0 | 0 | 0 | 2053817 | 113572.92
22141015 |  | 22141015 | 1 | Moraine Sands Wind |  |  | 0 | 0 | 0 | 31632361.99 | 233715.45
22141016 |  | 22141016 | 1 | Grand Meadow ADLS Repower |  |  | 0 | 0 | 0 | 151937 | 2542.15
22141017 |  | 22141017 | 1 | Skeleton Creek Grout Install |  |  | 0 | 0 | 0 | 35030.68 | 6224.71 | 152 | 0 | 0% | 0% | 0%
22141018 |  | 22141018 | 1 | Pyron Repower |  |  | 0 | 154 | 73 | 6564697.3 | 1653989.54 | 4410 | 3308.5 | 86.88% | 13.12% | 0%
22141019 |  | 22141019 | 1 | Pioneer Hutt Wind |  |  | 0 | 0 | 0 | 48426665.15 | 25
22141021 |  | 22141021 | 1 | Shamrock Wind |  |  | 0 | 0 | 0 | 72950887 | 1790.08
22141023 |  | 22141023 | 1 | Vestas 25 Mile Creek Wind |  |  | 0 | 9 | 0 | 498586.5 | 439258.18 | 3902.5 | 5981.5 | 81.74% | 18.26% | 0%
21024 |  | 21024 | 1 | 3M BLDG 220 INTERIORREMODEL | 2005-11-05 | 2005-09-02 | 0 | 163479 | 119905 | 8760201 | 9083594 | 0 | 19899 | 100% | 0% | 0%
21030 |  | 21030 | 1 | ALLINA-ABBOTT NORTHWESTERN HE | 2004-12-31 | 2005-01-14 | 419600 | 679171 | 829740 | 43362002 | 44034787 | 0 | 126524 | 100% | 0% | 0%
21020 |  | 21020 | 1 | ALLINA/MERCY HOSPITAL CARDIAC | 2004-05-31 | 2004-07-01 | 95000 | 213931 | 287004 | 12754593 | 12732663 | 0 | 45814 | 100% | 0% | 0%
21032 |  | 21032 | 1 | DICKINSON COMMUNITYCENTER | 2004-04-07 | 2004-05-13 | 0 | 0 | 0 | 713631 | 715572 | 0 | 3580 | 100% | 0% | 0%
21203 |  | 21203 | 1 | HAMMES-ST MARY'S HEALTHCARE C | 2004-03-14 | 2004-03-14 | 50500 | 0 | 0 | 10050580 | 9901859 | 0 | 8730 | 100% | 0% | 0%
21003 |  | 21003 | 1 | U OF MN /ANNUAL CONTRACT 2002 | 2002-12-31 | 2003-12-31 | 0 | 964 | 0 | 6201368 | 6206174 | 0 | 11062 | 100% | 0% | 0%
21040 |  | 21040 | 1 | WESTMINSTER CHURCH -MISC WORK | 2003-12-31 | 2003-12-31 | 0 | 0 | 0 | 10256 | 11630 | 0 | 94 | 100% | 0% | 0%
21026 |  | 21026 | 1 | WALKER ART CENTER -PARKING RA | 2003-11-01 | 2003-10-12 | 267493 | 10002747816 | 2467135 | 0 | 20418080 | 0 | 95271 | 100% | 0% | 0%
21038 |  | 21038 | 1 | ALLINA-ANW MRI ADDITION | 2003-06-30 | 2003-09-22 | 10200 | 41993 | 0 | 406597 | 412605 | 0 | 2429 | 100% | 0% | 0%
21021 |  | 21021 | 1 | 3M DATA CENTER | 2003-07-11 | 2003-08-08 | 0 | 1633293 | 925167 | 10256630 | 10843513 | 0 | 35451 | 100% | 0% | 0%
21014 |  | 21014 | 1 | RADISSON HOTELS -PLAZA VII RE | 2003-11-01 | 2003-07-01 | 0 | 229676 | 218130 | 6006022 | 6008075 | 0 | 17821 | 100% | 0% | 0%
21001 |  | 21001 | 1 | FAIRVIEW UMC ANNUAL-CONTRACT | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 0 | 796772 | 0 | 7753 | 100% | 0% | 0%
21002 |  | 21002 | 1 | FAIRVIEW UMC-MAINTENANCE CONT | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 0 | 42279 | 0 | 630 | 100% | 0% | 0%
21023 |  | 21023 | 1 | SPRC-LANDMARK PLAZA-PARK CONS | 2003-06-01 | 2002-11-27 | 21000 | 25657 | 25611 | 831372 | 1293351 | 0 | 4395 | 100% | 0% | 0%
21025 |  | 21025 | 1 | CARLSON-DEGERMAN FIELD | 2002-09-30 | 2002-09-30 | 500000 | 89 | 0 | 433040 | 432981 | 0 | 0 | 0% | 0% | 0%
21022 |  | 21022 | 1 | MHVP-XCEL CENTER BOARDROOM | 2002-09-20 | 2002-09-25 | 4000 | 1819 | 0 | 167056 | 259910 | 0 | 1799 | 100% | 0% | 0%
21011 |  | 21011 | 1 | WATEROUS -MID-SHIP -PUMP TEST | 2002-07-01 | 2002-08-27 | 4000 | 106629 | 44573 | 4472022 | 5313301 | 0 | 13231 | 100% | 0% | 0%
21007 |  | 21007 | 1 | BETHEL COLLEGE - CLCORGAN | 2002-09-01 | 2002-08-20 | 0 | 2362 | 0 | 416036 | 416346 | 0 | 1243 | 100% | 0% | 0%
21010 |  | 21010 | 1 | MORTENSON 4TH FLOORSLT OFFICE | 2002-03-31 | 2002-03-31 | 192 | 5 | 0 | 5310 | 5672 | 0 | 40 | 100% | 0% | 0%
21015 |  | 21015 | 1 | U OF MN-HUMPHREY MUSEUM | 2002-02-28 | 2002-02-28 | 0 | 0 | 0 | 0 | 1583 | 0 | 0 | 0% | 0% | 0%
21090002 |  | 21090002 | 1 | RUMC - 2021 Small Projects |  |  | 0 | 59391.39 | 0 | 1714223.85 | 2075388.8 | 5 | 4867.5 | 96.5% | 2.969% | 0.5342%
21090003 |  | 21090003 | 1 | LCH - 2021 Small Projects |  |  | 0 | 699 | 0 | 4012824.1362 | 3357422.36 | 4280.17 | 9855.5 | 85.15% | 10.09% | 4.764%
21090005 |  | 21090005 | 1 | NWM - Delnor Cancer Center |  |  | 0 | 0 | 0 | 68763 | 100781.15 | 0 | 21 | 0% | 19.05% | 80.95%
21090991 |  | 21090991 | 1 | Chicago 2021 Prefab Shop |  |  | 0 | 1189 | 738 | 0 | 447911.22 | 106 | 4141.5 | 99.28% | 0.6278% | 0.09658%
21090004 |  | 21090004 | 1 | SAIC-MacLean & Lakeview |  |  | 5900 | 50176 | 1 | 2016518.2 | 1799244.21 | 1500.88 | 1220.5 | 89.55% | 9.34% | 1.106%
21090001 |  | 21090001 | 1 | WR Meadows - Innovation Center |  |  | 30356 | 231222.27 | 59592 | 12499905.5408 | 11369946.5 | 6603.58 | 5190 | 92.94% | 6.811% | 0.2505%
21148001 |  | 21148001 | 1 | Emerald Grove Solar - Civil |  |  | 0 | 3148525.35 | 173445 | 3286433.86 | 2761468.89 | 8019.8 | 5351.5 | 84.51% | 15.49% | 0%
21148002 |  | 21148002 | 1 | Glass Sands Wind - Civil |  |  | 0 | 7161369.6 | 501299 | 9706820.48 | 11503246.03 | 29694.71 | 49859.5 | 80.43% | 19.57% | 0%
21141001, 21148003 |  | 21148003 | 11 | Pocahontas Repower - Civil |  |  | 0 | 21535.39 | 36676 | 2507303.49 | 2194055.57 | 7116.9 | 10215 | 76.32% | 23.43% | 0.2496%
21148005 |  | 21148005 | 1 | Chokecherry Sierra Madre 2021 |  |  | 0 | 809966.44 | 816231 | 17288938.52 | 14519868.32 | 60845.78 | 51949.5 | 83.74% | 16.1% | 0.1598%
21148006 |  | 21148006 | 1 | Richland (Sac) Wind - Civil |  |  | 0 | 5045033 | 340839 | 5777493.1646 | 6204060.39 | 18812.26 | 19413.5 | 77.01% | 22.98% | 0.0103%
21148007 |  | 21148007 | 1 | Mountain View I & II - Civil |  |  | 0 | 4650563 | 72632 | 4439146.14 | 3611841.8 | 19259.96 | 15241.5 | 79.29% | 20.15% | 0.5577%
21148008 |  | 21148008 | 1 | Midland Wind - Civil |  |  | 0 | 12642566.16 | 221787 | 14045325.86 | 15510797.43 | 40300.5 | 53340.8 | 68.24% | 30.63% | 1.138%
21148009 |  | 21148009 | 1 | Pomeroy Repower Civil |  |  | 0 | 2246318.32 | 20882.69 | 2060474.4542 | 1394311.77 | 6166.78 | 4420 | 74.4% | 24.72% | 0.8824%
21148010 |  | 21148010 | 1 | Laurel Repower Civil |  |  | 0 | 5297409.79 | 1750 | 6572756.2408 | 4825090.39 | 19440.57 | 14905.5 | 78.21% | 20.11% | 1.674%
21148011 |  | 21148011 | 1 | Rolling Hills Repower Civil |  |  | 0 | 18245742.83 | 166546.25 | 22911594.3217 | 20185545.05 | 43821.49 | 72012.5 | 70.99% | 27.68% | 1.336%
21148012 |  | 21148012 | 1 | Sheph Flats(NorH) Wind - Civil |  |  | 0 | 2030296.42 | 15338 | 5969002.85 | 5021551.62 | 5663.75 | 11053.75 | 70.35% | 28.13% | 1.52%
21148013 |  | 21148013 | 1 | Sheph Flats(SthH) Wind - Civil |  |  | 0 | 2396970.85 | 130 | 5180391.68 | 4244971 | 6280.85 | 12326.31 | 74.89% | 24.44% | 0.6652%
21148014 |  | 21148014 | 1 | Sheph Flats (HoB) Wind - Civil |  |  | 0 | 2281370.85 | 87 | 2645740.29 | 2261825.78 | 6875.13 | 9408 | 69.94% | 29.44% | 0.6271%
21148015 |  | 21148015 | 1 | 25 Mile Creek Wind - Civil |  |  | 0 | 12308824.17 | 1671260 | 14819898.8468 | 14112373.56 | 53130.65 | 58306.33 | 75.74% | 24.26% | 0%
21148016 |  | 21148016 | 1 | Nobles Repower - Civil |  |  | 0 | 5835882.2 | 40095 | 7403314.08 | 6544641.57 | 20344.46 | 23259.5 | 76.63% | 23.29% | 0.07954%
21148017 |  | 21148017 | 1 | Sagebrush Storage - Civil |  |  | 0 | 938461.5 | 0 | 1115023.64 | 936284.15 | 794.36 | 622 | 72.35% | 27.65% | 0%
21148018 |  | 21148018 | 1 | UNO1A Mass Grading |  |  | 0 | 4931871.08 | 5084686.75 | 38521111.1245 | 29763847.03 | 113517.87 | 112345 | 75.94% | 24.06% | 0%
21120001 |  | 21120001 | 1 | Google - CLB Masterplan |  |  | 0 | 10 | 0 | 172745 | 111836.05
21120002 |  | 21120002 | 1 | Google-UNO1-A Master Planning |  |  | 0 | 0 | 0 | 171389.09 | 80158.63
21120004 |  | 21120004 | 1 | Facebook - Lego Phase 3 DC |  |  | 0 | 2816 | 0 | 1921084.75 | 815375.6
21120005 |  | 21120005 | 1 | Facebook - Community Relations |  |  | 0 | 0 | 0 | 490000 | 443573.08
21120006 |  | 21120006 | 1 | Google - UNO1 Data Center |  |  | 0 | 219152.32 | 0 | 315027854.09 | 116381374.38 | 4870.1 | 6861.5 | 78.44% | 19.83% | 1.727%
21120007 |  | 21120007 | 1 | Meta - 2021 MCM |  |  | 0 | 2 | 0 | 1396863.8 | 1164672.71
21120008 |  | 21120008 | 1 | Meta - DC Type X Product DFMA |  |  | 0 | 0 | 0 | 520960 | 403456.7
21126001 |  | 21126001 | 1 | Facebook - Prg Serv. 2021 |  |  | 0 | 9 | 0 | 2557258 | 2193414.58
21120003 |  | 21120003 | 1 | Facebook - DKL 3¦5¦6 |  |  | 1507646 | 3598017.15 | 667849.26 | 1392024809.63 | 566043337.71 | 431420.68 | 122536.83 | 87.2% | 10.03% | 2.768%
21060004 |  | 21060004 | 1 | SCL-LMC Sprinkler |  |  | 0 | 18 | 565.01 | 220151.65 | 241157.4 | 274.2 | 721.5 | 92.24% | 7.762% | 0%
21060005 |  | 21060005 | 1 | SCL-LMC Chapel AHU Replacement |  |  | 0 | 159 | 15 | 19883.81 | 19957.38 | 46 | 32 | 96.88% | 3.125% | 0%
21060009 |  | 21060009 | 1 | 324 Office Building |  |  | 0 | 0 | 0 | 0.01 | 0
21060011 |  | 21060011 | 1 | SCL-Butte Transformer |  |  | 0 | 5889.91 | 0 | 257970.15 | 270409.83 | 241.2 | 0 | 0% | 0% | 0%
21060017 |  | 21060017 | 1 | SCL-LMC Steam Blow Down |  |  | 0 | 7.5 | 0 | 16693.46 | 16394.66
21060018 |  | 21060018 | 1 | SCL-SJH Restrooms |  |  | 0 | 493 | 183 | 275030.19 | 254322.07 | 131 | 98 | 98.47% | 1.531% | 0%
21060020 |  | 21060020 | 1 | SCL-SJB Elevator Refurbishment |  |  | 0 | 1141.21 | 0 | 1249183.1804 | 1131353.15 | 40 | 0 | 0% | 0% | 0%
21060023 |  | 21060023 | 1 | MC G150 Utilities Package |  |  | 0 | 0 | 1 | 1383873.19 | 1183830.51 | 0 | 143 | 95.1% | 4.895% | 0%
21060025 |  | 21060025 | 1 | Vestas Project X |  |  | 0 | 0 | 0 | 5558.41 | 6326.98
21060026 |  | 21060026 | 1 | Modern Aviation-Hangar |  |  | 0 | 462024.31 | 334799.75 | 18648227.365 | 18918663.84 | 19317.3 | 27959.53 | 93.57% | 6.428% | 0%
21060029 |  | 21060029 | 1 | Aurora One Develop - Precon |  |  | 0 | 0 | 0 | 0.01 | 3722.98
21060033 |  | 21060033 | 1 | WCR2 Borrow Pit |  |  | 0 | 92884.97 | 59460 | 501909 | 0 | 1810.97 | 0 | 0% | 0% | 0%
21060041 |  | 21060041 | 1 | WCR 2 Borrow Pit |  |  | 0 | 132193.34 | 79189 | 714533.3117 | 793314.27 | 1810.97 | 1839.5 | 71.92% | 28.08% | 0%
21060042 |  | 21060042 | 1 | SCL-SJD Medivator |  |  | 0 | 85 | 95 | 25054.73 | 25902.6 | 108 | 150 | 86.67% | 13.33% | 0%
21060044 |  | 21060044 | 1 | SCL-Lutheran CT Equipment |  |  | 0 | 1703 | 91 | 28939.1 | 32126.81 | 440.8 | 253 | 92.49% | 7.51% | 0%
21060046 |  | 21060046 | 1 | Park Creek Filing 34 |  |  | 0 | 0 | 3595 | 1298683 | 1246658.31 | 3161 | 3764.5 | 98.62% | 1.381% | 0%
21060048 |  | 21060048 | 1 | Park Creek-Civil Phase 3 |  |  | 0 | 0 | 914 | 515830 | 525001.44 | 1505 | 2025 | 100% | 0% | 0%
21060050 |  | 21060050 | 1 | MC 2022 Capital Improvements |  |  | 0 | 19129.13 | 6648 | 827677.57 | 810024.3 | 314.5 | 3416.5 | 88% | 12% | 0%
21060056 |  | 21060056 | 1 | CoorsTek-CCAM R&D |  |  | 0 | 78 | 16 | 598016.12 | 580921.19 | 347 | 180 | 82.5% | 17.5% | 0%
21060062 |  | 21060062 | 1 | Park Creek- Filing 60 |  |  | 0 | 0 | 134 | 306472 | 307316.58 | 873 | 214 | 100% | 0% | 0%
21060063 |  | 21060063 | 1 | DHHA Sterile Processing Dept |  |  | 0 | 1366 | 199.26 | 297373.7 | 283122.34 | 1234.7 | 368.5 | 75.31% | 24.69% | 0%
21060064 |  | 21060064 | 1 | Box Elder Infrastruct Phas 1 |  |  | 0 | 509432.8 | 302200.5 | 25733405.54 | 18191955.47 | 15181.38 | 7356.2 | 81.43% | 18.57% | 0%
21060065 |  | 21060065 | 1 | CoorsTek 9th St Utility |  |  | 0 | 7447.5 | 5071.5 | 1780234.387 | 1698977.45 | 7562.5 | 11419.5 | 97.19% | 2.811% | 0%
21060003 |  | 21060003 | 1 | SCL-LMC DA Tank Controls |  |  | 1 | 136 | 15 | 42921.16 | 42576.17 | 55 | 36 | 97.22% | 2.778% | 0%
21060053 |  | 21060053 | 1 | SCL-SJH Brachy Therapy |  |  | 1 | 26726 | 1768.83 | 1204750.2285 | 1217582.53 | 4011.29 | 4462.59 | 87.88% | 12.12% | 0%
21060030 |  | 21060030 | 1 | SCL-SJH Midtown Roof |  |  | 2 | 27018 | 608.26 | 1382945.59 | 1410244.1 | 115 | 1272 | 91.19% | 8.805% | 0%
21060031 |  | 21060031 | 1 | SCL-LMC W Pines Security |  |  | 2 | 330.6 | 0 | 52823.62 | 52405.09 | 325.4 | 69 | 100% | 0% | 0%
21060015 |  | 21060015 | 1 | SCL SJD Misc AV Support |  |  | 100 | 18.85 | 24 | 19910.06 | 20076.15 | 129 | 70.5 | 90.78% | 9.22% | 0%
21060039 |  | 21060039 | 1 | SCL-SJB Steam Hot Water |  |  | 100 | 1020.21 | 0 | 90422.44 | 90043.14
21060032 |  | 21060032 | 1 | DHHA -Payroll Suite Renovation |  |  | 120 | 38 | 49 | 11540.88 | 11433.4 | 83 | 72 | 87.5% | 12.5% | 0%
21060057 |  | 21060057 | 1 | DHHA-Pav C Milk Prep |  |  | 150 | 261 | 74.2 | 76525.49 | 74124.8 | 214.45 | 338.5 | 88.04% | 11.96% | 0%
21060027 |  | 21060027 | 1 | SCL-SJB Butte Humidity |  |  | 500 | 1022.17 | 0 | 272353.06 | 270277.18
21060028 |  | 21060028 | 1 | SCL-SJB Butte Life Safety |  |  | 500 | 1132.27 | 0 | 392598.34 | 410811.72 | 106.6 | 0 | 0% | 0% | 0%
21060036 |  | 21060036 | 1 | SCL-SJB Fire Doors |  |  | 500 | 1093.67 | 0 | 132677.95 | 135343.03
21060038 |  | 21060038 | 1 | SCL-SJB MRI Roof Replacement |  |  | 500 | 817.6 | 0 | 660661.65 | 676302.2
21060055 |  | 21060055 | 1 | Highpoint-Phase 1 Metro Dist |  |  | 500 | 70291 | 44340.1 | 7551226.35 | 6857298.97 | 10403.61 | 15239.45 | 79.42% | 20.58% | 0%
21060059 |  | 21060059 | 1 | SCL-SJB Card Reader Precon |  |  | 500 | 0 | 0 | 0.01 | 0
21060006 |  | 21060006 | 1 | SCL-SJB RAMP Chiller |  |  | 1000 | 1132.5 | 0 | 411069.03 | 425144.92 | 381.2 | 0 | 0% | 0% | 0%
21060007 |  | 21060007 | 1 | SCL-SJB Deareator Tank |  |  | 1000 | 2858.55 | 0 | 688556.32 | 717909.41 | 347.6 | 0 | 0% | 0% | 0%
21060052 |  | 21060052 | 1 | CHCO-AMC Kitchen Remodel |  |  | 1500 | 1343.5 | 1798.99 | 1278046 | 953958.15 | 3888.3 | 2769 | 85.61% | 14.39% | 0%
21060021 |  | 21060021 | 1 | CoorsTek-STM Gov't Storage |  |  | 2100 | 0 | 41 | 197055.01 | 185830.09 | 412 | 266 | 99.62% | 0.3759% | 0%
21060047, 20060058, 18000015-040, 18060047, 20060042 |  | 21060047 | 1 | SCL-Candelas Pharmacy TI's |  |  | 2100 | 0 | 0 | 361027.07 | 360454.97
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 21060002 | 11 | SCL-SJB Pneumatic Tube System |  |  | 2500 | 21 | 0 | 183983.45 | 190354.87
21060049 |  | 21060049 | 1 | CoorsTek Pilot Plant Cell |  |  | 5000 | 4 | 214 | 820705.11 | 1156955.18 | 222 | 3364.71 | 92.51% | 7.49% | 0%
21060010 |  | 21060010 | 1 | SCL-NJH Primary Care Clinic |  |  | 9000 | 190 | 0 | 1613950.38 | 1612235.99 | 190 | 66 | 100% | 0% | 0%
21060040 |  | 21060040 | 1 | Girls Inc. Courtyard |  |  | 9360 | 6190.39 | 5876 | 404339.31 | 406582.04 | 1394.2 | 2203 | 93.92% | 6.083% | 0%
21060016 |  | 21060016 | 1 | SCL Butte Flats Primary Clinic |  |  | 10000 | 2314 | 0 | 2001598.69 | 2062900.54 | 708.1 | 0 | 0% | 0% | 0%
21060008 |  | 21060008 | 1 | SCL-LMC Cancer Center |  |  | 12000 | 110188 | 41788.25 | 2811289.9086 | 2884669.35 | 4370.92 | 5429.5 | 95.27% | 4.733% | 0%
21060045 |  | 21060045 | 1 | AEI - Ft Collins Refresh |  |  | 20000 | 11471 | 37.5 | 6449194.41 | 6414181.87 | 4900.3 | 3888.91 | 91.63% | 8.373% | 0%
21060051 |  | 21060051 | 1 | CHCO-Research Enterprise |  |  | 21000 | 7241.5 | 199.41 | 272330.64 | 285193.29 | 1052.8 | 1454.5 | 91.51% | 8.491% | 0%
21060066 |  | 21060066 | 1 | SCL-Midtown Fireproofing |  |  | 25000 | 294 | 707.85 | 2185730.3552 | 2183983.67 | 3206 | 5564.22 | 84.68% | 15.32% | 0%
21060022 |  | 21060022 | 1 | TerraCO Comm Plant 1 |  |  | 30000 | 0 | 0 | 20072 | 20071.97
21060035 |  | 21060035 | 1 | Willis Towers 20th & 21st TI |  |  | 40000 | 117089 | 75954.97 | 5957945.3267 | 5661634.67 | 5739.99 | 11795 | 96.21% | 3.79% | 0%
21060013 |  | 21060013 | 1 | Tritower - Sterling Campus Lab |  |  | 95292 | 0 | 0 | 76402 | 109429.81
21060061 |  | 21060061 | 1 | Centura-SAN Tower & Renovation |  |  | 112500 | 788051.3 | 145 | 65750616.09 | 4778134.9 | 38298.9 | 953 | 90.03% | 9.969% | 0%
21060034 |  | 21060034 | 1 | BCSP 1740 Broadway |  |  | 113084 | 50128.58 | 49943 | 14629833.234 | 12432192.39 | 9941.1 | 8978 | 87.1% | 12.9% | 0%
21060024 |  | 21060024 | 1 | Train Denver CM Phase I Office |  |  | 125000 | 0 | 0 | 0.01 | 8548.03
21060037 |  | 21060037 | 1 | MDI-Walnut Park Multifamily |  |  | 269000 | 0 | 0 | 0.01 | 70707.26
21060001 |  | 21060001 | 1 | CoorsTek 9th St. Precon |  |  | 400000 | 0 | 0 | 25000 | 107981.35 | 0 | 0 | 0% | 0% | 0%
21060043 |  | 21060043 | 1 | MDI-SLC Industrial |  |  | 465000 | 0 | 0 | 0.01 | 62023.73
21060060 |  | 21060060 | 1 | Dollar General |  |  | 918000 | 1778946.96 | 745910 | 120918244.0504 | 39880276.65 | 51149.72 | 23353 | 74.02% | 25.98% | 0%
21149001 |  | 21149001 | 1 | CATS EV Bus |  |  | 0 | 45097.16 | 41144 | 3407815.16 | 3254909.92 | 2015.31 | 2560.5 | 89.14% | 10.86% | 0%
21149002 |  | 21149002 | 1 | Fighting Jays BESS |  |  | 0 | 0 | 113 | 748117.4 | 497921.29 | 0 | 123 | 100% | 0% | 0%
21149003 |  | 21149003 | 1 | Sagebrush BESS |  |  | 0 | 342253.64 | 270802.12 | 60448661.8404 | 57040100.64 | 49526.89 | 63227.77 | 82.91% | 16.34% | 0.7544%
21110001 |  | 21110001 | 1 | AMJV Tropical Pyramid JV-Int |  |  | 0 | 0 | 0 | 35019 | 32547.94
21110002 |  | 21110002 | 1 | AMJV Backsaw JV-Int |  |  | 0 | 0 | 0 | 297 | 462.5
21110003-159 |  | 21110003-159 | 1 | McCarthy/Mortenson JV-NBAF 8 |  |  | 0 | 0 | 0 | 53237697 | 0
21110004 |  | 21110004 | 1 | AMJV SCADA Upgrades JV-Int |  |  | 0 | 0 | 0 | 524060 | 485586.27 | 0 | 1100 | 100% | 0% | 0%
21110006 |  | 21110006 | 1 | AMJV CHW Upgrade JV-Int |  |  | 0 | 0 | 0 | 21575 | 29706.78
21110008 |  | 21110008 | 1 | Bolling AFB Photolab |  |  | 0 | 5822 | 0 | 644249.09 | 490565.63
21110009 |  | 21110009 | 1 | AMJV Abundant Shield JV-Int |  |  | 0 | 0 | 0 | 5572 | 1484.45
21110009-174 |  | 21110009-174 | 1 | UDC Abundant Shield |  |  | 0 | 0 | 0 | 128796 | 117205.11
21110010 |  | 21110010 | 1 | AMJV DCM 4 Pre-Fit Up JV-Int |  |  | 0 | 0 | 0 | 1060138 | 679918.31 | 0 | 1640 | 100% | 0% | 0%
21110010-174 |  | 21110010-174 | 1 | UDC DCM 4 Pre-Fit Up |  |  | 0 | 0 | 0 | 18842330 | 8795209.09
21110002-174 |  | 21110002-174 | 1 | UDC Backsaw |  |  | 2000 | 0 | 0 | 12939 | 12072.26
21110006-174 |  | 21110006-174 | 1 | UDC Chilled Water Upgrades |  |  | 2000 | 0 | 0 | 276003 | 272960.64
21110001-174 |  | 21110001-174 | 1 | UDC Tropical Pyramid |  |  | 6000 | 0 | 0 | 189062 | 181166.84
21060012 |  | 21060012 | 1 | NREL RAIL |  |  | 16500 | 3360 | 1493.4 | 16367611.45 | 17282503.05 | 2221 | 10374.55 | 88.01% | 11.99% | 0%
21110003 |  | 21110003 | 1 | McCarthy/Mortenson NBAF 8 |  |  | 18000 | 0 | 0 | 390000.01 | 2210868.12 | 0 | 7420 | 91.39% | 8.612% | 0%
21110004-174 |  | 21110004-174 | 1 | UDC SCADA Upgrades |  |  | 25000 | 0 | 0 | 3046382 | 2997885.3
21110007 |  | 21110007 | 1 | Bldg 9840 AHU 6 Cooling Coil |  |  | 34306 | 36 | 0 | 319423 | 301269.37
21110005 |  | 21110005 | 1 | NGIC Rivanna |  |  | 88000 | 117643 | 0 | 62961278.015 | 19661576.47 | 0 | 2067.5 | 99.9% | 0.09674% | 0%
21080005 |  | 21080005 | 1 | DRS-Dallas Masterplan Study |  |  | 0 | 0 | 0 | 10000 | 9991.72
21080010 |  | 21080010 | 1 | Ever Green Misc Project 21-22 |  |  | 0 | 13 | 1 | 112155 | 121549.9 | 700 | 676 | 97.63% | 2.367% | 0%
21080015 |  | 21080015 | 1 | RockGen Concrete Pad 3-3 |  |  | 0 | 804.45 | 0 | 41918.96 | 25195.18 | 280.7 | 227 | 100% | 0% | 0%
21080018 |  | 21080018 | 1 | WisDOT I43 North |  |  | 0 | 0 | 0 | 0.01 | 13139.71
21080004 |  | 21080004 | 1 | MRMC Cooling Tower Basin |  |  | 100 | 9881.16 | 5974 | 556964.92 | 553310.58 | 1405.4 | 1507.5 | 98.54% | 1.459% | 0%
21080002 |  | 21080002 | 1 | AAH Misc Projects 2021-2022 |  |  | 200 | 19 | 0 | 1357307.48 | 1016449.78 | 2448 | 3043.98 | 94.12% | 5.782% | 0.09856%
21080012 |  | 21080012 | 1 | MRMC City Water Office |  |  | 400 | 4125.3 | 0 | 113021.81 | 113894.92 | 304.6 | 258 | 100% | 0% | 0%
21080007 |  | 21080007 | 1 | AMCMP Misc Projects 21-22 |  |  | 1500 | 39037.61 | 11761 | 2431298 | 2097083.69 | 3108.8 | 1977.5 | 96.79% | 3.211% | 0%
21080017 |  | 21080017 | 1 | Froedtert - MF Pharm Reno |  |  | 3800 | 90710 | 13019 | 5844470.28 | 1672524.89 | 4879.5 | 2430.5 | 94.65% | 5.225% | 0.1234%
21080013 |  | 21080013 | 1 | Froedtert Complex Intervention |  |  | 10856 | 102223 | 5394 | 5653850.7 | 5096856.38 | 7434.3 | 9104 | 91.48% | 7.958% | 0.5602%
21080011 |  | 21080011 | 1 | Froedtert GI Diagnostic |  |  | 53500 | 736877 | 56 | 18545006.8 | 8787473.96 | 24690.1 | 10343 | 98.46% | 1.503% | 0.03867%
21080014 |  | 21080014 | 1 | Dane Cty Arpt CA Phase STE |  |  | 60000 | 0 | 0 | 64488 | 31862.34
21080006 |  | 21080006 | 1 | Mulva Cultural Center |  |  | 80000 | 328608.5 | 5584 | 78591777.2602 | 51279707.92 | 18212.04 | 8644.48 | 88.91% | 10.94% | 0.1446%
21080019 |  | 21080019 | 1 | MCW Cancer Research |  |  | 150000 | 40586.63 | 3619.5 | 13891384.42 | 2468612.36 | 7417.1 | 1859 | 96.88% | 3.093% | 0.0269%
21080016 |  | 21080016 | 1 | Embassy Suites Madison |  |  | 153800 | 1275910.07 | 226604.5 | 58778015.418 | 20216895.81 | 43483.72 | 21071.25 | 89.24% | 10.72% | 0.03797%
21080001 |  | 21080001 | 1 | Milwaukee Public Museum |  |  | 200000 | 844 | 575 | 874379.93 | 451826.51 | 96 | 133 | 98.5% | 1.504% | 0%
21080008 |  | 21080008 | 1 | UW Madison - CDIS |  |  | 310000 | 0 | 0 | 19800 | 3667.62
21080009 |  | 21080009 | 1 | Milwaukee Tool-ProjRed Beacon |  |  | 370000 | 2883936.47 | 1492184.76 | 88187650.43 | 81043608.81 | 76900.7 | 71137.04 | 95.23% | 4.671% | 0.09629%
21080003 |  | 21080003 | 1 | ULINE DISTRIBUTION FAC - FL |  |  | 937000 | 82890 | 0 | 93978580.96 | 88223984.19 | 0 | 2243.5 | 86.56% | 13.44% | 0%
21008 |  | 21008 | 1 | MORTENSON PROPERTIESMORTENSON | 2002-12-31 |  | 0 | 0 | 0 | 0 | 6956 | 0 | 102 | 100% | 0% | 0%
21009 |  | 21009 | 1 | NORTHWIRTH ASSOCIATET.I. 2002 | 2002-12-31 |  | 0 | 0 | 0 | 9087 | 36245 | 0 | 310 | 100% | 0% | 0%
21016 |  | 21016 | 1 | MSFC- MISC CONSULTING | 2002-12-31 |  | 0 | 0 | 0 | 0 | 18163 | 0 | 5 | 100% | 0% | 0%
21019 |  | 21019 | 1 | HGA-WAC TEAM BUILD -OUT | 2002-04-29 |  | 0 | 0 | 1324 | 0 | 11705 | 0 | 196 | 100% | 0% | 0%
21027 |  | 21027 | 1 | HABITAT FOR HUMANITY | 2002-10-31 |  | 0 | 0 | 0 | 0 | 11193 | 0 | 121 | 100% | 0% | 0%
21029 |  | 21029 | 1 | MORTENSON DEVELOPMENT-FAIRVIE | 2003-10-30 |  | 0 | 129527 | 87770 | 1868019 | 1876591 | 0 | 4599 | 100% | 0% | 0%
21030001 |  | 21030001 | 1 | Fairview Facility Annual 2021 |  |  | 0 | 778 | 0 | 3093971.36 | 3742040.32 | 0 | 7598 | 94.12% | 4.271% | 1.606%
21030002 |  | 21030002 | 1 | Allina Annual Contract 2021 |  |  | 0 | 3519 | 0 | 5105415.26 | 4554673.58 | 23028.5 | 20023.25 | 85.13% | 14.42% | 0.4545%
21030003 |  | 21030003 | 1 | Fairview Small Cap Proj 2021 |  |  | 0 | 52 | 0 | 880892.4 | 854171.41 | 0 | 1805.5 | 97.76% | 1.8% | 0.4431%
21030008 |  | 21030008 | 1 | Allina Mercy EP 2 Replacement |  |  | 0 | 15 | 0 | 304482.72 | 320305.42 | 1002 | 1065.5 | 97.28% | 2.722% | 0%
21030014 |  | 21030014 | 1 | BSC - Access Drive/Parking Exp |  |  | 0 | 24 | 0 | 4375232.19 | 4402212.27 | 24 | 0 | 0% | 0% | 0%
21030015 |  | 21030015 | 1 | MMC - Sanford Cooling Tower |  |  | 0 | 0 | 0 | 172153.1 | 175793.51 | 30 | 8 | 100% | 0% | 0%
21030018 |  | 21030018 | 1 | TA - Edgewood Demo |  |  | 0 | 0 | 0 | 2513015.587 | 2607033.92 | 8 | 225 | 81.78% | 18.22% | 0%
21030025 |  | 21030025 | 1 | Allina ANW Road Curb Walkway |  |  | 0 | 372 | 0 | 316885.58 | 278351.86 | 1601 | 1310.5 | 92.22% | 6.257% | 1.526%
21030026 |  | 21030026 | 1 | Skogman Office Bldg Renovation |  |  | 0 | 0 | 0 | 299214 | 240474.13 | 612 | 306 | 77.45% | 22.55% | 0%
21030029 |  | 21030029 | 1 | Augustana - East Granskou Park |  |  | 0 | 13 | 0 | 551513.77 | 552491.44
21030030 |  | 21030030 | 1 | Basilica 2021 Masonry Restore |  |  | 0 | 4109 | 0 | 505321.23 | 471745.61 | 4489 | 2361.18 | 89.29% | 10.71% | 0%
21030032 |  | 21030032 | 1 | Augustana - Electrical Infrast |  |  | 0 | 13 | 0 | 539386.45 | 541130.94
21030033 |  | 21030033 | 1 | Augustana - Bergsaker Hall Ren |  |  | 0 | 105832.66 | 47438 | 8670418.1 | 8752313.02 | 5765.72 | 5619.5 | 87% | 13% | 0%
21030034 |  | 21030034 | 1 | Augustana - Campus Greens Impr |  |  | 0 | 27 | 0 | 2486112.1 | 2318185.5 | 432 | 1079.5 | 89.53% | 10.47% | 0%
21030037 |  | 21030037 | 1 | The Basilica - School Foundati |  |  | 0 | 50 | 0 | 217867.52 | 192859.49 | 424 | 344.59 | 95.5% | 4.498% | 0%
21030044 |  | 21030044 | 1 | Cirrus Aircraft - Master Plann |  |  | 0 | 304 | 0 | 139675 | 348987.96
21030045 |  | 21030045 | 1 | IDT - ECO Stack Replacement |  |  | 0 | 973.06 | 0 | 129279.33 | 108259.85 | 173.6 | 141.5 | 93.29% | 6.714% | 0%
21030049 |  | 21030049 | 1 | ANW-CK LL Cafeteria Plmb Rpr |  |  | 0 | 57 | 0 | 414460.29 | 411200.81 | 1437 | 1259.5 | 88.13% | 11.71% | 0.1588%
21030053 |  | 21030053 | 1 | Swervo - Ampitheater |  |  | 0 | 0 | 0 | 249438.46 | 185192.93 | 0 | 11 | 27.27% | 72.73% | 0%
21030054 |  | 21030054 | 1 | IDT - 2400 Oakdale |  |  | 0 | 157751.41 | 54812 | 11658216.82 | 9778811.4 | 5733.5 | 8054.5 | 93.17% | 6.704% | 0.1242%
21030055 |  | 21030055 | 1 | Allina-Security Upgrd-Clinics |  |  | 0 | 501 | 0 | 3321290.5 | 2476409.64 | 10999 | 5880.45 | 73.36% | 26.32% | 0.3231%
21030056 |  | 21030056 | 1 | Allina-Security Upgrd-Hospital |  |  | 0 | 37 | 0 | 1300502 | 985084.5 | 580 | 4436.05 | 72.77% | 27.23% | 0%
21036 |  | 21036 | 1 | EILA KORPI TRUSTEE HUGH-EDINA | 2002-10-31 |  | 0 | 0 | 0 | 0 | 3381 | 0 | 45 | 100% | 0% | 0%
21901 |  | 21901 | 1 | CLOSED JOB - MINNEAPOLIS - MA | 2002-12-31 |  | 0 | 0 | 0 | 0 | 27568 | 0 | 0 | 0% | 0% | 0%
21999 |  | 21999 | 1 | MORTENSON-CLOSED JOBMINNEAPOL | 2002-12-31 |  | 0 | 0 | 0 | 0 | 195510 | 0 | 469 | 100% | 0% | 0%
21030013 |  | 21030013 | 1 | UMN - Rebld Tool Shed/PH |  |  | 500 | 180 | 0 | 98644.47 | 85401.91 | 265 | 267 | 100% | 0% | 0%
21031 |  | 21031 | 1 | GLASRUD ASSOCIATES /WIRTH PAR | 2002-09-30 |  | 550 | 0 | 0 | 10393 | 10967 | 0 | 48 | 100% | 0% | 0%
21041 |  | 21041 | 1 | NORTH STAR STEEL-FURNACE/RAIL | 2003-01-10 |  | 775 | 1424 | 1116 | 135234 | 136601 | 0 | 1118 | 100% | 0% | 0%
21017 |  | 21017 | 1 | MINNESOTA VIKINGS-MEDIA ROOM | 2002-04-30 |  | 895 | 0 | 0 | 21460 | 21478 | 0 | 142 | 100% | 0% | 0%
21030005 |  | 21030005 | 1 | MNU Mt Airy B&G Club STEM/Gym |  |  | 1000 | 1 | 0 | 447196 | 430408.85 | 898 | 1515.55 | 100% | 0% | 0%
21012 |  | 21012 | 1 | WALKER - GUTHRIETHEATER SELEC | 2002-03-30 |  | 1200 | 2043 | 0 | 25839 | 128585 | 0 | 157 | 100% | 0% | 0%
21030046 |  | 21030046 | 1 | CentraCare Monticello - Linear |  |  | 1500 | 5 | 0 | 513483.73 | 504081.07 | 1028 | 999 | 76.58% | 23.22% | 0.2002%
21030007 |  | 21030007 | 1 | Twins - Target Field Market |  |  | 1630 | 7381 | 0 | 774283.82 | 1179589.1 | 1123.8 | 2520 | 97.5% | 2.5% | 0%
21030042 |  | 21030042 | 1 | 4150 LLC - MNUFC TI |  |  | 1630 | 0 | 0 | 136659 | 127978.39 | 280 | 269.5 | 100% | 0% | 0%
21030038 |  | 21030038 | 1 | Dunwoody Classroom 78 & 80 |  |  | 1700 | 256 | 0 | 158745.1 | 127788.36 | 132 | 101 | 96.04% | 3.96% | 0%
21030052 |  | 21030052 | 1 | Allina Health - Mercy CV-1 |  |  | 2000 | 6 | 0 | 305010.95 | 305229.35 | 1123 | 973.5 | 93.27% | 6.728% | 0%
21030009 |  | 21030009 | 1 | Allina ANW SPS Sinks/Caviwaves |  |  | 2200 | 938 | 0 | 292820.16 | 284531.7 | 905 | 619 | 85.7% | 13.49% | 0.8078%
21030051 |  | 21030051 | 1 | Marvin Fargo West - Breakroom |  |  | 5000 | 23800 | 0 | 985434.58 | 992366.21 | 1321.8 | 1001.5 | 97.15% | 2.846% | 0%
21030040 |  | 21030040 | 1 | Allina - Mercy PET/CT |  |  | 8500 | 26 | 0 | 1250860.9 | 1212289.48 | 5495 | 4881.2 | 95.44% | 3.948% | 0.6146%
21030028 |  | 21030028 | 1 | UMN Lind Hall Temp Space |  |  | 9000 | 1 | 0 | 73669 | 66655.96 | 15 | 0 | 0% | 0% | 0%
21030036 |  | 21030036 | 1 | Fairview UMMCH WB AAR 3.0 |  |  | 11200 | 4 | 0 | 401560.28 | 172409.76 | 727 | 865 | 99.71% | 0.289% | 0%
21030031 |  | 21030031 | 1 | UIHC - JohnPappaPav 5FL OR Exp |  |  | 11437 | 35191.72 | 12457 | 830924.88 | 977395.63 | 1711.4 | 1706 | 83.91% | 15.18% | 0.9086%
21013 |  | 21013 | 1 | GORDY AAMOTH, JR. MEMORIAL ST | 2002-09-11 |  | 20000 | 113224 | 113315 | 2078379 | 2224771 | 0 | 11470 | 100% | 0% | 0%
21030041 |  | 21030041 | 1 | Sanford - 7CD Build-out |  |  | 25677 | 36815 | 14763 | 6842499.85 | 6833947.95 | 7018.1 | 8351.95 | 84.99% | 14.26% | 0.7543%
21030011 |  | 21030011 | 1 | Fairview UMMC Corp Bldg Refrsh |  |  | 30000 | 69 | 0 | 1445541.71 | 1432009.85 | 3646 | 3192.5 | 98.1% | 1.895% | 0%
21030027 |  | 21030027 | 1 | NS IV - Business Essentials TI |  |  | 31216 | 614 | 24 | 1002360.96 | 988431.85 | 905 | 1424 | 96.88% | 3.125% | 0%
21030048 |  | 21030048 | 1 | Blake School - New Early Learn |  |  | 33250 | 615453.41 | 120498 | 15244392.06 | 6441676.85 | 36070.12 | 20553.5 | 96.86% | 3.141% | 0%
21030043 |  | 21030043 | 1 | St. Michael Addition & Alterat |  |  | 34980 | 74034.78 | 0 | 6134762.814 | 6038545.81 | 5997.8 | 8474.6 | 97.37% | 2.537% | 0.0944%
21030012 |  | 21030012 | 1 | NS IV - Red Bull TI |  |  | 42994 | 12 | 0 | 1327210.11 | 1124630.35 | 1912 | 1510 | 98.87% | 1.126% | 0%
21030039 |  | 21030039 | 1 | Wuollet Bakery Commissary Kitc |  |  | 54020 | 406802.96 | 0 | 20059851.27 | 967701.27 | 18665.09 | 0 | 0% | 0% | 0%
21030021 |  | 21030021 | 1 | Target Corp - Plymouth T-0664 |  |  | 55000 | 8 | 0 | 934569.71 | 960615.67 | 3028 | 1631.5 | 84.34% | 15.66% | 0%
21030022 |  | 21030022 | 1 | Target Corp - Knollwood T-2189 |  |  | 55000 | 5 | 0 | 768602.6525 | 818833.36 | 2347 | 2284.15 | 99.65% | 0.3502% | 0%
21030024 |  | 21030024 | 1 | Target Corp - Chaska T-1352 |  |  | 55000 | 246 | 0 | 1069174.4714 | 1096508.55 | 2613.64 | 2076.33 | 95.16% | 4.84% | 0%
21030050 |  | 21030050 | 1 | Augustana University - Solberg |  |  | 56938 | 91931.32 | 39579 | 8116026.84 | 4256853.67 | 3783.3 | 4698.5 | 84.88% | 15.12% | 0%
21030035 |  | 21030035 | 1 | BSC - Weaver Lake 4 Expansion |  |  | 74000 | 214260 | 56837.97 | 46921894.09 | 48330684.46 | 9969.3 | 19686 | 94.8% | 5.019% | 0.1829%
21030023 |  | 21030023 | 1 | Target Corp-Eden PrairieT-0220 |  |  | 100000 | 503.28 | 8 | 3617880.2955 | 3645156.89 | 5507.16 | 5118.5 | 85.85% | 14.15% | 0%
21030019 |  | 21030019 | 1 | MDI - AU South Residence Hall |  |  | 120000 | 145139 | 14113 | 16661900.17 | 16510642.66 | 5889 | 4040.22 | 81.08% | 18.84% | 0.07425%
21030016 |  | 21030016 | 1 | Tri-County -Replcment Hospital |  |  | 126000 | 186189 | 61920 | 29973964.513 | 27754637.27 | 32659.3 | 31054.5 | 92.13% | 7.87% | 0%
21028 |  | 21028 | 1 | MINNESOTA PUBLIC RADIO EXPANS |  |  | 129858 | 1650494 | 1431854 | 34807648 | 32809650 | 0 | 84166 | 100% | 0% | 0%
21030006 |  | 21030006 | 1 | Vermeer Legacy 7 Cooling |  |  | 150000 | 714 | 0 | 3033497.35 | 3014841.02 | 789 | 1090.5 | 55.94% | 35.17% | 8.895%
21030047 |  | 21030047 | 1 | Fairview - Unit J Nurse Call |  |  | 207481 | 0 | 0 | 1326110.21 | 396790 | 4488 | 1532 | 96.41% | 3.003% | 0.5875%
21030020 |  | 21030020 | 1 | Oberlin - Sustain Infra Prog |  |  | 238660 | 71843.5 | 0 | 89533047.3292 | 59123786.05 | 13223 | 15830.25 | 76.99% | 22.33% | 0.6822%
21004 |  | 21004 | 1 | CITY OF SIOUX CITY -TYSON/IBP | 2003-12-20 |  | 250000 | 0 | 0 | 699038 | 685608 | 0 | 358 | 100% | 0% | 0%
21035 |  | 21035 | 1 | RAMSEY COUNTY PUBLICWORKS | 2004-10-01 |  | 250000 | 3406282 | 2271715 | 43636884 | 43635397 | 0 | 94425 | 100% | 0% | 0%
21030017 |  | 21030017 | 1 | TA - 6400 Replace HVAC/RTU |  |  | 270000 | 6 | 0 | 4156040.3269 | 4096181.84 | 1810.18 | 2161 | 78.85% | 21.15% | 0%
21030004 |  | 21030004 | 1 | MDI - Augustana Univ Housing |  |  | 280000 | 0 | 0 | 965658.26 | 54536.87
21030010 |  | 21030010 | 1 | Allina ANW Care Pavilion |  |  | 500000 | 0 | 0 | 261226 | 214711.48 | 100 | 0 | 0% | 0% | 0%
21157001 |  | 21157001 | 1 | Prairie Hills Blade Re-Tension |  |  | 0 | 0 | 0 | 0 | 331870.93 | 0 | 6437.46 | 78.35% | 21.65% | 0%
21157002 |  | 21157002 | 1 | Sungrow- MN Support 2021 |  |  | 0 | 0 | 0 | 0 | 4772.97 | 0 | 90.5 | 91.16% | 8.84% | 0%
21157003 |  | 21157003 | 1 | Great Plains T63 & T104 GBX Ex |  |  | 0 | 0 | 0 | 0 | 288046.56 | 0 | 1594 | 92.35% | 7.654% | 0%
21157004 |  | 21157004 | 1 | Roundhouse T52 Rebuild |  |  | 0 | 0 | 0 | 0 | 803782.75 | 0 | 2531 | 79.87% | 20.13% | 0%
21157005 |  | 21157005 | 1 | GE Gearbox Slip Ring Retrofit |  |  | 0 | 0 | 0 | 0 | 11293.34 | 0 | 133.5 | 97% | 2.996% | 0%
21157006 |  | 21157006 | 1 | Chisholm Battery Commissioning |  |  | 0 | 0 | 0 | 0 | 68025.9 | 0 | 995 | 93.92% | 6.08% | 0%
21157007 |  | 21157007 | 1 | Battle Mtn. Battery Commission |  |  | 0 | 0 | 0 | 0 | 13635.83 | 0 | 301 | 61.46% | 38.54% | 0%
21157008 |  | 21157008 | 1 | Blue Canyon T-283 Removal |  |  | 0 | 0 | 0 | 0 | 70987.89
21157009 |  | 21157009 | 1 | Diamond Springs T36 Tower Demo |  |  | 0 | 0 | 0 | 0 | 53619.82
21080018-063 |  | 21080018-063 | 1 | WISDOT Proj I43 North |  |  | 0 | 2 | 0 | 265979.95 | 201103.95
21018 |  | 21018 | 1 | MAPBA-MEMPHIS GRIZZLIES NBA A | 2004-08-01 |  | 1444385 | 1000715 | 2360430 | 174430351 | 174516331 | 0 | 203716 | 100% | 0% | 0%
21040001 |  | 21040001 | 1 | ASU Misc Small Works |  |  | 0 | 1 | 0 | 35311.99 | 17199.63 | 0 | 166.5 | 91.89% | 8.108% | 0%
21040004 |  | 21040004 | 1 | Allstate InfoArmor Mod |  |  | 0 | 7 | 0 | 47890.49 | 45265.74 | 21 | 0 | 0% | 0% | 0%
21040011 |  | 21040011 | 1 | AlaskaUSA Branch Flr Repl |  |  | 0 | 1545 | 0 | 26693.39 | 15487.89 | 147.4 | 66 | 35.61% | 64.39% | 0%
21040008 |  | 21040008 | 1 | Allstate Chandler Legal Off TI |  |  | 1100 | 1956 | 0 | 90075.5 | 68132.66 | 347.8 | 303 | 85.48% | 14.52% | 0%
21040006 |  | 21040006 | 1 | PCH Mercy Ophthalmology |  |  | 2000 | 220 | 784 | 545634.27 | 519784.87 | 285.3 | 232.75 | 98.71% | 1.289% | 0%
21040009 |  | 21040009 | 1 | PCH Mercy Cardiology |  |  | 2147 | 206 | 1241 | 567943.42 | 542285.18 | 299.9 | 226.5 | 93.16% | 6.843% | 0%
21040002 |  | 21040002 | 1 | PCH Mercy Gilbert Audiology TI |  |  | 2700 | 220 | 7 | 540688.15 | 528122.3 | 247.6 | 209.75 | 94.28% | 5.721% | 0%
21040005 |  | 21040005 | 1 | SanCarlos Hosp JOC |  |  | 5000 | 349.5 | 0 | 79819.17 | 78285.97 | 307.3 | 322.5 | 75.66% | 24.34% | 0%
21040010 |  | 21040010 | 1 | The Beam Mortenson Office TI |  |  | 15527 | 21433.4 | 0 | 4353344.68 | 287106.13 | 829.3 | 2051 | 85.2% | 14.8% | 0%
21040012 |  | 21040012 | 1 | COT Diablo Stadium Reno |  |  | 40000 | 18 | 0 | 834577.23 | 263570.58
21040003 |  | 21040003 | 1 | Kohler Vikrell West Manu Fac |  |  | 455000 | 191410 | 52756 | 257668584.48 | 121853471.54 | 37731 | 16920.5 | 85.85% | 14.15% | 0%
21040013 |  | 21040013 | 1 | MDI Signal Butte |  |  | 896281 | 652195.44 | 83 | 51806855.05 | 11299437.25 | 4849.6 | 112 | 100% | 0% | 0%
21055002 |  | 21055002 | 1 | Kaiser WMC SPD Ultra |  |  | 0 | 27 | 0 | 143747.53 | 133649.18 | 284 | 375.02 | 92.53% | 5.866% | 1.6%
21055003 |  | 21055003 | 1 | Kaiser WMS Kiosks |  |  | 0 | 237 | 8 | 143943 | 146872.27 | 416 | 464 | 100% | 0% | 0%
21055005 |  | 21055005 | 1 | BPA T03 HMB Adaptive |  |  | 0 | 42 | 0 | 1824809.53 | 1511108.64
21055009 |  | 21055009 | 1 | OHSU CDRC Feasibility Study |  |  | 0 | 7 | 0 | 2014.18 | 1289.92 | 0 | 5 | 100% | 0% | 0%
21055010 |  | 21055010 | 1 | OHSU HRC to CDW Relocation |  |  | 0 | 8056.01 | 0 | 870579.8253 | 702481.64 | 438.3 | 734.3 | 98.64% | 1.362% | 0%
21055011 |  | 21055011 | 1 | OHSU Sample Prep Microscope |  |  | 0 | 2872.98 | 0 | 677327.05 | 627319.96 | 324.8 | 295 | 97.63% | 2.373% | 0%
21055012 |  | 21055012 | 1 | OHSU CCSR Seismic Resil |  |  | 0 | 9 | 0 | 6986.26 | 8132.07 | 12 | 21 | 100% | 0% | 0%
21055013 |  | 21055013 | 1 | Kaiser SAL Arc Flash Upgrade |  |  | 0 | -1039.52 | 0 | 329955.14 | 324700.93 | 446 | 79 | 73.42% | 24.05% | 2.532%
21055014 |  | 21055014 | 1 | Kaiser TUA Nurse Call Precon |  |  | 0 | 24 | 0 | 17810.86 | 18899.21 | 36 | 48 | 100% | 0% | 0%
21055015 |  | 21055015 | 1 | OHSU Urology Adv POB2 |  |  | 0 | 14 | 0 | 5305.09 | 5519.49 | 6 | 32 | 100% | 0% | 0%
21055016 |  | 21055016 | 1 | OHSU Vollum Inst PH3 |  |  | 0 | 33424.39 | 0 | 3898541.25 | 3689631.24 | 867 | 1075.85 | 97.86% | 1.766% | 0.3718%
21055017 |  | 21055017 | 1 | Kaiser TNB HW 3rd Floor Loop |  |  | 0 | 23 | 0 | 75820.76 | 76374.69 | 136 | 155.98 | 91.02% | 1.923% | 7.052%
21055018 |  | 21055018 | 1 | Kaiser WMC Patient Rm Light |  |  | 0 | 9 | 0 | 839399.49 | 840670.83 | 814 | 514 | 97.28% | 2.335% | 0.3891%
21055019 |  | 21055019 | 1 | OHSU HMC OBYN |  |  | 0 | 13 | 0 | 11791.26 | 10626.65 | 16 | 0 | 0% | 0% | 0%
21055020 |  | 21055020 | 1 | Kaiser SST Air Hndlg Precon |  |  | 0 | 13 | 0 | 62609.45 | 65925.17 | 100 | 48 | 100% | 0% | 0%
21055021 |  | 21055021 | 1 | OHSU Urology Adven POB1 |  |  | 0 | 0 | 0 | 0.01 | 0
21055022 |  | 21055022 | 1 | Kaiser WMC Ultrasound Const |  |  | 0 | 29 | 0 | 332311.06 | 334737.93 | 596 | 422 | 100% | 0% | 0%
21055023 |  | 21055023 | 1 | Kaiser BVT Qmatics |  |  | 0 | 38.25 | 0 | 7438.55 | 7565.71 | 44 | 24 | 100% | 0% | 0%
21055024 |  | 21055024 | 1 | Kaiser SST Arc Flash Const |  |  | 0 | 30 | 0 | 119688.87 | 111601.4 | 52 | 97 | 86.6% | 10.31% | 3.093%
21055026 |  | 21055026 | 1 | OHSU MNP DOM Reloc |  |  | 0 | 9200.5 | 0 | 387480.3 | 336730.91 | 378.1 | 219 | 100% | 0% | 0%
21055027 |  | 21055027 | 1 | OHSU HMC Cath Lab |  |  | 0 | 12 | 0 | 5541.2 | 5623.07 | 6 | 0 | 0% | 0% | 0%
21055028 |  | 21055028 | 1 | OHSU CEDAR Lab Buildout |  |  | 0 | 10 | 0 | 2283.71 | 2789.84 | 2 | 0 | 0% | 0% | 0%
21055029 |  | 21055029 | 1 | OHSU CHH1 Family Med Exp |  |  | 0 | 1 | 0 | 6476.86 | 6757.98 | 16 | 0 | 0% | 0% | 0%
21055030 |  | 21055030 | 1 | OHSU RJH Pathology Lab |  |  | 0 | 6472.59 | 0 | 1375843.21 | 303080.92 | 1294.74 | 739.1 | 99.86% | 0.1353% | 0%
21055031 |  | 21055031 | 1 | OHSU EJH Bldg Feas Study |  |  | 0 | 11 | 0 | 9206.69 | 9089.84 | 16 | 0 | 0% | 0% | 0%
21055032 |  | 21055032 | 1 | Kaiser MHO Decommissioning |  |  | 0 | 155 | 0 | 43873.35 | 40276.89 | 136 | 204 | 100% | 0% | 0%
21055034 |  | 21055034 | 1 | Kaiser WMC Scope Wash Const |  |  | 0 | 361 | 0 | 196474.47 | 30764.61 | 440 | 36 | 100% | 0% | 0%
21055035 |  | 21055035 | 1 | Kaiser TNB Exam Lane |  |  | 0 | 37 | 0 | 14833.85 | 16369.54 | 97 | 110 | 100% | 0% | 0%
21055036 |  | 21055036 | 1 | Kaiser ORC Exam Lane Precon |  |  | 0 | 0 | 0 | 3862.26 | 3601.09
21055037 |  | 21055037 | 1 | Kaiser ORC Boiler Repl Precon |  |  | 0 | 0 | 0 | 0.01 | 0
21055038 |  | 21055038 | 1 | Kaiser SST Nurse Call Precon |  |  | 0 | 15 | 0 | 10382.7 | 12044.95
21055039 |  | 21055039 | 1 | OHSU HMC IM GME Remodel |  |  | 0 | 5031.18 | 0 | 1342685.48 | 1169011.52 | 526.8 | 1071.5 | 92.81% | 5.693% | 1.493%
21055040 |  | 21055040 | 1 | OHSU FG XRAY |  |  | 0 | 12 | 0 | 3527.61 | 4279.64 | 12 | 0 | 0% | 0% | 0%
21055044 |  | 21055044 | 1 | Microchip Fab 4.3 Study |  |  | 0 | 0 | 0 | 636100.01 | 578587.79
21055045 |  | 21055045 | 1 | Kaiser TUA NCPA Repl Const |  |  | 0 | 19 | 0 | 217710.11 | 230077.87 | 196 | 304 | 100% | 0% | 0%
21055046 |  | 21055046 | 1 | OHSU DCH Exp Feas. |  |  | 0 | 6 | 0 | 59910.78 | 61557.83
21055047 |  | 21055047 | 1 | Microchip Fab 4 D-B Scoping |  |  | 0 | 14 | 0 | 309780.78 | 344336.4
21055048 |  | 21055048 | 1 | Microchip New Office Study |  |  | 0 | 4 | 0 | 156606.07 | 153956.67
21055049 |  | 21055049 | 1 | Microchip Fab 4 Support Svcs |  |  | 0 | 11 | 0 | 48738.09 | 814.68
21055050 |  | 21055050 | 1 | Kaiser SST Lghtg Repl Prec |  |  | 0 | 17 | 0 | 13069.63 | 13605.69
21055051 |  | 21055051 | 1 | OHSU Dotter Seismic Impro |  |  | 0 | 6484.04 | 0 | 455541.46 | 402860.35 | 928.2 | 1076.6 | 99.44% | 0.5573% | 0%
21055052 |  | 21055052 | 1 | OHSU KVCI Cardiology |  |  | 0 | 12 | 0 | 4217.29 | 4874.94 | 4 | 0 | 0% | 0% | 0%
21055043 |  | 21055043 | 1 | Microchip Thin Film Exp |  |  | 4500 | -308 | 0 | 156771.316 | 149426.7 | 962 | 805.96 | 100% | 0% | 0%
21055033 |  | 21055033 | 1 | Microchip Implant Annex |  |  | 9000 | 75631.13 | 7785 | 11852266.4 | 11637698.62 | 5300.2 | 4280.65 | 96.1% | 3.574% | 0.3271%
21055025 |  | 21055025 | 1 | Micro Systems Flagship Bld |  |  | 40000 | 19 | 0 | 34032.72 | 48473.15 | 0 | 0 | 0% | 0% | 0%
21055001 |  | 21055001 | 1 | BPA T01 TSB |  |  | 60000 | 294429.64 | 185616.5 | 59415006.7956 | 41333333.69 | 15998 | 10279.25 | 93.16% | 6.725% | 0.1167%
21055004 |  | 21055004 | 1 | BPA T02.1 VCC |  |  | 150000 | 294 | 0 | 71631164.89 | 11871938.13
21055008 |  | 21055008 | 1 | Nordstrom Dist Cntr |  |  | 200000 | 3 | 0 | 62939.36 | 62501.68 | 23 | 260.62 | 91.94% | 8.058% | 0%
21146002 |  | 21146002 | 1 | Glass Sands Wind - Power |  |  | 0 | 242762.4 | 193052 | 12841360.04 | 13790645.27 | 8787.74 | 27933 | 77.59% | 22.41% | 0%
21146003 |  | 21146003 | 1 | Orsted Series Cap |  |  | 0 | 47 | 0 | 17486.68 | 10597.34 | 76 | 40 | 100% | 0% | 0%
21146004 |  | 21146004 | 1 | Kirchhoff Series Cap |  |  | 0 | 49 | 0 | 31739.97 | 18614.32 | 60 | 80 | 87.5% | 12.5% | 0%
21146005 |  | 21146005 | 1 | 25 Mile Creek Wind - Power |  |  | 0 | 482351.1 | 281886.44 | 23654245.29 | 21379265.37 | 17920.03 | 23133 | 87.09% | 12.91% | 0%
21146006 |  | 21146006 | 1 | Abilene Data Center |  |  | 0 | 133697.45 | 108517 | 14927046.77 | 12605004.16 | 5643.23 | 5465 | 86.94% | 12.99% | 0.07319%
21146007 |  | 21146007 | 1 | Brass Fork Interconnect |  |  | 0 | 893 | 0 | 6812447.56 | 930490.27
21146008 |  | 21146008 | 1 | Forest Grove Solar - Power |  |  | 0 | 0 | 0 | 213750 | 150387.26
21146009 |  | 21146009 | 1 | Oak Hill Solar - Power |  |  | 0 | 0 | 0 | 180805 | 125327
21146010 |  | 21146010 | 1 | AEP Rio Hondo |  |  | 0 | 0 | 0 | 148598.04 | 121435.63 | 48 | 374 | 95.59% | 4.412% | 0%
21146011 |  | 21146011 | 1 | Greenfield Substation #498 |  |  | 0 | 148 | 0 | 12767998.57 | 8233352.24 | 0 | 308.5 | 90.76% | 9.238% | 0%
21146012 |  | 21146012 | 1 | Hildreth Solar - Power |  |  | 0 | 69437.23 | 0 | 3678908.76 | 3513138.8 | 3192.24 | 4083.5 | 96.74% | 3.257% | 0%
21146013 |  | 21146013 | 1 | Ft Stockton |  |  | 0 | 202521.91 | 180328 | 14998579.64 | 14083754.44 | 7774.76 | 6856.5 | 75.38% | 24.62% | 0%
21146014 |  | 21146014 | 1 | Greenville |  |  | 0 | 0 | 0 | 113210 | 93432.78 | 0 | 16 | 100% | 0% | 0%
21146015 |  | 21146015 | 1 | Northern Wind Repower-Power |  |  | 0 | 4986.46 | 0 | 3885513.93 | 3418734.82
21146016 |  | 21146016 | 1 | Stampede Project |  |  | 0 | 439018.72 | 84100 | 16866588.6175 | 15497017.57 | 27379.76 | 36011 | 78.28% | 21.72% | 0%
21146017 |  | 21146017 | 1 | Wolf Hollow Phase 0 |  |  | 0 | 55761.6 | 0 | 2475236.18 | 2559581.66 | 4022.08 | 7756.09 | 84.16% | 15.84% | 0%
21146018 |  | 21146018 | 1 | Colorado Bend Phase 0 |  |  | 0 | 0 | 0 | 934804 | 847115.21
21146019 |  | 21146019 | 1 | Wolf Hollow Phase 1 |  |  | 0 | 612933.38 | 174705 | 30232878.89 | 27469416.25 | 79722.12 | 81763.77 | 80.96% | 19.04% | 0%
21146020 |  | 21146020 | 1 | Rob Park |  |  | 0 | 88164.03 | 0 | 14788148.34 | 627886.52 | 26106.48 | 0 | 0% | 0% | 0%
21146021 |  | 21146021 | 1 | Chevelon Butte Wind - Power |  |  | 0 | 569177.61 | 538803 | 32565763.87 | 29748069.83 | 16642.09 | 25726.5 | 78.38% | 21.62% | 0%
21146022 |  | 21146022 | 1 | Texas Solar Nova 1 - Power |  |  | 0 | 198064.17 | 97362 | 6666937.33 | 4602138.87 | 6187.92 | 3960 | 93.51% | 6.49% | 0%
21146023 |  | 21146023 | 1 | Texas Solar Nova 2 - Power |  |  | 0 | 103429.26 | 41591 | 5135474.89 | 2050589.97 | 3916.33 | 1092 | 84.02% | 15.98% | 0%
21146024 |  | 21146024 | 1 | King Mountain |  |  | 0 | 490358.86 | 4 | 26369996 | 23387280.97 | 78890.84 | 78380.8 | 75.68% | 24.32% | 0%
21146025 |  | 21146025 | 1 | Angus Solar - Power |  |  | 0 | 0 | 0 | 180805 | 140432.86
21146026 |  | 21146026 | 1 | Abilene - Phase 2 |  |  | 0 | 0 | 0 | 58995 | 46716.13
21060014 |  | 21060014 | 1 | 324 Office Bldg |  |  | 0 | 1 | 7 | 1676423.85 | 693573.01 | 230 | 295 | 81.36% | 18.64% | 0%
21060067 |  | 21060067 | 1 | SLC Industrial Inland Logisti |  |  | 0 | 480868 | 0 | 36502649.62 | 33221964.33 | 737 | 1508.25 | 93.49% | 6.514% | 0%
21050001 |  | 21050001 | 1 | 2021 Virtual Insights |  |  | 0 | 0 | 0 | 0.06 | 16519.01
21050002 |  | 21050002 | 1 | Arnold Water Intrusion - Swed |  |  | 0 | 0 | 1364 | 3190657.83 | 1592637.29 | 0 | 2744.29 | 96.45% | 2.988% | 0.5648%
21050003 |  | 21050003 | 1 | CBRE - Arnold Water Intrusion |  |  | 0 | 0 | 208 | 440492.76 | 440441.59 | 0 | 397.89 | 83.16% | 14.07% | 2.765%
21050004 |  | 21050004 | 1 | PRMCE Instr. Washer Replace |  |  | 0 | 469.9 | 221 | 439146.5675 | 426083.11 | 924.5 | 1102 | 96.82% | 2.813% | 0.363%
21050005 |  | 21050005 | 1 | Cutline - Swedish |  |  | 0 | 4178.8 | 2994.5 | 10312545.27 | 9459826.88 | 4168.3 | 9278.77 | 95.87% | 3.411% | 0.7167%
21050006 |  | 21050006 | 1 | American Air 3428B TI |  |  | 0 | 833 | 6737 | 188278.3 | 190011.81 | 400.83 | 487 | 98.87% | 1.129% | 0%
21050007 |  | 21050007 | 1 | WWU EE/CSE Building |  |  | 0 | 973 | 44 | 5028016.49 | 1968980.16 | 2.1 | 51.5 | 82.52% | 16.5% | 0.9709%
21050008 |  | 21050008 | 1 | PRMCE CM Services |  |  | 0 | 0 | 0 | 1352.12 | 1500.07
21050009 |  | 21050009 | 1 | Delta A12A Boarding Bridge |  |  | 0 | 5326.3 | 0 | 5866842.84 | 2095822.1 | 299.9 | 185 | 97.3% | 2.703% | 0%
21050010 |  | 21050010 | 1 | UW Basketball H2P Center |  |  | 0 | 0 | 0 | 2385533.32 | 2186010.89 | 40 | 40 | 100% | 0% | 0%
21050011 |  | 21050011 | 1 | Swedish NT - Constr |  |  | 0 | 98 | 0 | 13964630.58 | 4698820.62
21050012 |  | 21050012 | 1 | Four106 |  |  | 0 | 5428785.75 | 1578 | 211971447.01 | 16428527.12 | 132886.63 | 3283 | 95.51% | 3.914% | 0.5787%
21050013 |  | 21050013 | 1 | Swedish Cancer Institute |  |  | 0 | 0 | 0 | 4378661.24 | 2615068.11
21050050 |  | 21050050 | 1 | KP Everett IDIQ 2021 |  |  | 0 | 12.5 | 0 | 60220.15 | 70591.84 | 13 | 158 | 90.82% | 9.177% | 0%
21050051 |  | 21050051 | 1 | KP Cap Hill IDIQ 2022 |  |  | 0 | 311 | 16 | 2626368.4917 | 1752850.14 | 341 | 400 | 89.88% | 10.12% | 0%
21145003 |  | 21145003 | 1 | Monticello Solar - Vistra |  |  | 0 | 46 | 0 | 137694 | 137603.75 | 40 | 390 | 82.82% | 17.18% | 0%
21145005 |  | 21145005 | 1 | Misae Solar 1 - Defective Mod |  |  | 0 | 5596 | 0 | 227722.5 | 235446.51 | 2632 | 3613 | 65.25% | 34.75% | 0%
21145006 |  | 21145006 | 1 | TSN 1 - Clearway |  |  | 0 | 6545913.72 | 708656.5 | 160412656.74 | 104588729.51 | 436141.84 | 132974 | 90.02% | 9.976% | 0%
21145007 |  | 21145007 | 1 | TSN 2 - Clearway |  |  | 0 | 8191324.11 | 0 | 123728184.94 | 15132961.65 | 368094.35 | 302.5 | 80.99% | 19.01% | 0%
21145008 |  | 21145008 | 1 | Angus Solar - Vistra |  |  | 154 | 93 | 0 | 819067.02 | 825418.62 | 520 | 1327.5 | 70.85% | 29.15% | 0%
21145001 |  | 21145001 | 1 | Forest Grove Solar - Vistra |  |  | 260 | 172 | 0 | 1551545 | 918416.34 | 500 | 836.5 | 82.68% | 17.32% | 0%
21145002 |  | 21145002 | 1 | Oak Hill Solar - Vistra |  |  | 260 | 88 | 0 | 1464672 | 851672.85 | 500 | 937 | 87.08% | 12.92% | 0%
21145004 |  | 21145004 | 1 | Hildreth Solar |  |  | 106606800 | 3178185.63 | 1960390 | 59979283.03 | 57272031.31 | 184310.59 | 137300.02 | 83.7% | 16.3% | 0.0007283%
21150001 |  | 21150001 | 1 | Pitt New Football Stadium |  |  | 0 | 0 | 0 | 15000 | 2001.47
21150002 |  | 21150002 | 1 | Hudson Valley Renegades |  |  | 0 | 0 | 0 | 9380.01 | 9166.72
21150004 |  | 21150004 | 1 | DAS MLS - St. Louis |  |  | 0 | 0 | 0 | 342145 | 311937.08
21150004-164 |  | 21150004-164 | 1 | MLS - St. Louis DAS |  |  | 0 | 0 | 0 | 803780 | 519825.2
21150006 |  | 21150006 | 1 | Gaylord Pacific Resort |  |  | 0 | 0 | 0 | 0.01 | 0
21150007 |  | 21150007 | 1 | MDI - Titan Industrial Storage |  |  | 0 | 0 | 0 | 52285134.53 | 30009661.28 | 0 | 607.5 | 65.84% | 34.16% | 0%
21150005 |  | 21150005 | 1 | DAS - ASU Multi Purpose Arena |  |  | 1000 | 0 | 0 | 1504402 | 1253909.74
21150003 |  | 21150003 | 1 | MLB - Tampa Bay Rays Precon |  |  | 690000 | 0 | 0 | 103378.54 | 66448.55
21141001, 21148003 |  | 21141001 | 1 | Pocahontas Prairie Repower |  |  | 0 | 10438.02 | 745 | 16687154.83 | 15725114.6 | 51509 | 48709.5 | 72.97% | 26.21% | 0.8161%
21141002 |  | 21141002 | 1 | Golden Hills Wind |  |  | 0 | 7139.2 | 2518 | 94772963.3005 | 90024634.33 | 125801 | 98243.36 | 73.48% | 23.91% | 2.614%
21141003 |  | 21141003 | 1 | Shep Flats (NorH) Repower |  |  | 0 | 13177.59 | 1000 | 32408252.64 | 34044809.75 | 82767 | 135903.7 | 66.33% | 24.97% | 8.698%
21141004 |  | 21141004 | 1 | Sac County Wind |  |  | 0 | 9993.65 | 1247 | 27559923.623 | 27843531.39 | 37526 | 38317.4 | 66.52% | 30.99% | 2.494%
21141005 |  | 21141005 | 1 | Cedro Hill Repower |  |  | 0 | 0 | 0 | 110235.66 | 65378.78
21141006 |  | 21141006 | 1 | Midland Wind |  |  | 0 | 4551.82 | 2440 | 56511014.5996 | 55422028.51 | 75386 | 79370.72 | 67.32% | 31.59% | 1.09%
21141007 |  | 21141007 | 1 | Shep Flats (SouH) Repower |  |  | 0 | 1906 | 1124 | 30554240.8314 | 31855389.71 | 76459 | 129251.65 | 64.43% | 29.69% | 5.872%
21141008 |  | 21141008 | 1 | Shep Flats (HorB) Repower |  |  | 0 | 1455 | 1129 | 29310464.8895 | 30212099.21 | 79185 | 124274 | 67.12% | 30.29% | 2.588%
21141009 |  | 21141009 | 1 | Mountain View I & II Full RP |  |  | 0 | 4373.73 | 1460 | 39950179.91 | 35314338.69 | 46555 | 39241.6 | 77.98% | 20.4% | 1.618%
21141010 |  | 21141010 | 1 | 25 Mile Creek Wind |  |  | 0 | 21153.09 | 5178 | 89634628.31 | 80195025.73 | 119062 | 113317.5 | 82.74% | 17.26% | 0%
21141011 |  | 21141011 | 1 | Nobles Repower |  |  | 0 | 17528.86 | 923 | 41101725.5214 | 31882276.57 | 88655.5 | 75951.5 | 76.35% | 23.65% | 0%
21141012 |  | 21141012 | 1 | Northern Full Repower |  |  | 0 | 3583.4 | 2538 | 53152898.06 | 47808476.96 | 56703 | 49428.5 | 73.8% | 26.11% | 0.09711%
21141013 |  | 21141013 | 1 | Steelhead - 25 Mile Creek Wind |  |  | 0 | 0 | 0 | 659490 | 529372.09
21141014 |  | 21141014 | 1 | Chevelon Butte Wind |  |  | 0 | 18550.9 | 2420.5 | 99886068.5624 | 87379423.33 | 138084 | 74026.25 | 88.94% | 11.06% | 0%
21141015 |  | 21141015 | 1 | Laurel Mtn AES Repower |  |  | 0 | 0 | 0 | 5242221 | 4379108.27
21141016 |  | 21141016 | 1 | Laurel Mtn GE Repower |  |  | 0 | 2628.32 | 1318 | 28468629 | 18600726.48 | 63006 | 115200.34 | 82.72% | 13.75% | 3.526%
21141017 |  | 21141017 | 1 | Appaloosa Run Wind |  |  | 0 | 18317.15 | 3210 | 41512364.25 | 40574956.18 | 68272 | 62092.92 | 75.06% | 24.93% | 0.003221%
21141018 |  | 21141018 | 1 | Inertia Wind |  |  | 0 | 22460.1 | 4927.5 | 76615614.294 | 75483978.23 | 115720 | 110115.93 | 75.34% | 24.66% | 0%
21141019 |  | 21141019 | 1 | Eclipse/Morning Light Repower |  |  | 0 | 4805.73 | 1790 | 43128440.08 | 40660102.37 | 109745 | 139882.8 | 63.13% | 31.97% | 4.892%
21141020 |  | 21141020 | 1 | Cimarron Grout Install Wind |  |  | 0 | 4 | 4 | 42490.68 | 22706.32 | 152 | 168 | 61.9% | 38.1% | 0%
21141021 |  | 21141021 | 1 | White Rock Wind |  |  | 0 | 4001.21 | 0 | 114748898.68 | 20810726.9 | 171070 | 2715.5 | 86.3% | 13.7% | 0%
21141022 |  | 21141022 | 1 | Marshal Yd - Laurel Mt GE RP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -65565.84 | 92.86% | 5.277% | 1.862%
20090005 |  | 20090005 | 1 | QTS - Misc Projects |  |  | 0 | 48 | 146.5 | 2763551 | 2578027.49 | 329.5 | 602.5 | 89.29% | 10.71% | 0%
20090009 |  | 20090009 | 1 | QTS - DH3 E1 E2 |  |  | 0 | 3028 | 156 | 22769795.33 | 22485966.48 | 1384.1 | 4360.5 | 94.61% | 5.263% | 0.1261%
20090991 |  | 20090991 | 1 | Chicago 2020 Prefab Shop |  |  | 0 | 121 | 52 | 0 | 129499.29 | 212 | 1421.86 | 99.33% | 0.3517% | 0.3165%
20090992 |  | 20090992 | 1 | Chicago Laser Scanning 2020 |  |  | 0 | 0 | 0 | 0 | 68859.64 | 0 | 237 | 86.08% | 13.92% | 0%
20090006 |  | 20090006 | 1 | Northwestern-Welsh Ryan Floor |  |  | 20000 | 479.5 | 0 | 421068.05 | 422158.47 | 294 | 167 | 91.02% | 5.389% | 3.593%
20090004 |  | 20090004 | 1 | QTS - DH2W 3MW D1 D2 |  |  | 39899 | 5682.8 | 209 | 17247458.93 | 17081202.25 | 4224 | 4615.5 | 83.3% | 14.64% | 2.069%
20090008 |  | 20090008 | 1 | UIC - CDRLC Construction |  |  | 65000 | 570.5 | 0 | 7307028 | 2240576.06 | 10460 | 3 | 100% | 0% | 0%
20090003 |  | 20090003 | 1 | Wheaton - Traber Hall Reno |  |  | 70000 | 155637.57 | 8.5 | 9050509.75 | 8907815.57 | 2767.8 | 3289 | 82.53% | 15.37% | 2.098%
20090007 |  | 20090007 | 1 | FDB&R - Chicago Office |  |  | 105000 | 16670 | 209 | 17787126.07 | 16246289.59 | 8204 | 7058 | 80.88% | 11.63% | 7.495%
20090002 |  | 20090002 | 1 | UIC - CDRLC Precon |  |  | 160000 | 304 | 0 | 201236 | 204431.18 | 0 | 20 | 100% | 0% | 0%
20090001 |  | 20090001 | 1 | DeKalb Data Center |  |  | 980000 | 0 | 20 | 0 | 55.49 | 0 | 0 | 0% | 0% | 0%
20148001, 19141030, 19146024 |  | 20148001 | 1 | TG East Civil (Wind) |  |  | 0 | 14396148 | 840261 | 18289500 | 14749088.15 | 54323.17 | 54183.7 | 81.06% | 18.94% | 0%
20148002 |  | 20148002 | 1 | Snipesville Civil (Solar) |  |  | 0 | 2820797.62 | 168415 | 2714599.4 | 2545533.42 | 5346.24 | 3740 | 82.13% | 17.87% | 0%
20148003 |  | 20148003 | 1 | Chokecherry Sierra Madre 2020 |  |  | 0 | 20407680.84 | 820131 | 17455480.41 | 15635223.41 | 62797.97 | 61934 | 82.13% | 17.51% | 0.3593%
20148004 |  | 20148004 | 1 | Smoky Hills 2 Civil (Wind) |  |  | 0 | 3218196.04 | 110 | 3626246.63 | 2859388.13 | 10617.97 | 4493 | 78.51% | 21.49% | 0%
20148005, 20141002 |  | 20148005 | 1 | Hawkeye Civil (Wind) |  |  | 0 | 2214265.72 | 82461 | 3418141.2902 | 2718910.17 | 11379.82 | 8766.5 | 84.45% | 15.07% | 0.4848%
20148006, 19145015 |  | 20148006 | 1 | Santa Fe Civil (Solar) |  |  | 0 | 3722575.02 | 160667 | 2865587.3232 | 2145765.53 | 11509.26 | 6288.42 | 79.84% | 20.16% | 0%
19145005, 19146017, 20148007 |  | 20148007 | 21 | Phoenix Civil (Solar) |  |  | 0 | 4011675.47 | 229034 | 3974819.45 | 3995743.12 | 13149.09 | 18469.5 | 85.45% | 14.55% | 0%
20148008 |  | 20148008 | 1 | Langford Civil (Wind) |  |  | 0 | 3160519.77 | 55484 | 3733933.2905 | 2443741.13 | 16314.26 | 10327 | 79.59% | 20.41% | 0%
19145012, 20148009 |  | 20148009 | 11 | Maiden Creek Civil (Solar) |  |  | 0 | 2019442 | 59765 | 1755947.71 | 1816313 | 5516.92 | 6171 | 86.7% | 13.3% | 0%
20148010 |  | 20148010 | 1 | Trent Mesa Civil (Wind) |  |  | 0 | 0 | 0 | 510659.81 | 308318.12 | 0 | 1442.5 | 80.1% | 19.9% | 0%
20148011 |  | 20148011 | 1 | Fighting Jays Civil (Solar) |  |  | 0 | 12169845.69 | 285334 | 10141490.15 | 9559503.62 | 19988.65 | 21607 | 85.22% | 14.78% | 0%
20148012 |  | 20148012 | 1 | Desert Sky Civil (Wind) |  |  | 0 | 2 | 0 | 416689.61 | 334037.05 | 0 | 891 | 86.53% | 13.47% | 0%
20148013 |  | 20148013 | 1 | Blue Canyon II RePower Civil |  |  | 0 | 2725795.59 | 140509 | 4449524.56 | 3018492.52 | 17135.17 | 12312.27 | 80.01% | 19.99% | 0%
20148014, 20141012, 20146011 |  | 20148014 | 1 | Rockhaven Civil (Wind) |  |  | 0 | 740130.62 | 437134 | 16252070.38 | 15037743.2 | 46829.15 | 49803.75 | 77.11% | 22.89% | 0%
20120001 |  | 20120001 | 1 | Facebook-Program Services 2020 |  |  | 0 | 11 | 0 | 1351814 | 1349206.05
20120002 |  | 20120002 | 1 | Google - Mesa Data Center-MP |  |  | 0 | 1122 | 0 | 267542 | 198978.45
20120003 |  | 20120003 | 1 | Lego - Facebook Data Centers |  |  | 0 | 0 | 0 | 421834 | 315955.88
20126002 |  | 20126002 | 1 | Facebook - EAG 5/6 |  |  | 0 | 3002553.2 | 458745.62 | 642714803.6686 | 555767799.29 | 253676.23 | 261130.37 | 82.34% | 17.66% | 0%
20126001 |  | 20126001 | 1 | EAG IBOS Building |  |  | 30000 | 557 | 160 | 9902581.82 | 10070523.77 | 144 | 1320.5 | 84.85% | 15.15% | 0%
20030079 |  | 20030079 | 1 | Google - SLN4A Data Center |  |  | 350000 | 0 | 0 | 545094 | 582649.18
20126004 |  | 20126004 | 1 | Facebook - DKL 1/2 |  |  | 998280 | 1192210.03 | 827920 | 722631143.1765 | 705265919.49 | 216228 | 212599.05 | 83.12% | 12.41% | 4.465%
20060035 |  | 20060035 | 1 | Facebook EAG 5/6 |  |  | 1000000 | 0 | 0 | 0.01 | 0
20060008 |  | 20060008 | 1 | Northridge Behavioral Health |  |  | 0 | 0 | 0 | 0.01 | 1106.51
20060017 |  | 20060017 | 1 | SCL Lutheran COVID 19 |  |  | 0 | 797 | 0 | 65187.397 | 59164.4 | 6 | 0 | 0% | 0% | 0%
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 20060018 | 71 | SCL SJH COVID |  |  | 0 | 0 | 0 | 124525.68 | 125892.03
20060019 |  | 20060019 | 1 | SCL Lutheran West Hospice |  |  | 0 | 12 | 90 | 183753.99 | 187170.9 | 258 | 106 | 100% | 0% | 0%
20060020 |  | 20060020 | 1 | St Anthony North Rehab |  |  | 0 | 14496.5 | 61 | 1656074.13 | 1674504.87 | 2462.7 | 710.5 | 90.15% | 9.852% | 0%
20060022 |  | 20060022 | 1 | Highpoint Logistics Park |  |  | 0 | 937373.48 | 733186.35 | 39356686.5865 | 38749934.57 | 59365.6 | 31197.25 | 83.75% | 16.25% | 0%
20060023 |  | 20060023 | 1 | Molson Coors G150 |  |  | 0 | 3 | 0 | 228785.56 | 299510.95
20060027 |  | 20060027 | 1 | MC-Golden Valley |  |  | 0 | 5811.02 | 3492 | 1132548.45 | 1047772.14 | 3095.85 | 2414.25 | 80.94% | 19.06% | 0%
20060031 |  | 20060031 | 1 | FRA-FIC3 UCH Parking Lot |  |  | 0 | 0 | 0 | 39361.2 | 39404.47
20060033 |  | 20060033 | 1 | MC Bridge Demo |  |  | 0 | 1298.7 | 858 | 543962.72 | 557841.04 | 790.6 | 901 | 91.68% | 8.324% | 0%
20060034 |  | 20060034 | 1 | FRA Infrastructure-23rd Ave |  |  | 0 | 0 | 0 | 34000 | 38384.72
20060037 |  | 20060037 | 1 | NJH-UPS800 PHarmacy Remodel |  |  | 0 | 3291.56 | 365 | 187035.04 | 193610.83 | 348.96 | 745 | 95.57% | 4.43% | 0%
20060038 |  | 20060038 | 1 | MC Capital Improve |  |  | 0 | 695.64 | 351 | 366372.1675 | 448937.93 | 589.2 | 512 | 84.67% | 15.33% | 0%
20060048 |  | 20060048 | 1 | SCL-LMC COVID19 Exhaust Fans |  |  | 0 | 126 | 30 | 234913.87 | 231947.8 | 120 | 30 | 100% | 0% | 0%
20060049 |  | 20060049 | 1 | MC-Kennys Run Enab |  |  | 0 | 61477.23 | 36693 | 1883646.87 | 1868713.81 | 7641.4 | 7655 | 87.16% | 12.84% | 0%
20060003 |  | 20060003 | 1 | SCL SJD Cancer Cntr |  |  | 1 | 6 | 44 | 6443.27 | 6930.43 | 0 | 38 | 55.26% | 44.74% | 0%
20060005 |  | 20060005 | 1 | SCL SJD CCC Roof Replacement |  |  | 1 | 35984.5 | 1457 | 1035284.1 | 1077176.39 | 1145 | 1635.5 | 91.56% | 8.438% | 0%
20060026 |  | 20060026 | 1 | SCL - Lutheran CT (8) Machine |  |  | 1 | 3179.23 | 455 | 141118.24 | 143739.89 | 294.7 | 472 | 94.92% | 5.085% | 0%
20060030 |  | 20060030 | 1 | DHHA - CT Replacement |  |  | 1 | 5752.96 | 1604 | 396591.0268 | 352310.65 | 1498.28 | 703.5 | 87.21% | 12.79% | 0%
20060045 |  | 20060045 | 1 | SCL-LMC 2020 Sewer Line |  |  | 1 | 28 | 28.01 | 75396.14 | 56415.35 | 42 | 168 | 82.14% | 17.86% | 0%
20060046 |  | 20060046 | 1 | SCL-LMC West Pines Exhaust Fan |  |  | 1 | 56 | 74 | 221970.04 | 220389.62 | 200 | 66 | 100% | 0% | 0%
20060053 |  | 20060053 | 1 | CHCO Dental Clinic Remodel |  |  | 1 | 1190.25 | 515 | 156261.79 | 208528.47 | 612.9 | 627.5 | 82.39% | 17.61% | 0%
20060054 |  | 20060054 | 1 | SCL-SJH SPD Medivator |  |  | 1 | 128.75 | 62 | 161713.74 | 160959.05 | 108 | 108 | 100% | 0% | 0%
20060055 |  | 20060055 | 1 | SCL-West Campus Signage |  |  | 1 | 58 | 0 | 17683.52 | 10528.01 | 0 | 27 | 100% | 0% | 0%
20060057 |  | 20060057 | 1 | NJH Test Pod |  |  | 300 | 305 | 0 | 175506 | 190472.01 | 305 | 1236 | 92.44% | 7.565% | 0%
20060043 |  | 20060043 | 1 | NJH - Radiology Remodels |  |  | 400 | 317 | 0 | 36453.83 | 48042.7 | 308 | 356.5 | 89.06% | 10.94% | 0%
20060047 |  | 20060047 | 1 | SCL-LMC Front Range Command |  |  | 400 | 108 | 26 | 73088.29 | 72567.8 | 88 | 26 | 96.15% | 3.846% | 0%
20060001 |  | 20060001 | 1 | SCL - SJH SPD Medivator |  |  | 500 | 82 | 26 | 13344.54 | 14634.47 | 153.4 | 259.5 | 87.09% | 12.91% | 0%
20060040 |  | 20060040 | 1 | SCL-SJB Mezzaine Repairs |  |  | 1000 | 975.17 | 0 | 127680.9 | 151744.86 | 90 | 0 | 0% | 0% | 0%
20060041 |  | 20060041 | 1 | SCL-SJB Oncology AHU |  |  | 1000 | 33 | 0 | 117358.42 | 123176.3
20060059 |  | 20060059 | 1 | CoorsTek Small Projects |  |  | 1000 | 133 | 8 | 384617.665 | 403442.42 | 2247.1 | 2497 | 97.32% | 2.683% | 0%
20060010 |  | 20060010 | 1 | Stoltz Cable Building |  |  | 2000 | 13438.7 | 4502 | 1051254.87 | 376922.45 | 1221.77 | 1274 | 92.27% | 7.732% | 0%
20060024 |  | 20060024 | 1 | Stadium Mgmt Broncos 2020 |  |  | 2000 | 14 | 116 | 291357.59 | 277406.44 | 1286 | 596 | 90.02% | 9.983% | 0%
20060060 |  | 20060060 | 1 | SCL-SJB MRI Corridor |  |  | 2000 | 16 | 0 | 70935.2 | 78106.29
20060036 |  | 20060036 | 1 | DHHA-Pav K (Office Reno) |  |  | 2212 | 849.5 | 0 | 99491.51 | 106414.22 | 217.8 | 136 | 82.72% | 17.28% | 0%
20060025 |  | 20060025 | 1 | Tiny Homes Project |  |  | 5000 | 378 | 164 | 641149 | -1.6303e-10 | 1584 | 4416 | 98.4% | 1.596% | 0%
20060050 |  | 20060050 | 1 | CO Rockies-Coors Field Gate E |  |  | 5000 | 60074.89 | 19237 | 593609.743 | 628873.04 | 1931.39 | 2660.5 | 86.26% | 13.74% | 0%
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 20060056 | 21 | SCL St James Foundation Roof |  |  | 5000 | 11 | 0 | 43344.07 | 45954.47 | 0 | 0 | 0% | 0% | 0%
20060062 |  | 20060062 | 1 | DHHA 4C |  |  | 6000 | 15 | 397 | 151032.43 | 158010.17 | 602 | 495 | 95.15% | 4.848% | 0%
20060014 |  | 20060014 | 1 | Stoltz Wazee Exchange |  |  | 7000 | 65346.95 | 28642 | 1883033.06 | 1894931.08 | 2128.43 | 4602.5 | 95.61% | 4.389% | 0%
20060012 |  | 20060012 | 1 | Aramark Concessions 2020 |  |  | 8500 | 0 | 0 | 0.01 | 41919.44
20060004 |  | 20060004 | 1 | Stadium Mgmt - Bronco 2020 |  |  | 8520 | 1454.5 | 556 | 2026435.57 | 2015753.86 | 2821.7 | 2449 | 99.04% | 0.9596% | 0%
21060047, 20060058, 18000015-040, 18060047, 20060042 |  | 20060058 | 11 | SCL Candelas Primary Care |  |  | 9000 | 274 | 38 | 2010240.76 | 2011888.29 | 272 | 396.5 | 96.47% | 3.531% | 0%
17060034, 20060007 |  | 20060007 | 11 | RMPM - 3rd Floor TI |  |  | 10000 | 12954 | 23 | 900219.3865 | 917619.23 | 261.3 | 369.5 | 99.59% | 0.406% | 0%
20060013 |  | 20060013 | 1 | Stoltz - Blake Street |  |  | 11500 | 109413.85 | 56191 | 3398990.4079 | 3320578.47 | 6790 | 7279.5 | 96.75% | 3.249% | 0%
20060044 |  | 20060044 | 1 | NJH-Bridge |  |  | 15000 | 12898 | 1516 | 5941440.484 | 6043227.45 | 2969.7 | 6336.5 | 80.53% | 19.47% | 0%
19110001, 20060028, 20060006 |  | 20060006 | 21 | MIC-Buckley SBIRS Operations |  |  | 20000 | 0 | 23414 | 0 | -1296 | 0 | 0 | 0% | 0% | 0%
19110001, 20060028, 20060006 |  | 20060028 | 11 | MIC-Buckley SBIRS Operation |  |  | 20000 | 153331.11 | 203565 | 1290035.7904 | 1561183.12 | 13670.9 | 15082 | 93.16% | 6.843% | 0%
20060052 |  | 20060052 | 1 | Woodward-Windsor Campus |  |  | 20000 | 68131 | 49175.5 | 22826206.6724 | 20110024.21 | 5620 | 17395.04 | 89.73% | 10.27% | 0%
20060029 |  | 20060029 | 1 | UofU-Public Safety Building |  |  | 26000 | 0 | 0 | 32153 | 31102.51
20060011 |  | 20060011 | 1 | Facebook-EAG IBOS Building |  |  | 30000 | 0 | 0 | 0.01 | 0
17000003-040, 17060025, 17060014, 18060057, 20060016 |  | 20060016 | 45 | FRA Bioscience 3 Bldg Mgt |  |  | 50000 | 600 | 2113 | 91600 | 98795.53 | 600 | 1301 | 93.31% | 6.687% | 0%
21060047, 20060058, 18000015-040, 18060047, 20060042 |  | 20060042 | 45 | SCL Candelas 12" Water Line |  |  | 50000 | 1029 | 965 | 125179.12 | 137165.24 | 616 | 632.5 | 91.46% | 8.538% | 0%
20060021 |  | 20060021 | 1 | St Mary-Corwin Med Cntr Rehab |  |  | 80000 | 91319.71 | 0 | 6652916.18 | 6720007.99 | 3850.6 | 1444 | 76.7% | 23.3% | 0%
20060015 |  | 20060015 | 1 | FRA Bioscience 5 |  |  | 98000 | 0 | 0 | 227128 | 223011.59
20060002 |  | 20060002 | 1 | 2424 Larimer |  |  | 98254 | 15 | 0 | 45768 | 45333.83
20060039 |  | 20060039 | 1 | Stoltz-Checkr Atrium Reno |  |  | 180000 | 111010.4 | 21 | 3825876.99 | 3786891.65 | 3376.5 | 4658.5 | 91.95% | 8.05% | 0%
20060061 |  | 20060061 | 1 | MDI-2506 W Colfax Multifamily |  |  | 234156 | 0 | 16 | 60419545 | 2389825.52 | 0 | 24 | 100% | 0% | 0%
20060009 |  | 20060009 | 1 | Township Resident Apartment |  |  | 400000 | 4 | 0 | 599664.84 | 575833.5 | 3 | 165.5 | 89.12% | 10.88% | 0%
20060032 |  | 20060032 | 1 | 76 Comm Bldg 1 |  |  | 546000 | 1703956.79 | 834323.62 | 38239452.15 | 36528971.87 | 28691.97 | 32855.78 | 82.69% | 17.31% | 0%
20149001 |  | 20149001 | 1 | Upton 1 BESS |  |  | 0 | 242 | 0 | 228183 | 166861.37
20149004 |  | 20149004 | 1 | Valley Center Energy Storage |  |  | 0 | 235542 | 260391 | 54914777.3554 | 63745201.61 | 31673.31 | 103437.71 | 71.05% | 19.52% | 9.429%
20149005 |  | 20149005 | 1 | Crossett Battery Storage |  |  | 0 | 399427.17 | 301645 | 15365690.86 | 15664912.05 | 33992.56 | 43381.5 | 78.42% | 21.58% | 0%
20149006 |  | 20149006 | 1 | Decordova Battery Storage |  |  | 0 | 622662.68 | 354518 | 27398591.31 | 26371911.31 | 46380.14 | 43824.25 | 86% | 14% | 0%
20149007 |  | 20149007 | 1 | Brookville Bus Depot MicroGrid |  |  | 0 | 182272.28 | 25449 | 10778930.9568 | 10230105 | 14131.96 | 24237 | 76.08% | 23.92% | 0%
20110001 |  | 20110001 | 1 | Site R ITIU |  |  | 0 | 3925 | 0 | 6985160.368 | 6985490.17
15110002-151, 15110002, 20110002-151, 20110002 |  | 20110002 | 25 | ECB-MC Elevators JV-Internal |  |  | 0 | 0 | 0 | 82102 | 131721.01 | 0 | 362 | 99.45% | 0.5525% | 0%
15110002-151, 15110002, 20110002-151, 20110002 |  | 20110002-151 | 25 | ECB-MC Elevators |  |  | 0 | 0 | 0 | 181720.65 | 199597
20110004-144 |  | 20110004-144 | 1 | Kings Bay Dry Dock |  |  | 0 | 0 | 0 | 536777413 | 0
20110012 |  | 20110012 | 1 | Storm Window Prototypes |  |  | 0 | 12 | 0 | 1887827.9999 | 687052.62
20110014 |  | 20110014 | 1 | Aberdeen Proving Ground |  |  | 500 | 579 | 0 | 544692.29 | 471401.53
20110003 |  | 20110003 | 1 | Tech Library 3B34 Renovation |  |  | 1000 | 502 | 0 | 290930.02 | 225394.45
20110013 |  | 20110013 | 1 | General Briefing Room |  |  | 1000 | 2069 | 0 | 788425.82 | 775770.82 | 0 | 525 | 99.05% | 0.9524% | 0%
20110005 |  | 20110005 | 1 | UDC Gremlin Prank |  |  | 2000 | 0 | 0 | 35706 | 30670.13
20110011 |  | 20110011 | 1 | 9800 Toilet Room Reno |  |  | 15413 | 37 | 0 | 18650974.58 | 12624874.14 | 0 | 3380.89 | 96.07% | 3.934% | 0%
20110009 |  | 20110009 | 1 | Building 9838 Renovation |  |  | 16611 | 17130 | 0 | 15423545.3758 | 14474864.82 | 0 | 36 | 100% | 0% | 0%
20110004 |  | 20110004 | 1 | A-M JV Kings Bay Dry Dock Int |  |  | 21373 | 0 | 8 | 27612978.77 | 25992933.45 | 0 | 23839.88 | 75.75% | 23.17% | 1.078%
20110015 |  | 20110015 | 1 | Fort McNair Building 60 |  |  | 22657 | 129 | 0 | 16338382.18 | 16054421 | 0 | 1050 | 98.29% | 1.714% | 0%
20110010 |  | 20110010 | 1 | Bldg 9840 AHU Replacement |  |  | 34306 | 46283 | 0 | 13363460.5 | 11974851.54 | 0 | 16.7 | 100% | 0% | 0%
20110007 |  | 20110007 | 1 | 9800 Core Renovation |  |  | 65000 | 8182 | 0 | 26910039.738 | 26680736.07 | 63 | 7924.05 | 87.11% | 12.89% | 0%
20110016 |  | 20110016 | 1 | BAO North Parking Lot |  |  | 97621 | 88 | 0 | 3410441.56 | 3409448.5
20110006 |  | 20110006 | 1 | USDA - ARTC |  |  | 108000 | 154501 | 0 | 88530366.35 | 70690450.76 | 12040 | 4854 | 100% | 0% | 0%
20110008 |  | 20110008 | 1 | Big 4 Fence Removal |  |  | 2100000 | 263 | 0 | 25654008.45 | 13784139.99 | 0 | 62 | 64.52% | 35.48% | 0%
20080001 |  | 20080001 | 1 | Froedtert - Park Temp Lighting |  |  | 0 | 13827.06 | 5039 | 895972.5 | 993356.8 | 2742 | 3154.5 | 80.38% | 9.574% | 10.05%
20080009 |  | 20080009 | 1 | AMC Sheboygan Union Ave |  |  | 0 | 229.5 | 0 | 4695286.03 | 4563492.43 | 277.5 | 32.5 | 92.31% | 7.692% | 0%
20080011 |  | 20080011 | 1 | Foxconn - Utility Upgrades |  |  | 0 | 3 | 0 | 126272 | 115778.05
20080014 |  | 20080014 | 1 | RockGen Concrete Repairs |  |  | 0 | 456.27 | 0 | 12176.28 | 11933.89 | 63.6 | 120 | 96.25% | 3.75% | 0%
20080010 |  | 20080010 | 1 | Harley Davidson Kitch Remodel |  |  | 100 | 65 | 0 | 19993.3 | 23284.9 | 40 | 89 | 93.26% | 6.742% | 0%
20080004 |  | 20080004 | 1 | MRMC E. Tunnel N. Junc |  |  | 500 | 8686.83 | 93 | 699634.4 | 687176.23 | 1538.1 | 1516.08 | 94.46% | 5.508% | 0.03298%
20080007 |  | 20080007 | 1 | Delta DNC Refresh |  |  | 500 | 0 | 0 | 3396 | 3416.48
20080006 |  | 20080006 | 1 | AHC - At Home Pharm Remodel |  |  | 944 | 13343.32 | 7373 | 1673054.53 | 1729626.43 | 1722.1 | 3445.2 | 93.83% | 5.852% | 0.3193%
20080013 |  | 20080013 | 1 | DRS - CT Equip Demo |  |  | 2000 | 3 | 0 | 11145.44 | 10372.76
20080003 |  | 20080003 | 1 | Froedtert IPP 9,8,1 Equip Swap |  |  | 2381 | 25313 | 1464 | 1077024.43 | 1113684.42 | 2437.9 | 4104 | 91.35% | 5.592% | 3.058%
20080008 |  | 20080008 | 1 | Leonardo DRS Cafe Reno |  |  | 3550 | 5990.33 | 2539 | 217201.64 | 187145.08 | 304.6 | 374 | 99.6% | 0.4011% | 0%
20080012 |  | 20080012 | 1 | Lodge Kohler Spa Exp |  |  | 14000 | 204 | 0 | 601873.26 | 633288.16 | 0 | 30.67 | 100% | 0% | 0%
20080002 |  | 20080002 | 1 | Froedtert - North Tower Elev |  |  | 27380 | 201823.76 | 5355 | 16762355.23 | 697993.08 | 15596.61 | 863 | 99.77% | 0.2317% | 0%
20080005 |  | 20080005 | 1 | Fii 5052020 |  |  | 98000 | 0 | 0 | 0.01 | 0
20030001 |  | 20030001 | 1 | Fairview Facility Annual 2020 |  |  | 0 | 0 | 0 | 1826490.57 | 1945158.19 | 0 | 5453 | 95.19% | 4.814% | 0%
20030002 |  | 20030002 | 1 | Allina Annual Contract 2020 |  |  | 0 | 141355 | 2 | 3648025.8434 | 3964892.18 | 24581.2 | 23682.71 | 91.11% | 8.694% | 0.1942%
20030004 |  | 20030004 | 1 | Marvin Master Agreement |  |  | 0 | 139.03 | 0 | 807288.62 | 726746.28 | 1570 | 1362 | 79% | 21% | 0%
20030005 |  | 20030005 | 1 | Fairview - Unit J CW Infra |  |  | 0 | 0 | 0 | 433434.2 | 431469.26
20030010 |  | 20030010 | 1 | Fairview -Northland Nurse Call |  |  | 0 | 0 | 0 | 45502.07 | 41310.98 | 1595 | 75 | 85.33% | 14.67% | 0%
20030013 |  | 20030013 | 1 | MSFA - USB Exterior Envelope |  |  | 0 | 120 | 1000 | 21716975.89 | 19662555.26 | 7497 | 8304.5 | 98.59% | 1.319% | 0.09633%
20030015 |  | 20030015 | 1 | Allianz Field 2020 Sponsor Act |  |  | 0 | 0 | 0 | 212675.58 | 206956.79 | 48 | 40 | 100% | 0% | 0%
20030017 |  | 20030017 | 1 | Sunny Hollow Life Safety |  |  | 0 | 0 | 0 | 157037 | 157768.71 | 280 | 352 | 100% | 0% | 0%
20030025 |  | 20030025 | 1 | Lansing Tenant Improvements |  |  | 0 | 0 | 0 | 1622923 | 1559331.07 | 2002 | 1594 | 99.44% | 0.5646% | 0%
20030028 |  | 20030028 | 1 | City of Mpls - NPSB Site Imprv |  |  | 0 | 40822.18 | 8557 | 766945.8 | 638451.21 | 2935.5 | 1440 | 96.77% | 3.229% | 0%
20030030 |  | 20030030 | 1 | Fairview - Princeton ED Rm #2 |  |  | 0 | 0 | 0 | 23229 | 23411.03 | 45 | 77 | 89.61% | 10.39% | 0%
20030031 |  | 20030031 | 1 | Fairview FRH ED BH Ligature |  |  | 0 | 0 | 0 | 97965 | 96248.14 | 146 | 146.5 | 98.63% | 1.365% | 0%
20030039 |  | 20030039 | 1 | Fairview - Unit J Cath Lab #5 |  |  | 0 | 70 | 0 | 561948.36 | 564418.8 | 1142.5 | 1048.5 | 87.17% | 12.83% | 0%
20030040 |  | 20030040 | 1 | Twin Cities Community Re-Build |  |  | 0 | 0 | 0 | 0.01 | 149442.63 | 0 | 3338.48 | 96.54% | 3.34% | 0.1198%
20030041 |  | 20030041 | 1 | JR Ferche - Miss Heights |  |  | 0 | 1424 | 17259 | 96586 | 121694.26 | 538 | 834 | 91.07% | 8.933% | 0%
20030043 |  | 20030043 | 1 | MAM Mortenson-M |  |  | 0 | 0 | 0 | 0.01 | 65814.78 | 0 | 502.5 | 99.5% | 0.4975% | 0%
20030046 |  | 20030046 | 1 | UMN PAN Water Infiltration |  |  | 0 | 40 | 0 | 153226.57 | 153431.95 | 68 | 31 | 100% | 0% | 0%
20030047 |  | 20030047 | 1 | Fairview UMMC EB CSSD Washers |  |  | 0 | 119 | 0 | 1041931.105 | 1010097.89 | 2878 | 2310.5 | 95.78% | 0.6276% | 3.592%
20030048 |  | 20030048 | 1 | EGE Oberlin Sustainable Infra |  |  | 0 | 0 | 0 | 374425 | 555783.74 | 0 | 90 | 100% | 0% | 0%
20030051 |  | 20030051 | 1 | Fairview MH Unit J Chiller Rep |  |  | 0 | 0 | 0 | 756265.5 | 752484.25 | 62 | 59.5 | 100% | 0% | 0%
20030063 |  | 20030063 | 1 | Baker - Vermeer Sewer Main |  |  | 0 | 0 | 0 | 154030.25 | 131247.18 | 754 | 907 | 81.15% | 18.41% | 0.441%
20030067 |  | 20030067 | 1 | Tri-County - Front Entry Mod |  |  | 0 | 64 | 0 | 120381.76 | 125027.63 | 248 | 357 | 100% | 0% | 0%
20030068 |  | 20030068 | 1 | Fairview UMMC WB PCW Upgrade |  |  | 0 | 2 | 0 | 602866.82 | 613399.02 | 532 | 442.5 | 99.77% | 0.226% | 0%
20030069 |  | 20030069 | 1 | Harris - River Towers HVAC |  |  | 0 | 20 | 0 | 347181.79 | 296501.96 | 2675 | 2212.5 | 99.73% | 0.2712% | 0%
20030071 |  | 20030071 | 1 | FRB MN Security Enhancements |  |  | 0 | 91842.29 | 48760 | 4462359.87 | 4617320.64 | 10877.3 | 10906.5 | 87.78% | 11.85% | 0.3668%
20030076 |  | 20030076 | 1 | Faegre - Capital Improv WO#1 |  |  | 0 | 0 | 0 | 15419.26 | 15216.46 | 72 | 62.5 | 100% | 0% | 0%
20030077 |  | 20030077 | 1 | Innovation Assoc Program Mgmt |  |  | 0 | 3 | 0 | 471943.34 | 376904.37
20030009 |  | 20030009 | 1 | Welltower - Roseville Canopy |  |  | 50 | 0 | 0 | 12193.02 | 12910.59 | 52 | 52 | 100% | 0% | 0%
20030033 |  | 20030033 | 1 | State of Minnesota - ACF |  |  | 50 | 0 | 0 | 185156.77 | 189415.8 | 0 | 80 | 100% | 0% | 0%
20030019 |  | 20030019 | 1 | Cuningham Office Elevator Rpl |  |  | 500 | 0 | 0 | 317514.49 | 323136.58 | 263 | 516 | 99.42% | 0.5814% | 0%
20030022 |  | 20030022 | 1 | BluVera Plant TI |  |  | 500 | 3377 | 0 | 265096.32 | 273630.28 | 792 | 987.5 | 99.49% | 0.5063% | 0%
20030053 |  | 20030053 | 1 | Allina Buffalo Hospital PT/OT |  |  | 700 | 691 | 10 | 243823.29 | 242010.15 | 1229 | 1548 | 99.35% | 0.646% | 0%
20030024 |  | 20030024 | 1 | FV - UMMC EB Rplc TomoTherapy |  |  | 800 | 4 | 0 | 376475.87 | 374402.38 | 460 | 449.5 | 84.87% | 13.79% | 1.335%
20030044 |  | 20030044 | 1 | Blake Northrop Campus 2020 |  |  | 1000 | 12395.07 | 0 | 513192.7612 | 509512.5 | 681.93 | 872.04 | 98.62% | 1.376% | 0%
20030055 |  | 20030055 | 1 | Basilica 2020 Masonry Restore |  |  | 1000 | 4 | 0 | 93557.46 | 75714.06 | 1527 | 563.67 | 85.63% | 14.37% | 0%
20030054 |  | 20030054 | 1 | Fairview UMMC MFM Clinic US |  |  | 1271 | 7 | 0 | 148558.09 | 135202.88 | 625 | 403.5 | 98.39% | 1.611% | 0%
20030074 |  | 20030074 | 1 | Fairview UMMC WB EB 5B 6B |  |  | 1404 | 339109.71 | 25689 | 13798261.5 | 14331653.6 | 28409.1 | 33657.6 | 97.15% | 2.477% | 0.3744%
20030027 |  | 20030027 | 1 | UMN Larson FB Perf Ctr Rec Ste |  |  | 1500 | 4767 | 2359 | 650995.87 | 646250.74 | 793.2 | -1267.38 | 100.6% | -0.5918% | 0%
20030008 |  | 20030008 | 1 | SLI - ODS100,280 RTU240,350 |  |  | 1587 | 0 | 0 | 585308 | 525300.45 | 412 | 334 | 98.8% | 1.198% | 0%
20030018 |  | 20030018 | 1 | FV -UMMC EB CathLab (OR 18/19) |  |  | 1803 | 0 | 0 | 153549.16 | 164344.81 | 316 | 231 | 91.34% | 8.658% | 0%
20030056 |  | 20030056 | 1 | Fairview UMMC WB EB IR Suite |  |  | 2261 | 0 | 0 | 573653.8 | 550953.1 | 1199 | 989 | 96.41% | 3.589% | 0%
20030034 |  | 20030034 | 1 | Allina ANW Omnicell Carousels |  |  | 3800 | 131.61 | 0 | 208062.96 | 199308.23 | 600.5 | 652.33 | 90.11% | 6.209% | 3.679%
20030042 |  | 20030042 | 1 | Cemstone Project Refresh |  |  | 4000 | 9 | 0 | 20293 | 30332.41 | 164 | 220.5 | 97.05% | 2.948% | 0%
20030007 |  | 20030007 | 1 | Target Field - Clubhse/Bullpen |  |  | 4300 | 0 | 0 | 339528.56 | 361760.36 | 652 | -35119.46 | 100.1% | -0.07546% | 0%
20030036 |  | 20030036 | 1 | Allina Mercy MPP Relocation |  |  | 4500 | 61 | 0 | 695828.77 | 688871.26 | 998 | 1571.58 | 94.91% | 2.545% | 2.545%
20030012 |  | 20030012 | 1 | Allina - Mercy Oncology AHG |  |  | 6300 | 36 | 0 | 1287956.9984 | 1243021.86 | 5951.38 | 5192.91 | 95.22% | 4.622% | 0.1541%
20030016 |  | 20030016 | 1 | Vermeer Central Utility Plant |  |  | 7100 | 51509.58 | 13995 | 10377590.33 | 10371853.5 | 3293.2 | 2886 | 80.2% | 19.46% | 0.3465%
20030026 |  | 20030026 | 1 | Allina ANW 2020 Roof Replace |  |  | 7800 | 32 | 0 | 551089.93 | 549491.64 | 150 | 150.27 | 76.71% | 23.29% | 0%
20030057 |  | 20030057 | 1 | Allina Courage Kenny Kids |  |  | 8550 | 29 | 0 | 1239828.78 | 1339532.93 | 4322 | 4385 | 98.19% | 1.562% | 0.2509%
20030052 |  | 20030052 | 1 | Sanford 8th Flr B wing Bld-out |  |  | 9400 | 11436 | 7510 | 2461155.19 | 2476569 | 3379 | 2999.5 | 83.31% | 16.59% | 0.1%
20030072 |  | 20030072 | 1 | Blake Hopkins Campus 2021 |  |  | 10000 | 3617 | 8 | 1234624.032 | 1242268.57 | 3498 | 2495.64 | 99.14% | 0.8615% | 0%
20030029 |  | 20030029 | 1 | Fairview 10A ICU UMMC EB |  |  | 10661 | 0 | 0 | 4086996.92 | 4066264.1 | 8054 | 6624 | 93.75% | 6.25% | 0%
20030014 |  | 20030014 | 1 | The Bakken Museum Renovation |  |  | 11600 | 46294.78 | 4 | 3782590.66 | 3771709.91 | 7278 | 8190 | 97.61% | 2.393% | 0%
20030058 |  | 20030058 | 1 | St Cloud Surgical Ctr Exp P1 |  |  | 12935 | 101693 | 73698 | 7035682.23 | 6865132.37 | 7832 | 9475 | 94.23% | 5.641% | 0.1266%
20030049 |  | 20030049 | 1 | Fairfax-Parsons Building |  |  | 13000 | -7500.21 | 0 | 846533.55 | 1227409.23 | 4914 | 6624 | 99.49% | 0.5133% | 0%
20030021 |  | 20030021 | 1 | HHS Redleaf Ctr Family Healing |  |  | 14980 | 83592.58 | 23040 | 4904930.65 | 4903638.14 | 6482.5 | 6586 | 97.84% | 2.156% | 0%
20030073 |  | 20030073 | 1 | HHS CSC Front Entrance Repairs |  |  | 14980 | 2 | 0 | 130941 | 97206.09 | 148 | 24.5 | 87.76% | 12.24% | 0%
20030066 |  | 20030066 | 1 | Cornell College Storm Remed |  |  | 16000 | 2056 | 0 | 2926031.46 | 2094389.19 | 5066.61 | 4376 | 85.83% | 13.48% | 0.6856%
20030032 |  | 20030032 | 1 | Allina Mercy Onc Womens Health |  |  | 22500 | 15076 | 0 | 3278429.5361 | 3275617.26 | 5961.83 | 6118.56 | 96.81% | 3.187% | 0%
20030037 |  | 20030037 | 1 | Cornell - College Hall Renov |  |  | 30000 | 115175.33 | 39502 | 3092281.74 | 3147948.98 | 4337.6 | 6473.5 | 73.31% | 23.97% | 2.719%
20030061 |  | 20030061 | 1 | Legacy Mpls Data Center Renov |  |  | 34734 | 80 | 0 | 6276071.7706 | 6157160.36 | 3014 | 3752 | 98.59% | 1.413% | 0%
20030006 |  | 20030006 | 1 | TFP - The Family Partnership |  |  | 42450 | 359549.07 | 206305 | 10538171.24 | 9620081.54 | 23987.18 | 20923.87 | 98.02% | 1.933% | 0.04301%
20030038 |  | 20030038 | 1 | Cornell - Small Sport Center |  |  | 45000 | 418611.35 | 114495 | 17130164.12 | 17378621.85 | 21314.4 | 27934.2105 | 83.01% | 16.35% | 0.6372%
20030070 |  | 20030070 | 1 | UMN Lind Hall Renovations |  |  | 58687 | 467608.89 | 101134 | 14081854.8475 | 13672413.41 | 29713.21 | 31657.83 | 96.68% | 3.215% | 0.1011%
20030075 |  | 20030075 | 1 | UMN - Mech Eng Phase III |  |  | 59286 | 288222.18 | 89868 | 10986950.0166 | 11103097.86 | 17345.9 | 17727.05 | 98.37% | 1.227% | 0.4062%
20030035 |  | 20030035 | 1 | State MN - ACF Presb Langton S |  |  | 80000 | 310299 | 0 | 1283995.68 | 1308361.39 | 3574.7 | 3077.5 | 88.66% | 11.34% | 0%
20030045 |  | 20030045 | 1 | UMN Fraser Hall Chemistry |  |  | 101600 | 77 | 0 | 278372.2 | 270320.97 | 76 | 72 | 100% | 0% | 0%
20030062 |  | 20030062 | 1 | HERC Hmong College Prep PhV |  |  | 107000 | 517792.48 | 386925 | 15523002.945 | 14759618.83 | 26448 | 26394.04 | 98.19% | 1.811% | 0%
20030011 |  | 20030011 | 1 | Target Corp - Sun PrairieT2491 |  |  | 110000 | 1779.4 | 0 | 1519304.48 | 1480976.83 | 2598 | -5949 | 108.7% | -7.943% | -0.8069%
20030023 |  | 20030023 | 1 | Target Corp - Aberdeen T-0848 |  |  | 110000 | -2025 | 0 | 77411.41 | 55291.34 | 2145 | 94 | 95.74% | 4.255% | 0%
20030050 |  | 20030050 | 1 | Midway Shopping Cntr-Dmg Asmt |  |  | 120000 | 204 | 0 | 1420852.97 | 1347896.39 | 396 | 20 | 100% | 0% | 0%
20030064 |  | 20030064 | 1 | Transamerica Storm Response |  |  | 150000 | 2440 | 0 | 1017267.47 | 1076443.44 | 1441 | 1312 | 54.34% | 34.45% | 11.2%
20030065 |  | 20030065 | 1 | US Bank Storm Response |  |  | 150000 | 583 | 0 | 128229.31 | 146487.32 | 346 | 405.56 | 57.71% | 33.66% | 8.63%
20030059 |  | 20030059 | 1 | MDI Platia Place (i4) |  |  | 248000 | 0 | 0 | 72150 | 194441.41
20030078 |  | 20030078 | 1 | NWA - Bldg Automation Upgrades |  |  | 284000 | 0 | 0 | 612270.75 | 591316.92
20030020 |  | 20030020 | 1 | Allina ANW Hospital Trans Hub |  |  | 683962 | 3803714.24 | 1960647.2 | 44064770.6545 | 40156905.54 | 114541.87 | 111192.31 | 91.55% | 8.329% | 0.1234%
20030060 |  | 20030060 | 1 | MDI US Bank Edina Dev (i4) |  |  | 1000000 | 0 | 0 | 1348654 | 1160878.79 | 0 | 9 | 100% | 0% | 0%
20157001 |  | 20157001 | 1 | GE Hub Stiffener Plates TM |  |  | 0 | 0 | 0 | 0.02 | 1265815.32 | 0 | 26618 | 73.94% | 26.06% | 0%
20157002 |  | 20157002 | 1 | Chisolm View M08 BT Scrap |  |  | 0 | 0 | 0 | 0 | 33799.72 | 0 | 246.5 | 87.42% | 12.58% | 0%
20157003 |  | 20157003 | 1 | Canadian Hill T-44 Dismantle |  |  | 0 | 0 | 0 | 0 | 425109.95 | 0 | 681 | 74.08% | 25.92% | 0%
20157004 |  | 20157004 | 1 | Alamo 6 O&M 2020 Extension |  |  | 0 | 0 | 0 | 1394858 | 1015024.51 | 0 | 11514 | 88.84% | 11.16% | 0%
20157005 |  | 20157005 | 1 | Pearl O&M 2020 Extension |  |  | 0 | 0 | 0 | 557310 | 247296.17 | 0 | 2520 | 90% | 10% | 0%
20157006 |  | 20157006 | 1 | GE Commissioning Support |  |  | 0 | 0 | 0 | 0.03 | 716002.2 | 0 | 13937.5 | 70.95% | 29.05% | 0%
20157007 |  | 20157007 | 1 | Torrecillas WTG T-115 Demo |  |  | 0 | 0 | 0 | 0.01 | 269908.16 | 0 | 1699.5 | 70.81% | 29.19% | 0%
20157008 |  | 20157008 | 1 | Rim Rock WTG 198 Re-Assembly |  |  | 0 | 0 | 0 | 0 | 116674.15 | 0 | 1966.5 | 67.3% | 32.7% | 0%
20157009 |  | 20157009 | 1 | Colorado Green MET Tower Demo |  |  | 0 | 0 | 0 | 0.01 | 24245.61 | 0 | 189 | 86.24% | 13.76% | 0%
20157010 |  | 20157010 | 1 | Mortenson New Wind Assistance |  |  | 0 | 0 | 0 | 0 | 636563.75 | 0 | 17453 | 73.24% | 26.76% | 0%
20157011 |  | 20157011 | 1 | Rocksprings Tower Disposal |  |  | 0 | 0 | 0 | 0 | 27244.67 | 0 | 239.5 | 77.24% | 22.76% | 0%
20157012 |  | 20157012 | 1 | Torrecillas T-115 Rebuild |  |  | 0 | 0 | 0 | 0 | 579306.08 | 0 | 1135.5 | 76.27% | 23.73% | 0%
20040001 |  | 20040001 | 1 | Allstate Facilities Requests |  |  | 0 | 2 | 0 | 14439.46 | 14645.25 | 160 | 169.5 | 94.1% | 5.9% | 0%
20040003 |  | 20040003 | 1 | San Carlos T&M |  |  | 0 | 0 | 0 | 25087.18 | 24637.01 | 0 | 107.5 | 100% | 0% | 0%
20040005 |  | 20040005 | 1 | Allstate Tempe Facilities |  |  | 0 | 0 | 0 | 0.01 | 0
20040006 |  | 20040006 | 1 | Allstate-Tempe Facilities |  |  | 0 | 16 | 0 | 11119.08 | 10400.38 | 16 | 44.5 | 100% | 0% | 0%
20040007 |  | 20040007 | 1 | Lucid Tempe Renovation |  |  | 0 | 27447.62 | 3502 | 3451381.9072 | 3248499.99 | 1172.1 | 994.5 | 96.88% | 3.117% | 0%
20040008 |  | 20040008 | 1 | AlaskaUSA Safeway Peoria |  |  | 0 | 2647 | 2616 | 53339.34 | 56670.82 | 273.1 | 302.5 | 80% | 20% | 0%
20040009 |  | 20040009 | 1 | AlaskaUSA Safeway Arcadia |  |  | 0 | 2048 | 0 | 52281.48 | 49663.62 | 215.7 | 305 | 88.2% | 11.8% | 0%
20040010 |  | 20040010 | 1 | AlaskaUSA Frys Tempe |  |  | 0 | 2572 | 2540 | 64168.85 | 56968.38 | 319.9 | 279 | 98.57% | 1.434% | 0%
20040004 |  | 20040004 | 1 | AlaskaUSA 2nd Floor TI |  |  | 25000 | 27910 | 10910 | 3433225.11 | 3235182.93 | 1579.7 | 2170 | 93.27% | 6.728% | 0%
20040002 |  | 20040002 | 1 | MDI-ASU Arena |  |  | 166500 | 4793524.58 | 123075 | 117336071.78 | 111117966.11 | 47289.4 | 49949.35 | 87.49% | 12.51% | 0%
20055004 |  | 20055004 | 1 | OHSU Baird Hall Lab |  |  | 0 | 8 | 0 | 883.05 | 542.31
20055005 |  | 20055005 | 1 | Kaiser WMC Emerg Triage |  |  | 0 | 1 | 0 | 73604.47 | 73910.9 | 0 | 140.5 | 86.48% | 13.52% | 0%
20055007 |  | 20055007 | 1 | Kaiser Sunset Boiler Constr |  |  | 0 | 677 | 0 | 426686.0445 | 434363.04 | 885 | 843.58 | 99.76% | 0.2371% | 0%
20055008 |  | 20055008 | 1 | Adventist Med Air Compressor |  |  | 0 | 25 | 0 | 229967.22 | 223157.63 | 31 | 0 | 0% | 0% | 0%
20055011 |  | 20055011 | 1 | Kaiser WMU Vaporizer Replace |  |  | 0 | 19 | 0 | 28927.74 | 28738.26 | 80 | 44 | 100% | 0% | 0%
20055012 |  | 20055012 | 1 | Kaiser WMC SPD Ultrasonics |  |  | 0 | 15 | 0 | 12147.14 | 12754.59 | 24 | 8 | 100% | 0% | 0%
20055013 |  | 20055013 | 1 | Kaiser WMC Radio Rd |  |  | 0 | 61 | 56 | 98038.19 | 93604.77 | 208 | 176.85 | 100% | 0% | 0%
20055014 |  | 20055014 | 1 | Kaiser SST Infusion Clinic |  |  | 0 | 1925 | 0 | 162491.21 | 170070.84 | 345 | 438 | 98.86% | 1.142% | 0%
20055015 |  | 20055015 | 1 | Kaiser Fac Direct Sml Wrks |  |  | 0 | 65 | 10 | 392165.63 | 357355.93 | 753 | 1167 | 94.17% | 5.827% | 0%
20055016 |  | 20055016 | 1 | Kaiser Red Message Mgmt Precon |  |  | 0 | 15 | 0 | 10776.55 | 10352.24 | 24 | 0 | 0% | 0% | 0%
20055017 |  | 20055017 | 1 | Kaiser WMC TJC Door Mod Constr |  |  | 0 | 87 | 0 | 48199.75 | 48914.59 | 152 | 133 | 36.09% | 63.91% | 0%
20055019 |  | 20055019 | 1 | OHSU/Adven WHV Fam Med Clinic |  |  | 0 | 145.8 | 0 | 115836.33 | 112835.3 | 505 | 427 | 99.06% | 0.9368% | 0%
20055020 |  | 20055020 | 1 | UO Huestis Hall Surge |  |  | 0 | 26523.65 | 1605 | 2969457.23 | 3086484.95 | 3848.5 | 4048.07 | 89.17% | 10.19% | 0.6423%
20055021 |  | 20055021 | 1 | Kaiser Red Message Mgmt |  |  | 0 | 63 | 0 | 28877.99 | 30010.64 | 138 | 149 | 96.64% | 3.356% | 0%
20055022 |  | 20055022 | 1 | Kaiser WMC Ultrasound Precon |  |  | 0 | 9 | 0 | 11250.38 | 9171.45 | 16 | 0 | 0% | 0% | 0%
20055025 |  | 20055025 | 1 | Kaiser WMC Replace SPB |  |  | 0 | 10 | 0 | 6506.98 | 7187.9 | 16 | 8 | 100% | 0% | 0%
20055003 |  | 20055003 | 1 | OHSU Emerg Med Off Reloc |  |  | 1400 | 8 | 0 | 983.33 | 565.78
20055002 |  | 20055002 | 1 | OHSU 9A Remodel |  |  | 6000 | 13 | 0 | 5518.62 | 8096.33
20055001 |  | 20055001 | 1 | Nike Cool Pads |  |  | 16000 | 13 | 0 | 23929.54 | 10616.51
20055006 |  | 20055006 | 1 | Studio PPS Terwilliger Study |  |  | 21000 | 0 | 0 | 9000 | 1167.96
20055024 |  | 20055024 | 1 | UO Huestis Hall Renovation |  |  | 60000 | 22314.89 | 0 | 29395131.52 | 5452996 | 3796.5 | 2024.43 | 93.41% | 6.57% | 0.0247%
20055010 |  | 20055010 | 1 | CitizenM Hotel - FB Menlo |  |  | 90868 | 493629.22 | 5084.59 | 87844527.26 | 42565862.54 | 6039.2 | 929 | 94.89% | 5.113% | 0%
20055009 |  | 20055009 | 1 | PPS Emerg COVID Support |  |  | 2500000 | 25 | 0 | 119242.57 | 102041.39 | 256 | 411.5 | 98.18% | 1.823% | 0%
20146001 |  | 20146001 | 1 | Corazon Solar Interconnection |  |  | 0 | 280328.92 | 254705 | 12552025.93 | 12608755.32 | 14280.67 | 16347 | 76.29% | 23.71% | 0%
20146002 |  | 20146002 | 1 | West Raymond Interconnect |  |  | 0 | 144337.16 | 161307 | 4381781.6 | 4018678.95 | 4863.47 | 7406.5 | 78.11% | 21.89% | 0%
20146003 |  | 20146003 | 1 | Blackjack Creek Interconnect |  |  | 0 | 391370 | 377076 | 8799109.08 | 8357171.43 | 11845.34 | 9745.5 | 90.71% | 9.291% | 0%
20146004 |  | 20146004 | 1 | Dakota Range Wind - Power |  |  | 0 | 618915.97 | 613472 | 21073600 | 20035902.71 | 23565.84 | 21477 | 82.17% | 17.83% | 0%
20146005 |  | 20146005 | 1 | Toms Fork |  |  | 0 | 957 | 0 | 7237514.25 | 29182.66
20146006 |  | 20146006 | 1 | Fighting Jays Solar - Power |  |  | 0 | 191200.8 | 191448.8 | 7563984 | 7364813.64 | 7972.25 | 12907 | 89.01% | 10.99% | 0%
20146007 |  | 20146007 | 1 | Andrews 4 Solar - Power |  |  | 0 | 0 | 0 | 1399065 | 945979.39
20146008 |  | 20146008 | 1 | Emerald Grove Solar - Power |  |  | 0 | 94420.46 | 86813 | 6208916.76 | 6163106.29 | 4928.69 | 4746 | 87.85% | 12.15% | 0%
20146009 |  | 20146009 | 1 | Dawn Solar - Power |  |  | 0 | 240 | 0 | 1444815 | 1039331.91
20146010 |  | 20146010 | 1 | Blue Canyon II Repower-Power |  |  | 0 | 33537.56 | 1652 | 3792652.05 | 3815632.05 | 5737 | 7309.5 | 80.41% | 19.59% | 0%
20148014, 20141012, 20146011 |  | 20146011 | 21 | Rockhaven Wind - Power |  |  | 0 | 170082.69 | 161860 | 12593137.54 | 14039633.03 | 6529.54 | 15203.5 | 79.14% | 20.86% | 0%
20050001 |  | 20050001 | 1 | PRMCE Colby 4A Behavioral |  |  | 0 | 34931.3 | 2440 | 7014752.8576 | 7145040.4 | 2530.1 | 4431 | 91.57% | 8.023% | 0.4062%
20050002 |  | 20050002 | 1 | PRMCE Colby D Wing CT Install |  |  | 0 | 4302 | 509 | 451496.772 | 440220.7 | 452.2 | 604.74 | 85.82% | 10.38% | 3.803%
20050003 |  | 20050003 | 1 | Hyla Crossing Pump Station |  |  | 0 | 0 | 0 | 12141.06 | 8745.85
20050004 |  | 20050004 | 1 | KP ESC Demolition |  |  | 0 | 284 | 0 | 553260.17 | 523244.61 | 282.4 | 307.81 | 100% | 0% | 0%
20050005 |  | 20050005 | 1 | Make Ready - Swedish |  |  | 0 | 31 | 495 | 1306111.45 | 1301925.73 | 960 | 715 | 97.48% | 2.517% | 0%
20050006 |  | 20050006 | 1 | Swedish NT - Demo/Abatement |  |  | 0 | 5746 | 0 | 26601901.97 | 19126341.11 | 7531.5 | 5485.1 | 94.61% | 5.35% | 0.03646%
20050007 |  | 20050007 | 1 | Block 95 - Swedish |  |  | 0 | 32969.5 | 32 | 42016452.39 | 12883303.76 | 7939.4 | 1717 | 96.59% | 2.941% | 0.4659%
20050008 |  | 20050008 | 1 | KP ESC Site Prep |  |  | 0 | 21 | 0 | 303001.52 | 284289.65 | 8 | 4 | 0% | 100% | 0%
20050009 |  | 20050009 | 1 | Swedish COVID19 Response |  |  | 0 | 0 | 2 | 416668.62 | 378954.69 | 0 | 5 | 100% | 0% | 0%
20050010 |  | 20050010 | 1 | Bend Interceptor Phase 2 |  |  | 0 | 1392 | 1 | 19647142.83 | 20134910.92 | 254 | 24 | 100% | 0% | 0%
20050011 |  | 20050011 | 1 | Fifth and Union Hotel (Mstrwrk |  |  | 0 | 0 | 0 | 43228.32 | 49891.52
20050012 |  | 20050012 | 1 | Kaiser ASC Parking Garage |  |  | 0 | 1103397.77 | 21724.96 | 23388914.9 | 4813468.56 | 19664 | 7840.5 | 94.87% | 4.681% | 0.4528%
20050013 |  | 20050013 | 1 | Fana Four106 |  |  | 0 | 0 | 0 | 507127.75 | 546825.97
20050014 |  | 20050014 | 1 | Prov NWSA EP Lab Reno |  |  | 0 | 3165.1 | 430 | 1048236.1 | 1039431.21 | 568.2 | 746.76 | 61.07% | 36.46% | 2.477%
20050015 |  | 20050015 | 1 | Cedar Mills No 6882 |  |  | 0 | 55 | 0 | 11553677.6471 | 11177565.44
20050050 |  | 20050050 | 1 | Kaiser Everett IDIQ 2020 |  |  | 0 | 1008.13 | 483 | 626237.3545 | 641456.84 | 708.13 | 728 | 95.54% | 2.266% | 2.198%
20050051 |  | 20050051 | 1 | Kaiser Lynwood IDIQ 2020 |  |  | 0 | 2319 | 0 | 4368.72 | 5874.33 | 0 | 0 | 0% | 0% | 0%
20050052 |  | 20050052 | 1 | KP Port Orchard IDIQ 2020 |  |  | 0 | 1232 | 0 | 384987.95 | 394749.53 | 701.8 | 725.95 | 98.9% | 1.102% | 0%
20050053 |  | 20050053 | 1 | KP EVM Roof Replacement |  |  | 0 | 39.5 | 0 | 518237.35 | 480019.79 | 34.3 | 0 | 0% | 0% | 0%
20145002 |  | 20145002 | 1 | Texas Solar Nova 2 Geotech |  |  | 0 | 260 | 0 | 194265 | 187905.75 | 160 | 276 | 86.96% | 13.04% | 0%
20145006 |  | 20145006 | 1 | Emerald Grove Solar - Vistra |  |  | 140 | 3023127.7112 | 2724497.39 | 65503365.33 | 66327681.08 | 261326.74 | 317287.34 | 86.19% | 13.81% | 0%
20145005 |  | 20145005 | 1 | Andrews 4 Solar - Vistra |  |  | 261 | 585 | 0 | 4302346.04 | 2639820.77 | 386 | 384.5 | 72.43% | 27.57% | 0%
20145001 |  | 20145001 | 1 | Fighting Jays Solar-CIP |  |  | 476 | 12961792.56 | 8790948.73 | 236866438.17 | 232598848.77 | 1054810.02 | 1131922.42 | 86.36% | 13.64% | 0.0004859%
20145008 |  | 20145008 | 1 | Dawn Solar-Blue Planet |  |  | 683 | 1387 | 0 | 7796037 | 2896120.54 | 600 | 238 | 79.83% | 20.17% | 0%
20145007 |  | 20145007 | 1 | Edwards & Sanborn 1A&1B |  |  | 1113 | 16817754.46 | 14360299.08 | 836870271.29 | 732549556.05 | 2155844.61 | 2180545.52 | 84.46% | 14.55% | 0.9959%
20150003 |  | 20150003 | 1 | MPLS Enterprise DAS Projects |  |  | 0 | 0 | 0 | 115208 | 130924.12
20150004 |  | 20150004 | 1 | MCC - CANA - Calgary Flames |  |  | 0 | 0 | 0 | 0.02 | 578583.72
20150004-110 |  | 20150004-110 | 1 | CANA - Calgary Flames Arena |  |  | 0 | 0 | 0 | 1069573.98 | 756106.4
20150006 |  | 20150006 | 1 | Climate Pledge Arena DAS |  |  | 0 | 1 | 0 | 12957558.8358 | 12093720.93 | 16435 | 0 | 0% | 0% | 0%
20150007 |  | 20150007 | 1 | MLS - Nashville - DAS |  |  | 100 | 0 | 0 | 606593.712 | 666102.89
20150005 |  | 20150005 | 1 | PSU - Lasch Phase 4 - QB Lab |  |  | 1200 | 1227 | 0 | 1975172.73 | 1930091.65
20150001 |  | 20150001 | 1 | MLS - Sacramento Republic FC |  |  | 404875 | 0 | 0 | 1 | 1078098.42
20141001 |  | 20141001 | 1 | Smoky Hills II Repower |  |  | 0 | 1601.68 | 734 | 16294067.102 | 10931550.62 | 38410 | 31350 | 81.32% | 18.68% | 0%
20148005, 20141002 |  | 20141002 | 11 | Hawkeye Wind |  |  | 0 | 13562.18 | 643 | 25703700.52 | 16812095.93 | 31640 | 21618.5 | 78.57% | 18.16% | 3.263%
20141003 |  | 20141003 | 1 | Langford Repower |  |  | 0 | 2984 | 1285 | 23227823.88 | 18687352.52 | 78840 | 81256.58 | 79.77% | 20.23% | 0%
20141004 |  | 20141004 | 1 | Dakota Range Wind |  |  | 0 | 11456.68 | 4726 | 101827957.5718 | 91177666.12 | 159155.5 | 115278.5 | 78.23% | 21.03% | 0.7378%
20141005 |  | 20141005 | 1 | Trent Mesa Repower |  |  | 0 | 6 | 0 | 599210.14 | 595006.6
20141006 |  | 20141006 | 1 | Mesa Alta & Mesa Wind |  |  | 0 | 0 | 0 | 758962.5 | 671012.09
20141007 |  | 20141007 | 1 | Mulqueeney Ranch Wind |  |  | 0 | 0 | 0 | 340349 | 259112.45
20141008 |  | 20141008 | 1 | Desert Sky Repower |  |  | 0 | 4 | 0 | 860359 | 477135.83 | 0 | 145 | 100% | 0% | 0%
20141009 |  | 20141009 | 1 | Big Sky Repower |  |  | 0 | 0 | 0 | 154035.67 | 147415.4
20141010 |  | 20141010 | 1 | Blue Canyon Repower |  |  | 0 | 3944 | 2555 | 39353923.7198 | 34076940.33 | 81081 | 82518 | 74.2% | 25.8% | 0%
20141011 |  | 20141011 | 1 | Oasis Wind |  |  | 0 | 1772 | 1295 | 38618613.98 | 36561723.04 | 47420 | 43481.5 | 75.68% | 20% | 4.324%
20148014, 20141012, 20146011 |  | 20141012 | 11 | Rockhaven Wind |  |  | 0 | 27206.77 | 5950 | 65035217.1587 | 62157948.23 | 106504 | 89888.33 | 79.45% | 20.55% | 0%
20141013 |  | 20141013 | 1 | Glass Sands Wind |  |  | 0 | 6128 | 6172 | 52718623.0132 | 52828054.31 | 69002.09 | 86343.35 | 79.34% | 20.66% | 0%
19090001 |  | 19090001 | 1 | FermiLab Engineering Research | 2019-07-01 | 2023-08-01 | 102000 | 404891 | 8487 | 62164929.9174 | 59937279.78 | 13485.14 | 15106.5 | 82.98% | 15.56% | 1.463%
19030027 |  | 19030027 | 1 | HCMC - MCP Phase 2A | 2020-02-01 | 2022-02-28 | 100000 | 0 | 0 | 45162 | 29437.12
18080008, 19080004 |  | 19080004 | 11 | AMC Mount Pleasant | 2019-09-01 | 2022-02-01 | 299000 | 3552220.89 | 2252566 | 155409326.9107 | 155865635.3 | 137235.84 | 159813.37 | 90.78% | 9.166% | 0.05475%
19000004-040, 19060011, 19060050 |  | 19060011 | 15 | MDI-NJH COH | 2019-10-01 | 2021-07-30 | 104820 | 1425129.76 | 901412 | 62888862.2096 | 60432420.69 | 82353.96 | 85860.5 | 88.85% | 11.15% | 0%
19030008 |  | 19030008 | 1 | UMN-CMRR MDT Optical Imaging | 2019-06-07 | 2021-03-26 | 30170 | 285346.52 | 158967 | 12809997.99 | 13215131.1 | 21088.7 | 24339.47 | 98.2% | 1.795% | 0%
19110001, 20060028, 20060006 |  | 19110001 | 1 | SBIRS Operations Facility | 2019-06-01 | 2021-03-11 | 58760 | 1308 | 0 | 33895292.38 | 35924451.92 | 0 | 0 | 0% | 0% | 0%
19090991 |  | 19090991 | 1 | Chicago 2019 Prefab Shop | 2019-01-01 | 2020-12-31 | 0 | 1921 | 2990 | 226487 | 617038.24 | 1044 | 3479.45 | 99.4% | 0.6035% | 0%
19060019 |  | 19060019 | 1 | EX Vail-Vail Four Seasons | 2019-04-22 | 2020-12-07 | 0 | 161115 | 10769 | 5696911.17 | 5833592.67 | 14595.1 | 14192 | 93.46% | 6.542% | 0%
19141018 |  | 19141018 | 1 | Gonzaga Ridge Wind | 2020-04-06 | 2020-12-01 | 0 | 0 | 0 | 91100 | 72401.66
19141015, 19148011 |  | 19141015 | 1 | Diamond Trail Wind | 2019-08-01 | 2020-11-09 | 0 | 6811 | 4016 | 122586746.1894 | 109282444.93 | 240797.2 | 146442.75 | 66.48% | 33.03% | 0.4923%
19040004 |  | 19040004 | 1 | MDI - The Beam on Farmer | 2019-04-19 | 2020-10-31 | 0 | 866886.6 | 0 | 52557329.8 | 54088575.7 | 7855.6 | 9981.78 | 83.71% | 16.29% | 0%
19146003, 19148003, 19145001 |  | 19145001 | 21 | Crane Solar - CED Crane Solar | 2019-01-14 | 2020-10-31 | 212592800 | 1814148.54 | 9321186 | 84328075.02 | 87807940.38 | 378456.13 | 407869.83 | 85.02% | 14.98% | 0.0009807%
19060029 |  | 19060029 | 1 | LoneTree-Ridgegate Pkwy Exp P2 | 2019-06-01 | 2020-10-28 | 0 | 390843.08 | 508776 | 11411748.85 | 16364311.16 | 29700 | 56951 | 78.04% | 21.96% | 0%
17141013, 18148024, 19146004 |  | 19146004 | 21 | Palo Alto Wind - HVT | 2019-04-01 | 2020-10-17 | 0 | 804789 | 38375 | 30701338.89 | 30458883.91 | 21257 | 34863.5 | 78.88% | 21.12% | 0%
19146006, 19141003, 19148013 |  | 19141003 | 11 | El Campo | 2019-06-17 | 2020-10-01 | 0 | 4841 | 3710 | 69310825.0776 | 70827585.39 | 154313 | 169954.75 | 82.04% | 17.96% | 0%
18000014-040, 19090002, 19090012, 19090011 |  | 19090002 | 15 | MDI-Hilton Garden Inn Madison | 2019-06-03 | 2020-09-30 | 220000 | 97515.65 | 5860 | 38200931.96 | 38169437.03 | 4990.2 | 2824.4 | 85.18% | 13.86% | 0.956%
19148012, 19146015, 19141011 |  | 19146015 | 11 | Cheyenne Ridge Wind - HVT | 2019-05-01 | 2020-09-01 | 0 | 641887 | 610941 | 48921315.33 | 47594183.34 | 141513 | 87180.76 | 72.29% | 27.71% | 0%
19146013 |  | 19146013 | 1 | Misae II Interconnect | 2020-03-01 | 2020-08-31 | 0 | 360838.11 | 255306 | 12485275.45 | 6221918.39 | 12680.7 | 3195 | 80.23% | 19.77% | 0%
19030017 |  | 19030017 | 1 | RiverView Health - AC&IP | 2019-04-29 | 2020-08-28 | 80657 | 244252.26 | 71670 | 24308389.436 | 24540639.65 | 27721.1 | 25587.5 | 94.82% | 5.081% | 0.1016%
19030015 |  | 19030015 | 1 | Blake Lobby Addition | 2019-06-03 | 2020-08-11 | 19617 | 329537.79 | 151810 | 7878956.5 | 8008407.3 | 20134.8 | 23567.67 | 96.54% | 3.445% | 0.01697%
19030016 |  | 19030016 | 1 | Vermeer Building 5 & 6 | 2019-06-01 | 2020-08-01 | 500000 | 618522.4 | 49852 | 73830787.48 | 73280737.43 | 17569.6 | 18158.25 | 74.58% | 24.67% | 0.7545%
19146008, 19141005, 19148020, 19146023, 19141024 |  | 19146008 | 1 | Kings Point Wind Design-HVT | 2020-02-01 | 2020-08-01 | 0 | 8 | 0 | 231306 | 211742
19060023 |  | 19060023 | 1 | Park Creek-Filing MF Dstrct IV |  | 2020-07-30 | 0 | 0 | 0 | 989999.7 | 982037.74 | 3750 | 4389 | 96.39% | 3.611% | 0%
19146016 |  | 19146016 | 1 | Chisholm Energy Storage | 2019-07-08 | 2020-07-24 | 0 | 292464.06 | 229691 | 20736968.63 | 18007760.03 | 38673.11 | 39370.5 | 80.5% | 19.5% | 0%
18000001-040, 18040002, 19040002 |  | 19040002 | 25 | MDI-ASU HH/HP FFE | 2019-02-11 | 2020-07-21 | 156611 | 7 | 0 | 4262041.39 | 4235659.99
19050003 |  | 19050003 | 1 | PRMCE Colby 9D Patient Rms | 2019-04-01 | 2020-06-30 | 0 | 136839.13 | 4524 | 17740173.8161 | 17597139.51 | 9500.18 | 8387.74 | 93.03% | 4.697% | 2.271%
19141013, 19146012, 19148017 |  | 19146012 | 11 | King Plains Wind - HVT | 2019-08-15 | 2020-06-29 | 0 | 567317 | 640552 | 20785778.7425 | 20534244.82 | 59027.3 | 35908.5 | 84.12% | 15.88% | 0%
19146010, 19141010, 19148015 |  | 19146010 | 1 | Nobles 2 Wind - HVT | 2019-09-10 | 2020-06-09 | 0 | 3092 | 0 | 6600792.43 | 6063273.25
19145005, 19146017, 20148007 |  | 19145005 | 1 | Phoenix Solar - Pattern Energy | 2019-07-29 | 2020-06-05 | 0 | 2320878.09 | 2581904 | 58248046.22 | 63617220.62 | 218675.17 | 281291.25 | 88.4% | 11.6% | 0%
19146006, 19141003, 19148013 |  | 19146006 | 1 | El Campo Wind - HVT | 2019-08-01 | 2020-06-01 | 0 | 0 | 0 | 108697.7 | 148702.61
19146009, 19141004, 19148019, 19146022, 19141022 |  | 19146009 | 1 | North Fork Rdg Wind Design-HVT | 2019-10-01 | 2020-06-01 | 0 | 195367 | 0 | 270750 | 184118.13
19060020 |  | 19060020 | 1 | MDI-Bioscience 5 | 2019-08-01 | 2020-05-01 | 90000 | 0 | 0 | 373718 | 391969.66
19146003, 19148003, 19145001 |  | 19146003 | 1 | Crane I Solar - HVT | 2019-10-17 | 2020-04-29 | 0 | 103822.75 | 66329 | 5291076.72 | 5050260.47 | 3614.68 | 3973 | 85.04% | 14.96% | 0%
19080003 |  | 19080003 | 1 | Project Walleye | 2019-04-08 | 2020-04-01 | 350098 | 11 | 0 | 1026419.09 | 873427.94
19030012 |  | 19030012 | 1 | Thrivent Financial TI | 2019-10-01 | 2020-04-01 | 110000 | 304175 | 81018 | 14667001.55 | 14705950.41 | 11380.6 | 15200 | 92.96% | 6.99% | 0.05263%
19090003 |  | 19090003 | 1 | Allstate Jacksonville 2019 | 2019-04-01 | 2020-03-31 | 27750 | 1003 | 0 | 3699934.8662 | 3581834.83
19060022 |  | 19060022 | 1 | Broadmoor Exhibit Hall |  | 2020-03-20 | 172988 | 951312.66 | 619504 | 37503685.44 | 37496766.89 | 40684.6 | 43022.75 | 79.53% | 20.47% | 0%
19060001 |  | 19060001 | 1 | BMD-Baseline W Sheridan | 2019-01-04 | 2020-01-31 | 0 | 0 | 0 | 14581 | 8189.67
19060010 |  | 19060010 | 1 | CDOT-Hwy 72 Coal Creek Canyon | 2019-04-01 | 2020-01-13 | 0 | 640445.45 | 136268 | 13066982.97 | 16418354.06 | 49488 | 78835.25 | 76.09% | 23.91% | 0%
19060007 |  | 19060007 | 1 | Park Creek - Filing PC Park | 2019-04-01 | 2019-12-31 | 0 | 1 | 0 | 577344.9974 | 605189.41 | 482 | 215 | 99.3% | 0.6977% | 0%
19060009 |  | 19060009 | 1 | Woodward-2019 Misc Projects | 2019-01-28 | 2019-12-31 | 0 | 623 | 164 | 296952.6886 | 304539.71 | 376 | 1486.5 | 89.84% | 10.16% | 0%
19060012 |  | 19060012 | 1 | SCL-LMC Foothills Renovation | 2019-02-18 | 2019-12-31 | 0 | 20890.82 | 381 | 2581422.57 | 2784058.73 | 1615.6 | 5406 | 85.15% | 14.85% | 0%
19030001 |  | 19030001 | 1 | FUMC-Annual Contract 2019 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0 | 1183843.94 | 1195962.18 | 0 | 3955.5 | 92.34% | 5.916% | 1.744%
19030002 |  | 19030002 | 1 | Allina Annual Contract - 2019 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0 | 5931787.07 | 5931786.98 | 0 | 28840.13 | 91.43% | 7.982% | 0.586%
19030013 |  | 19030013 | 1 | Basilica Annual 2019 | 2019-05-01 | 2019-12-31 | 0 | 672 | 176 | 293976.8603 | 338402.5 | 1412 | -1976.67 | 103.8% | -3.491% | -0.3541%
19145002, 19148010 |  | 19145002 | 1 | Grazing Yak - NextEra Energy | 2019-06-07 | 2019-12-31 | 47251000 | 7687464 | 1130118 | 21019294.33 | 19789713.98 | 90270 | 74350 | 81.41% | 18.59% | 0%
19146014 |  | 19146014 | 1 | Asheville Rock Hill BESS | 2019-04-01 | 2019-12-20 | 0 | 176562 | 22265 | 2575676.29 | 2574732.41 | 3004 | 5860 | 78.24% | 21.76% | 0%
19030023 |  | 19030023 | 1 | Philips Elec Realty - TI DS | 2019-09-20 | 2019-12-09 | 5973 | 6500 | 0 | 1642487.08 | 1494179.26 | 477.7 | 575.5 | 98.09% | 1.911% | 0%
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 19060015 | 61 | SCL-SJB P Tube Expansion | 2019-01-01 | 2019-12-01 | 0 | 0 | 0 | 852026.33 | 853632.22
19060016 |  | 19060016 | 1 | SCL-SJB Boiler Phase II | 2019-01-01 | 2019-12-01 | 0 | 0 | 0 | 550796.11 | 550833.01
19148001 |  | 19148001 | 1 | Chokecherry Sierra Madre 2019 | 2019-03-18 | 2019-11-30 | 0 | 1174897 | 725358 | 17298436.15 | 18145102.16 | 73310 | 71736.5 | 76.23% | 23.45% | 0.322%
19050004 |  | 19050004 | 1 | PRMCE Colby 2D OR Pre OP | 2019-06-01 | 2019-11-30 | 0 | 28881 | 2539 | 2754581.2704 | 2704985.13 | 2127.9 | 1334.5 | 82.58% | 15.96% | 1.461%
19146007, 19148006, 19141002 |  | 19146007 | 1 | Ida Grove II Wind - HVT | 2019-04-01 | 2019-11-23 | 0 | 497926 | 5588 | 21258838.88 | 19430680.13 | 25932 | 22566.5 | 79.41% | 20.59% | 0%
19060030 |  | 19060030 | 1 | SCL-LMC Foothills PrimCare |  | 2019-11-22 | 11500 | 28482.12 | 3000 | 1965241.06 | 2063237.22 | 2238.8 | 5802.5 | 89.8% | 10.2% | 0%
19030024 |  | 19030024 | 1 | Boston Scientific - TI DS | 2019-08-28 | 2019-11-22 | 5973 | 3769 | 0 | 487657.41 | 480722.05 | 370.9 | 376 | 98.94% | 1.064% | 0%
19146011, 19141012, 19148009 |  | 19146011 | 1 | Arbor Hill 2019 Wind - HVT | 2019-07-08 | 2019-11-18 | 0 | 382143 | 150669 | 8661883.84 | 7984380 | 7596 | 2965 | 80.03% | 19.97% | 0%
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 19060002 | 41 | SCL-SJB 4th Floor-AHU | 2019-01-01 | 2019-11-01 | 0 | 0 | 0 | 399622.08 | 400245.84
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 19060003 | 31 | SCL-SJB Admin/Cath/Enab | 2019-01-01 | 2019-11-01 | 0 | 2 | 0 | 3597140.52 | 3707737.58 | 0 | 0 | 0% | 0% | 0%
19060013 |  | 19060013 | 1 | SCL-SJB Facilities Agreement | 2019-01-01 | 2019-11-01 | 0 | 0 | 0 | 1047603.87 | 1362052.02
19060026 |  | 19060026 | 1 | SCL-SJB Fluoroscopy Ph2 | 2019-01-01 | 2019-11-01 | 0 | 0 | 0 | 113845 | 113683.93 | 0 | 0 | 0% | 0% | 0%
19146001, 18141021, 19148002 |  | 19146001 | 1 | Clear Creek Wind - HVT | 2019-06-01 | 2019-11-01 | 0 | 8409 | 9240 | 7370991 | 6308965.02 | 8381 | 9211.5 | 78.41% | 21.59% | 0%
19141016 |  | 19141016 | 1 | Glenrock-Rolling Hills Repower | 2019-04-01 | 2019-10-31 | 0 | 2007 | 1868 | 22677279.86 | 22181079.18 | 64928 | 88060.79 | 79.22% | 20.51% | 0.2771%
19060031 |  | 19060031 | 1 | SCL-LMC Foothills Scheduling | 2019-06-01 | 2019-10-23 | 7000 | 22211.76 | 1098 | 921833.42 | 952097.42 | 1556 | 2835 | 83.23% | 16.77% | 0%
19146005 |  | 19146005 | 1 | Rondo SVC | 2019-07-15 | 2019-10-15 | 0 | 94750 | 4579 | 1370711 | 1070694.75 | 10496 | 3434 | 82.27% | 17.73% | 0%
19146002 |  | 19146002 | 1 | Stadium Rebuild | 2019-01-21 | 2019-09-30 | 0 | 27312 | 14831 | 2132339.94 | 1952621.8 | 6459 | 6334.75 | 74.45% | 25.55% | 0%
19145003 |  | 19145003 | 1 | Alamo 7 Expansion | 2019-04-29 | 2019-09-06 | 993630 | 23889 | 45190 | 1133919 | 1155307.69 | 8490 | 5605.5 | 81.28% | 18.72% | 0%
19030028 |  | 19030028 | 1 | NS II - Certified Power TI | 2019-05-13 | 2019-09-03 | 55237 | 144 | 0 | 1966531.44 | 1994000.38 | 1622 | 1073 | 94.41% | 5.592% | 0%
19060025 |  | 19060025 | 1 | Westfield-Parcel B/C Demo | 2019-04-15 | 2019-09-01 | 0 | 0 | 0 | 1716388.6 | 1719292.77
19060027 |  | 19060027 | 1 | Westfield-Pecos Logistics Park | 2019-04-15 | 2019-09-01 | 0 | 0 | 0 | 0 | -4019.17
19060018 |  | 19060018 | 1 | Murphy-AB Clarifier | 2019-04-09 | 2019-08-30 | 0 | 0 | 0 | 0.01 | 0
19060024 |  | 19060024 | 1 | Stadium Mgmt-Aramark Conc |  | 2019-08-30 | 13684 | 0 | 1080 | 2634323.61 | 2756130.24 | 366.4 | 4101.5 | 81.36% | 18.64% | 0%
19030007 |  | 19030007 | 1 | UMN Volleyball Remodel | 2019-04-01 | 2019-08-23 | 9000 | 56190.15 | 44002 | 3080257.51 | 3115299.79 | 4892.7 | 4294.5 | 99.17% | 0.6404% | 0.1863%
19030026 |  | 19030026 | 1 | MPI-Upper Miss Academy TI | 2019-05-06 | 2019-08-16 | 35160 | 23 | 55 | 1628183.68 | 1587808.57 | 1642 | 2212.5 | 98.37% | 1.627% | 0%
19110003 |  | 19110003 | 1 | DC Office Remodel-To Be Cap. | 2019-01-01 | 2019-08-09 | 12000 | 0 | 0 | 1397721 | 2.3283e-10
19145004 |  | 19145004 | 1 | Alamo 4 ACT Labor - OCI | 2019-04-15 | 2019-08-02 | 0 | 142668 | 124605 | 2079297.81 | 1356520.36 | 33561 | 27333 | 88.93% | 11.07% | 0%
19030010 |  | 19030010 | 1 | ANW-Punched Windows | 2018-12-26 | 2019-07-31 | 0 | 9988.6 | 0 | 2850440 | 2774861.37 | 7605.6 | 5283 | 95.69% | 4.155% | 0.1514%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030021 | 1 | Target Corp - StillwaterT0931 | 2019-04-15 | 2019-07-31 | 110000 | 0 | 0 | 1194268.39 | 1202164.76 | 1680 | 1876 | 94.35% | 5.65% | 0%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030022 | 11 | Target Corp - Crystal T0003 | 2019-04-15 | 2019-07-31 | 110000 | 5 | 0 | 2063757.82 | 1927390.14 | 1680 | 1866.83 | 91.72% | 8.276% | 0%
19030029 |  | 19030029 | 1 | Fairview - SBldg AV 5122-5123 | 2019-06-20 | 2019-07-20 | 2000 | 0 | 0 | 87035.11 | 84375.88 | 56 | 56.5 | 99.12% | 0.885% | 0%
19145008, 19148024, 19146021 |  | 19145008 | 1 | Greasewood Solar - Concho | 2019-04-15 | 2019-06-28 | 0 | 8461855.75 | 8718497 | 136700537.036 | 126952753.44 | 575202.73 | 513053.3 | 87.42% | 12.58% | 0%
19040006 |  | 19040006 | 1 | Allstate Tempe | 2019-04-22 | 2019-06-13 | 2000 | 28483 | 0 | 860313.15 | 646017.31 | 406 | 1797.5 | 92.71% | 7.288% | 0%
19141001 |  | 19141001 | 1 | WY Reload Repower Wind | 2019-01-16 | 2019-06-01 | 0 | 201 | 0 | 6142681.54 | 4745100.21 | 11000 | 16249.41 | 80.13% | 19.87% | 0%
19060014 |  | 19060014 | 1 | Ardent Mills-Commerce City Br | 2019-03-01 | 2019-05-31 | 0 | 0 | 0 | 3623 | 4740.61 | 0 | 48 | 87.5% | 12.5% | 0%
19060004 |  | 19060004 | 1 | SCL-LMC Security Camera Prep | 2019-02-01 | 2019-05-31 | 480 | 806 | 131 | 114074.67 | 115357.82 | 659 | 263 | 89.54% | 10.46% | 0%
19060017 |  | 19060017 | 1 | Mile High United Way Tenant | 2019-04-01 | 2019-05-31 | 2600 | 4774 | 0 | 188595.302 | 189569.48 | 1939.9 | 493 | 94.73% | 5.274% | 0%
19157016 |  | 19157016 | 1 | Horse Hollow Main Bearing Rep | 2019-05-21 | 2019-05-25 | 0 | 0 | 0 | 46562 | 41408.2 | 320 | 698 | 67.62% | 32.38% | 0%
19060006 |  | 19060006 | 1 | MillerCoors-Condenser Pads | 2019-01-18 | 2019-05-13 | 282 | 3 | 0 | 72800.3 | 54854.86 | 255 | 468 | 95.94% | 4.06% | 0%
19060008 |  | 19060008 | 1 | SCL-SJH Cancer Center Pharmacy | 2019-01-21 | 2019-05-01 | 0 | 23 | 60 | 11602.45 | 17612.03 | 59 | 67 | 94.03% | 5.97% | 0%
19080002 |  | 19080002 | 1 | Fiserv Forum New Signage Work | 2019-01-21 | 2019-05-01 | 0 | 399 | 0 | 2844848.48 | 2925976.3 | 255 | 244 | 85.04% | 14.96% | 0%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030005 | 31 | Target Corp - BlmngtonT-0005 | 2019-01-01 | 2019-05-01 | 0 | 3756 | 0 | 2066049.02 | 2040417.6 | 2008 | 2377 | 96.68% | 3.324% | 0%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030006 | 21 | Target Corp - CottGroveT-0062 | 2019-02-01 | 2019-05-01 | 0 | 1607 | 0 | 1299715.91 | 1323654.94 | 906 | 2176.5 | 96.67% | 3.331% | 0%
19030014 |  | 19030014 | 1 | Fairview-MB236 & MB241 | 2019-02-04 | 2019-04-30 | 0 | 1 | 0 | 22446.11 | 23268.41 | 93.5 | 88.5 | 100% | 0% | 0%
19040001 |  | 19040001 | 1 | Allstate Chandler Bldg 5 | 2019-02-01 | 2019-04-30 | 118953 | 0 | 0 | 2052182.52 | 2109691.89 | 16 | 2070 | 92.71% | 7.295% | 0%
19030011 |  | 19030011 | 1 | Allina-Cambridge USP-800 Ph | 2018-11-19 | 2019-04-12 | 950 | 0 | 0 | 465273.48 | 438167.06 | 1919 | 2242.5 | 93.71% | 6.288% | 0%
19030004 |  | 19030004 | 1 | NS VI-ThyssenKrupp TI | 2019-01-14 | 2019-04-01 | 23938 | 0 | 0 | 1153212.51 | 1091074.17 | 1169 | 1360.5 | 99.08% | 0.9188% | 0%
19030009 |  | 19030009 | 1 | ANW-Curtainwall | 2018-12-26 | 2019-03-15 | 0 | 162 | 0 | 153627 | 124661.48 | 90 | 60 | 96.67% | 3.333% | 0%
19030018 |  | 19030018 | 1 | MPR-Fitzgerald Satellite | 2019-02-01 | 2019-02-08 | 0 | 0 | 0 | 248246.7 | 248183.54 | 1491.12 | 1509.12 | 99.17% | 0.8283% | 0%
19060005 |  | 19060005 | 1 | Molson Coors-Keenesburg Energy | 2019-01-01 | 2019-02-01 | 0 | 0 | 0 | 15000 | 723.88
19030003 |  | 19030003 | 1 | Cresa Minneapolis Inc-CresaTI | 2018-12-18 | 2019-01-30 | 1500 | 0 | 0 | 57490.57 | 58670.45 | 120 | 122.67 | 100% | 0% | 0%
19090008 |  | 19090008 | 1 | AHC-AMC Sheboygan Wall Panels |  |  | 0 | 211476 | 27223 | 2849752.81 | 3198251.8 | 5076.8 | 3165.93 | 92.48% | 7.028% | 0.4896%
19090009 |  | 19090009 | 1 | Sheboygan Wall Panels Install |  |  | 0 | 36357 | 68749 | -1.1096e-10 | -2.0009e-11 | 10940.2 | 16207.5 | 96.03% | 3.97% | 0%
19090010 |  | 19090010 | 1 | RRU 134-Robbins Biorefinery |  |  | 0 | 2 | 0 | 99206 | 92121.42
19090013 |  | 19090013 | 1 | QTS - South DH Munters Install |  |  | 0 | 939 | 4 | 852998.52 | 800318.26 | 716.4 | 618 | 98.38% | 1.618% | 0%
19090016 |  | 19090016 | 1 | Ascent - Project Consulting |  |  | 0 | 0 | 0 | 171600 | 170759.62
19090018 |  | 19090018 | 1 | SAIC - 25 E Washington |  |  | 0 | 0 | 0 | 133111 | 116203.75
19090017 |  | 19090017 | 1 | Allstate - Drift |  |  | 1500 | 0 | 0 | 10644 | 8364.5 | 0 | 97 | 56.7% | 43.3% | 0%
19090019 |  | 19090019 | 1 | Lurie - Pharmacy 7-18 |  |  | 2500 | 14989.54 | 2 | 3529523 | 3326029.69 | 12548.01 | 4826.5 | 85.79% | 9.531% | 4.682%
19090006 |  | 19090006 | 1 | COD Gallery Addition |  |  | 3000 | 9253.09 | 8 | 2426682.7 | 2368572.29 | 1991.5 | 2052.18 | 96.13% | 3.484% | 0.3898%
19090005 |  | 19090005 | 1 | Mercy Riverside Misc. |  |  | 5000 | 131 | 72 | 406575.337 | 383782.71 | 586.2 | 367 | 73.57% | 17.71% | 8.719%
19090004 |  | 19090004 | 1 | Mercy Riverside MPUS |  |  | 5500 | 48241.31 | 26084 | 2037118.27 | 1982613.9 | 1256.8 | 2064.82 | 94.62% | 4.94% | 0.4359%
19090021 |  | 19090021 | 1 | Mercy Rockton - GI Suite Reno |  |  | 12381 | 35410 | 3530 | 2497110.18 | 2505412.74 | 1717.1 | 2046.81 | 85.25% | 13.14% | 1.612%
19090020 |  | 19090020 | 1 | QTS - DH2W B1 C3 |  |  | 42500 | 1717 | 2302 | 9548207.72 | 9409335.95 | 1600 | 2740.5 | 93.6% | 6.076% | 0.3284%
19090014 |  | 19090014 | 1 | MDI-Ann Arbor Campus Hotel |  |  | 85000 | 0 | 0 | 0 | 187322.42
18000014-040, 19090002, 19090012, 19090011 |  | 19090011 | 35 | Madison HGI Light Gauge Panels |  |  | 104936 | 214844.94 | 131435 | 2306347.36 | 2932267.06 | 5690.9 | 6988.48 | 93.81% | 6.146% | 0.04293%
18000014-040, 19090002, 19090012, 19090011 |  | 19090012 | 25 | HGI Light Gauge Panels Install |  |  | 104936 | 171678 | 32341 | -3.8654e-11 | 6.0027e-11 | 3679.6 | 5322.5 | 90.22% | 9.46% | 0.3194%
19090007 |  | 19090007 | 1 | Ferrero - Master Plan |  |  | 150000 | 15746.66 | 0 | 7654407.12 | 7392185.3 | 937.6 | 1144.5 | 76.71% | 18.17% | 5.111%
19090015 |  | 19090015 | 1 | PGA-Four Winds Casino & Hotel |  |  | 417771 | 240 | 0 | 5212945.88 | 5075152.99 | 477 | 2452.21 | 96.55% | 2.936% | 0.5097%
19146001, 18141021, 19148002 |  | 19148002 | 21 | Clear Creek Civil (Wind) | 2019-02-06 |  | 0 | 4391454 | 2622299 | 33188179.1627 | 42113777.16 | 111697 | 182761.21 | 73% | 27% | 0%
19146003, 19148003, 19145001 |  | 19148003 | 11 | Crane I Civil (Solar) | 2019-01-17 |  | 0 | 3571657.5 | 175626 | 4252755.05 | 4465275.6 | 8433.46 | 13635 | 79.07% | 20.93% | 0%
19148004 |  | 19148004 | 1 | Wilkinson Civil (Solar) | 2019-04-29 |  | 0 | 38432 | 14895 | 3482590.0852 | 3424152.57 | 20410 | 10501.5 | 83.16% | 16.84% | 0%
18146024, 19148005 |  | 19148005 | 11 | Bonilla Station Civil |  |  | 0 | 221 | 233235 | 2791834.76 | 2360231.11 | 5301 | 4462.5 | 73.4% | 26.6% | 0%
19146007, 19148006, 19141002 |  | 19148006 | 11 | Ida Grove II Civil (Wind) | 2019-04-01 |  | 0 | 972269.07 | 446908 | 18927419.2938 | 15542005.28 | 54907.9 | 55336.55 | 65.93% | 33.74% | 0.328%
19148007, 18145015 |  | 19148007 | 1 | Trenton Solar - Civil | 2019-05-13 |  | 0 | 343038 | 228949 | 2962056.36 | 3849081.44 | 8700 | 15684.5 | 74.01% | 25.99% | 0%
18145016, 19148008 |  | 19148008 | 11 | Columbia Civil (Solar) |  |  | 0 | 4637340.1 | 243642 | 2662128.23 | 2841052.85 | 7521.54 | 9857.5 | 70.65% | 29.35% | 0%
19146011, 19141012, 19148009 |  | 19148009 | 21 | Arbor Hill 2019 Civil (Wind) | 2019-08-01 |  | 0 | 3368353.08 | 111885 | 4986903.265 | 4630267.23 | 10299.52 | 16313.25 | 64.24% | 35.07% | 0.6927%
19145002, 19148010 |  | 19148010 | 11 | Grazing Yak Civil (Solar) |  |  | 0 | 204 | 0 | 1955558 | 2305865.8
19141015, 19148011 |  | 19148011 | 11 | Diamond Trail Civil (Wind) | 2019-08-05 |  | 0 | 1383924.84 | 1264255 | 18281953.5865 | 15978016.44 | 62591.93 | 56563.25 | 71.54% | 28.35% | 0.1149%
19148012, 19146015, 19141011 |  | 19148012 | 1 | Cheyenne Ridge Civil (Wind) | 2019-05-15 |  | 0 | 21109936 | 2277818 | 23474911.49 | 22207298.18 | 75085.97 | 85991.3 | 77.99% | 22.01% | 0%
19146006, 19141003, 19148013 |  | 19148013 | 21 | El Campo Civil (Wind) |  |  | 0 | 4249894.62 | 588432 | 9444392.03 | 9720547.16 | 25019.89 | 34301 | 83.72% | 16.28% | 0%
19148014 |  | 19148014 | 1 | Walnut Repower Civil (Wind) |  |  | 0 | 18 | 332 | 2892275.6762 | 2620479.13 | 8781.5 | 10596.5 | 71.56% | 27.84% | 0.604%
19146010, 19141010, 19148015 |  | 19148015 | 21 | Nobles 2 Civil (Wind) |  |  | 0 | 8637346.4 | 427473 | 17304386.3863 | 16660011.6 | 51795.66 | 52665.5 | 73.29% | 26.22% | 0.4937%
19141009, 19148016 |  | 19148016 | 11 | Bitter Ridge Civil (Wind) |  |  | 0 | 11162343.5 | 384947 | 8400240.08 | 9279446.39 | 24062.36 | 32396 | 71.69% | 27.66% | 0.6482%
19141013, 19146012, 19148017 |  | 19148017 | 21 | King Plains Civil (Wind) |  |  | 0 | 10888027.5 | 848653 | 14437586.78 | 15316114.49 | 49066.96 | 63163.5 | 78.27% | 21.7% | 0.03008%
18146023, 19148018 |  | 19148018 | 11 | Grissom Substation (HVT) |  |  | 0 | 1802226.29 | 80903 | 2592359.9 | 1894648.1 | 4597.38 | 3629.5 | 76.61% | 23.39% | 0%
19146009, 19141004, 19148019, 19146022, 19141022 |  | 19148019 | 21 | North Fork Ridge Civil (Wind) |  |  | 0 | 8210413.73 | 762585 | 15784736.3823 | 15801231.22 | 309803.17 | 59101 | 75.3% | 24.7% | 0%
19146008, 19141005, 19148020, 19146023, 19141024 |  | 19148020 | 21 | Kings Point Civil (Wind) |  |  | 0 | 8532717.01 | 823078 | 21588398.95 | 23413752.64 | 38771.59 | 75690.5 | 76.36% | 23.64% | 0%
19148021, 19141027 |  | 19148021 | 1 | White Hills Civil (Wind) |  |  | 0 | 21890510.48 | 2247818 | 27405427.8275 | 24318731.28 | 96819.04 | 87808.5 | 75.62% | 24.38% | 0%
19148022, 19141023 |  | 19148022 | 1 | Pryor Mountain Civil (Wind) |  |  | 0 | 13458843 | 778195 | 13599567.9588 | 10654932.28 | 41765.19 | 35023 | 82.58% | 17.42% | 0%
19141017, 19148023, 19146019 |  | 19148023 | 11 | Prairie Hill Civil (Wind) |  |  | 0 | 16746899.12 | 671061 | 21318623.6099 | 19444651.66 | 74529.58 | 80578.56 | 80.44% | 19.56% | 0%
19145008, 19148024, 19146021 |  | 19148024 | 11 | Greasewood Civil (Solar) |  |  | 0 | 5489583.55 | 288275 | 6009647.83 | 5960952.76 | 22185.37 | 17485.5 | 78.91% | 21.09% | 0%
17141026, 18146020, 19148025 |  | 19148025 | 21 | Blazing Star II Civil (Wind) |  |  | 0 | 9426201 | 990054 | 16668060.55 | 17159729.9 | 50183.39 | 61737.1 | 75.46% | 24.42% | 0.1182%
19126001 |  | 19126001 | 1 | Facebook EAG 3 |  |  | 450000 | 1558763 | 465739.4 | 371701186.5858 | 343485684.59 | 226102.38 | 202813.27 | 83.51% | 16.49% | 0.002465%
19060033 |  | 19060033 | 1 | City of CO Spg-Garden of Gods | 2019-06-01 |  | 0 | 680666 | 538230 | 7678608.05 | 9922862.33 | 30212 | 33318.25 | 73.36% | 26.64% | 0%
19060036 |  | 19060036 | 1 | MillerCoors-CBU Floor Penetrat | 2019-05-28 |  | 0 | 680 | 1698 | 379634.9519 | 363623.85 | 2431 | 2033 | 88.34% | 11.66% | 0%
19060039 |  | 19060039 | 1 | Charles Schwab P3 Parking |  |  | 0 | 0 | 0 | 993427.08 | 1006897.9
19060040 |  | 19060040 | 1 | SCL-SJB Exhaust Fans |  |  | 0 | 0 | 0 | 288787.56 | 292278.41
19060041 |  | 19060041 | 1 | SCL-SJB Laundry HVAC Upgrades |  |  | 0 | 0 | 0 | 1250487.21 | 1203634.48
19060042 |  | 19060042 | 1 | SCL-SJB Window Repl/Bldg Envel |  |  | 0 | 0 | 0 | 258288.13 | 218163.75
19060043 |  | 19060043 | 1 | SCL-SJB MPOP/CPOP Upgrades |  |  | 0 | 0 | 0 | 1056671.35 | 1052695.36
19060044 |  | 19060044 | 1 | SCL-SJB Life Safety Deficiency |  |  | 0 | 0 | 0 | 449931 | 434233.29 | 0 | 0 | 0% | 0% | 0%
19000004-040, 19060011, 19060050 |  | 19060050 | 25 | NJH-Non MDI COH |  |  | 0 | 0 | 212 | 682334 | 553999.53 | 0 | 926.5 | 66.32% | 33.68% | 0%
19060052 |  | 19060052 | 1 | SCL-SJH MPOP UPS |  |  | 0 | 7634.3 | 48 | 194753.43 | 195313.34 | 547.3 | 837 | 91.76% | 8.244% | 0%
19060057 |  | 19060057 | 1 | Park Creek-Filing 59 |  |  | 0 | 150 | 0 | 196358 | 224627.26 | 190 | 1005.5 | 96.92% | 3.083% | 0%
19060058 |  | 19060058 | 1 | Stadium Mgmt-Light Pole Work |  |  | 0 | 0 | 0 | 155451 | 136983.91 | 0 | 0 | 0% | 0% | 0%
19060059 |  | 19060059 | 1 | MillerCoors RMCC Bldg 33 Concr |  |  | 0 | 16 | 897 | 117912 | 104174.05 | 1068 | 991.5 | 86.74% | 13.26% | 0%
19060034 |  | 19060034 | 1 | SCL-LMC Sewer Line Repl |  |  | 100 | 726 | 38 | 47971.89 | 55450.63 | 386 | 915 | 93.83% | 6.175% | 0%
19060051 |  | 19060051 | 1 | SCL-LMC CT Equipment |  |  | 336 | 571 | 0 | 87336.73 | 87174.88 | 284 | 11.5 | 100% | 0% | 0%
19060070 |  | 19060070 | 1 | SCL SJH SPD Sonic Irrigator |  |  | 500 | 20 | 29 | 44534.96 | 45402.4 | 14 | 446.5 | 94.4% | 5.599% | 0%
19060071 |  | 19060071 | 1 | SCL-SJH Pharmacy Workstations |  |  | 500 | 415.4 | 3 | 7377.48 | 8906.69 | 108 | 135.5 | 80.81% | 19.19% | 0%
19060028 |  | 19060028 | 1 | NJH-NucMed Spect/CT Repl |  |  | 504 | 645 | 485 | 139267 | 137480.09 | 496 | 580 | 83.19% | 16.81% | 0%
19060062 |  | 19060062 | 1 | Lockheed Martin-ADM Restrm |  |  | 550 | 1186.2 | 0 | 188217.95 | 195479.25 | 577.2 | 681.5 | 92.44% | 7.557% | 0%
19060060 |  | 19060060 | 1 | SCL-SJH Mammography Reno |  |  | 600 | 40 | 0 | 10084.04 | 11550 | 24 | 11 | 81.82% | 18.18% | 0%
19060021 |  | 19060021 | 1 | NJH-Boiler Replacement |  |  | 676 | 208 | 966 | 545405.22 | 534210.78 | 1093 | 1144 | 89.25% | 10.75% | 0%
19060064 |  | 19060064 | 1 | NJH Tunnel Washer |  |  | 1000 | 518 | 316 | 107239 | 107688.91 | 469 | 377 | 70.03% | 29.97% | 0%
19060037 |  | 19060037 | 1 | SCL-SJH LinAcc Remodel | 2019-06-11 |  | 1240 | 10344.5 | 733 | 1119652.13 | 1143292.4 | 3602.9 | 4558 | 82.62% | 17.38% | 0%
19060045 |  | 19060045 | 1 | SCL SJH Spec CT Replacement |  |  | 1240 | 6374.75 | 197 | 645233.33 | 647319.16 | 1962.25 | 2495 | 80.26% | 19.74% | 0%
19060049 |  | 19060049 | 1 | SCL-MG Wellmore Decommiss |  |  | 1240 | 0 | 17 | 31708.98 | 29552.42 | 90 | 62.5 | 84.8% | 15.2% | 0%
19060066 |  | 19060066 | 1 | NJH - USP800 |  |  | 1500 | 102 | 8 | 163741.01 | 158065.27 | 250 | 223.5 | 74.94% | 25.06% | 0%
19060047 |  | 19060047 | 1 | Lockheed-FAC Chem Lab |  |  | 2964 | 14104 | 0 | 7378488.554 | 7798534.7 | 2692.7 | 6669.5 | 87.52% | 12.48% | 0%
19060067 |  | 19060067 | 1 | SCL-LMC Temp Conference Space |  |  | 4500 | 1643 | 0 | 263938.35 | 271346.75 | 294 | 297 | 96.63% | 3.367% | 0%
19060054 |  | 19060054 | 1 | Childrens Hospital-Tejon UC |  |  | 10000 | 18 | 0 | 630303.94 | 722041.46 | 0 | 382.5 | 96.86% | 3.137% | 0%
19060053 |  | 19060053 | 1 | Childrens Hosp-Briargate MOB |  |  | 12000 | 19270.9 | 813.01 | 2872294.45 | 3035264.14 | 3434.4 | 5341 | 86.79% | 13.21% | 0%
19060046 |  | 19060046 | 1 | Dominican Friars-St Dominic |  |  | 24761 | 83036.51 | 33978 | 6724028.6001 | 7057229.1 | 7715 | 13973.75 | 93.33% | 6.668% | 0%
19060068 |  | 19060068 | 1 | FireFly-Hoyt School Renova |  |  | 30000 | 87525.86 | 68225 | 2344338.0664 | 2235089.69 | 2546.23 | 5471 | 92.33% | 7.668% | 0%
19060055 |  | 19060055 | 1 | Children's Hosp-Telstar MOB |  |  | 30001 | 7 | 0 | 35811.53 | 87131.89
19060065 |  | 19060065 | 1 | Clayton ELC Bldg 3506 Office |  |  | 35000 | 20486.98 | 8745 | 447251.4 | 453264.77 | 681.76 | 785 | 98.22% | 1.783% | 0%
19060063 |  | 19060063 | 1 | Stoltz-Denver Renovations |  |  | 37945 | 42205.76 | 32930 | 1359904.93 | 1371069.51 | 1347.37 | 3804.5 | 96.89% | 3.115% | 0%
19060035 |  | 19060035 | 1 | MIC-Buckley AFB Doc Dest Fac | 2019-06-03 |  | 50000 | 45194.23 | 6095 | 408984.1836 | 592613.79 | 1992.6 | 6347.25 | 90.46% | 9.536% | 0%
19060061 |  | 19060061 | 1 | WelArm-EG Glenarm Retail |  |  | 50000 | 274 | 20 | 3746503.24 | 3779296.61 | 141 | 506 | 91.8% | 8.202% | 0%
19060032 |  | 19060032 | 1 | MDI-Bio3 Parking Garage | 2019-05-13 |  | 153000 | 805066.67 | 504514 | 9328049.1802 | 9525803.24 | 31067.3 | 39861.5 | 90.6% | 9.399% | 0%
19060072 |  | 19060072 | 1 | Wiens-8383 Arista Place |  |  | 194000 | 0 | 0 | 117753 | 107949.02
19060048 |  | 19060048 | 1 | 76 Commerce Bldg 4 |  |  | 352240 | 413792.08 | 274634 | 23041045.9973 | 21329306.63 | 10977.74 | 15396 | 92.17% | 7.833% | 0%
19060069 |  | 19060069 | 1 | Wewatta-Dwntwn Denver Marriott |  |  | 433858 | 3008 | 0 | 505079.7 | 543292.25 | 0 | 129.5 | 100% | 0% | 0%
19060056 |  | 19060056 | 1 | 76 Commerce Bldg 3 |  |  | 526400 | 407978.68 | 385712 | 27867060.6733 | 25199542.43 | 18696.82 | 21154.5 | 84.04% | 15.96% | 0%
19110010 |  | 19110010 | 1 | ECB Elevator Inspection |  |  | 0 | 31 | 0 | 559684.13 | 539831.79 | 720 | 499 | 96.19% | 3.808% | 0%
19110012 |  | 19110012 | 1 | 21ST BDE HEMP - VA |  |  | 0 | 0 | 0 | 534882.45 | 533882.49
19110013 |  | 19110013 | 1 | 21ST BDE HEMP - PA |  |  | 0 | 0 | 0 | 476396 | 474224.18
19110014 |  | 19110014 | 1 | 21ST BDE HEMP - MD |  |  | 0 | 0 | 0 | 175944 | 175192.86
19110006 |  | 19110006 | 1 | UDC Turtle Power |  |  | 1000 | 0 | 0 | 29756 | 25057.29
19110008 |  | 19110008 | 1 | UDC HVAC Replacements |  |  | 1000 | 0 | 0 | 1695708.01 | 1713953.87
19110002 |  | 19110002 | 1 | UDC Mystic Potions 3 | 2019-01-22 |  | 2000 | 0 | 0 | 480502.98 | 476462.67
19110015 |  | 19110015 | 1 | UDC Typhoon Vortex |  |  | 2000 | 0 | 0 | 30740 | 30685.87
19110007 |  | 19110007 | 1 | Sugar Grove Research Station |  |  | 3200 | 0 | 0 | 9533937.67 | 8969127.07 | 0 | 6562.8 | 96.52% | 3.482% | 0%
19110016 |  | 19110016 | 1 | UDC Silvermind |  |  | 4000 | 0 | 0 | 2088584.92 | 2090174.68
19110009 |  | 19110009 | 1 | Bldg 3245 Cages |  |  | 8000 | 1069 | 0 | 1712771.19 | 1715331.6
19110011 |  | 19110011 | 1 | BAO Bldg 13 Renovation |  |  | 8820 | 0 | 0 | 1519681.85 | 1552119.32
19110005 |  | 19110005 | 1 | Chiller Plant Building 9706 |  |  | 13800 | 0 | 0 | 11647008.7092 | 11323043.26 | 0 | 204.38 | 100% | 0% | 0%
19110004 |  | 19110004 | 1 | SAB4 Renovation | 2019-07-23 |  | 19667 | 0 | 0 | 6368367.24 | 6163361.79
19150002-LOW |  | 19150002-LOW | 1 | St Louis MLS - SPW Low Voltage |  |  | 0 | 0 | 0 | 19543600 | 0
19150002-ETH |  | 19150002-ETH | 1 | St Louis MLS - SPW Earthwork |  |  | 0 | 0 | 0 | 72185058 | 0
19150002-STE |  | 19150002-STE | 1 | St Louis MLS - SPW Steel |  |  | 0 | 0 | 0 | 58633641 | 0
19080005 |  | 19080005 | 1 | 2019 Master Agmt Fiserv Forum | 2019-04-24 |  | 0 | -629 | 0 | 134814 | 133707.23 | 222 | 284 | 99.65% | 0.3521% | 0%
19080013 |  | 19080013 | 1 | AAH Misc Jobs 2019-2020 |  |  | 500 | 139 | 0 | 543664 | 474232.58 | 889 | 1050.5 | 87.39% | 12.61% | 0%
19080007 |  | 19080007 | 1 | Intel 360 Cameras |  |  | 3000 | 0 | 0 | 780332.76 | 752558.71 | 336 | 320.5 | 97.82% | 2.184% | 0%
19080014 |  | 19080014 | 1 | AHC Grafton Medical Obs |  |  | 6060 | 14731.43 | 5459 | 665251.35 | 655560.2 | 1364.4 | 1616.96 | 87.88% | 11.26% | 0.8658%
19080001 |  | 19080001 | 1 | Froedtert - Loading Dock Reno | 2019-08-19 |  | 11500 | 59108.29 | 29143 | 2411723.6 | 2442581.47 | 4503.7 | 5281 | 91.92% | 7.697% | 0.3787%
19080012 |  | 19080012 | 1 | Fii HPC DC |  |  | 28000 | 379095.06 | 201052 | 30104819.1441 | 28841788.63 | 25501.13 | 22997.89 | 92.44% | 7.226% | 0.3305%
19080006 |  | 19080006 | 1 | WEC - Master Planning |  |  | 30000 | 798 | 0 | 389652.51 | 432638.98
19080011 |  | 19080011 | 1 | NM Data Center Mod |  |  | 31600 | 116775.18 | 4461 | 25850702.64 | 24448211.59 | 7086.7 | 5946.44 | 94.24% | 5.608% | 0.1514%
19080008 |  | 19080008 | 1 | UHS/West Allis - Psych Hosp. |  |  | 78000 | 932338.65 | 480130 | 33721466.0641 | 33553251.03 | 31572.55 | 37454.76 | 94.71% | 5.221% | 0.07342%
19080009 |  | 19080009 | 1 | Fii SMC |  |  | 290023 | 272800.48 | 84647 | 54236408.285 | 50134415.87 | 22824.2 | 18407.32 | 93.01% | 6.962% | 0.0326%
19080010 |  | 19080010 | 1 | UW Health ECD |  |  | 440000 | 1754202.8 | 0 | 22381147.4609 | 7482637.39 | 51528.25 | 6140.75 | 92.86% | 7.137% | 0%
19080010-142 |  | 19080010-142 | 1 | UW Health ECD-JV |  |  | 440000 | 3257817.75 | 0 | 247499802.01 | 54945585.08 | 179963.65 | 34311.75 | 93.14% | 6.86% | 0%
19030020 |  | 19030020 | 1 | Fairview-M246 2FL Pharm Mech |  |  | 0 | 1 | 0 | 580589.39 | 570438.74 | 1008 | 972.25 | 97.81% | 2.186% | 0%
19030032 |  | 19030032 | 1 | Colwell Partners -Glenwd Site |  |  | 0 | 1685.44 | 7744 | 154428.93 | 198867.86 | 1057 | 1480 | 98.89% | 1.115% | 0%
19030033 |  | 19030033 | 1 | 30 Group - YMCA Demolition |  |  | 0 | 5936.3 | 46463 | 2375901.465 | 2599923.32 | 8021.85 | 20326.5 | 97.24% | 2.755% | 0%
18030003, 19030044 |  | 19030044 | 11 | City of Mpls - NPSB Carpentry |  |  | 0 | 162516.5 | 71645 | 6114883.93 | 6212186.02 | 27906.8 | 19935 | 96.95% | 3.055% | 0%
19030054 |  | 19030054 | 1 | FUMC -UMMC WB EB M2722 Rad RM3 |  |  | 0 | 0 | 0 | 79746.31 | 80222.53 | 0 | 197 | 99.75% | 0.2538% | 0%
19030055 |  | 19030055 | 1 | MAM - Kimball Misc 2019 |  |  | 0 | 0 | 0 | 0.01 | 1727.08
19030056 |  | 19030056 | 1 | WFPS - Heritage MS Consultant |  |  | 0 | 0 | 0 | 9858 | 7910.64
19030062 |  | 19030062 | 1 | Transamerica 6910 Bollard Proj |  |  | 0 | 0 | 0 | 142152.87 | 112400.96 | 348 | 126 | 100% | 0% | 0%
19030063 |  | 19030063 | 1 | Target Field Scoreboard 2.0 DP |  |  | 0 | 13194 | 0 | 25268403.42 | 15722369.4 | 3796 | 3315 | 99.88% | 0.1207% | 0%
19030064 |  | 19030064 | 1 | FUMC -UMMC Unit-J Nurse Call |  |  | 0 | 3 | 0 | 163426.34 | 137844.43 | 6662 | 516 | 94.96% | 5.039% | 0%
19030066 |  | 19030066 | 1 | Fairview-WB InPatient PhrmM246 |  |  | 0 | 199 | 0 | 51803.62 | 49823.46 | 199 | 175.5 | 82.91% | 10.26% | 6.838%
19030067 |  | 19030067 | 1 | Fairview -1 FL Bridging Clinic |  |  | 0 | 0 | 0 | 174525.475 | 187272.2 | 473.5 | 469 | 99.68% | 0.3198% | 0%
19030068 |  | 19030068 | 1 | Fairview -WB Lact MB106 & F190 |  |  | 0 | 0 | 0 | 15421.11 | 14807.12 | 0 | 58 | 100% | 0% | 0%
1999 |  | 1999 | 1 | MORTENSON-CLOSED JOBMINNEAPOL | 2000-12-31 |  | 0 | 0 | 0 | 0 | 327608 | 0 | 1118 | 100% | 0% | 0%
19030051 |  | 19030051 | 1 | ANW - ETO Sterilizer Replcmnt |  |  | 150 | -171 | 0 | 263845.4 | 227920.29 | 760 | 529.1 | 71.65% | 28.35% | 0%
19030065 |  | 19030065 | 1 | St. Davids -Wall Removal et al |  |  | 400 | 81.3 | 0 | 16010.97 | 23402.08 | 3.5 | 205.5 | 99.76% | 0.2433% | 0%
19030043 |  | 19030043 | 1 | SCCR - Site Concrete Repair |  |  | 450 | 100 | 0 | 12264 | 10163.94 | 96 | 87 | 65.52% | 34.48% | 0%
19030045 |  | 19030045 | 1 | CentraCare - Master Ag 2019 |  |  | 896 | 0 | 0 | 228629.01 | 189786.27 | 712 | 633.51 | 96.05% | 3.946% | 0%
19030030 |  | 19030030 | 1 | Fairview - SBldg PICULight3123 |  |  | 1000 | 0 | 0 | 5144.07 | 2555.54 | 0 | 2 | 100% | 0% | 0%
19030060 |  | 19030060 | 1 | Westminster - WPC Bells Tower |  |  | 1000 | 13917.75 | 0 | 338244.75 | 363611.97 | 279 | 444.5 | 88.75% | 5.849% | 5.399%
19030025 |  | 19030025 | 1 | ANW Imaging Prep and Recovery | 2019-04-08 |  | 1489 | 12866.73 | 0 | 626547.91 | 594479.42 | 1792 | 2011.91 | 94.68% | 4.97% | 0.3479%
19030036 |  | 19030036 | 1 | Blake Black Box Restoration |  |  | 2682 | 2331.5 | 0 | 787037.48 | 806418.83 | 1606 | 2580.12 | 98.26% | 1.744% | 0%
19030042 |  | 19030042 | 1 | ES - Suite240 TI - Disc Sq |  |  | 2885 | 2700 | 0 | 773327.59 | 642898.62 | 228 | -2258.56 | 100% | 0% | 0%
19030049 |  | 19030049 | 1 | Fairview - M-Health MG LINAC |  |  | 3000 | 447 | 0 | 860803.8 | 851608.72 | 1555 | 1805.5 | 78.7% | 21.3% | 0%
19030057 |  | 19030057 | 1 | Graco Koch PO Work |  |  | 3600 | 0 | 143 | 270725.01 | 215908.15 | 752 | 277.5 | 92.79% | 7.207% | 0%
19030059 |  | 19030059 | 1 | Target Field 2020 Improvements |  |  | 4300 | 95 | 0 | 656000.81 | 669274.32 | 1939 | 2418 | 99.71% | 0.2895% | 0%
19030052 |  | 19030052 | 1 | Fairview-MHealthWB EB 1.5T MRI |  |  | 4371 | 19535.81 | 0 | 1328799.34 | 1313217.8 | 1918.4 | 2076 | 86.73% | 11.68% | 1.59%
19030069 |  | 19030069 | 1 | Fairview - UMH FV E 11FL NICU |  |  | 4531 | 24789 | 0 | 1200437.96 | 1179091.57 | 2101 | 2467.5 | 96.09% | 3.911% | 0%
19030034 |  | 19030034 | 1 | Fairview - L4&5 B2512 Nurse |  |  | 5000 | 0 | 0 | 310282.82 | 284135.24 | 1178 | 1072 | 99.58% | 0.4198% | 0%
19030048 |  | 19030048 | 1 | Nura PA - Edina 7400 Remodel |  |  | 7600 | 26 | 1367 | 2577737.29 | 2522789.04 | 3431 | 2923.5 | 97.9% | 2.104% | 0%
19030041 |  | 19030041 | 1 | UGC - McNamara Alumni TO |  |  | 8000 | 57442 | 24500 | 1436814.4 | 1203465.54 | 5739 | 3875.5 | 96.84% | 3.161% | 0%
19030058 |  | 19030058 | 1 | ANW - TAF 3FL HIM Renovation |  |  | 9000 | 49 | 0 | 475310.57 | 433110.94 | 714 | 792.3 | 97.79% | 2.209% | 0%
19030035 |  | 19030035 | 1 | UMN Moos 2FL CancerCtr Lab Exp |  |  | 12000 | 37271.98 | 538 | 2563800.62 | 2676798.78 | 1745.8 | 1807.5 | 99.06% | 0.9405% | 0%
19030037 |  | 19030037 | 1 | Axalta Coatings Expansion |  |  | 15000 | 0 | 0 | 1835650.57 | 1689610.63 | 1299 | 946 | 95.93% | 4.07% | 0%
19030050 |  | 19030050 | 1 | Fabcon - Roof Repair & Modif |  |  | 15500 | 11610 | 2 | 1940696.9956 | 1816438.99 | 2730 | 6404.25 | 84.76% | 11.24% | 3.997%
19030061 |  | 19030061 | 1 | NS VII - Laird Plastics TI |  |  | 25475 | 0 | 0 | 824534.07 | 710092.68 | 769 | 629.5 | 94.6% | 5.401% | 0%
19030019 |  | 19030019 | 1 | Marvin Windows Corp Office Ren | 2019-03-25 |  | 30000 | 465679.69 | 255850 | 29126742.19 | 23708234.37 | 46461.6 | 37041.5 | 76.22% | 23.7% | 0.08369%
19030046 |  | 19030046 | 1 | NS V - Heraeus Medical TI |  |  | 62257 | 0 | 0 | 3865381.46 | 3901247.53 | 4393 | 3205 | 94.4% | 5.351% | 0.2496%
19030053 |  | 19030053 | 1 | Ramsey - Vadnais Sports Turf |  |  | 80000 | 140914.33 | 18252 | 7816003.71 | 7816377.5 | 3763.5 | -4472.5 | 101.1% | -1.118% | 0%
19030031 |  | 19030031 | 1 | Sanford - Ortho Clinic Relo |  |  | 81685 | 166138.73 | 162096 | 18068311.0773 | 18541618.88 | 13610.46 | 18975.03 | 93.84% | 5.731% | 0.4242%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030038 | 61 | Target Corp - VadnaisHtsT0751 |  |  | 110000 | 6 | 0 | 1634116.3 | 1624918.81 | 1120 | 1277.5 | 92.72% | 7.28% | 0%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030039 | 51 | Target Corp - HutchinsonT1210 |  |  | 110000 | 6 | 0 | 1283459.59 | 1260574.12 | 1120 | 1280 | 90.94% | 9.062% | 0%
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 |  | 19030040 | 41 | Target Corp - Carson CityT1239 |  |  | 110000 | 178 | 0 | 1421806 | 1492455.54 | 800 | 1375 | 96% | 4% | 0%
19030047 |  | 19030047 | 1 | BSC - Bldg 2 East Expansion |  |  | 110000 | 840474.7 | 486589 | 41771089.0525 | 42837255.71 | 36681.16 | 39465.5 | 85.62% | 13.42% | 0.9641%
19157001 |  | 19157001 | 1 | GE 2019 MSA MCE |  |  | 0 | 0 | 0 | 2.08 | 7991830.8 | 0 | 201574.6 | 73.35% | 26.62% | 0.02952%
19157002 |  | 19157002 | 1 | GE 2019 MCE MSA LS |  |  | 0 | 0 | 0 | 0.01 | 2660552.33 | 0 | 53580.5 | 69.22% | 30.78% | 0%
19157003 |  | 19157003 | 1 | GE Gen Alignment LS |  |  | 0 | 0 | 0 | 0 | 168095.29 | 0 | 1681 | 88.99% | 11.01% | 0%
19157004 |  | 19157004 | 1 | GE Mech/Electrical CP |  |  | 0 | 0 | 0 | 0.03 | 5099160.71 | 0 | 115202.5 | 74.81% | 25.19% | 0%
19157005 |  | 19157005 | 1 | GE Blades 2019 CP |  |  | 0 | 0 | 0 | 0.04 | 2962229.83 | 0 | 68787.52 | 84.99% | 15.01% | 0%
19157006 |  | 19157006 | 1 | GE Blades 2019 LS |  |  | 0 | 0 | 0 | 57637.01 | 24483.74 | 272 | 273 | 87.91% | 12.09% | 0%
19157007 |  | 19157007 | 1 | Mortenson Repower |  |  | 0 | 0 | 0 | 0.02 | 614524.73 | 0 | 13468 | 75.74% | 23.93% | 0.3267%
19157008 |  | 19157008 | 1 | FPL No Co Pitch Cylinder RE |  |  | 0 | 0 | 0 | 0 | 20953.12 | 0 | 262.5 | 62.1% | 37.9% | 0%
19157009 |  | 19157009 | 1 | BLUEarth A&D Wind Farm 2019 |  |  | 0 | 0 | 0 | 0 | 18226.43 | 0 | 530.5 | 72.67% | 27.33% | 0%
19157010 |  | 19157010 | 1 | Ewington Due Diligence Walk D |  |  | 0 | 0 | 0 | 0 | 9369.28 | 0 | 182 | 92.31% | 7.692% | 0%
19157011 |  | 19157011 | 1 | Nextera-No Co Main Shaft Rep |  |  | 0 | 0 | 0 | 0 | 74537.97 | 0 | 704.5 | 63.59% | 36.41% | 0%
19157012 |  | 19157012 | 1 | GE Casa Mesa Wind Demolition | 2019-04-15 |  | 0 | 0 | 0 | 433132.0001 | 246774.49 | 2043 | 1377 | 69.86% | 30.14% | 0%
19157013 |  | 19157013 | 1 | Rim Rock Wind Farm Decomm |  |  | 0 | 0 | 0 | 0 | 75334.56 | 0 | 835 | 61.8% | 38.2% | 0%
19157014 |  | 19157014 | 1 | OG&E MISC SERVICES |  |  | 0 | 0 | 0 | 0.02 | 545867.54 | 0 | 9657 | 72.9% | 27.1% | 0%
19157015 |  | 19157015 | 1 | Geronimo Nordic 1 SWPPP Mon |  |  | 0 | 0 | 0 | 0.01 | 42347.7 | 0 | 317.5 | 88.35% | 11.65% | 0%
19157017 |  | 19157017 | 1 | Chisolm View II Wind Farm Demo |  |  | 0 | 0 | 0 | 377875 | 233003.86 | 1320 | 1461.5 | 69.14% | 30.86% | 0%
19157018 |  | 19157018 | 1 | GE Garden City Hub Stiffeners |  |  | 0 | 267 | 0 | 688095.02 | 705412.53 | 4145 | 7516.5 | 64.08% | 34.2% | 1.716%
19157019 |  | 19157019 | 1 | Sungrow Commissioning Support |  |  | 0 | 0 | 0 | 0.02 | 308799.81 | 0 | 6458 | 86.24% | 13.76% | 0%
19157020 |  | 19157020 | 1 | GE Upstream T-57 Tower Demo |  |  | 0 | 0 | 0 | 374529 | 211178.28 | 1320 | 1806.5 | 64.82% | 35.18% | 0%
19157021 |  | 19157021 | 1 | Stockyard Due Diligence Inspec |  |  | 0 | 0 | 0 | 0.01 | 34183.95 | 0 | 501 | 79.54% | 20.46% | 0%
19157022 |  | 19157022 | 1 | GE Bolt Tensioning LS |  |  | 0 | 180 | 0 | 243336 | 280097.87 | 1920 | 5313 | 80.68% | 19.32% | 0%
19157997 |  | 19157997 | 1 | Direct Overhead SC |  |  | 0 | 0 | 0 | 0.05 | 21723481.54 | 0 | 109617.92 | 93.93% | 6.072% | 0%
19156001 |  | 19156001 | 1 | Engineering Svs Direct Costs |  |  | 0 | 0 | 0 | 42.78 | 15465646.54
19040003 |  | 19040003 | 1 | Chandler Office Remodel | 2019-01-14 |  | 0 | 0 | 0 | 0 | 0
19040011, 19000009-040, 19040008 |  | 19040011 | 1 | MDI - Hyatt DT - FFE |  |  | 0 | 0 | 0 | 4140860.49 | 4118145.06
19040015 |  | 19040015 | 1 | SRF Patio Bars |  |  | 0 | 9376.35 | 9204 | 169215.44 | 191138.5 | 495.34 | 804.5 | 75.08% | 24.92% | 0%
19040010 |  | 19040010 | 1 | White Sox Expansion |  |  | 9132 | 51744 | 28065 | 3012194.3 | 2951514.39 | 378 | 469.5 | 94.68% | 5.325% | 0%
19040013 |  | 19040013 | 1 | Clarence Wesley Health Center |  |  | 19325 | 0 | 0 | 19337.28 | 23241.98 | 0 | 35 | 0% | 100% | 0%
19040014 |  | 19040014 | 1 | Allstate InfoArmor 2 |  |  | 24000 | 132338 | 132323 | 290311.7 | 290311.7 | 1649.9 | 1031 | 84.48% | 15.52% | 0%
19040009 |  | 19040009 | 1 | Allstate - InfoArmor TI |  |  | 36805 | 39277 | 0 | 4780233.33 | 4483800.27 | 252.7 | 2734.5 | 76.91% | 23.09% | 0%
19040005 |  | 19040005 | 1 | Alaska USA GDC TI | 2019-05-13 |  | 60000 | 15134 | 0 | 675373.22 | 676989.95 | 325 | 198 | 56.57% | 43.43% | 0%
19040011, 19000009-040, 19040008 |  | 19040008 | 25 | MDI Hyatt Place - Downtn PHX |  |  | 111885 | 411681 | 0 | 38511301.04 | 37409173.78 | 7402.7 | 9248.5 | 92.18% | 7.817% | 0%
19040012 |  | 19040012 | 1 | SRP ISB Modernization Precon |  |  | 303902 | 0 | 0 | 101391.28 | 51871.39
19055001, 19040007 |  | 19040007 | 11 | Nike - Project 40 |  |  | 900000 | 317062.18 | 140956 | 47303012.5277 | 46727128.65 | 32102.32 | 33376 | 96.94% | 3.056% | 0%
19055003 |  | 19055003 | 1 | Mortenson Portland 2nd Flr Exp |  |  | 0 | 0 | 1 | 0.01 | -1.819e-11 | 0 | 1258.5 | 92.65% | 6.397% | 0.9535%
19055004 |  | 19055004 | 1 | OHSU Tram Laser Scanning |  |  | 0 | 0 | 0 | 15550.28 | 27085.81
19055005 |  | 19055005 | 1 | OHSU Building ReAddressing |  |  | 0 | 0 | 0 | 8478.2 | 26433.69
19055006 |  | 19055006 | 1 | OHSU Tuality Block 67 TI |  |  | 0 | 0 | 0 | 9677.63 | 37206.59
19055007 |  | 19055007 | 1 | OHSU Modular Bldg/Assoc Moves |  |  | 0 | 0 | 0 | 14025.08 | 19965.18
19055008 |  | 19055008 | 1 | Kaiser SST Boiler Replacement |  |  | 0 | 7 | 0 | 38862.7068 | 30814.83
19055012 |  | 19055012 | 1 | Adventist Mill Plain Sign |  |  | 0 | 0 | 0 | 8101.13 | 7733.51
19055014 |  | 19055014 | 1 | Everett Hotel 14th & Everett |  |  | 0 | 0 | 0 | 0.01 | 99724.76
19055015 |  | 19055015 | 1 | PAM Ceiling Emergency |  |  | 0 | 10 | 1917 | 989464.84 | 1000865.51 | 1312 | 1726.07 | 98.96% | 1.043% | 0%
19055016 |  | 19055016 | 1 | Metro Schnitzer Concert Hall |  |  | 0 | 66119.54 | 20740 | 7126171.0652 | 7125196.57 | 3135.7 | 4444.22 | 99.71% | 0.2925% | 0%
19055021 |  | 19055021 | 1 | Prosper - OCC Off Exp |  |  | 0 | 25 | 0 | 1434196.01 | 1282385.57
19055022 |  | 19055022 | 1 | OHSU KPV-6 Controls |  |  | 0 | 0 | 0 | 0.01 | 0
19055023 |  | 19055023 | 1 | OHSU Tuality Forest Grove TI |  |  | 0 | 10 | 0 | 2482.32 | 179.99
19055025 |  | 19055025 | 1 | LOSD Hallinan Elementary |  |  | 0 | 0 | 0 | 65000 | 75001.66 | 0 | 64 | 100% | 0% | 0%
19055027 |  | 19055027 | 1 | JLL Fac Direct Small Works |  |  | 0 | 1 | 3 | 12391 | 9730.81 | 86 | 79.5 | 85.53% | 14.47% | 0%
19055028 |  | 19055028 | 1 | OHSU CCSR Study |  |  | 0 | 0 | 0 | 5683.64 | 8390.76
19055011 |  | 19055011 | 1 | Kaiser WMC TJC OR |  |  | 500 | 13 | 0 | 18630.335 | 17407.17 | 83.5 | 80 | 75% | 25% | 0%
19055024 |  | 19055024 | 1 | Oregon Sport Office TI |  |  | 2200 | 86 | 0 | 217233.4 | 217295.4 | 718 | 671.5 | 94.64% | 3.574% | 1.787%
19055018 |  | 19055018 | 1 | OHSU MRB Survivial |  |  | 4000 | 10 | 0 | 2126.33 | 7171.97
19055019 |  | 19055019 | 1 | OHSU CDRC Feasibility |  |  | 4000 | 10 | 0 | 14126.88 | 14811.24
19055020 |  | 19055020 | 1 | Crane Bldg TI |  |  | 5000 | 16645.57 | 0 | 371528.25 | 396692.18 | 397.5 | 962 | 92.1% | 7.9% | 0%
19055009 |  | 19055009 | 1 | Adventist West HV Clinic TI |  |  | 20250 | 7905.27 | 62 | 4349423.72 | 4243450.79 | 3349.08 | 3035 | 91.35% | 6.458% | 2.191%
19055017 |  | 19055017 | 1 | Multnomah Behavioral Health |  |  | 27000 | 91099 | 60838 | 18163149.8269 | 19493310.15 | 17511.43 | 25566.5 | 91.83% | 8.109% | 0.05671%
19055002 |  | 19055002 | 1 | KYDO Dalles Data Center |  |  | 51000 | 0 | 0 | 25179 | 27381.66
19055013 |  | 19055013 | 1 | OHSU CHH-2 I-2 |  |  | 60000 | 0 | 0 | 52803.62 | 98542.34
19055026 |  | 19055026 | 1 | MDI - Prov Reeds Crossing |  |  | 118000 | 593794.97 | 324119.72 | 53872853 | 54754503.18 | 30200.08 | 27665.07 | 91.52% | 8.415% | 0.06868%
19055001, 19040007 |  | 19055001 | 1 | Nike Project 40 |  |  | 160000 | 0 | 0 | 91055 | 81532.51
19055010 |  | 19055010 | 1 | Nike Dunk |  |  | 210000 | 1023.5 | 0 | 600386 | 510388.04 | 12 | 936 | 100% | 0% | 0%
19145005, 19146017, 20148007 |  | 19146017 | 11 | Phoenix Solar - HVT |  |  | 0 | 89785.26 | 93709 | 3522167.78 | 3454142.98 | 3038.54 | 5217 | 94.52% | 5.485% | 0%
19146018 |  | 19146018 | 1 | Solemio Solar - HVT |  |  | 0 | 0 | 0 | 52999 | 11178.86
19141017, 19148023, 19146019 |  | 19146019 | 21 | Prairie Hill Wind - HVT |  |  | 0 | 653487 | 668531 | 24893846 | 23496316.8 | 32555 | 38571 | 80.42% | 19.58% | 0%
19146020 |  | 19146020 | 1 | Old Jackson Solar - HVT |  |  | 0 | 0 | 0 | 59383 | 38675.71
19145008, 19148024, 19146021 |  | 19146021 | 21 | Greasewood Solar - HVT |  |  | 0 | 163570.06 | 73588 | 8835274.26 | 8637634.57 | 6676.18 | 6264 | 84.9% | 15.1% | 0%
19146009, 19141004, 19148019, 19146022, 19141022 |  | 19146022 | 31 | North Fork Ridge Wind - HVT |  |  | 0 | 311826 | 33266 | 20111992.78 | 19262952.87 | 13453.23 | 20152.5 | 80.34% | 19.66% | 0%
19146008, 19141005, 19148020, 19146023, 19141024 |  | 19146023 | 31 | Kings Point Wind - HVT |  |  | 0 | 331030.26 | 100115 | 28358161.48 | 27622693.57 | 14364.59 | 23665 | 84.64% | 15.36% | 0%
20148001, 19141030, 19146024 |  | 19146024 | 21 | TG East Wind - Power |  |  | 0 | 198529.33 | 549121 | 18912147.37 | 17766932.1 | 16878.81 | 22964.05 | 88.09% | 11.91% | 0%
19146025 |  | 19146025 | 1 | Liberty 91-0 Line Rebuild |  |  | 0 | 1002 | 2070 | 33138305.36 | 31564205.53 | 14842.42 | 25140.5 | 82.45% | 17.55% | 0%
19050001 |  | 19050001 | 1 | WWU Academic Facility | 2019-07-03 |  | 0 | 1087.02 | 0 | 437069.7 | 425648.34 | 188.14 | 14.5 | 96.55% | 3.448% | 0%
19050002 |  | 19050002 | 1 | 2019/2020 Virtual Insights |  |  | 0 | 0 | 0 | 137465 | 335958.62
19050005 |  | 19050005 | 1 | UW Softball Performance Center |  |  | 0 | 37439 | 27647 | 4247299.99 | 5055867.73 | 2415.5 | 4868.5 | 91.17% | 8.832% | 0%
19050006 |  | 19050006 | 1 | Swedish Edmonds Behavioral |  |  | 0 | 28091.83 | 512 | 2164348.51 | 2182750.8 | 1865.7 | 1430.5 | 92.42% | 7.585% | 0%
19050008 |  | 19050008 | 1 | POS MTLV (MC-0320490/U00159) |  |  | 0 | 63389.44 | 0 | 72755363.94 | 3168457.52 | 15160.9 | 204.5 | 98.29% | 1.711% | 0%
19050009 |  | 19050009 | 1 | KP Everett Specialty Center |  |  | 0 | 1072945.67 | 140650.24 | 96311699.8813 | 28941755.3 | 38701.07 | 26975.6 | 89.17% | 10.62% | 0.2141%
19050010 |  | 19050010 | 1 | Everett CC LRC |  |  | 0 | 251285.87 | 251420.5 | 32289406.89 | 29723115.06 | 14129.1 | 14750.93 | 90.75% | 8.83% | 0.4169%
19050011 |  | 19050011 | 1 | 5th & John Hotel |  |  | 0 | 0 | 0 | 86168.42 | 77314.79
19050012 |  | 19050012 | 1 | Kaiser Yesler Terrace |  |  | 0 | 27 | 0 | 435303.2 | 113067.32
19050050 |  | 19050050 | 1 | KPWA PBO Brand |  |  | 0 | 2516.25 | 0 | 276180.1139 | 263242.9 | 343.83 | 310.14 | 87.91% | 12.09% | 0%
19050051 |  | 19050051 | 1 | KP Master Plan Cost Model |  |  | 0 | 0 | 0 | 17519.65 | 17323.64
19145007 |  | 19145007 | 1 | Solemio Solar - Pattern Energy | 2019-10-07 |  | 0 | 764 | 0 | 464146 | 329118.1 | 0 | 136.5 | 87.91% | 12.09% | 0%
19145009 |  | 19145009 | 1 | Old Jackson - Pattern Energy |  |  | 0 | 201 | 0 | 175448.3 | 93834.28
19145010 |  | 19145010 | 1 | Renegade - Blue Planet |  |  | 0 | 0 | 0 | 120897 | 61128.04
19145011 |  | 19145011 | 1 | Texas Solar Nova 1 - Clearway |  |  | 0 | 295 | 0 | 223137 | 216096.36 | 600 | 475.5 | 73.76% | 26.24% | 0%
19145012, 20148009 |  | 19145012 | 1 | Maiden Creek Solar - Duke |  |  | 0 | 3013835.45 | 3396721 | 41010356.88 | 46191290 | 210537.85 | 276050 | 85.55% | 14.45% | 0%
19145013 |  | 19145013 | 1 | Alamo 5 - DC Addition |  |  | 0 | 0 | 0 | 82114.98 | 46874.07
19145014 |  | 19145014 | 1 | Snipesville I - Silicon Ranch |  |  | 0 | 3279971.59 | 3665057 | 58085762.41 | 63973749.54 | 237783.19 | 307536.68 | 84.84% | 15.16% | 0%
20148006, 19145015 |  | 19145015 | 11 | Santa Fe Solar - Duke Energy |  |  | 0 | 3384092.54 | 2905406 | 52112309.7871 | 47831327.94 | 216933.47 | 165008.5 | 88.9% | 11.1% | 0%
19150001 |  | 19150001 | 1 | Mortenson/Consigli - NER SS |  |  | 0 | 0 | 0 | 1015000 | 521203.05
19150002 |  | 19150002 | 1 | MAK - St Louis MLS |  |  | 0 | 0 | 266 | 59960055.21 | 48328399.81 | 0 | 0 | 0% | 0% | 0%
19150005 |  | 19150005 | 1 | PSU - Holuba Hall Renovations |  |  | 0 | 0 | 0 | 109089 | 14993.57
19150006 |  | 19150006 | 1 | PSU - Nittany Outdoor Football |  |  | 0 | 0 | 0 | 856815.634 | 792904.98
19150004 |  | 19150004 | 1 | PSU - Lasch Phase 6 |  |  | 53100 | 675 | 0 | 37200138.7906 | 35488928.49 | 436 | 1052 | 86.69% | 13.31% | 0%
19150001-172 |  | 19150001-172 | 1 | New England Revolution Soccer. |  |  | 450000 | 0 | 0 | 818284.98 | 1076955.99
19150002-164 |  | 19150002-164 | 1 | TKFC - St Louis MLS |  |  | 520000 | 5229427.56 | 0 | 484540873.8602 | 486561788 | 632534.38 | 698570.75 | 100% | 0% | 0%
19146007, 19148006, 19141002 |  | 19141002 | 21 | Ida Grove II Wind | 2019-04-15 |  | 0 | 9217 | 5892 | 82715590.35 | 80259602.74 | 95747 | 108556.2 | 65.2% | 33.99% | 0.8185%
19146009, 19141004, 19148019, 19146022, 19141022 |  | 19141004 | 11 | North Fork Ridge Wind - Design | 2019-09-15 |  | 0 | 0 | 0 | 302669.52 | 318412.6
19146008, 19141005, 19148020, 19146023, 19141024 |  | 19141005 | 11 | Kings Point Wind - Design | 2019-09-15 |  | 0 | 0 | 0 | 249810.1 | 289442.19
19141006 |  | 19141006 | 1 | Bright Stalk - Wind - EDPR | 2019-04-01 |  | 0 | 985 | 653 | 41536655.3954 | 42469063.22 | 15115 | 23045.83 | 74.07% | 25.55% | 0.3775%
19141007 |  | 19141007 | 1 | Wildorado Repower Wind | 2019-04-08 |  | 0 | 1892 | 1319 | 21862755.19 | 20546946.85 | 64943 | 85423.35 | 83.08% | 16.92% | 0%
19141008 |  | 19141008 | 1 | Elbow Creek Repower Wind | 2019-05-06 |  | 0 | 7865.03 | 1418 | 10847149.8772 | 12120383.82 | 25890 | 68228.75 | 80.84% | 19.16% | 0%
19141009, 19148016 |  | 19141009 | 1 | Bitter Ridge Wind | 2019-06-24 |  | 0 | 25096.85 | 2990 | 48772150.72 | 49169553.52 | 79274 | 82558.25 | 70.21% | 23.87% | 5.919%
19146010, 19141010, 19148015 |  | 19141010 | 11 | Nobles 2 Wind Project | 2019-08-15 |  | 0 | 4415 | 3883 | 77773246.5633 | 81149311.24 | 112838 | 117228 | 71.78% | 27.92% | 0.299%
19148012, 19146015, 19141011 |  | 19141011 | 21 | Cheyenne Ridge Wind | 2019-05-01 |  | 0 | 27237.63 | 17419 | 144705439.95 | 144160558.44 | 248911 | 222345.6 | 81.3% | 18.7% | 0%
19146011, 19141012, 19148009 |  | 19141012 | 11 | Arbor Hill 2019 | 2019-07-01 |  | 0 | 3155 | 1531 | 38784214.64 | 38914783.95 | 49260 | 66734.54 | 63.39% | 31.66% | 4.952%
19141013, 19146012, 19148017 |  | 19141013 | 1 | King Plains Wind | 2019-07-24 |  | 0 | 458317.85 | 437230 | 75649851.5455 | 81160982.82 | 119321 | 102699.28 | 81.71% | 18.29% | 0%
19141014 |  | 19141014 | 1 | GE MISC. REPOWER |  |  | 0 | 0 | 0 | 142339.56 | 158060.5 | 0 | 3910.5 | 73.75% | 26.25% | 0%
19141017, 19148023, 19146019 |  | 19141017 | 1 | Prairie Hill Wind | 2019-07-01 |  | 0 | 26974.2 | 9938 | 112966183.95 | 109800158.52 | 211760 | 175054.9 | 77.2% | 22.8% | 0%
19141019 |  | 19141019 | 1 | High Plains/McFadden Repower |  |  | 0 | 0 | 0 | 85133.31 | 97415.36
19141020 |  | 19141020 | 1 | Walnut Repower Wind |  |  | 0 | 1239 | 1057 | 21240119.377 | 18119714.63 | 66402 | 69963 | 66.07% | 29.84% | 4.094%
19141021 |  | 19141021 | 1 | Colorado Green Repower |  |  | 0 | 3348 | 3320 | 27615741.0926 | 21741182.91 | 102553.7 | 87519.5 | 83.97% | 16.03% | 0%
19146009, 19141004, 19148019, 19146022, 19141022 |  | 19141022 | 41 | North Fork Ridge Wind |  |  | 0 | 17739.44 | 4176 | 92592497.0523 | 89308087.19 | 120511 | 142609.63 | 81.37% | 18.63% | 0%
19148022, 19141023 |  | 19141023 | 11 | Pryor Mountain Wind |  |  | 0 | 36965.04 | 6673 | 116934959.89 | 93924194.3 | 109148 | 114600.48 | 72.96% | 25.86% | 1.18%
19146008, 19141005, 19148020, 19146023, 19141024 |  | 19141024 | 41 | Kings Point Wind |  |  | 0 | 8053.41 | 4643 | 114586334.7416 | 108437161.1 | 151510 | 152932.27 | 87.7% | 12.3% | 0%
19141025 |  | 19141025 | 1 | Dunlap Repower |  |  | 0 | 100 | 74 | 2860752.72 | 2072798.84 | 7890 | 8506 | 88.75% | 11.25% | 0%
19141026 |  | 19141026 | 1 | Trimont Repower |  |  | 0 | 924 | 561 | 16892294.89 | 15241772.22 | 55711.5 | 54307.4 | 65.64% | 28% | 6.368%
19148021, 19141027 |  | 19141027 | 11 | White Hills Wind |  |  | 0 | 32977.18 | 6913 | 108289439.6614 | 99723721.82 | 152829 | 100924.88 | 75.27% | 24.73% | 0%
19141028 |  | 19141028 | 1 | Adair Repower Wind |  |  | 0 | 0 | 0 | 2901231.78 | 1599588.68 | 0 | 10475.5 | 62.54% | 25.46% | 12%
19141029 |  | 19141029 | 1 | High Plains Repower |  |  | 0 | 11 | 4 | 102305.66 | 81696.08 | 6936 | 970 | 98.71% | 1.289% | 0%
20148001, 19141030, 19146024 |  | 19141030 | 11 | Truscott Gilliland East Wind |  |  | 0 | 3351 | 2138 | 71933089.19 | 70134193.6 | 22088 | 23756.03 | 85.15% | 14.85% | 0%
18150006 |  | 18150006 | 1 | Mortenson/Consigli - NER | 2018-05-14 | 2022-12-31 | 0 | 0 | 0 | 0.01 | -4.5475e-13
18050030 |  | 18050030 | 1 | AMLI 1101 Western Res Tower | 2020-12-01 | 2022-12-01 | 0 | 3988 | 0 | 2259348.47 | 2414651.17 | 0 | 260 | 100% | 0% | 0%
18060001 |  | 18060001 | 1 | MAM/McCarthy-Gaylord Pacific | 2020-01-01 | 2022-08-01 | 1784035 | 0 | 0 | 0 | -2624
18080010 |  | 18080010 | 1 | WI DOT - Foxconn Dev | 2018-06-07 | 2022-03-31 | 0 | 0 | 4 | 0.01 | -3.74 | 0 | 0 | 0% | 0% | 0%
18080010-063 |  | 18080010-063 | 1 | WI DOT-Foxconn Roads Develpmnt | 2018-06-07 | 2022-03-31 | 0 | 0 | 0 | 736829 | 772106.19
18110012 |  | 18110012 | 1 | DON-EHW Repairs Phases 2 and 3 | 2019-01-02 | 2022-03-19 | 133795 | 217 | 0 | 104162229.41 | 77861693.85 | 4880 | 2270 | 99.6% | 0.3965% | 0%
18080011 |  | 18080011 | 1 | WI DOT-Const Project Ctrls | 2018-07-01 | 2021-12-31 | 0 | 0 | 0 | 0.01 | 115.1
18080011-063 |  | 18080011-063 | 1 | WI DOT-IH 94 N-S Corridor | 2018-08-01 | 2021-12-31 | 0 | 0 | 0 | 2025737 | 1518308.76
18150001 |  | 18150001 | 1 | Rapid City - Rushmore Plaza | 2018-03-08 | 2021-07-31 | 250000 | 1330950.62 | 1277642 | 110010384.6157 | 109128213.66 | 81372.1 | 70865 | 85.25% | 14.75% | 0.005645%
18080008, 19080004 |  | 18080008 | 1 | AHC - Mount Pleasant | 2019-06-01 | 2021-07-21 | 0 | 816 | 0 | 1638116.97 | 1732390.92 | 0 | 25 | 96% | 4% | 0%
18030007 |  | 18030007 | 1 | PureCycle Technologies | 2018-02-15 | 2021-07-15 | 200000 | 0 | 0 | 2711670.4461 | 2638732.63
18146017, 18141017 |  | 18146017 | 1 | Ekola Flats Wind - HVT | 2019-05-20 | 2021-06-30 | 0 | 715372 | 719211 | 26658660.2258 | 25745651.66 | 21766 | 28344 | 82.25% | 17.72% | 0.03528%
18060005 |  | 18060005 | 1 | CCD-DIA On-Call | 2018-06-01 | 2021-06-01 | 0 | 0 | 0 | 286928.27 | 331268.26 | 0 | 130 | 100% | 0% | 0%
18126001 |  | 18126001 | 1 | Facebook-EAG 1/2 | 2018-07-03 | 2021-04-21 | 986000 | 1054958.3 | 935052 | 651059982.3058 | 640336992.31 | 87314.78 | 153710.2 | 66.83% | 33.17% | 0%
18050042 |  | 18050042 | 1 | Climate Pledge Arena | 2018-12-10 | 2021-04-01 | 0 | 4750703.81 | 3446885 | 841948897.9186 | 843073902.61 | 446258.59 | 533641.02 | 79.95% | 17.77% | 2.28%
18050027 |  | 18050027 | 1 | Port Angeles Waterfront Center | 2019-09-03 | 2021-03-01 | 0 | 356646.69 | 249227 | 38914390.2316 | 28262206.37 | 24901.7 | 19584.25 | 94.41% | 5.53% | 0.06127%
18150008 |  | 18150008 | 1 | Mortenson/Messer - Nashville |  | 2021-03-01 | 0 | 0 | 0 | 23458451.23 | 21616087.68
18060048 |  | 18060048 | 1 | LPMD-I-70/32nd Avenue | 2019-01-28 | 2021-01-28 | 0 | 3981537 | 59887 | 7912251.185 | 9212986.49 | 10391 | 20851.5 | 85.02% | 14.97% | 0.01439%
18090991, 18090001, 17090009 |  | 18090991 | 1 | Chicago Prefabrication Shop | 2018-01-01 | 2020-12-31 | 0 | 127567.61 | 63243 | 813261.7478 | 994717.84 | 6414.77 | 11719.32 | 91.65% | 7.082% | 1.271%
18060008 |  | 18060008 | 1 | CoorsTek-Capital Improvements | 2018-02-07 | 2020-12-31 | 0 | 0 | 0 | 0.01 | 26.73
18060028 |  | 18060028 | 1 | Forest City-FC Directed Work | 2018-05-01 | 2020-12-31 | 0 | 1 | 0 | 730648 | 593363.1 | 0 | 323.5 | 94.74% | 5.255% | 0%
17141026, 18146020, 19148025 |  | 18146020 | 11 | Blazing Star 2 Wind - HVT | 2019-07-15 | 2020-12-01 | 0 | 1042 | 0 | 34375016.66 | 33294396.82
18146016 |  | 18146016 | 1 | TB Flats I & II Wind HVT | 2019-05-20 | 2020-11-01 | 0 | 1371645 | 1231223 | 52317676.343 | 50736472.57 | 40957 | 79960.5 | 84.52% | 15.47% | 0.01251%
18141013 |  | 18141013 | 1 | TB Flats Wind | 2019-04-01 | 2020-11-01 | 0 | 11051 | 12494 | 136193192.3912 | 146007131.41 | 260284.5 | 321035.25 | 78.38% | 21.6% | 0.02025%
18146017, 18141017 |  | 18141017 | 11 | Ekola Flats Wind | 2019-04-01 | 2020-11-01 | 0 | 19132 | 22470 | 73439435.0062 | 78588654.17 | 84250 | 140719.3 | 80.78% | 19.22% | 0%
18040006 |  | 18040006 | 1 | Steeplechase | 2018-07-03 | 2020-10-30 | 986000 | 0 | 0 | 0.01 | 0
18050007 |  | 18050007 | 1 | citizenM Downtown LA | 2019-06-04 | 2020-10-20 | 0 | 150138.36 | 1982 | 68037369.1607 | 71177072.99 | 2768 | 3667.79 | 82.48% | 16.96% | 0.5589%
18110007 |  | 18110007 | 1 | JBLM Shopping Center | 2018-07-20 | 2020-10-05 | 291000 | 0 | 0 | 57687784.84 | 59112914.91 | 0 | 2004 | 100% | 0% | 0%
18060051 |  | 18060051 | 1 | MDI-2099 Chestnut Courtyard | 2019-08-01 | 2020-09-30 | 110000 | 0 | 0 | 0.01 | 826320.31
18126002 |  | 18126002 | 1 | Facebook-Program Services |  | 2020-09-17 | 0 | 2520 | 0 | 1460502 | 1495886.24
18110019 |  | 18110019 | 1 | S1S Roof Reinforcement Renov. | 2019-08-05 | 2020-09-03 | 14000 | 0 | 0 | 946316.2493 | 902971.31
18030003, 19030044 |  | 18030003 | 1 | City of Mpls-NPSB | 2018-06-18 | 2020-08-31 | 330000 | 305733 | 11 | 15698572.8259 | 16053437.34 | 61837.17 | 68374.5 | 87.7% | 11.85% | 0.4527%
18090014 |  | 18090014 | 1 | Wheels Inc HQ Addition & Ren | 2019-08-01 | 2020-07-31 | 49245 | 0 | 0 | 24750 | 24816.42
18040012 |  | 18040012 | 1 | SRP PAB Phase 4 Center Core | 2018-10-15 | 2020-07-31 | 143680 | 18419 | 8211 | 49089220.87 | 48315277.2 | 13316.3311 | 18327.05 | 85.83% | 14.17% | 0%
18050038 |  | 18050038 | 1 | DaVita CBO Expansion | 2019-03-01 | 2020-07-31 | 0 | 704650.65 | 675443 | 44511072.2449 | 44455907.89 | 16991.6 | 23573.73 | 92.49% | 7.108% | 0.403%
18060002 |  | 18060002 | 1 | MDI-St. John's XXII Student | 2019-01-01 | 2020-06-30 | 0 | 0 | 0 | 0.01 | 3608.61
19146001, 18141021, 19148002 |  | 18141021 | 11 | Tenaska Clear Creek Wind | 2019-01-01 | 2020-06-26 | 0 | 8216 | 7236 | 114378918.3589 | 119271696.67 | 147992 | 153343.1 | 79.18% | 20.82% | 0%
18000001-040, 18040002, 19040002 |  | 18040002 | 15 | MDI - HP/HH Tempe Downtown | 2019-01-01 | 2020-06-01 | 149000 | 572352.67 | 3982 | 40983283.53 | 42175036.69 | 12758.2 | 16430 | 82.66% | 17.34% | 0%
18090015 |  | 18090015 | 1 | Glen Ellyn Parking Garage | 2019-08-01 | 2020-05-31 | 116234 | 209922.01 | 39254 | 15217524.77 | 15169887.83 | 10201.4 | 10718.5 | 88.61% | 10.99% | 0.3965%
18146015 |  | 18146015 | 1 | Tesla Phase 1 | 2018-08-02 | 2020-05-30 | 0 | 333931.08 | 335487 | 6183833.003 | 6086143.31 | 15000.56 | 7940.5 | 77.49% | 22.51% | 0%
18110004 |  | 18110004 | 1 | DON P-930 Combat Veh Rpr Fac | 2018-12-01 | 2020-05-02 | 61193 | 0 | 0 | 21650499.83 | 20621570.97 | 0 | 3352 | 100% | 0% | 0%
18148013 |  | 18148013 | 1 | Blazing Star I - Civil | 2018-07-31 | 2020-05-01 | 0 | 646021 | 453439 | 12617660.72 | 15169675.5 | 31268 | 56549.94 | 72.7% | 26.77% | 0.5296%
18050034 |  | 18050034 | 1 | PCC OMIC | 2019-05-01 | 2020-05-01 | 0 | 51629.82 | 0 | 20721311.79 | 20650667.56 | 2180.4 | 4531.96 | 98.83% | 1.169% | 0%
18040007 |  | 18040007 | 1 | SRP PAB Expense and Repair PO | 2018-05-01 | 2020-04-30 | 80000 | 0 | 0 | 0.01 | 1694.86
18148020, 18146021, 18141012 |  | 18146021 | 11 | East Fork Wind - HVT | 2019-01-18 | 2020-04-21 | 0 | 264689 | 257800 | 16542177.57 | 15655462.59 | 29333 | 32259.05 | 80.71% | 19.29% | 0%
18060058 |  | 18060058 | 1 | WBVP-Northridge Behaviorial | 2019-02-07 | 2020-04-16 | 82627 | 468118.52 | 0 | 29693544.55 | 116547.33 | 20520.3 | 0 | 0% | 0% | 0%
18050008 |  | 18050008 | 1 | citizenM Sea Pioneer Square | 2019-01-15 | 2020-04-11 | 66640 | 277100.73 | 82838.5 | 54378167.4462 | 58188100.27 | 25842.9 | 46538.22 | 85.06% | 13.65% | 1.287%
18141020 |  | 18141020 | 1 | Seneca Wind | 2019-04-01 | 2020-04-01 | 0 | 0 | 0 | 1048700 | 876029.31
18080016 |  | 18080016 | 1 | Kohler Co - North Crane Yard | 2018-09-17 | 2020-03-31 | 13120 | 14627.91 | 58024 | 5527447.2352 | 4998905.42 | 7360.4 | 4139.23 | 93.5% | 6.318% | 0.1812%
21060047, 20060058, 18000015-040, 18060047, 20060042 |  | 18060047 | 35 | MDI-Candelas MOB | 2019-06-01 | 2020-03-30 | 40000 | 453127.81 | 209398 | 8670348.4206 | 8934704.66 | 17338.64 | 16435.5 | 88% | 12% | 0%
18060050 |  | 18060050 | 1 | MDI-Arista MOB | 2019-06-01 | 2020-03-30 | 60000 | 0 | 0 | 115531.25 | 242258.74
17000003-040, 17060025, 17060014, 18060057, 20060016 |  | 18060057 | 35 | FRA-BioScience 3-TI | 2019-01-01 | 2020-02-28 | 90000 | 261768.07 | 25416 | 15379814.15 | 15261935.52 | 5477.5 | 11232.5 | 92.63% | 7.371% | 0%
18060025 |  | 18060025 | 1 | BCSP Rino-Hub Phase 2 | 2018-11-01 | 2020-02-21 | 110606 | 493569.66 | 252058 | 23888440.27 | 23904463.6 | 23581.7 | 28631 | 91.53% | 8.472% | 0%
18110009 |  | 18110009 | 1 | Buckley AFB Document Dest | 2019-05-09 | 2020-02-10 | 4377 | 0 | 0 | 4882603.24 | 5405997.72 | 0 | 0 | 0% | 0% | 0%
18145013 |  | 18145013 | 1 | Terrell - Silicon Ranch | 2018-04-22 | 2020-02-04 | 103289550 | 5869277 | 8276895 | 57784700.14 | 69591027.98 | 233845 | 514634.39 | 86.89% | 13.11% | 0%
18040003 |  | 18040003 | 1 | Downtown Phx Hyatt Place | 2018-12-15 | 2020-02-01 | 126214 | 0 | 0 | 0.01 | 34117.45
18146023, 19148018 |  | 18146023 | 1 | Grissom Interconnect | 2019-06-03 | 2020-01-31 | 0 | 863584 | 773677 | 22267822.87 | 20820748.39 | 17251 | 21028 | 79.19% | 20.81% | 0%
18150004-168, 18150004 |  | 18150004 | 1 | Mortenson/GE Johnson - K-State | 2019-01-03 | 2020-01-30 | 0 | 0 | 0 | 2187309.77 | 1371637.23 | 0 | 11 | 0% | 100% | 0%
18150004-168, 18150004 |  | 18150004-168 | 1 | K-State Baseball/Soccer | 2019-01-03 | 2020-01-30 | 58818 | 24458 | 0 | 19038022.11 | 19634468.97 | 2302.1 | 1968.75 | 86.08% | 13.92% | 0%
18146019 |  | 18146019 | 1 | CTA EV Bus Charging Stn | 2018-05-17 | 2020-01-14 | 0 | 4728 | 5114 | 9790711.2 | 10689204.65 | 10 | 5479.92 | 90.61% | 7.902% | 1.487%
18146014 |  | 18146014 | 1 | Misae I Solar - HVT | 2018-06-25 | 2020-01-10 | 0 | 179631 | 166790 | 8137904.53 | 8219947.82 | 8203 | 8670.6 | 83.37% | 16.63% | 0%
18060014 |  | 18060014 | 1 | SCL-St Joe's Facilities Agree | 2018-03-01 | 2019-12-31 | 0 | 117 | 498 | 333836.04 | 362754.31 | 234 | 2214.23 | 84.85% | 15.15% | 0%
18060035 |  | 18060035 | 1 | Children's Hosp.-Potomac MOB | 2018-10-01 | 2019-12-31 | 114000 | 179545 | 33793 | 24468365.4698 | 24456902.26 | 11000.1 | 15419.5 | 89.39% | 10.61% | 0%
18080025 |  | 18080025 | 1 | Kohler - Misc Projects 18-19 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0 | 0.01 | 26062.61
18030025 |  | 18030025 | 1 | Sanford Fargo-Master Agrmt | 2018-05-07 | 2019-12-31 | 1020 | -3684.5 | 40 | 2812012.372 | 2889613.51 | 3737.07 | 5222.97 | 91.35% | 8.242% | 0.4116%
18050037 |  | 18050037 | 1 | OHSU Chem Bio Relocation | 2019-05-01 | 2019-12-31 | 0 | 13275 | 6 | 1104552.49 | 1105936.2 | 652.6 | 1363.25 | 91.25% | 8.161% | 0.5868%
18146006 |  | 18146006 | 1 | Blazing Star 1 Wind - HVT | 2018-08-06 | 2019-12-31 | 0 | 1499 | 0 | 19486890.22 | 18798198.89
18146024, 19148005 |  | 18146024 | 1 | Bonilla Interconnect | 2019-05-01 | 2019-12-31 | 0 | 779595 | 762175 | 23089643.91 | 22627623.55 | 19564 | 32009.5 | 71.13% | 28.87% | 0%
18050025 |  | 18050025 | 1 | Kaiser WA IDIQ Everett Misc | 2018-07-18 | 2019-12-31 | 0 | 477.91 | 364 | 418812.88 | 388926.37 | 232 | 561.02 | 77.01% | 11.23% | 11.76%
18145008 |  | 18145008 | 1 | Misae I Solar | 2018-06-25 | 2019-12-31 | 326810540 | 8044264 | 9094356 | 122299437 | 124076779.11 | 531290 | 594505.31 | 86.95% | 13.05% | 0%
18060007 |  | 18060007 | 1 | Park Creek-Filing ME | 2018-01-02 | 2019-12-30 | 0 | 287 | 33 | 696632 | 677189.32 | 1280 | 4515 | 96.95% | 3.045% | 0%
18060039 |  | 18060039 | 1 | SCL-SJH NICU Expansion | 2019-01-14 | 2019-12-20 | 14100 | 132397.5 | 4614 | 4338493.97 | 4396260.12 | 5398.8 | 14049.27 | 89.56% | 10.44% | 0%
18148011, 17141024, 18146004 |  | 18146004 | 21 | Solomon Forks Wind - HVT | 2018-04-10 | 2019-12-17 | 0 | 431698 | 432292 | 30930056.315 | 30115995.93 | 35893 | 40827 | 81.58% | 18.42% | 0%
18050006 |  | 18050006 | 1 | Bend WRF Cap Improvement Proj | 2018-02-22 | 2019-11-30 | 0 | 198029.07 | 57760 | 7390721.867 | 16470271.18 | 24814.8 | 70523.76 | 92.54% | 6.653% | 0.8104%
18110015 |  | 18110015 | 1 | DCNG Armory Ventilation Rehab | 2019-05-20 | 2019-11-27 | 29937 | 0 | 0 | 1987453.94 | 1965710.47 | 0 | 138 | 100% | 0% | 0%
18060060 |  | 18060060 | 1 | SCL-LMC Main Pharmacy USP 800 | 2019-02-11 | 2019-11-26 | 0 | 1812.14 | 1968 | 993877.28 | 1006465.9 | 2517.39 | 3185.5 | 91.45% | 8.554% | 0%
18030048 |  | 18030048 | 1 | Graco Koch Center Expansion | 2018-10-29 | 2019-11-21 | 795970 | 2324475.86 | 2332581 | 78522078.7635 | 78797731.23 | 103685.3 | 93047 | 89.95% | 9.868% | 0.1768%
18110025 |  | 18110025 | 1 | UDC LSI Upgrades | 2018-10-15 | 2019-11-15 | 10000 | 0 | 0 | 3227659.44 | 3179110.23
18110026 |  | 18110026 | 1 | UDC Roll-Up Fire Door Mech. | 2018-10-15 | 2019-11-15 | 13800 | 0 | 0 | 878979 | 889435.64
18060006 |  | 18060006 | 1 | MDI-Pine Creek MOB | 2019-03-04 | 2019-11-04 | 0 | 0 | 0 | 0.01 | 31110.21
18110008 |  | 18110008 | 1 | Fort Shafter Data Center 2 | 2018-09-06 | 2019-11-04 | 4320 | 0 | 0 | 117477.98 | 1952610.87
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, |  | 18060056 | 51 | SCL-SJB Mom/Baby/Women's | 2019-01-01 | 2019-11-01 | 11000 | 0 | 0 | 1765218.04 | 1813460.73
18146025 |  | 18146025 | 1 | Highlander Solar - HVT | 2019-03-01 | 2019-11-01 | 0 | 417106 | 457003 | 21490733.21 | 22212014.5 | 14169 | 26184.92 | 79.5% | 20.5% | 0%
18050035 |  | 18050035 | 1 | Swedish Ballard South Wing AHU | 2019-03-01 | 2019-11-01 | 0 | 6734.86 | 26 | 1263936.1854 | 1189492.95 | 433.82 | 442.12 | 94.01% | 5.315% | 0.6785%
18146018 |  | 18146018 | 1 | Gillrina Cut-In | 2019-03-01 | 2019-10-31 | 0 | 1046 | 398 | 498475.51 | 508794.59 | 2234 | 1292 | 85.9% | 14.1% | 0%
18050039 |  | 18050039 | 1 | AAFES 03X Concrete Package | 2018-11-01 | 2019-10-31 | 0 | 833891.85 | 500512 | 3207352.6295 | 3307023.54 | 17887.9 | 16126.37 | 92.61% | 6.641% | 0.7503%
18030033 |  | 18030033 | 1 | Allina-Schulze Neuroscience C | 2018-08-01 | 2019-10-21 | 42000 | 63891.5 | 66400 | 11020199.925 | 11212337.36 | 25198 | 29883.1 | 89.26% | 9.95% | 0.7897%
18110020 |  | 18110020 | 1 | 21st Shielding Cert.-MD | 2019-01-14 | 2019-10-12 | 1 | 0 | 0 | 209940 | 203847.46
18110021 |  | 18110021 | 1 | 21st Shielding Cert. -VA | 2019-02-04 | 2019-10-12 | 1 | 0 | 0 | 450222.15 | 444374.96
18110022 |  | 18110022 | 1 | 21st Shielding Cert. -PA | 2019-01-14 | 2019-10-12 | 1 | 0 | 0 | 438589 | 440487.52
18060049 |  | 18060049 | 1 | LPMD-CC Ph 2 Utilities | 2019-03-01 | 2019-10-01 | 0 | 20118 | 28246 | 1954644.6296 | 2069199.22 | 4727.1 | 3967 | 84.32% | 15.68% | 0%
18090013 |  | 18090013 | 1 | SAIC Wellness Center | 2019-05-15 | 2019-09-30 | 5000 | 47431.15 | 13504 | 1305726.61 | 1218672.56 | 1612.84 | 1580.61 | 88.17% | 9.49% | 2.341%
18090004 |  | 18090004 | 1 | Lurie Inpatient Exp2 -17th FL | 2018-07-01 | 2019-09-30 | 35000 | 21748 | 17015 | 19229564.88 | 15695157.35 | 22658 | 23835.76 | 89.67% | 8.892% | 1.435%
18090002 |  | 18090002 | 1 | Performing Arts Center | 2019-02-04 | 2019-09-30 | 35506 | 224752.5 | 121374 | 25940397.6072 | 26777833.84 | 22828 | 23953.78 | 90.76% | 8.718% | 0.5239%
18040009 |  | 18040009 | 1 | Arroyo Seco Well Site | 2018-03-19 | 2019-09-30 | 187900 | 67319 | 15964 | 7815000.64 | 9645390.93 | 9317 | 19464.5 | 87.74% | 12.26% | 0%
18148020, 18146021, 18141012 |  | 18148020 | 1 | East Fork - Civil (Wind) | 2018-11-01 | 2019-09-14 | 0 | 650842 | 270434 | 7741710.3774 | 10773355.27 | 27056.5 | 30923.5 | 72.55% | 27.45% | 0%
18050051 |  | 18050051 | 1 | Kaiser WA LYM Rebranding | 2019-03-22 | 2019-09-04 | 0 | 32683.5 | 2347 | 1619806.8982 | 1696869.95 | 2354.71 | 3523.78 | 91.6% | 6.385% | 2.015%
18030012 |  | 18030012 | 1 | Blake Classroom Refresh | 2018-06-11 | 2019-09-02 | 57000 | 177890 | 101184 | 2436648.75 | 2471663.29 | 7904.1 | 6204.68 | 77.3% | 22.02% | 0.6769%
18030013 |  | 18030013 | 1 | MCTC-Hennepin Ave Skyway | 2019-05-01 | 2019-09-01 | 3232 | 31760.1 | 19396 | 2767329.93 | 2750641.66 | 4019.7 | 4273 | 90.43% | 8.168% | 1.404%
18141014 |  | 18141014 | 1 | Glenrock Repower Wind | 2018-09-10 | 2019-09-01 | 0 | 503 | 243 | 2993794.13 | 2536592.95 | 9140 | 9972.09 | 77.19% | 22.81% | 0%
18141015 |  | 18141015 | 1 | Seven Mile Repower Wind | 2018-09-10 | 2019-09-01 | 0 | 1059 | 972 | 13807519.54 | 12307350.73 | 42711 | 48198.3 | 77.4% | 22.6% | 0%
18090017 |  | 18090017 | 1 | Faegre Baker Daniels-45th Exp. | 2018-10-23 | 2019-08-31 | 1830 | 6682.52 | 0 | 232411.11 | 234204.57 | 417.68 | 361.95 | 85.63% | 5.526% | 8.841%
18090991, 18090001, 17090009 |  | 18090001 | 11 | CHI Bears Halas Hall | 2017-12-04 | 2019-08-31 | 198000 | 657708.51 | 449945 | 77242395.8359 | 79033178.02 | 41884.5 | 52911.04 | 82.18% | 11.86% | 5.965%
18060031 |  | 18060031 | 1 | Woodward-Drake Equip Fit Up | 2018-06-25 | 2019-08-30 | 0 | 10631 | 0 | 4730168.82 | 4526862.77 | 1112.3 | 5138 | 96.34% | 3.659% | 0%
18030057 |  | 18030057 | 1 | WuXi Diagnostic TI - Dis Sq | 2019-06-03 | 2019-08-30 | 2367 | 341 | 0 | 744228.09 | 659655.81 | 419.6 | 321 | 99.07% | 0.9346% | 0%
18110014 |  | 18110014 | 1 | DCNG Armory HVAC | 2019-03-01 | 2019-08-25 | 15450 | 0 | 0 | 703760.3 | 653348.07
18080001 |  | 18080001 | 1 | MSOE-ComputationalScienceHall | 2018-05-04 | 2019-08-22 | 64000 | 822132.37 | 543836 | 29622287.7602 | 29659942.13 | 37603.91 | 46101.61 | 90.29% | 9.477% | 0.2299%
18110017 |  | 18110017 | 1 | DCNG Armory Museum North | 2019-03-01 | 2019-08-14 | 1967 | 0 | 0 | 1184449.65 | 1180666.93
18110016 |  | 18110016 | 1 | DCNG Armory Restroom Renov | 2019-04-01 | 2019-08-06 | 2156 | 0 | 0 | 1151707.27 | 1175832.25 | 0 | 2 | 100% | 0% | 0%
18060041 |  | 18060041 | 1 | WelArm-Glenarm Bldgs Remodel | 2018-09-01 | 2019-08-01 | 72000 | 0 | 0 | 0.01 | 0
18060062 |  | 18060062 | 1 | AIMCO 21-Faculty Club Hotel | 2018-11-15 | 2019-08-01 | 108000 | 0 | 0 | 0.01 | 147239.97
18050031 |  | 18050031 | 1 | OHSU Vollum Phase II | 2018-08-01 | 2019-08-01 | 0 | 5896.3 | 1986 | 4342409.85 | 4350045.05 | 3192.18 | 1629.89 | 91.89% | 7.316% | 0.7976%
18150009 |  | 18150009 | 1 | Mortenson/Clark - Chase Cen | 2018-12-01 | 2019-08-01 | 0 | 0 | 0 | 1334535.94 | 843049.28
18080015 |  | 18080015 | 1 | Dane Cnty Terminal Mod | 2020-01-01 | 2019-07-31 | 0 | 0 | 0 | 344835 | 277767.8
18050018 |  | 18050018 | 1 | Harborview 2MB Cart Washers | 2018-10-01 | 2019-07-31 | 2375 | 39095.35 | 8227 | 2929653.35 | 2431358.46 | 6032.4 | 3993.16 | 99.55% | 0.3756% | 0.07513%
18141019 |  | 18141019 | 1 | Carroll Repower Wind | 2018-10-15 | 2019-07-31 | 0 | 1268 | 926 | 20333500.67 | 16840478.69 | 65295 | 67255.51 | 66% | 30.28% | 3.728%
18080027 |  | 18080027 | 1 | Milwaukee Office Buildout | 2019-02-18 | 2019-07-30 | 19200 | 68177 | 86566 | 4354164.75 | 1.5334e-09 | 3975.1 | 5166.15 | 87.66% | 11.24% | 1.103%
18060040 |  | 18060040 | 1 | Faegre Baker Daniels-TI. | 2018-10-04 | 2019-07-25 | 0 | 97577 | 4 | 7727203.1872 | 7698295.68 | 1359.5 | 224 | 77.68% | 22.32% | 0%
18110003 |  | 18110003 | 1 | UDC Silver Universe 3&4 | 2018-06-01 | 2019-07-22 | 12500 | 88 | 0 | 5509273.65 | 5360445.1
18080012 |  | 18080012 | 1 | Kohler-Water Spa Lincoln Comm | 2018-12-17 | 2019-07-20 | 17830 | 69456 | 0 | 6856768.25 | 7253753.08 | 2188.2 | 3057.71 | 95.36% | 3.418% | 1.226%
18060030 |  | 18060030 | 1 | Considine-Compositive Primary | 2018-09-01 | 2019-07-19 | 0 | 393900.16 | 176923 | 12918200.3647 | 13357559.11 | 22092.47 | 34957.5 | 89.46% | 10.54% | 0%
18148018 |  | 18148018 | 1 | Panther Creek Repower - Civil | 2018-10-01 | 2019-07-15 | 0 | 62106.92 | 27 | 3595246.068 | 3243067.17 | 16310 | 19176 | 76.22% | 23.78% | 0%
18060052 |  | 18060052 | 1 | SCL-Superior Primary & OBGYN | 2019-01-14 | 2019-07-12 | 0 | 51299 | 24826 | 2720447.6 | 2774866.66 | 1900.8 | 3050 | 88.07% | 11.93% | 0%
18060010, 17060007, 17060006, 16060029 |  | 18060010 | 1 | Westfield-Parcel E Office Bldg | 2018-08-01 | 2019-07-01 | 0 | 261146 | 94688 | 14350285.75 | 14190758.94 | 10722 | 14399 | 87.79% | 12.21% | 0%
18030047 |  | 18030047 | 1 | Sanford 8th Floor Build Out | 2018-10-15 | 2019-07-01 | 11759 | 12389 | 10333 | 3345113.89 | 3326833.9 | 3141 | 3418.5 | 90.42% | 9.405% | 0.1755%
18090016 |  | 18090016 | 1 | Rush MC Transplant Ren. | 2019-01-03 | 2019-06-30 | 3980 | 457.46 | 0 | 240605.35 | 207410.9 | 434 | 396 | 61.62% | 15.4% | 22.98%
18148004, 18141005 |  | 18148004 | 1 | Meadow Lake VI - Civil | 2018-04-04 | 2019-06-30 | 0 | 747140 | 1287947 | 14094955.14 | 14188923.99 | 33376 | 34025.5 | 67.92% | 30.83% | 1.251%
18060046 |  | 18060046 | 1 | Park Creek-Filing 56 | 2018-11-01 | 2019-06-30 | 0 | 150 | 0 | 348558 | 352555.2 | 1600 | 3119.5 | 97.74% | 2.26% | 0%
18110018 |  | 18110018 | 1 | DCNG Davison Airfield ACLS | 2019-02-04 | 2019-06-30 | 1600 | 0 | 0 | 700836.97 | 663756.41
18030054 |  | 18030054 | 1 | NS VIII Renovation | 2018-12-05 | 2019-06-30 | 180188 | 385 | 0 | 5736028.3672 | 5751710.62 | 5460 | 6696 | 96.39% | 3.614% | 0%
18050057 |  | 18050057 | 1 | Adventist Electrophysiology | 2019-01-02 | 2019-06-30 | 4700 | 47813.3 | 551 | 3862698.3432 | 3753949.24 | 9356.21 | 7580.6 | 95.89% | 2.579% | 1.53%
18141002 |  | 18141002 | 1 | Mendota Hills Wind | 2018-06-01 | 2019-06-30 | 0 | 2754 | 2363 | 29877257.26 | 31165810.19 | 40927 | 65765.25 | 67.11% | 27.36% | 5.533%
18141010, 18148010 |  | 18141010 | 1 | Heartland Divide Wind | 2018-08-06 | 2019-06-29 | 0 | 3236 | 2194 | 31054234.88 | 34418406.86 | 46291 | 71517.25 | 60.12% | 33.45% | 6.429%
18060034 |  | 18060034 | 1 | Woodward-Drake Campus Site Imp | 2018-08-01 | 2019-06-28 | 0 | 141 | 0 | 419452.45 | 394983.05 | 32 | 220 | 97.27% | 2.727% | 0%
18080024 |  | 18080024 | 1 | Johnson Controls - B1F3 Reno | 2018-12-10 | 2019-06-28 | 15340 | 63731 | 43733 | 1208009.08 | 1164594.48 | 2161.7 | 2243.91 | 88.44% | 11.3% | 0.2674%
18030042 |  | 18030042 | 1 | MDI-Blaine BTS-Site Prep | 2018-09-27 | 2019-06-24 | 0 | 0 | 0 | 1687141.59 | 1739829.95
18060053 |  | 18060053 | 1 | SCL-Denver West Foothills | 2019-01-14 | 2019-06-21 | 0 | 54563 | 97665 | 1775303.45 | 1808145.37 | 2664.4 | 7137.5 | 93.17% | 6.83% | 0%
18080020 |  | 18080020 | 1 | Froedtert - Cath Lab FitOut | 2019-02-21 | 2019-06-21 | 1250 | 11615.6 | 7819 | 801278.6 | 805206.72 | 1098.3 | 1072.5 | 90.49% | 7.879% | 1.632%
18080023 |  | 18080023 | 1 | MRMC - East Tunnel Repair | 2019-04-03 | 2019-06-17 | 2500 | 34007.37 | 24010 | 1599644.64 | 1589808.1 | 2548.3 | 3089.12 | 93.59% | 6.41% | 0%
18080019 |  | 18080019 | 1 | S.C. Johnson - Lighthouse Exp | 2018-10-22 | 2019-06-17 | 10378 | 1374 | 0 | 2345046.55 | 2339924.11
18060054 |  | 18060054 | 1 | SCL-Cherry Creek Primary | 2019-01-14 | 2019-06-14 | 8200 | 45803 | 13572 | 1430842.95 | 1474626.95 | 2325 | 3301.5 | 84.49% | 15.51% | 0%
18110013 |  | 18110013 | 1 | DIA Parking Garage Repairs | 2018-11-12 | 2019-06-14 | 0 | 0 | 0 | 702640.27 | 952891.45
18148020, 18146021, 18141012 |  | 18141012 | 21 | East Fork Wind | 2018-10-15 | 2019-06-13 | 0 | 16665 | 101113 | 58033160.7 | 59610132.61 | 69364 | 85416.59 | 76.16% | 23.83% | 0.01346%
18148011, 17141024, 18146004 |  | 18148011 | 1 | Solomon Forks | 2018-07-23 | 2019-06-10 | 0 | 1096317 | 217084 | 8832101.6 | 9629715.05 | 28047.24 | 34255.5 | 75.24% | 24.76% | 0%
18030011 |  | 18030011 | 1 | UMN Biological Sciences | 2018-08-01 | 2019-06-07 | 16300 | 45329.3 | 13859 | 6566227.7 | 6588035.73 | 4351.3 | 5082.02 | 99.36% | 0.6395% | 0%
18080021 |  | 18080021 | 1 | Froedtert - Food Service Reno | 2019-03-27 | 2019-06-06 | 1000 | 17989 | 8114 | 1466343.23 | 1505285.45 | 2009.35 | 2081 | 89.16% | 10.6% | 0.2403%
18030039 |  | 18030039 | 1 | Epic Systems Corp - Epic TI DS | 2019-02-19 | 2019-06-04 | 4306 | 6681.76 | 1942 | 980786.05 | 871967.32 | 338.8 | 152 | 89.47% | 10.53% | 0%
18030049 |  | 18030049 | 1 | Silver Lake - UMR TI Disc Sq | 2018-12-17 | 2019-06-03 | 8382 | 14441.5 | 2925 | 2879798.7 | 2634554 | 1255.9 | 627.5 | 93.39% | 6.614% | 0%
18060033 |  | 18060033 | 1 | FRA-FIC Phase 1 Infrastructure | 2018-10-01 | 2019-06-01 | 0 | 487109.51 | 252327 | 8949960.6409 | 12481922.3 | 20611 | 41889.5 | 80.75% | 19.25% | 0%
18030045 |  | 18030045 | 1 | Mayo TI - Discovery Square | 2018-10-08 | 2019-06-01 | 22400 | 50944.77 | 5779 | 9237090.44 | 9165883.92 | 3501.8 | 4363 | 96.81% | 3.14% | 0.04584%
18030058 |  | 18030058 | 1 | Xcel-Becker Sands-UMN Lease | 2019-02-01 | 2019-06-01 | 24088 | 0 | 0 | 166078.1 | 182272.34 | 60 | 72 | 100% | 0% | 0%
18060059 |  | 18060059 | 1 | FRA-FIC Pond 374 | 2018-12-17 | 2019-05-31 | 0 | 235798.04 | 98701 | 1472360.49 | 1810960.01 | 9711 | 14324.33 | 82.64% | 17.36% | 0%
18110011 |  | 18110011 | 1 | Pearl Harbor Bldg 221 Reno | 2019-04-29 | 2019-05-24 | 6600 | 0 | 0 | 161658 | 163672.75
18030055 |  | 18030055 | 1 | Allina-ANW Pharmacy USP | 2019-01-07 | 2019-05-24 | 1055 | 12 | 0 | 557175.35 | 556487.73 | 1943 | 2410.25 | 96.1% | 2.074% | 1.826%
18141011, 18148016 |  | 18148016 | 11 | Bobcat Bluff RePower | 2018-09-11 | 2019-05-15 | 0 | 6358 | 226 | 3136701.38 | 3369645.87 | 9497.76 | 12165.5 | 82.27% | 17.73% | 0%
18060021 |  | 18060021 | 1 | Stadium Mgmt-Denver Bronc | 2018-05-01 | 2019-05-01 | 5000 | 924 | 830 | 289429 | 353672 | 1166 | 2605 | 93.86% | 6.142% | 0%
18146026 |  | 18146026 | 1 | Horseshoe Draw SVC | 2019-07-01 | 2019-05-01 | 0 | 97549 | 93890 | 2620134.07 | 2910335.17 | 10968 | 16151.5 | 71.5% | 28.5% | 0%
18090008 |  | 18090008 | 1 | Mercyhealth-Water Event | 2018-06-20 | 2019-04-30 | 0 | 328 | 674 | 5222332 | 4988979.29 | 9900 | 9817.91 | 90.71% | 6.87% | 2.419%
18090011 |  | 18090011 | 1 | Allstate-Rochelle PLC Replace | 2018-11-19 | 2019-04-30 | 0 | 10415 | 0 | 160910 | 126481.12 | 550.6 | 539.25 | 89.99% | 7.603% | 2.411%
18060061 |  | 18060061 | 1 | SCL-LMC Rad Room 3 | 2019-02-18 | 2019-04-30 | 270 | 868 | 222 | 136149.7 | 136680.28 | 639 | 221 | 74.89% | 25.11% | 0%
18080004 |  | 18080004 | 1 | AHC - Summit Main Pharm Reno | 2018-07-20 | 2019-04-30 | 670 | 14673 | 11471 | 899790.38 | 835743.15 | 873.5 | 1047 | 84.91% | 14.04% | 1.051%
18040017 |  | 18040017 | 1 | San Carlos Rural Health | 2018-12-10 | 2019-04-30 | 6684 | 0 | 0 | 1743982.71 | 1613357.77 | 536 | 685 | 74.74% | 25.26% | 0%
18080022 |  | 18080022 | 1 | Kohler - ABP Cooling Tower | 2018-10-29 | 2019-04-29 | 4800 | 18113.74 | 5637 | 1056524.5382 | 1011792.45 | 1130.1 | 1578.5 | 90.75% | 6.208% | 3.041%
18110024 |  | 18110024 | 1 | UDC Chemical Treat. Upgrades | 2018-10-29 | 2019-04-27 | 40000 | 0 | 0 | 1823767.93 | 1798061.76
18060032 |  | 18060032 | 1 | FRA-AIMCO Phase 3A | 2018-08-13 | 2019-04-26 | 0 | 21414.7 | 19011 | 1624730.8192 | 1736918.25 | 12729.07 | 5454 | 86.48% | 13.52% | 0%
18000004-040, 18040004, 18040011 |  | 18040011 | 25 | Ellsworth Adhesives | 2017-09-18 | 2019-04-26 | 158726 | 0 | 0 | 16053735.77 | 16171498.6 | 0 | 4 | 100% | 0% | 0%
18141007, 18148015 |  | 18141007 | 1 | Pomeroy I/II Repower Wind | 2018-06-11 | 2019-04-26 | 0 | 1918 | 1629 | 35406593.61 | 28914248.91 | 123355.5 | 117402.3 | 65.4% | 28.96% | 5.635%
18090010 |  | 18090010 | 1 | QTS-Hogan 3/2 | 2018-10-29 | 2019-04-12 | 0 | 416 | 126 | 5102903.12 | 5108737.91 | 2873 | 3554.08 | 94.19% | 5.219% | 0.5909%
18050053 |  | 18050053 | 1 | Kaiser WA PRT Rebranding | 2018-12-01 | 2019-04-12 | 0 | 30404 | 0 | 789623.1643 | 767195.84 | 1518 | 1377.09 | 96.55% | 3.449% | 0%
18080007 |  | 18080007 | 1 | AHC-IR/Hybrid OR Suite | 2018-07-09 | 2019-04-11 | 6060 | 68633 | 48790 | 2967723.77 | 2978729.15 | 2914.9 | 3937 | 77.89% | 19.75% | 2.362%
18110010 |  | 18110010 | 1 | Westway CRAC Replace UPS | 2018-10-29 | 2019-04-05 | 1000 | 0 | 0 | 717610.11 | 694622.45
18060063 |  | 18060063 | 1 | Co Rockies-Coors Field Grease | 2018-12-26 | 2019-04-01 | 8000 | 5 | 0 | 457845.27 | 390079.9 | 689 | 954 | 89.41% | 10.59% | 0%
18060055 |  | 18060055 | 1 | Co Rockies-Coors Field 18-19 | 2018-10-29 | 2019-04-01 | 33600 | 0 | 0 | 3109508 | 3018951.41 | 6530 | 10141.55 | 80.7% | 19.3% | 0%
18060026 |  | 18060026 | 1 | CO Rockies-Coors Field 2018 | 2018-10-01 | 2019-04-01 | 45500 | 3385.75 | 2432 | 6508029.89 | 6784857.75 | 4730 | 18484 | 85.26% | 14.74% | 0%
18090003 |  | 18090003 | 1 | QTS ComEd Substation | 2017-11-01 | 2019-03-31 | 0 | 198 | 45 | 9814244 | 9755485.83 | 2044 | 2656.5 | 96.2% | 3.614% | 0.1882%
18090006 |  | 18090006 | 1 | Allstate Jcksnville 2018 Misc. | 2018-03-01 | 2019-03-31 | 0 | 7 | 0 | 308511 | 296495.53 | 0 | 40 | 100% | 0% | 0%
18090012 |  | 18090012 | 1 | Mercyhealth - Rockton Misc | 2018-06-20 | 2019-03-31 | 0 | 1865 | 46 | 588892.85 | 594846.48 | 733.1 | 651.5 | 93.71% | 6.293% | 0%
18080002 |  | 18080002 | 1 | Kohler Co - Foundry Bldg | 2018-01-27 | 2019-03-31 | 0 | 72.5 | 2 | 6381827.18 | 6451875.6 | 5085.28 | 5387.28 | 88.72% | 10.41% | 0.8631%
18080026 |  | 18080026 | 1 | MDI - Hilton Garden Inn |  | 2019-03-31 | 170000 | 0 | 0 | 0.01 | 0
18030043 |  | 18030043 | 1 | Target Field 2019 Improvements | 2018-10-08 | 2019-03-31 | 13000 | 142966.24 | 31330 | 5256898 | 5256907.43 | 8095.4 | 10850.11 | 82.59% | 13.03% | 4.378%
18050023 |  | 18050023 | 1 | PRMCE Colby Lab Automation | 2018-10-01 | 2019-03-31 | 0 | 0 | 0 | 4620 | 4994.75
18030056 |  | 18030056 | 1 | Coralville Marriott & Conf Ctr | 2018-12-09 | 2019-03-28 | 108000 | 313893 | 0 | 1711471.0125 | 1732973.02 | 5603.41 | 4787 | 68.16% | 27.3% | 4.533%
18090009 |  | 18090009 | 1 | QTS-DH1 B11-DH2 B2 | 2018-09-24 | 2019-03-23 | 0 | 203 | 43 | 2726951.9 | 2627601.06 | 1436 | 1236.5 | 94.66% | 5.135% | 0.2022%
18030031 |  | 18030031 | 1 | Land O'Lakes - WT2 and Pilot | 2018-07-20 | 2019-03-15 | 6555 | 16874.3 | 0 | 4661570.4856 | 4639271.35 | 933.87 | 1092.5 | 99.45% | 0.5492% | 0%
18146013 |  | 18146013 | 1 | Falfurrias SVC | 2018-07-02 | 2019-03-15 | 0 | 59800 | 51992 | 2487767.72 | 2954632.97 | 4565 | 13391 | 89.53% | 10.47% | 0%
18080028 |  | 18080028 | 1 | Miller Park - SRF Master Plan |  | 2019-03-12 | 0 | 0 | 0 | 27621.6 | 23427.08
18145005 |  | 18145005 | 1 | Target Solar Remediation | 2018-04-01 | 2019-03-08 | 0 | 65639 | 136182 | 5439340.81 | 5388419.42 | 0 | 26506.32 | 93.04% | 6.932% | 0.03018%
18030052 |  | 18030052 | 1 | UMN-CCRB Mass Spec | 2018-11-12 | 2019-03-01 | 2635 | 0 | 0 | 743096.88 | 720488.73 | 744.5 | 721 | 100% | 0% | 0%
18050024 |  | 18050024 | 1 | Kaiser WMC IR Project | 2018-06-01 | 2019-03-01 | 0 | 4409 | 36286 | 2779134.285 | 2796891.58 | 4152.4 | 3561.86 | 89.92% | 8.858% | 1.221%
18060022 |  | 18060022 | 1 | SCL-LMC Poz Lok Fire Prot | 2018-04-03 | 2019-02-28 | 0 | 39 | 58 | 88370.07 | 88423.36 | 60 | 57.5 | 58.26% | 41.74% | 0%
18060024 |  | 18060024 | 1 | SCL-LMC Transformer and Fire | 2018-06-01 | 2019-02-28 | 0 | 631.35 | 358 | 233366.45 | 232497.69 | 347 | 392 | 87.24% | 12.76% | 0%
18060042 |  | 18060042 | 1 | SCL-LMC ED X Ray | 2018-11-09 | 2019-02-28 | 480 | 865 | 931 | 276059.45 | 276114.86 | 1174 | 949 | 90.67% | 9.326% | 0%
18110023 |  | 18110023 | 1 | Moss Landing Demo & Upgrade | 2018-11-29 | 2019-02-28 | 0 | 0 | 0 | 270000 | 273445.73
18080014 |  | 18080014 | 1 | Johnson Controls - Misc. Jobs | 2018-07-31 | 2019-02-28 | 0 | 0 | 54 | 59025 | 62205.05 | 306 | 267 | 94.94% | 5.056% | 0%
18050005 |  | 18050005 | 1 | 5th & Stewart Hotel | 2018-01-09 | 2019-02-28 | 0 | 0 | 0 | 342743.99 | 645189.49
18050050 |  | 18050050 | 1 | KP Everett Rebranding | 2018-11-09 | 2019-02-28 | 0 | 20275.7 | 2049 | 1709091.8709 | 1642469.38 | 1954.6 | 2314 | 89.91% | 5.38% | 4.71%
18030044 |  | 18030044 | 1 | Renaissance Sq-The Andrus | 2018-10-12 | 2019-02-18 | 14469 | 51581.75 | 10 | 2526602.24 | 2533841.37 | 4342 | 6089.25 | 81.04% | 18.87% | 0.09853%
18110006 |  | 18110006 | 1 | ECB1 Market Square | 2018-10-01 | 2019-02-15 | 2000 | 57 | 0 | 1193712.18 | 1149059.95
18040008 |  | 18040008 | 1 | Salt River Fields Restroom | 2018-10-01 | 2019-02-11 | 2236 | 0 | 0 | 639981.1 | 592414.76 | 0 | 8 | 100% | 0% | 0%
18060036 |  | 18060036 | 1 | CCC-Phase 1 Utilities | 2018-07-18 | 2019-02-05 | 0 | 8233 | 15332 | 1201513.799 | 1709704.48 | 3366 | 8180 | 86.52% | 13.48% | 0%
18060037 |  | 18060037 | 1 | Longs Peak Metro - Clear Creek | 2018-07-20 | 2019-02-05 | 0 | 4977 | 1710 | 6735772.2598 | 6749039.24 | 4370 | 8773 | 84.09% | 15.91% | 0%
18000004-040, 18040004, 18040011 |  | 18040004 | 15 | Ellsworth Adhesives-Reno | 2018-05-01 | 2019-02-01 | 120000 | 0 | 0 | 0 | 1312.46
18141016 |  | 18141016 | 1 | Leaning Juniper Repower Wind | 2018-10-12 | 2019-02-01 | 0 | 977 | 785 | 8926195.95 | 6121734.27 | 21844 | 21681.5 | 72.81% | 26.42% | 0.7737%
18040015 |  | 18040015 | 1 | USS Arizona Memorial | 2018-10-18 | 2019-01-31 | 0 | 0 | 0 | 60000 | 4924.07
18040016 |  | 18040016 | 1 | CoG-Cost Estimating Support | 2018-10-25 | 2019-01-31 | 0 | 0 | 0 | 45662 | 1376.3
18050052 |  | 18050052 | 1 | Kaiser WA RVM Rebranding | 2018-12-01 | 2019-01-31 | 0 | 11219.5 | 0 | 560368.22 | 496222.48 | 1031.4 | 540.74 | 96.3% | 3.699% | 0%
18030053 |  | 18030053 | 1 | Allina-Mercy CV-4 | 2018-09-03 | 2019-01-29 | 1400 | 0 | 0 | 383670.68 | 382950.59 | 2120 | 1551.5 | 92.56% | 7.444% | 0%
18040014 |  | 18040014 | 1 | Allstate One Chandler | 2018-10-22 | 2019-01-23 | 118953 | 0 | 0 | 7379128.892 | 7285997.44 | 396.5 | 1528.5 | 89.7% | 10.3% | 0%
18030008 |  | 18030008 | 1 | FBD Wells Fargo TI | 2018-01-02 | 2019-01-21 | 0 | 17 | 133235 | 12439742.103 | 12026944.18 | 16600.5 | 15900 | 92.58% | 7.374% | 0.05031%
18060038 |  | 18060038 | 1 | SCL-LMC Nuclear Medicine | 2018-08-24 | 2019-01-16 | 0 | -3 | 1187 | 415050 | 421812.18 | 1314 | 1187 | 87.83% | 12.17% | 0%
18030010 |  | 18030010 | 1 | UMN-Golf Practice Facility | 2018-06-01 | 2019-01-15 | 5500 | 45809.13 | 28518 | 2985413.1787 | 3009583.87 | 2969.55 | 3379.82 | 98.39% | 1.613% | 0%
18110005 |  | 18110005 | 1 | USSS SCIF Conference Room | 2018-08-06 | 2019-01-09 | 606 | 0 | 0 | 668201.15 | 658009.44
18060043 |  | 18060043 | 1 | SCL-LMC W Pines Boiler Replace | 2018-11-01 | 2018-12-31 | 0 | -2 | 465 | 356612.39 | 357499.75 | 555 | 485 | 79.48% | 20.52% | 0%
18060044 |  | 18060044 | 1 | Park Creek-Filing 57 | 2018-10-05 | 2018-12-31 | 0 | 1 | 10 | 4417905.92 | 4696593.61 | 4600 | 11242.5 | 97.79% | 2.21% | 0%
18060017 |  | 18060017 | 1 | SCL-LMC Linear Accelerator | 2018-03-23 | 2018-12-31 | 1934 | 1460 | 1944 | 673899.76 | 685153.12 | 1884 | 1943.5 | 84.18% | 15.82% | 0%
18030001 |  | 18030001 | 1 | FUMC-Annual Contract 2018 | 2018-01-01 | 2018-12-31 | 0 | 0 | 0 | 1517640.42 | 1534850.34 | 0 | 4629.5 | 93.35% | 6.243% | 0.4104%
18030002 |  | 18030002 | 1 | Allina Annual Contract - 2018 | 2018-01-01 | 2018-12-31 | 0 | 0 | 25 | 11292062.15 | 11282412.55 | 0 | 57655.57 | 89.15% | 10.34% | 0.5117%
18030015 |  | 18030015 | 1 | Basilica Annual 2018 | 2018-05-13 | 2018-12-31 | 0 | 15952 | 16151 | 364155 | 378365.18 | 3129 | 1691.5 | 90.22% | 9.784% | 0%
18030034 |  | 18030034 | 1 | Fairview - Zucker Media Lounge | 2018-08-08 | 2018-12-31 | 709 | 87.4 | 0 | 359536.53 | 361523.91 | 699 | 584 | 98.03% | 1.969% | 0%
18030038 |  | 18030038 | 1 | Fairview-PEDs ED Remodel | 2018-09-05 | 2018-12-31 | 709 | 2 | 0 | 244830.87 | 232632.39 | 557 | 661 | 96.6% | 3.404% | 0%
18030014 |  | 18030014 | 1 | UMN Field House Ext & Flrg | 2018-09-01 | 2018-12-31 | 80000 | 206314.99 | 51940 | 7223842.9701 | 7236012.65 | 7810.3 | 9096.5 | 98.92% | 1.083% | 0%
18050011 |  | 18050011 | 1 | OHSU Micro Lab Rennovation | 2018-01-01 | 2018-12-31 | 0 | 20 | 0 | 3114.8 | 802.09
18050022 |  | 18050022 | 1 | KSMC FSD Testing & Replace | 2018-04-15 | 2018-12-31 | 0 | 12505.5 | 6136 | 276938.14 | 289814.24 | 470 | 1016.5 | 71.37% | 21.84% | 6.788%
18050026 |  | 18050026 | 1 | Kaiser SMC SPC Bridge for CSP2 | 2018-06-07 | 2018-12-31 | 0 | 236255 | 40909 | 2903983.425 | 2901845.45 | 8591 | 6285.5 | 95.62% | 4.113% | 0.2705%
18146002 |  | 18146002 | 1 | Beaver Creek II Wind - HVT | 2018-03-26 | 2018-12-31 | 0 | 1004861 | 371597 | 16578749.23 | 16173405.67 | 13254 | 16996.75 | 79.3% | 20.7% | 0%
18148009, 18146010, 18141008 |  | 18146010 | 11 | Ivester Wind - HVT | 2018-07-30 | 2018-12-31 | 0 | 445126 | 351610 | 7820035.8755 | 7835021.46 | 9428 | 12668.25 | 78.15% | 21.85% | 0%
18146022 |  | 18146022 | 1 | GE Rio Hondo 2 | 2018-11-05 | 2018-12-31 | 0 | 17 | 1 | 503433.17 | 382353.95 | 370 | 2427.5 | 78.06% | 21.94% | 0%
18141001 |  | 18141001 | 1 | Mezquite Wind | 2018-02-01 | 2018-12-31 | 0 | 0 | 0 | 19141.67 | 14091.26
18141009 |  | 18141009 | 1 | GE Foundation Analysis Wind | 2018-05-01 | 2018-12-31 | 0 | 0 | 0 | 21087.15 | 10912.37
18141011, 18148016 |  | 18141011 | 1 | Bobcat Bluff Repower Wind | 2018-06-05 | 2018-12-31 | 0 | 1791 | 1569 | 19797571.86 | 18950361.83 | 70906 | 85292.18 | 81.97% | 18.03% | 0%
18146009, 18148006, 18141004 |  | 18146009 | 1 | Arbor Hills Wind - HVT | 2018-05-21 | 2018-12-29 | 0 | 592995 | 453435 | 17748473.41 | 17657166.79 | 16616 | 18543.5 | 76.26% | 23.61% | 0.1294%
18030036 |  | 18030036 | 1 | NS VI-Intertek TI | 2018-08-13 | 2018-12-28 | 70509 | 1713 | 0 | 3078984.73 | 2987570.45 | 2059 | 3448.03 | 99.54% | 0.464% | 0%
18050040 |  | 18050040 | 1 | Swedish Edmonds Op Rm 5 | 2018-11-26 | 2018-12-21 | 0 | 2887.62 | 0 | 73954.69 | 70242.07 | 301.57 | 248 | 100% | 0% | 0%
18146009, 18148006, 18141004 |  | 18141004 | 21 | Arbor Hill Wind | 2018-06-01 | 2018-12-21 | 0 | 6674 | 3709 | 82254762.049 | 85272434.04 | 109139 | 140744.1 | 59.68% | 34.26% | 6.059%
18146008, 18148008, 18145004 |  | 18146008 | 1 | Hamilton Solar - HVT | 2018-08-18 | 2018-12-15 | 0 | 37953 | 34392 | 2434876.27 | 2884562.4 | 1461 | 4655.5 | 72.47% | 27.53% | 0%
18050009 |  | 18050009 | 1 | PRMCE Pacific Lab Equipment | 2018-09-15 | 2018-12-15 | 0 | 0 | 0 | 4620 | 7892.1
18146011 |  | 18146011 | 1 | Upton County 2 BESS | 2018-08-01 | 2018-12-14 | 0 | 22372 | 25751 | 3050937.68 | 3327438.42 | 3624 | 5774.75 | 74.97% | 25.03% | 0%
18148004, 18141005 |  | 18141005 | 11 | Meadow Lake VI Wind | 2018-04-02 | 2018-12-14 | 0 | 8052 | 7516 | 62367638.06 | 78148932.98 | 98993 | 195613.45 | 60.61% | 20.34% | 19.05%
18148009, 18146010, 18141008 |  | 18141008 | 21 | Ivester Wind | 2018-07-16 | 2018-12-07 | 0 | 3492 | 1601 | 29565394.08 | 31682082.21 | 31516 | 53435.3 | 60.82% | 33.7% | 5.479%
18148002 |  | 18148002 | 1 | Chokecherry Civil | 2018-04-02 | 2018-12-01 | 0 | 1237059 | 940274 | 14407678.616 | 14788980.14 | 84516 | 72171.5 | 76.04% | 23.54% | 0.4219%
18060045 |  | 18060045 | 1 | Mile High United Way-BTG | 2018-10-05 | 2018-12-01 | 0 | 716.37 | 16 | 25506.47 | 18993.02 | 68 | 32 | 75% | 25% | 0%
18148021 |  | 18148021 | 1 | Palo Alto Maintenance Subst | 2018-07-01 | 2018-11-30 | 0 | 0 | 0 | 56954.05 | 57389.61
18060029 |  | 18060029 | 1 | SCL-LMC First Responder | 2018-06-01 | 2018-11-30 | 0 | 1026 | 1398 | 1289562.94 | 1284063.69 | 1354 | 1556 | 90.17% | 9.833% | 0%
18080018 |  | 18080018 | 1 | IUOE - Shed Door Replacement | 2018-11-27 | 2018-11-30 | 0 | 0 | 0 | 4475 | 3997.53 | 30 | 23 | 100% | 0% | 0%
18040013 |  | 18040013 | 1 | APS Hub West - RID Relocation | 2018-11-05 | 2018-11-17 | 100000 | 666 | 0 | 73900.9 | 93525.72 | 389 | 584 | 71.23% | 28.77% | 0%
18030037 |  | 18030037 | 1 | Allina-Mercy CT #3 Renovation | 2018-07-23 | 2018-11-12 | 3500 | 0 | 11 | 698024.34 | 616846.88 | 2567 | 2226.5 | 90.52% | 9.297% | 0.1797%
18090005, 17090008 |  | 18090005 | 1 | UAL Pad of the Future (POTF) | 2018-03-01 | 2018-11-06 | 0 | 0 | 0 | 6344983.34 | 6015179.46
18030023 |  | 18030023 | 1 | Fairview-BH Ligature Phase 3 | 2018-05-28 | 2018-11-01 | 0 | 2091 | 2 | 683697.83 | 649139.24 | 3828 | 2848 | 93.35% | 6.654% | 0%
18030019 |  | 18030019 | 1 | UMN-Bierman Wrestling Prac | 2018-05-01 | 2018-11-01 | 13174 | 29854.59 | 0 | 1876237.9998 | 1908261.51 | 2158.05 | 2162.75 | 99.86% | 0.1387% | 0%
18090007 |  | 18090007 | 1 | Rush Univ Med Center HR Dept | 2018-06-01 | 2018-10-31 | 10661 | 6428.78 | 17 | 742871.6399 | 747445.73 | 503 | 715 | 72.73% | 22.17% | 5.105%
18060020 |  | 18060020 | 1 | Woodward-WLC Heat Treat | 2018-04-16 | 2018-10-31 | 0 | 2 | 0 | 898332 | 864808.36 | 0 | 959.5 | 93.85% | 6.149% | 0%
18030029 |  | 18030029 | 1 | Sanford Bio Skills Lab Fit Up | 2018-06-11 | 2018-10-31 | 4500 | 4 | 0 | 524870 | 496585.13 | 607 | 452 | 94.91% | 5.088% | 0%
18148007, 18141003 |  | 18141003 | 11 | Charles City Repower Wind | 2018-05-01 | 2018-10-31 | 0 | 4964.5 | 1764 | 10212716.3182 | 9765221.37 | 32140 | 33932.5 | 63.27% | 35.04% | 1.692%
18080006 |  | 18080006 | 1 | AHC - Suite 480 Remodel | 2018-07-03 | 2018-10-24 | 2350 | 22858 | 11014 | 675370.57 | 598345.48 | 1322.3 | 1029 | 95.34% | 4.665% | 0%
18030030 |  | 18030030 | 1 | Timberwolves - TIR & Bollards | 2018-08-31 | 2018-10-19 | 7362 | 94539.39 | 46340 | 2447248.93 | 2421365.32 | 4415.4 | 4227 | 90.89% | 9.061% | 0.04731%
18050036 |  | 18050036 | 1 | Alaska Fed Renton Branch | 2018-10-09 | 2018-10-15 | 0 | 11314.5 | 141 | 112399.83 | 109126.27 | 190.3 | 150.5 | 96.01% | 3.987% | 0%
18050019 |  | 18050019 | 1 | Kaiser SYB GenRad Replacement | 2018-08-20 | 2018-10-12 | 0 | 8286 | 1975 | 362452.73 | 359627.42 | 974 | 843 | 95.26% | 4.745% | 0%
18110001 |  | 18110001 | 1 | UDC Silver Universe LSI | 2018-01-02 | 2018-10-03 | 12500 | 15934 | 0 | 3855776.87 | 3575414.27
18080017 |  | 18080017 | 1 | Downstream - Fiserv Forum | 2018-09-25 | 2018-10-03 | 50 | 0 | 0 | 0.01 | 0
18060019 |  | 18060019 | 1 | FRA-Master Plan | 2018-04-01 | 2018-10-01 | 0 | 110 | 0 | 55000 | 80569.42
18060011 |  | 18060011 | 1 | SCL-LMC Cath Lab #3 | 2018-04-23 | 2018-10-01 | 936 | 1443 | 1742 | 737579.77 | 735664.72 | 1301 | 1727 | 89.87% | 10.13% | 0%
18060013 |  | 18060013 | 1 | SCL-LMC-Pharmacy Automation | 2018-05-01 | 2018-09-30 | 960 | 871 | 641 | 276092.06 | 276137.42 | 776 | 678 | 92.55% | 7.448% | 0%
18060004 |  | 18060004 | 1 | Woodward-Hydraulics Lab | 2018-01-29 | 2018-09-28 | 0 | 70627.64 | 6919 | 11643214.5 | 11150812.01 | 5924.02 | 6556.5 | 93.99% | 6.009% | 0%
18050002 |  | 18050002 | 1 | OHSU Pharmacy & Call Center | 2018-06-17 | 2018-09-28 | 0 | 11727.99 | 839 | 2888104.97 | 2901972.42 | 1579 | 2487.5 | 94.99% | 4.945% | 0.0603%
18080009 |  | 18080009 | 1 | S.C.Johnson-Rondelle | 2018-06-11 | 2018-09-24 | 5027 | 788 | 460 | 537824.35 | 739957.11 | 36 | 235.91 | 96.22% | 3.777% | 0%
18030024 |  | 18030024 | 1 | Fairview-ECT Bthrm Refurb | 2018-07-03 | 2018-09-15 | 0 | 177 | 0 | 69621.14 | 68485.71 | 199 | 119 | 99.16% | 0.8403% | 0%
18030032 |  | 18030032 | 1 | UMN-Anderson Hall Column | 2018-07-31 | 2018-09-01 | 0 | 6444 | 0 | 353500.414 | 321655.31 | 1145.87 | 1959.23 | 89.74% | 9.855% | 0.4083%
18030035 |  | 18030035 | 1 | UMN-TCF Bank Eng Review | 2018-07-31 | 2018-09-01 | 0 | 0 | 0 | 24963 | 16040.12 | 106 | 37 | 72.97% | 27.03% | 0%
18030016, 18030004 |  | 18030016 | 1 | Transamerica-6300 Bldg Reno | 2018-04-02 | 2018-08-31 | 160000 | 293629.5 | 17973 | 11535413.0265 | 11622900.04 | 10966 | 10648.74 | 77.74% | 21.45% | 0.8076%
18050017, 18050004 |  | 18050017 | 1 | PPS Tubman Middle School | 2018-04-05 | 2018-08-26 | 0 | 40889.31 | 11756 | 17007949.0555 | 15574863.32 | 5677.4 | 5262 | 91.25% | 7.839% | 0.9122%
18030026 |  | 18030026 | 1 | UMN Frontier Hall Int Upgrades | 2018-05-21 | 2018-08-24 | 8151 | 18360 | 12110 | 1071741.3 | 1128207.11 | 2835 | 2933.89 | 98.72% | 1.278% | 0%
18060023 |  | 18060023 | 1 | SCL-LMC ED Metal Detect | 2018-05-01 | 2018-08-17 | 0 | 60 | 80 | 40125 | 40593.8 | 76 | 89 | 82.58% | 17.42% | 0%
18030018 |  | 18030018 | 1 | Boiler Room Remodel | 2018-05-14 | 2018-08-17 | 0 | 4 | 0 | 1729923.1 | 1449518.04 | 2848 | 3613.74 | 97.87% | 2.131% | 0%
18050032 |  | 18050032 | 1 | Alaska Fed Kirkland Branch | 2018-07-18 | 2018-08-14 | 0 | 9758.37 | 128 | 339639.88 | 297201.34 | 693.2 | 497 | 94.77% | 5.231% | 0%
18030022 |  | 18030022 | 1 | UMN Yudof Hall Plaza Repair | 2018-05-21 | 2018-08-10 | 3500 | 17531 | 0 | 210458 | 198599.75 | 892 | 569.19 | 98.07% | 1.933% | 0%
18050021 |  | 18050021 | 1 | Kaiser MTS GenRad Replacement | 2018-05-15 | 2018-08-01 | 0 | 3270 | 339 | 300634.47 | 301096.65 | 531 | 610.5 | 85.34% | 11.88% | 2.785%
18146012, 16080015 |  | 18146012 | 1 | SC Johnson West MILW - HVT | 2018-01-17 | 2018-08-01 | 0 | 0 | 0 | 505283.38 | 490032.3
18060012 |  | 18060012 | 1 | SCL-LMC-USP 800 Infusion | 2018-05-01 | 2018-07-31 | 550 | 1197 | 355 | 137555.26 | 137490.26 | 550 | 364 | 89.42% | 10.58% | 0%
18050028 |  | 18050028 | 1 | 427 9th Ave - Design Phase T | 2018-05-01 | 2018-07-31 | 0 | 0 | 0 | 226800 | 291808.84
18040001 |  | 18040001 | 1 | EPCOR Sun City Well 2 Equip | 2018-03-19 | 2018-07-16 | 25000 | 53973 | 0 | 1177972.13 | 1453823.58 | 1616 | 4613.5 | 92.29% | 7.706% | 0%
18030027 |  | 18030027 | 1 | St Cloud Surg. Ctr-Master Ag | 2018-06-29 | 2018-07-14 | 2500 | 103 | 0 | 197224.1 | 189500.07 | 311 | 198.5 | 72.54% | 13.1% | 14.36%
18060016 |  | 18060016 | 1 | SCL-LMC RF Imaging Renovate | 2018-04-23 | 2018-07-09 | 800 | 1221.5 | 1178 | 474646.27 | 480860.37 | 1021.5 | 1206 | 88.1% | 11.9% | 0%
18060018 |  | 18060018 | 1 | SCL-St Joe's Heritage Russell | 2018-03-26 | 2018-07-01 | 0 | 87 | 0 | 13396 | 15223.62 | 82 | 65 | 63.85% | 36.15% | 0%
18141006 |  | 18141006 | 1 | Fenner RP Civil Works Wind | 2018-03-19 | 2018-07-01 | 0 | 0 | 0 | 70240 | 69561.59
18030020 |  | 18030020 | 1 | Swervo-Armory Sidewalk Impr | 2018-05-07 | 2018-06-30 | 0 | 9251 | 0 | 65013 | 63310.87 | 447 | 425.5 | 91.19% | 8.813% | 0%
18050015 |  | 18050015 | 1 | OHSU - MAC Auditorium Upgrades | 2018-03-01 | 2018-06-29 | 0 | 2079.1 | 223 | 588034.02 | 620797.43 | 1323.5 | 1922 | 90.63% | 8.949% | 0.4162%
18146005 |  | 18146005 | 1 | Kittie West Substation | 2018-03-22 | 2018-06-22 | 0 | 109600.8 | 120072 | 591723.7389 | 759423.94 | 2989 | 5934.5 | 84.36% | 15.64% | 0%
18060003 |  | 18060003 | 1 | SCL-LMC Data Ctr Renovations | 2018-01-03 | 2018-06-18 | 0 | 1798 | 2649 | 1163411.9525 | 1184103.83 | 2850 | 2724 | 89.61% | 10.39% | 0%
18050020 |  | 18050020 | 1 | Kaiser SMC GenRad Replacement | 2018-05-01 | 2018-06-15 | 0 | 1562 | 769 | 177075.19 | 177196.48 | 470 | 448 | 93.75% | 5.357% | 0.8929%
18080003 |  | 18080003 | 1 | AHC - Manitowoc MRI Swap | 2018-03-23 | 2018-06-11 | 0 | 5468.85 | 729 | 299250.84 | 321441.14 | 473 | 422 | 94.91% | 5.095% | 0%
18060027 |  | 18060027 | 1 | SCL-St. Joe's Salad Bar | 2018-05-08 | 2018-06-08 | 0 | 0 | 0 | 8985 | 8844.29 | 0 | 28 | 89.29% | 10.71% | 0%
18060015 |  | 18060015 | 1 | SCL-Mt St Vincent Ph1 | 2018-03-19 | 2018-06-01 | 0 | 472 | 1297 | 507788.56 | 513409.72 | 432 | 2185.5 | 92.88% | 7.115% | 0%
18145006 |  | 18145006 | 1 | Alamo 7 - MET Towers | 2018-04-23 | 2018-06-01 | 0 | 114 | 0 | 15249.19 | 13478.32 | 96 | 52 | 100% | 0% | 0%
18050001 |  | 18050001 | 1 | OHSU Voll. Inst. Bac. Remodel | 2018-03-09 | 2018-05-31 | 0 | 2165.6 | 2068 | 588733.98 | 616484.79 | 576.4 | 873 | 97.71% | 2.291% | 0%
18030041 |  | 18030041 | 1 | Silver Lake Investors-428 Demo | 2018-09-17 | 2018-05-25 | 42000 | 0 | 0 | 342186 | 334411.4 | 40 | 62.5 | 100% | 0% | 0%
18146001 |  | 18146001 | 1 | Bishop-Stratton HVT | 2018-02-20 | 2018-05-25 | 0 | 127446 | 126778 | 1560607.1 | 1601358.22 | 5932 | 6155 | 70.33% | 29.67% | 0%
18146003 |  | 18146003 | 1 | Hidalgo Fiber Rpr Wind - HVT | 2018-02-26 | 2018-05-25 | 0 | 5 | 173 | 48589.05 | 62973.54 | 0 | 173.5 | 69.16% | 30.84% | 0%
18040005 |  | 18040005 | 1 | Allstate-Chandler Desert MCO | 2018-02-19 | 2018-05-18 | 96859 | 30 | 0 | 2699634.2798 | 2665492.44 | 0 | 333 | 98.65% | 1.351% | 0%
18030021 |  | 18030021 | 1 | Mortenson Misc 2018 |  | 2018-05-11 | 0 | 0 | 0 | 0.01 | 286501.85 | 0 | 2277 | 98.46% | 1.537% | 0%
18030009 |  | 18030009 | 1 | Axalta Coatings-Mfg | 2018-02-19 | 2018-05-04 | 54990 | 0 | 0 | 4969357.6965 | 4273622.61 | 2935 | 2235.85 | 95.89% | 3.757% | 0.3578%
18050017, 18050004 |  | 18050004 | 11 | PPS Tubman Middle Sch. Precon | 2018-01-01 | 2018-04-30 | 0 | 856.4 | 0 | 385492.51 | 437496.14 | 0 | 96 | 100% | 0% | 0%
18030005 |  | 18030005 | 1 | NS-Resolution Medical TI | 2018-01-11 | 2018-04-15 | 35880 | 3575 | 5381 | 1603231.97 | 1339716.53 | 1817 | 1456 | 97.73% | 2.266% | 0%
18146007 |  | 18146007 | 1 | GE Rio Hondo HVT | 2018-04-09 | 2018-04-15 | 0 | 0 | 0 | 34506.34 | 19147.41 | 0 | 124 | 64.52% | 35.48% | 0%
18060009 |  | 18060009 | 1 | Park Creek-STP SML PRJ | 2018-03-12 | 2018-04-06 | 0 | 22 | 0 | 520926 | 518635.46 | 278 | 80.5 | 100% | 0% | 0%
18150007 |  | 18150007 | 1 | PSU - Lasch Player's Lounge | 2018-08-06 | 2018-04-01 | 4900 | 0 | 0 | 4158775.0441 | 4149691.11
18050016 |  | 18050016 | 1 | OHSU Compounding Pharmacy Duct | 2018-03-03 | 2018-03-03 | 0 | 398 | 0 | 18695.46 | 26206.9 | 25 | 9 | 0% | 100% | 0%
18030016, 18030004 |  | 18030004 | 11 | Transamerica 6350 Bldg Rmdl | 2018-01-08 | 2018-03-02 | 23620 | 5940 | 90859 | 286103.58 | 277941.42 | 243 | 287.5 | 100% | 0% | 0%
18145001 |  | 18145001 | 1 | Misae I Solar-Childress | 2018-01-22 | 2018-02-28 | 0 | 5 | 0 | 65044 | 60671.37
18030028 |  | 18030028 | 1 | MUSC-Allianz Field Exp Ctr | 2017-12-26 | 2018-02-02 | 1835 | 0 | 0 | 174754.65 | 173503.22 | 180 | 56 | 100% | 0% | 0%
18110002 |  | 18110002 | 1 | USACE Warehouse Floor Sealer | 2018-01-09 | 2018-01-31 | 8000 | 0 | 0 | 15156 | 15161.64 | 37 | 35.99 | 66.66% | 33.34% | 0%
18819 |  | 18819 | 1 | ENXCO-CHANARAMBIE WIND FARM | 2003-12-15 | 2003-10-31 | 0 | 3422358 | 60949 | 18012075 | 18012744 | 0 | 65664 | 100% | 0% | 0%
18805 |  | 18805 | 1 | CHI ENERGY INC.-FENNER WIND P |  | 2001-11-15 | 0 | 110060 | 107796 | 6791769 | 6803509 | 0 | 5073 | 100% | 0% | 0%
18806 |  | 18806 | 1 | NORTHERN IOWA WINDPOWER-TOP O | 2001-12-01 | 2001-10-12 | 0 | 112312 | 51910 | 11413621 | 11407031 | 0 | 11555 | 100% | 0% | 0%
18807 |  | 18807 | 1 | MILL RUN WINDPOWER-MILL RUN W | 2001-11-16 | 2001-09-28 | 0 | 773243 | 2806 | 2759073 | 2762007 | 0 | 3608 | 100% | 0% | 0%
18810 |  | 18810 | 1 | ENRON WIND-MILL RUN/SOMERSET | 2001-09-20 | 2001-09-20 | 0 | 301 | 177 | 670195 | 792433 | 0 | 5241 | 100% | 0% | 0%
18811 |  | 18811 | 1 | ENXCO-CHANDLER WINDFARM | 2001-09-01 | 2001-09-01 | 0 | 5406 | 3337 | 381592 | 384111 | 0 | 748 | 100% | 0% | 0%
18809 |  | 18809 | 1 | GREAT RIVER ENERGY-PLEASANT V | 2002-06-01 | 2001-05-24 | 0 | 204 | 0 | 5778285 | 5786677 | 0 | 5067 | 100% | 0% | 0%
18148001 |  | 18148001 | 1 | Century III Repowering Civil | 2018-01-09 |  | 0 | 0 | 0 | 182170.95 | 173090.75 | 165 | 0 | 0% | 0% | 0%
18148003 |  | 18148003 | 1 | Beaver Creek II Civil | 2018-01-25 |  | 0 | 328991 | 493154 | 9253759.999 | 8742226.77 | 31194 | 32720.78 | 66.12% | 33.39% | 0.4905%
18148005 |  | 18148005 | 1 | Fenner RePowering Civil | 2018-03-20 |  | 0 | 0 | 0 | 37636 | 27955.7
18146009, 18148006, 18141004 |  | 18148006 | 11 | Arbor Hill Wind - Civil | 2018-05-21 |  | 0 | 498529 | 635000 | 20700348.0141 | 19524419.78 | 55380.12 | 70691.5 | 64.23% | 34.44% | 1.328%
18148007, 18141003 |  | 18148007 | 1 | Charles City RePowering | 2018-04-26 |  | 0 | 466 | 51724 | 1814526.307 | 1673445.25 | 7469 | 6606 | 68.57% | 29.96% | 1.468%
18146008, 18148008, 18145004 |  | 18148008 | 11 | Hamilton Solar - Civil | 2018-06-18 |  | 0 | 151726 | 237482 | 2151914.86 | 1983225.88 | 8406 | 7186 | 76.34% | 23.66% | 0%
18148009, 18146010, 18141008 |  | 18148009 | 1 | Ivester - Civil | 2018-07-16 |  | 0 | 167193 | 143305 | 5708693.6107 | 5771061.52 | 17973.5 | 21843.2 | 69.77% | 28.05% | 2.184%
18141010, 18148010 |  | 18148010 | 11 | Heartland Divide Wind - Civil | 2018-07-30 |  | 0 | 557190 | 318357 | 6597638.0115 | 7367568.71 | 27198 | 30294.5 | 68.38% | 31.17% | 0.4506%
18148012 |  | 18148012 | 1 | Buffalo Ridge Decommissioning | 2018-06-11 |  | 0 | 34803 | 0 | 617685 | 645407.63 | 1561 | 3098 | 84.04% | 15.96% | 0%
17145018, 18148014 |  | 18148014 | 11 | Montross Solar - Civil | 2018-07-20 |  | 0 | 76961 | 20612 | 1637282.18 | 1547566.2 | 23822 | 4597.66 | 81.06% | 18.94% | 0%
18141007, 18148015 |  | 18148015 | 11 | Pomeroy Repower Civil | 2018-08-13 |  | 0 | 6068 | 724 | 3966364.2387 | 3639394.25 | 17520 | 15046 | 72.89% | 27.11% | 0%
18148017 |  | 18148017 | 1 | Misae I - Civil (Solar) | 2018-11-07 |  | 0 | 380633 | 268059 | 3971026.9633 | 3974717.98 | 30963 | 17638.5 | 79.78% | 20.22% | 0%
18148019 |  | 18148019 | 1 | Carroll Repower Wind - CIVIL | 2018-10-10 |  | 0 | 25796.1 | 66 | 2885517.1479 | 2499907.38 | 11969 | 9748 | 81.76% | 18.24% | 0%
18148022 |  | 18148022 | 1 | Terrell Civil (Solar) | 2019-02-07 |  | 0 | 392575 | 369971 | 11293157.212 | 11120143.88 | 27925 | 50651.08 | 81.66% | 18.33% | 0.01086%
18148023 |  | 18148023 | 1 | Arlington Civil (Solar) | 2019-01-17 |  | 0 | 326510 | 157965 | 3346521.02 | 3488770.83 | 9950 | 14615 | 81.68% | 18.32% | 0%
17141013, 18148024, 19146004 |  | 18148024 | 11 | Palo Alto Wind - CIVIL | 2019-05-06 |  | 0 | 941175 | 578925 | 19880460.2707 | 18497038.05 | 67307.5 | 63657 | 66.83% | 32.37% | 0.8067%
18080013 |  | 18080013 | 1 | Kohler - Riverbend Renovation | 2019-01-02 |  | 11896 | 73728 | 44224 | 2145265.98 | 1999286.68 | 1979.7 | 2096 | 90.62% | 9.065% | 0.3101%
18030006 |  | 18030006 | 1 | MDI-Blaine Industrial | 2018-09-01 |  | 0 | 320729.6 | 545 | 4570823.74 | 4480780.66 | 7296.9 | 6560.47 | 96.52% | 3.475% | 0%
18030040 |  | 18030040 | 1 | Snelling-Midway-Bank Demo | 2017-12-15 |  | 0 | 0 | 0 | 407036.84 | 405571.85 | 95.92 | 0 | 0% | 0% | 0%
18030050 |  | 18030050 | 1 | UMN-Mariucci Arena Weight Rm | 2019-04-01 |  | 8800 | 58311 | 2168 | 1583893.92 | 1631481.55 | 2076.9 | 2539 | 99.82% | 0.1772% | 0%
18030046 |  | 18030046 | 1 | Fed Re Bank - Heritage |  |  | 220000 | 0 | 0 | 0.01 | 0
18030051 |  | 18030051 | 1 | Fed Reserve Bank - Heritage |  |  | 220000 | 0 | 0 | 88158.7 | 102782.16
18040010 |  | 18040010 | 1 | ASU Multi-Purpose Arena |  |  | 405000 | 0 | 0 | 648016.02 | 749517.12
18040010-173 |  | 18040010-173 | 1 | Mortenson-McCarthy ASU Arenas |  |  | 405000 | 0 | 0 | 924329 | 803747.06
18050012 |  | 18050012 | 1 | OHSU NICU Flooring Replacement | 2017-10-18 |  | 0 | 20 | 0 | 3234.04 | 450.69
18050013 |  | 18050013 | 1 | OCC Office & Garage Expansion | 2020-01-01 |  | 0 | 0 | 0 | 1429378.75 | 1097834.27
18050033 |  | 18050033 | 1 | Portland Art Museum Rothko |  |  | 0 | 421575.71 | 0 | 73950228.39 | 2497116.67 | 23357.8 | 440.5 | 99.32% | 0.681% | 0%
18050054 |  | 18050054 | 1 | Nike Air Hangar 2019 | 2019-01-01 |  | 38392 | 68745.62 | 0 | 3566310.96 | 2983613.15 | 48 | 0 | 0% | 0% | 0%
18050056 |  | 18050056 | 1 | LOSD Westridge Elementary Reno | 2019-05-31 |  | 40000 | 239077.3 | 124582 | 11040334.05 | 10395518.17 | 16666.25 | 13784 | 84.8% | 13.25% | 1.948%
18050003 |  | 18050003 | 1 | 2018 VI Project |  |  | 0 | 0 | 0 | 87750 | 208877.56
18050010 |  | 18050010 | 1 | SEF New Yard TI |  |  | 0 | 0 | 0 | 1921633 | -2801.09 | 48 | 66.5 | 100% | 0% | 0%
18050014 |  | 18050014 | 1 | Seattle Sports Arena Precon | 2018-11-01 |  | 0 | 2105 | 0 | 275000 | 522930.18 | 0 | 56 | 100% | 0% | 0%
18050029 |  | 18050029 | 1 | Bend N Interceptor No 1SNIP |  |  | 0 | 76616.49 | 61858 | 27608625.695 | 25709230.19 | 12585.8 | 10482.39 | 94.08% | 5.772% | 0.1526%
18050041 |  | 18050041 | 1 | City of Ashland Pro Service |  |  | 0 | 0 | 0 | 112572.95 | 101407.79
18145009 |  | 18145009 | 1 | Alamo 4 - Expansion - OCI | 2018-09-20 |  | 0 | 0 | 0 | 0.01 | 328.03
18145010 |  | 18145010 | 1 | Misae II Geotech/PLT | 2018-09-20 |  | 0 | 1058 | 0 | 245312 | 247029.14 | 656 | 505 | 84.36% | 15.64% | 0%
18145011 |  | 18145011 | 1 | Spotsylvania Solar - SPower | 2019-03-19 |  | 0 | 38853631.78 | 18237641 | 301858678.0797 | 359631497.99 | 1300228.21 | 1941169.9 | 85.36% | 14.64% | 0.00103%
18145014 |  | 18145014 | 1 | Wilkinson Solar-Invenergy | 2019-04-01 |  | 95975000 | 10626768.8 | 3940059 | 41031573.182 | 50125076.69 | 205072.4 | 395166.85 | 82.17% | 17.82% | 0.003796%
19148007, 18145015 |  | 18145015 | 11 | Trenton Solar - Duke Energy | 2019-04-22 |  | 101847000 | 3214376 | 3446851 | 47892694.39 | 56161787.75 | 216711.25 | 329750.7 | 82.49% | 17.51% | 0%
18145016, 19148008 |  | 18145016 | 1 | Columbia Solar - Duke Energy | 2019-08-15 |  | 105319200 | 3027036 | 2648892 | 49639199 | 49328471.19 | 186171.66 | 216322 | 88.25% | 11.75% | 0%
18146008, 18148008, 18145004 |  | 18145004 | 21 | Duke-Hamilton Solar Facility | 2018-06-20 |  | 109589000 | 5033208 | 5314182 | 45758486.6 | 47629682.04 | 165306.36 | 244952.86 | 83.86% | 16.13% | 0.007552%
18145012 |  | 18145012 | 1 | Arlington II - Silicon Ranch | 2018-02-27 |  | 138498360 | 3564635 | 5309873 | 57796986.017 | 67950769.21 | 241554.05 | 548641.28 | 85.09% | 14.9% | 0.003099%
18150001-152 |  | 18150001-152 | 1 | Chase Center - Concrete | 2017-01-01 |  | 0 | 0 | 0 | 120727281 | 0
18150006-172 |  | 18150006-172 | 1 | New England Revolution Soccer |  |  | 0 | 0 | 0 | 0.01 | 0
18150009-152 |  | 18150009-152 | 1 | Verizon - Chase Center DAS | 2018-12-01 |  | 0 | 0 | 0 | 20560716 | 0
18150002 |  | 18150002 | 1 | PSU - Beaver Stadium 3rd Lvl |  |  | 9450 | 0 | 0 | 190621 | 168018.96
18150008-169 |  | 18150008-169 | 1 | Sports Auth Nashville - MLS St |  |  | 531467 | 92295 | 0 | 271238809.6167 | 261730943.82 | 153676.65 | 67301.75 | 94.85% | 5.148% | 0%
18141018 |  | 18141018 | 1 | Panther Creek Repower | 2018-10-08 |  | 0 | 1578 | 1462 | 27282501.06 | 31509397.45 | 109340 | 179088.13 | 78.81% | 21.19% | 0%
18801 |  | 18801 | 1 | POTLATCH-LEWISTON2001 SPRING | 2001-05-31 |  | 0 | 0 | 0 | 167966 | 190931 | 0 | 884 | 100% | 0% | 0%
18802 |  | 18802 | 1 | BOISE CASCADE-2001WORK | 2001-12-31 |  | 0 | 0 | 0 | 14862 | 14862 | 0 | 88 | 100% | 0% | 0%
18803 |  | 18803 | 1 | TRUS JOIST-2000 WORK | 2001-12-31 |  | 0 | 0 | 0 | 55492 | 58416 | 0 | 33 | 100% | 0% | 0%
18804 |  | 18804 | 1 | LAND O LAKES-MISC WORK 2001 | 2001-12-31 |  | 0 | 0 | 0 | 0 | 3222 | 0 | 4 | 100% | 0% | 0%
18808 |  | 18808 | 1 | KVAERNER-2001 SPRINGOUTAGE | 2001-05-25 |  | 0 | 0 | 0 | 250335 | 262046 | 0 | 1048 | 100% | 0% | 0%
18813 |  | 18813 | 1 | ENRON WIND-FENNER WIND ERECTI | 2001-11-19 |  | 0 | 371 | 280 | 1454462 | 1455998 | 0 | 8408 | 100% | 0% | 0%
18814 |  | 18814 | 1 | TEXAS WIND POWER-LLANO ESTACA | 2001-12-31 |  | 0 | 41475 | 37244 | 7025326 | 7029855 | 0 | 30037 | 100% | 0% | 0%
18816 |  | 18816 | 1 | POTLATCH-BRAINERD2002 WORK | 2002-11-30 |  | 0 | 0 | 0 | 63529 | 63528 | 0 | 166 | 100% | 0% | 0%
18817 |  | 18817 | 1 | TRUS JOIST-2002 WORK | 2002-11-30 |  | 0 | 0 | 0 | 0 | 648 | 0 | 0 | 0% | 0% | 0%
18818 |  | 18818 | 1 | CALPINE-METCALF ENERGY CENTER | 2002-06-01 |  | 0 | 0 | 0 | 3114471 | 3111317 | 0 | 54 | 100% | 0% | 0%
18899 |  | 18899 | 1 | MORTENSON-CLOSED JOBINDUSTRIA | 2001-12-31 |  | 0 | 0 | 0 | 0 | 157013 | 0 | 212 | 100% | 0% | 0%
18815 |  | 18815 | 1 | SHERBURNE ENVIROCK-2KF WEIGHT | 2001-10-10 |  | 1175 | 271 | 0 | 19676 | 19785 | 0 | 246 | 100% | 0% | 0%

## Data Pivot
Row Labels | Min of Construction Start Date | Max of Substantial Completion Date | Sum of Estimated Units | Sum of Actual Units | Sum of Estimated Cost | Sum of Actual Cost | Sum of Est Craft Labor Hours | Sum of Act Craft Labor Hours | Average of Act Craft NT % | Average of Act Craft OT % | Average of Act Craft DT %
14000002-040, 15050002 | 2015-09-01 | 2017-02-01 | 933650.76 | 933137 | 37740392.1058 | 41683714.41 | 25775 | 24745.15 | 0.83286 | 0.16027 | 0.00687
14030001 |  | 2014-12-31 | 35645.86 | 0 | 1857782.61 | 1841238.89 | 8880 | 10100 | 0.95975 | 0.027327 | 0.012921
14030002 | 2014-01-01 | 2016-12-31 | 0 | 0 | 504204.92 | 504007.8 | 1583.5 | 1922.5 | 0.98466 | 0.015345 | 0
14030003 | 2014-01-02 | 2014-01-24 | 249.06 | 0 | 39182 | 39440.93 | 129.5 | 133.01 | 1899-12-31 | 0 | 0
14030004 | 2014-01-06 | 2014-04-01 | 5098.2 | 0 | 863056.44 | 864560.95 | 1867 | 1394.5 | 0.97705 | 0.022947 | 0
14030005 | 2014-01-13 | 2014-05-30 | 1153.05 | 0 | 543068 | 530849.89 | 752 | 864.56 | 0.99075 | 0.0092533 | 0
14030006 | 2014-01-24 | 2014-01-29 | -9.64 | 0 | 22247 | 20860.42 | 98.5 | 99.5 | 0.72362 | 0.19095 | 0.085427
14030007 | 2014-02-03 | 2014-07-31 | 1082.33 | 0 | 1114412 | 1067357.14 | 1799 | 1807 | 0.98672 | 0.013282 | 0
14030008 | 2014-01-22 | 2014-12-31 | 513.65 | 0 | 1954997.4 | 0.42 | 1996 | 2291 | 0.77281 | 0.21803 | 0.0091663
14030009 | 2014-01-29 | 2016-03-17 | 372 | 0 | 78225.7 | 139584.12 | 8 | 383 | 0.96736 | 0.032637 | 0
14030010 | 2014-03-31 | 2014-08-15 | 7999 | 0 | 3339471.29 | 3274408.71 | 3129 | 2698.36 | 0.95108 | 0.048919 | 0
14030011 | 2014-02-25 |  | 16 | 0 | 573522 | 390754.9 | 962 | 666 | 0.91742 | 0.082583 | 0
14030012 | 2014-03-03 | 2014-05-23 | 5828.45 | 0 | 507966 | 505986.91 | 845 | 881.8 | 0.99773 | 0.0022681 | 0
14030013 | 2014-04-07 | 2014-10-31 | -823.43 | 4188 | 2995389 | 2931318.74 | 6411 | 5822.33 | 0.89824 | 0.10176 | 0
14030014 | 2014-05-14 | 2014-07-22 | 51 | 0 | 4770945.14 | 4752109.78 | 2438 | 3507.6 | 0.95624 | 0.043762 | 0
14030015 | 2014-02-23 | 2014-12-31 | 360034.572 | 0 | 10208750 | 9801370.77 | 9756.14 | 9084.5 | 0.82112 | 0.17888 | 0
14030016 | 2014-03-07 | 2015-05-29 | 341111.9 | 253478 | 22250346.23 | 21966534.48 | 39423.5 | 39313.07 | 0.96441 | 0.033322 | 0.0022639
14030017 | 2014-03-17 | 2014-06-30 | 2066 | 0 | 909466 | 865637.05 | 361 | 217 | 0.8894 | 0.1106 | 0
14030018 | 2014-03-17 | 2015-11-20 | 16993 | 0 | 878562.8116 | 719504.38 | 1969 | 1590.5 | 0.92801 | 0.07199 | 0
14030019 | 2014-03-13 | 2014-05-13 | 120.63 | 0 | 194879.38 | 191242.14 | 275 | 468.5 | 0.99787 | 0.0021345 | 0
14030020 | 2014-03-17 | 2014-12-31 | 370 | 0 | 120471.94 | 121670.3 | 394 | 448 | 0.96987 | 0.030134 | 0
14030021 | 2014-06-05 | 2014-10-16 | 6055.15 | 0 | 6325678.76 | 6318759.26 | 4155 | 3873.46 | 0.83503 | 0.16497 | 0
14030022 | 2014-06-16 | 2015-02-28 | 8722.36 | 0 | 2213713.79 | 2264764.52 | 2426 | 3195.5 | 0.99765 | 0.0023471 | 0
14030023 | 2014-07-07 | 2016-07-15 | 14799.7365 | 0 | 1641215.604 | 2002780.01 | 2706 | 2917 | 0.81282 | 0.18512 | 0.0020569
14030024 | 2014-03-07 |  | 0 | 0 | 0.01 | -0.07 | 0 | 8530 | 0.89695 | 0.10188 | 0.0011723
14030025 | 2014-04-03 |  | 0 | 0 | 70802 | 73591.79
14030026 | 2014-04-01 | 2014-12-30 | 2120.14 | 0 | 480673.23 | 461781.3 | 1079 | 1250.64 | 0.96002 | 0.03998 | 0
14030027 | 2014-02-27 | 2014-05-01 | 190.29 | 0 | 128647 | 104556.5 | 424 | 123 | 1899-12-31 | 0 | 0
14030028 | 2014-03-10 |  | 34 | 0 | 962410 | 985866.6 | 2542 | 2682.09 | 0.88293 | 0.11707 | 0
14030029 | 2014-06-09 | 2015-09-11 | 1494 | 0 | 3518068.54 | 3391267.86 | 2680 | 2649.8 | 0.94396 | 0.049626 | 0.0064156
14030030 | 2014-03-01 |  | 0 | 0 | 11574 | 17679.67
14030031 | 2014-05-22 | 2014-09-17 | 39799.33 | 0 | 783344.25 | 795923.74 | 2784 | 2475 | 0.93273 | 0.067273 | 0
14030032 | 2014-07-14 | 2015-01-02 | 823397 | 311899 | 10825927.23 | 10658924.79 | 13210 | 15752.7 | 0.88707 | 0.11141 | 0.0015235
14030033 | 2016-05-06 | 2018-09-07 | 1102439.46 | 760040 | 115862113.7914 | 114968520.37 | 95564.53 | 77651.48 | 0.88866 | 0.10428 | 0.0070572
14030034 | 2014-05-19 |  | 0 | 0 | 75720 | 74361.46 | 0 | 378.5 | 0.90225 | 0.097754 | 0
14030035 | 2014-06-03 | 2014-12-31 | 63 | 0 | 216725 | 230249.3 | 1877 | 901 | 0.73585 | 0.26415 | 0
14030036 | 2014-11-19 | 2015-05-15 | 18123 | 0 | 3559698.84 | 3597117.94 | 10041 | 10794.6 | 0.92839 | 0.066237 | 0.0053731
14030037 | 2014-07-13 |  | 20888.61 | 0 | 1251482.38 | 1181878.33 | 1115 | 737 | 0.79783 | 0.20217 | 0
14030038 | 2014-08-04 | 2014-12-26 | 228.2 | 0 | 173186.2 | 158497.6 | 290 | 311 | 0.96945 | 0.030547 | 0
14030039 | 2014-09-10 | 2015-03-15 | 1154.34 | 0 | 1739058.14 | 1674264.72 | 2163 | 2097 | 0.92895 | 0.059609 | 0.011445
14030040 | 2014-09-08 | 2014-10-20 | 4 | 0 | 121226 | 120937.28 | 336 | 312 | 0.87821 | 0.12179 | 0
14030041 | 2014-10-13 |  | 9 | 0 | 336744.39 | 353638 | 1212 | 1127.5 | 0.94457 | 0.055432 | 0
14030042 | 2014-10-30 | 2015-11-30 | 6 | 584567 | 24240248.84 | 23787912.72 | 21540 | 22114.14 | 0.81125 | 0.18432 | 0.0044316
14030043 | 2014-01-01 | 2015-06-30 | 0 | 0 | 0.01 | 29257404.55 | 0 | 127551.54 | 0.88763 | 0.10087 | 0.011505
14030044 | 2014-11-03 | 2014-12-31 | 6279.17 | 0 | 735678.57 | 711527.87 | 1863 | 1795.5 | 0.98329 | 0.016708 | 0
14030045 | 2015-03-01 | 2017-02-06 | 227472 | 169515 | 27905214.331 | 25960744.96 | 12526.44 | 11988.5 | 0.66585 | 0.29441 | 0.039746
14030046 | 2015-04-01 | 2016-07-20 | 380084 | 295430 | 28593981.61 | 26469012.17 | 28703.5 | 30819 | 0.94893 | 0.048639 | 0.0024336
14030047 | 2015-04-01 | 2016-10-14 | 1204930 | 718558 | 39303768.5716 | 37517067.95 | 39525 | 46939.5 | 0.92498 | 0.075022 | 0
14030048 | 2015-01-01 | 2016-01-15 | 81384.0041 | 0 | 13950491.26 | 13502534.68 | 14821 | 14004.5 | 0.80535 | 0.19379 | 0.00085687
14030049 | 2015-04-01 | 2015-05-08 | 0 | 0 | 90701 | 92464.66 | 0 | 24 | 1899-12-31 | 0 | 0
14030050 | 2014-12-01 | 2015-02-06 | 249 | 0 | 205963 | 196998.28 | 213 | 181.5 | 1899-12-31 | 0 | 0
14030051 | 2015-01-15 | 2015-08-14 | 236268 | 0 | 9557549.57 | 9602781.27 | 13923 | 10727.45 | 0.88021 | 0.11979 | 0
14030052 | 2015-05-11 | 2015-08-14 | 37587 | 32898 | 2687423.72 | 2433258.61 | 6251 | 4868.18 | 0.97679 | 0.019823 | 0.0033894
14030053 | 2015-01-26 |  | 143339 | 36627 | 12737225.38 | 12104260.5 | 6988 | 12616.18 | 0.95779 | 0.041336 | 0.0008719
14030054 | 2015-11-02 | 2018-09-04 | 3459675 | 2432594 | 107026144.0185 | 100531025.81 | 217683.1 | 152716.22 | 0.90964 | 0.089411 | 0.00094947
14030054-900 | 2015-11-02 | 2018-02-16 | 4 | 0 | 42449253.28 | 42453385.88
14030055 | 2014-12-15 | 2015-04-10 | 31581 | 0 | 1739078 | 1701226.8 | 3022 | 4091.5 | 0.92656 | 0.073445 | 0
14030997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -2279740.5
14030999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 26496.22 | 0 | 2617 | 0.93733 | 0.062667 | 0
14040001 | 2014-03-31 | 2014-03-25 | 0 | 0 | 38088 | 30180.97
14040002 | 2014-06-22 | 2014-08-31 | 4612.6 | 0 | 355140.92 | 352906.35 | 0 | 832 | 1899-12-31 | 0 | 0
14040003 | 2015-01-12 | 2014-08-15 | -300.44 | 0 | 38859.56 | 37180.73
14040004 |  |  | 0 | 0 | 0.01 | 0
14040005 | 2014-09-02 | 2017-12-31 | 490.72 | 0 | 80027668.2387 | 79801586.92 | 26226.77 | 32210 | 0.86479 | 0.13521 | 0
14040006 | 2014-08-25 | 2014-09-09 | 949 | 0 | 54117 | 51415.47
14040007 | 2014-10-06 | 2014-11-26 | 7171.54 | 0 | 428606.4 | 423236.57 | 0 | 0 | 0 | 0 | 0
14040008 |  | 2014-12-31 | 0 | 0 | 0.01 | 0 | 0 | -800 | 1899-12-31 | 0 | 0
14040009 | 2015-03-02 | 2016-12-31 | 1355184 | 652914 | 12322266.2675 | 17331690.58 | 56587.21 | 114109.25 | 0.95728 | 0.038963 | 0.0037617
14040010 | 2014-10-01 | 2014-10-25 | 112 | 0 | 151229 | 141892.97
14040011 | 2014-11-01 | 2015-10-01 | 0 | 0 | 1049055.79 | 1047980.81
14040012 | 2014-10-31 | 2015-01-31 | 0 | 0 | 169280.32 | 164699.55
14040013 | 2014-11-07 | 2015-01-31 | 4 | 0 | 769491.89 | 764710.3 | 32 | 0 | 0 | 0 | 0
14040997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 30220.23
14040999 | 2013-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 177.56
14050001 | 2016-09-01 | 2019-07-22 | 324516 | 329454 | 20581708.33 | 22610150.74 | 27093 | 36060.5 | 0.95811 | 0.040723 | 0.0011647
14050002 | 2014-04-03 | 2015-12-31 | 47115.8 | 0 | 5116514.51 | 4985761.65 | 6302 | 8267.34 | 0.90801 | 0.086666 | 0.0053221
14050003 | 2014-07-10 | 2015-05-31 | 561.47 | 0 | 3720998.4396 | 3711947.44 | 1330.47 | 1328.04 | 1899-12-31 | 0 | 0
14050004 | 2014-05-15 | 2016-05-31 | 43633.07 | 9423 | 11415903.4229 | 10376482.4 | 16305.25 | 13132.63 | 0.96676 | 0.029469 | 0.0037692
14050005 | 2017-08-09 | 2019-11-04 | 1962295.55 | 1576116 | 174850901.1072 | 175728472.35 | 78390.2 | 94370.89 | 0.8548 | 0.144 | 0.0011974
14050006 | 2015-02-02 | 2017-09-30 | 1468654 | 1535590 | 50870539.9097 | 50470832.9 | 69436 | 71825.3 | 0.84771 | 0.13939 | 0.012899
14050007 | 2014-06-06 | 2015-02-26 | 20 | 0 | 56855870.24 | 56184031.96 | 0 | 527.5 | 0.72038 | 0.27393 | 0.0056872
14050008 | 2015-08-05 | 2016-11-30 | 138901.65 | 99862 | 34622485.4418 | 34992924.42 | 15910.5 | 14827.31 | 0.90713 | 0.091554 | 0.0013151
14050009 | 2015-11-02 | 2016-03-04 | 569 | 0 | 1950357 | 1767233.36 | 31 | 344.73 | 1899-12-31 | 0 | 0
14050010 | 2015-08-30 | 2015-12-31 | 11 | 0 | 163699.16 | 156102.99
14050011 | 2014-12-01 | 2014-12-31 | 1 | 0 | 15630 | 17268.93 | 27 | 0 | 0 | 0 | 0
14050012 | 2014-12-01 | 2017-05-18 | 306391.5 | 213317 | 18694153.2515 | 18044259.8 | 20557.5 | 17681.43 | 0.96324 | 0.036026 | 0.00073523
14050013 | 2014-11-10 | 2016-02-28 | 84789 | 54501 | 8877598.555 | 7417648.03 | 12663.5 | 11143.99 | 0.89873 | 0.10001 | 0.0012563
14050997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -2391119.27
14050999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -6098.86
14060001 | 2014-01-09 | 2015-11-05 | 1830920.82 | 687059 | 78381470.81 | 75609518.15 | 110742.67 | 111081.99 | 0.86212 | 0.13788 | 0
14060002 | 2014-01-13 | 2014-12-31 | 0 | 0 | 347024 | 338194.27 | 28 | 21.5 | 0.65116 | 0.34884 | 0
14060003 | 2014-04-28 | 2014-10-01 | 49517 | 9525 | 905308 | 1136603.92 | 3384 | 7499 | 0.79577 | 0.20423 | 0
14060004 | 2014-05-01 | 2015-08-01 | 4590269.82 | 902045 | 145444737.15 | 161385313.74 | 216768.74 | 393937.25 | 0.81207 | 0.18793 | 0
14060005 | 2014-05-01 | 2016-12-31 | 686 | 0 | 194843.01 | 194900.34 | 5 | 83 | 0.98193 | 0.018072 | 0
14060006 | 2015-06-01 | 2017-12-04 | 757 | 0 | 1751415 | 1801957.39 | 1230 | 6850 | 0.96234 | 0.037664 | 0
14060007 | 2014-04-11 | 2014-05-23 | 32 | 0 | 228824 | 204396.38 | 16 | 666 | 0.87462 | 0.12538 | 0
14060008 | 2014-04-21 | 2014-06-17 | 12578 | 0 | 671013.28 | 742881.68 | 8 | 1433 | 0.80461 | 0.19539 | 0
14060009 | 2015-01-07 | 2017-06-01 | 743 | 0 | 1245565 | 1232569.59 | 1036 | 7429.5 | 0.95652 | 0.043475 | 0
14060010 | 2014-04-28 | 2020-03-01 | 0 | 0 | 532951 | 496849.89 | 0 | 15 | 1899-12-31 | 0 | 0
14060011 | 2014-12-13 | 2017-09-07 | 133704.05 | 65672 | 24986657.9226 | 25296024.25 | 27943.85 | 64224.5 | 0.91218 | 0.087825 | 0
14060012 | 2014-04-28 | 2014-05-14 | 0 | 0 | 61440 | 65206.44 | 0 | 84.5 | 0.73373 | 0.26627 | 0
14060013 | 2015-03-15 | 2016-04-30 | 1865980.9 | 1233265 | 9872095.6637 | 10565115.94 | 21430 | 48232 | 0.89987 | 0.10013 | 0
14060014 | 2015-02-16 | 2015-10-09 | 391.03 | 0 | 3270199.08 | 32386.8 | 1866 | 1084 | 0.95941 | 0.04059 | 0
14060016 | 2014-07-28 | 2015-06-30 | 545 | 0 | 55059 | 56021.94 | 175 | 187.5 | 0.98933 | 0.010667 | 0
14060017 | 2015-11-01 | 2016-11-30 | 0 | 0 | 0.01 | 0
14060018 | 2014-11-30 | 2015-12-31 | 22 | 0 | 0 | 0
14060021 | 2014-08-04 | 2014-10-31 | 1780 | 0 | 1132451.03 | 1020246.82 | 1138 | 821.5 | 0.7535 | 0.2465 | 0
14060022 | 2015-01-26 | 2016-06-17 | 426862 | 362465 | 40952456.74 | 41969495.15 | 33797 | 65599.5 | 0.92778 | 0.072219 | 0
14060023 | 2014-08-14 | 2018-07-01 | 32789 | 13363 | 10701134.13 | 11056173.64 | 7389 | 15741 | 0.93094 | 0.069055 | 0
14060024 | 2014-11-06 | 2016-01-14 | 6692232 | 120003 | 20346127.95 | 19023429.7 | 11339 | 26567 | 0.91553 | 0.084466 | 0
14060025 | 2014-10-01 | 2016-01-29 | 1344065 | 793825 | 21449173 | 21236483.74 | 56250.24 | 53613 | 0.81433 | 0.18552 | 0.00014922
14060026 | 2014-10-06 | 2015-03-31 | 408443 | 18746 | 4509248.35 | 4519427.74 | 11009.1 | 12807 | 0.82838 | 0.17162 | 0
14060027 | 2015-03-14 | 2017-03-31 | 100 | 0 | 468553 | 491718.11 | 380 | 154 | 0.77922 | 0.22078 | 0
14060028 | 2014-11-05 | 2016-12-16 | 100 | 0 | 1530678 | 1694726.14 | 1355 | 2751 | 0.97201 | 0.02799 | 0
14060029 | 2015-03-26 | 2016-02-29 | 168689.07 | 97836 | 2730418.2183 | 3553654.43 | 9625.87 | 21406.05 | 0.82746 | 0.17254 | 0
14060997 | 2013-01-01 | 2013-12-31 | 0 | 0 | 0.01 | -2899870.78
14060999 | 2012-01-01 | 2012-12-31 | 0 | 0 | 0.01 | 110900.99 | 0 | 103.5 | 0.88889 | 0.11111 | 0
14080001 | 2014-07-21 | 2015-12-15 | 2 | 0 | 49608546.81 | 50156415.61 | 0 | 4069.84 | 0.92813 | 0.070887 | 0.00098284
14080002 | 2014-03-15 | 2014-09-30 | 36659 | 25832 | 4672991.71 | 4862204.23 | 3239 | 3454 | 0.93819 | 0.061812 | 0
14080003 | 2014-03-15 | 2017-02-10 | 11215391.36 | 2416842 | 171798194.9892 | 174500254.73 | 217323.21 | 272124 | 0.85848 | 0.13891 | 0.0026036
14080004 | 2015-07-10 | 2016-09-01 | 125958 | 92117 | 3875608.44 | 3475400.47 | 7997.5 | 7947.78 | 0.91979 | 0.079079 | 0.0011324
14080005 | 2014-04-23 | 2014-05-30 | 2305.09 | 0 | 93221 | 78662.22 | 250 | 195.5 | 0.90793 | 0.092072 | 0
14080006 | 2015-01-05 | 2015-03-27 | 2079.27 | 0 | 632186.27 | 582744.18 | 764 | 775 | 0.89097 | 0.10903 | 0
14080007 | 2014-05-22 | 2017-12-31 | 2 | 0 | 182059 | 157733.88 | 582 | 577 | 0.96447 | 0.035529 | 0
14080009 | 2014-07-02 | 2014-08-29 | 1 | 0 | 54813 | 47591.47 | 0 | 239 | 0.93933 | 0.060669 | 0
14080010 | 2014-04-01 | 2014-12-31 | 0 | 0 | 63283.64 | 63283.64
14080011 | 2014-09-11 | 2016-06-17 | 2333785.3 | 235783 | 85118914.28 | 84417290.61 | 21282 | 30962.5 | 0.89809 | 0.10153 | 0.00038757
14080012 | 2014-01-01 | 2016-12-30 | 4462.26 | 0 | 238653.26 | 241801.15 | 686 | 786 | 0.83079 | 0.16921 | 0
14080013 | 2014-09-02 | 2015-06-01 | 73073.0875 | 0 | 1632135.6375 | 1609306.05 | 2458 | 3551.5 | 0.88695 | 0.1108 | 0.0022526
14080014 | 2015-01-19 | 2015-07-01 | 32949 | 0 | 1252211 | 1235910.12 | 1967 | 1686 | 0.93772 | 0.059312 | 0.0029656
14080014-064 | 2015-01-19 | 2015-07-01 | 0 | 0 | 87016.35 | 87016.35
14080015 | 2015-01-19 | 2015-07-01 | 6045 | 0 | 237759 | 239268.34 | 503 | 338.5 | 0.70753 | 0.29247 | 0
14080015-064 | 2015-01-19 | 2015-07-01 | 0 | 0 | 7236 | 7236
14080016 |  | 2014-12-31 | 0 | 0 | 38000 | 43416.44
14080017 | 2016-01-04 | 2016-06-15 | 887531 | 1080795 | 3536193.32 | 3515905.68 | 14488 | 15294.38 | 0.91791 | 0.077414 | 0.0046749
14080018 | 2015-06-11 | 2015-12-31 | 269537 | 104649 | 9397426.151 | 8523966.49 | 7012 | 5429 | 0.94566 | 0.048996 | 0.0053417
14080019 | 2015-01-15 | 2015-04-01 | 8965 | 0 | 196288 | 189644.4 | 638 | 559 | 0.92576 | 0.07424 | 0
14080019-064 | 2015-01-15 | 2015-05-08 | 0 | 0 | 13088 | 13088
14080020 | 2014-12-29 | 2015-01-08 | 0 | 0 | 3490 | 2601.25 | 0 | 21 | 1899-12-31 | 0 | 0
14080997 | 2014-01-01 | 2014-12-31 | 0 | 0 | -433968 | -526112
14080999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -110108.4 | 0 | 137.5 | 0.95273 | 0.047273 | 0
14090001 | 2013-10-01 | 2017-12-31 | 151342.5 | 132527 | 19967389.7552 | 19672885.96 | 14791 | 15301.89 | 0.91142 | 0.084728 | 0.0038557
14090002 | 2013-10-01 | 2014-08-31 | 10 | 0 | 3529426 | 3540577.01 | 1440 | 2259 | 0.73749 | 0.26251 | 0
14090003 | 2013-10-01 | 2016-12-31 | 0 | 0 | 33833.86 | 39631.21
14090004 | 2014-05-12 | 2015-03-31 | 144262.34 | 24978 | 5190573.37 | 4377438.56 | 10325.5 | 8431.86 | 0.98915 | 0.0096657 | 0.001186
14090005 | 2013-10-01 | 2015-06-30 | 0 | 0 | 278453 | 256549.54
14090006 | 2014-03-01 | 2015-03-31 | 16 | 0 | 989973 | 905451.25
14090007 | 2014-03-01 | 2014-12-31 | 0 | 0 | 19250 | 17536.86
14090008 | 2014-03-01 | 2014-12-31 | 200 | 0 | 73170 | 64614.18 | 0 | 115 | 0.93913 | 0.056522 | 0.0043478
14090009 | 2013-10-01 | 2014-12-31 | 18975 | 1880 | 1056665 | 1091220.98 | 492 | 1493.79 | 0.92937 | 0.067948 | 0.0026778
14090010 | 2015-06-01 | 2016-05-01 | 7 | 0 | 3055595.27 | 3051169.82 | 420 | 1014 | 0.90927 | 0.085306 | 0.0054241
14090012 | 2014-07-15 | 2014-09-30 | 216 | 0 | 1167544.43 | 1157540.43 | 867 | 1087.35 | 0.9416 | 0.053801 | 0.0045983
14090013 | 2014-07-01 | 2014-12-31 | 0 | 0 | 89784 | 74194.55 | 274 | 273.74 | 0.93424 | 0.04749 | 0.018266
14090014 | 2016-12-23 | 2016-06-30 | 795780 | 602113 | 76192992.47 | 75573181.03 | 23011 | 18939.51 | 0.94226 | 0.054014 | 0.0037224
14090015 | 2015-04-07 | 2016-10-27 | 16833.53 | 3490 | 2573817.6408 | 2525159.76 | 2052.12 | 3737.44 | 0.88802 | 0.084951 | 0.027024
14090016 | 2014-09-15 | 2015-10-31 | 0 | 0 | 402894 | 403086.33
14090017 | 2014-12-01 | 2016-05-01 | 97969 | 0 | 3898963.68 | 3667092.59 | 2307 | 2354.25 | 0.8868 | 0.10131 | 0.011893
14090997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -991469.06
14090999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -1830.7 | 0 | 166 | 1899-12-31 | 0 | 0
14110001 | 2015-04-06 | 2018-12-31 | 2421 | 0 | 23715115.26 | 24236022.1
14110002 | 2014-09-05 | 2017-05-04 | -3 | 0 | 26292883.77 | 28663615.84 | 4000 | 4232 | 1899-12-31 | 0 | 0
14110003 | 2015-04-06 | 2017-04-14 | 355362 | 0 | 31107486.802 | 31737579.7 | 0 | 3867.5 | 0.98849 | 0.011506 | 0
14110004 | 2015-03-06 | 2016-04-08 | 18 | 0 | 15937763.36 | 16621138.07 | 0 | 756.5 | 0.8189 | 0.1811 | 0
14110997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | -30018.99
14110999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | -452756.88
14120001 | 2014-01-14 | 2014-10-01 | 28475.82 | 0 | 1868784 | 1795772.14 | 4035 | 3696.5 | 0.98499 | 0.015014 | 0
14120002 | 2014-09-15 | 2015-09-25 | 32931 | 0 | 15098948.29 | 14213825.27 | 7292.07 | 6037.49 | 0.9783 | 0.021698 | 0
14120003 | 2014-11-05 | 2015-10-09 | 3 | 0 | 17755226.3 | 16667306.01
14135001 | 2015-11-01 | 2018-06-30 | 0 | 0 | 34220629 | 34220628.88 | 0 | -140765.96 | 1899-12-31 00:30 | -0.015831 | -0.0047916
14135001-110 | 2015-11-01 | 2018-06-30 | 185290.74 | 104874 | 438371573.2709 | 459645057.76 | 94719.5 | 37157.65 | -1.1207 | 1899-12-31 03:56 | 0.95687
14140001 | 2014-10-01 | 2015-07-31 | 11034.85 | 8501 | 45992204.8588 | 45040394.78 | 103787 | 114018 | 0.82389 | 0.17611 | 0
14140002 | 2014-04-24 | 2014-05-20 | 1 | 0 | 353171 | 482478.35 | 0 | 105.5 | 0.54502 | 0.25592 | 0.19905
14140003 | 2014-11-01 | 2014-11-01 | 0 | 0 | 15250 | 15233.02
14140004 | 2014-04-17 | 2014-04-28 | 7 | 0 | 447930 | 396159.61 | 300 | 508.5 | 0.75025 | 0.24975 | 0
14140005 | 2014-07-01 | 2015-07-03 | 7887 | 5128 | 77129390.78 | 87618710.89 | 83836 | 115109.98 | 0.65524 | 0.21847 | 0.1263
14140006 | 2014-07-07 | 2014-10-31 | 5839 | 3641 | 1804555.81 | 1949760.74 | 6438 | 7660 | 0.80907 | 0.19093 | 0
14140007 | 2015-04-01 | 2015-11-01 | 10971 | 7895 | 55185356.37 | 54058585.87 | 105339 | 102009.25 | 0.75329 | 0.24671 | 0
14140008 | 2014-07-07 | 2014-11-30 | 1545 | 1112 | 768439 | 617102.78 | 2058 | 1591 | 0.84994 | 0.15006 | 0
14140009 | 2014-07-21 | 2014-08-25 | 98 | 78 | 581473.74 | 516170.51 | 2552 | 2789.5 | 0.7288 | 0.2712 | 0
14140010 | 2015-03-15 | 2015-12-31 | 2 | 0 | 12154 | 34586.45
14140011 | 2014-07-22 | 2014-07-26 | 2 | 1 | 26756 | 23738.63 | 16 | 30 | 0 | 1899-12-31 | 0
14140012 | 2014-10-08 | 2015-12-31 | 801 | 193 | 3381492 | 2946513.76 | 163935 | 40054.5 | 0.82394 | 0.17556 | 0.00049932
14140013 | 2015-06-01 | 2015-10-31 | 1613 | 1231 | 17636914 | 17750774.43 | 23835 | 25296 | 0.63648 | 0.28362 | 0.079894
14140014 | 2013-10-21 | 2015-06-01 | 211969 | 0 | 4097047.19 | 3592241.34 | 0 | 4109.5 | 0.63195 | 0.26037 | 0.10768
14140015 | 2015-03-23 | 2016-06-30 | 17268 | 10536 | 72077363.8203 | 71914299.07 | 185355 | 188738 | 0.83166 | 0.16834 | 0
14140016 | 2015-04-01 | 2015-12-01 | 0 | 0 | 20660 | 22919.08
14140017 | 2014-12-12 | 2014-12-31 | 18 | 3 | 257671 | 238666.3 | 36 | 19.5 | 0 | 1899-12-31 | 0
14140018 | 2014-12-12 |  | 16 | 3 | 190162 | 185795.55 | 36 | 10 | 0 | 1899-12-31 | 0
14140019 | 2015-04-01 |  | 0 | 0 | 54300 | 53860.33
14140020 | 2014-12-16 | 2016-09-30 | 571595 | 572144 | 53196896.0826 | 52296993.5 | 74316 | 80956.5 | 0.82511 | 0.17489 | 0
14140021 | 2014-12-18 |  | 0 | 0 | 63100 | 62400.79
14140022 | 2014-12-18 |  | 0 | 0 | 63250 | 60274.16
14140023 | 2014-12-17 |  | 0 | 0 | 58628 | 58848.42
14140024 | 2015-03-30 | 2016-06-01 | 5291 | 5267 | 36950914.8 | 37241113.19 | 75492.5 | 98770.5 | 0.75135 | 0.24865 | 0
14140997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -3142190.97
14140999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 144852.24
14145001 | 2014-01-27 | 2015-02-07 | 830161.26 | 1029926 | 6349063 | 6459588.96 | 42955 | 53357.25 | 0.92086 | 0.078986 | 0.00014993
14145002 | 2014-02-05 | 2014-03-05 | 160.58 | 0 | 187808.99 | 187967.2 | 802 | 872.5 | 0.86877 | 0.13123 | 0
14145003 | 2014-04-10 | 2014-06-30 | 207 | 0 | 60278.66 | 33495.09 | 88 | 440 | 0.65455 | 0.20682 | 0.13864
14145004 | 2014-08-11 | 2016-02-27 | 47031316.95 | 22012894 | 76015715.9754 | 75086381.88 | 675943.91 | 717246.14 | 0.87177 | 0.12822 | 1.0457e-05
14145005 | 2014-06-23 | 2014-09-15 | 85253.4702 | 80256 | 2472661.0002 | 2587785.18 | 12378 | 8117 | 0.99661 | 0.003388 | 0
14145006 | 2014-07-25 | 2015-06-09 | 544354.12 | 271265 | 21525316.005 | 21328272.18 | 125455.13 | 139011 | 0.89869 | 0.096956 | 0.0043558
14145007 | 2014-08-18 | 2014-12-31 | 202 | 0 | 4147182 | 4285136.62 | 0 | 15.5 | 0.96774 | 0.032258 | 0
14145008 | 2014-08-18 | 2014-12-15 | 202 | 0 | 4072941 | 4272243.45 | 0 | 245.5 | 0.80041 | 0.19552 | 0.0040733
14145009 |  |  | 202 | 0 | 5358475 | 5429033.24 | 0 | 113.5 | 0.81938 | 0.15859 | 0.022026
14145010 | 2014-09-16 | 2015-01-31 | 3400 | 0 | 1749371 | 1794380.73
14145011 | 2014-10-27 | 2015-02-28 | 9862 | 0 | 4758195 | 4817923.41
14145012 | 2014-10-21 | 2015-01-28 | 6591 | 0 | 3193547 | 3259634.01
14145013 | 2014-10-21 | 2015-01-27 | 3379 | 0 | 1679915 | 1753617.32
14145014 | 2014-12-01 | 2015-04-30 | 148469.1361 | 100956 | 2678804.9691 | 2120392.34 | 13718.8 | 10643.5 | 0.86243 | 0.13757 | 0
14145016 |  |  | 1713 | 0 | 111158 | 0 | 246 | 0 | 0 | 0 | 0
14145017 | 2013-02-08 | 2014-10-31 | 69475.7021 | 22994 | 1264203.0109 | 1021839.76 | 17916.8 | 19876.25 | 0.89537 | 0.085995 | 0.01864
14145018 |  |  | 0 | 0 | 111158 | 0
14145997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -284987.62
14145999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 8277.52 | 0 | 1786.74 | 1899-12-31 | 0 | 0
14146001 | 2014-04-14 | 2014-12-31 | 1516582 | 221293 | 5451800.3 | 5933595.82 | 7615 | 22211.5 | 0.78086 | 0.21914 | 0
14146002 | 2014-01-10 | 2014-11-10 | 0 | 0 | 765552 | 765552.68
14146002-110 | 2014-01-10 | 2015-07-31 | 212097 | 0 | 15797292 | 16487613.56
14146003 | 2014-05-01 | 2015-12-31 | 0 | 0 | 9640 | 9640.66
14146003-110 | 2014-05-01 | 2015-12-31 | 8 | 0 | 77355 | 67162.17
14146004 | 2014-06-01 | 2015-12-31 | 0 | 0 | 5640 | 5640.43
14146004-110 | 2014-06-01 | 2015-12-31 | 8 | 0 | 70861 | 53003.72
14146005 | 2014-06-01 | 2015-12-31 | 0 | 0 | 3902 | 3902.11
14146005-110 | 2014-06-01 | 2015-12-31 | 8 | 0 | 68161 | 48524.49
14146006 | 2015-02-01 | 2016-12-31 | 181380 | 197549 | 15186884.37 | 14832501.27 | 28997 | 32736.25 | 0.84261 | 0.15688 | 0.00050403
14146007 | 2015-02-14 | 2015-08-21 | 205392 | 33987 | 3019372.55 | 2712718.8 | 7946 | 5174.5 | 0.87178 | 0.12822 | 0
14146997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -1027453.41
14146999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 47761.54 | 0 | 88.5 | 0.93785 | 0.062147 | 0
14147001 | 2014-01-14 | 2014-12-31 | 0 | 0 | 32909 | 32909.43
14147001-110 | 2014-01-14 | 2014-12-31 | 1 | 0 | 230282 | 231362.03
14147002 | 2014-01-14 | 2014-12-31 | 0 | 0 | 13827 | 13826.74
14147002-110 | 2014-01-14 | 2014-12-31 | 1 | 0 | 193887 | 187878.49
14147003 | 2014-01-14 | 2015-09-30 | 0 | 0 | 28321 | 28321.07
14147003-110 | 2014-01-14 | 2015-09-30 | 1 | 0 | 175743 | 164168.72
14147004-110 | 2014-06-27 | 2015-11-30 | 0 | 0 | 13766 | 1206.97
14147997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 0
14147999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | -75.45
14147999-110 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 437098.79
14148001 | 2014-03-10 | 2015-12-31 | 1132671 | 1132034 | 11024511.04 | 11142179.68 | 31740 | 48241.5 | 0.71463 | 0.27918 | 0.0061928
14148002 | 2014-04-01 | 2014-12-31 | 271542.15 | 176834 | 2119876.443 | 2453695.94 | 11905.5 | 10638.5 | 0.90088 | 0.099121 | 0
14148003 | 2014-08-15 | 2015-07-01 | 1254760 | 961981 | 9339893.4449 | 7404607.2 | 43088.35 | 39067.5 | 0.77022 | 0.22978 | 0
14148004 |  | 2014-12-10 | 2102 | 9 | 436057 | 313232.02 | 1716 | 836 | 0.76495 | 0.23505 | 0
14148005 | 2014-07-11 |  | 288416 | 158983 | 377520 | 291749.71 | 1977 | 1421 | 0.84412 | 0.15588 | 0
14148006 | 2014-09-01 | 2015-12-31 | 161069 | 160952 | 2975017.83 | 2874952.79 | 10299.5 | 7306.5 | 0.82769 | 0.17231 | 0
14148007 | 2014-09-01 | 2016-01-31 | 668895 | 611106 | 8553587.261 | 7437448.95 | 37402 | 23568.5 | 0.8325 | 0.1675 | 0
14148008 |  |  | 0 | 0 | 6662612 | 6664410.7
14148009 | 2014-08-15 | 2015-02-28 | 834292 | 710523 | 5355935.9152 | 4689174.19 | 25177.3 | 25582.5 | 0.79115 | 0.20885 | 0
14148010 | 2014-10-01 | 2015-06-01 | 12 | 12 | 760158.27 | 801039.3 | 721 | 1703 | 0.68086 | 0.30505 | 0.014093
14148011 |  | 2014-12-31 | 38877 | 32051 | 506191 | 0 | 3190 | 0 | 0 | 0 | 0
14148012 | 2014-12-13 |  | 32488 | 18341 | 186000 | 111097.99 | 650 | 313.5 | 0.54705 | 0.45295 | 0
14148013 | 2014-12-15 |  | 32490 | 17422 | 135232 | 87030.27 | 580 | 277 | 0.61733 | 0.38267 | 0
14148014 | 2014-12-19 | 2014-12-31 | 13 | 4 | 35758 | 37362.85 | 120 | 87.5 | 1899-12-31 | 0 | 0
14148015 | 2014-12-01 | 2014-12-31 | 12 | 4 | 38400 | 52068.25 | 120 | 100 | 1899-12-31 | 0 | 0
14148017 | 2014-12-17 |  | 13 | 5 | 41760 | 22075.26 | 500 | 186.5 | 0.68901 | 0.31099 | 0
14148018 | 2014-12-17 |  | 14 | 8 | 31520 | 23298.4 | 200 | 70 | 0.071429 | 0.92857 | 0
14148019 |  | 2014-12-31 | 38881 | 6800 | 517250.74 | 257594.37 | 3222 | 840 | 0.76905 | 0.22381 | 0.0071429
14148020 | 2014-12-18 | 2014-12-31 | 13 | 4 | 36480 | 46597.91 | 120 | 165 | 1899-12-31 | 0 | 0
14148021 | 2015-03-30 | 2016-06-30 | 460911 | 461851 | 5725521.6097 | 5218679.61 | 24401.19 | 23759 | 0.80748 | 0.19252 | 0
14148997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -509053.82
14148999 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 8471.04
14150001 | 2014-02-01 | 2014-10-20 | 0 | 0 | 78690 | 70688.08
14150002 | 2014-12-01 | 2015-09-30 | 0 | 0 | 3487890 | 3551673.49 | 0 | 8979.55 | 0.7815 | 0.21405 | 0.0044546
14150002-155 | 2014-05-01 | 2015-09-30 | 22459 | 0 | 55897335.68 | 53142179.97 | 26240 | 10628.11 | 0.77742 | 0.22258 | 0
14150004 | 2014-09-16 |  | 3 | 0 | 11667010.01 | 12940093.92 | 0 | 4261 | 0.76414 | 0.21298 | 0.022882
14150004-141 | 2014-09-16 |  | 0 | 0 | 600600984 | 0
14150005 | 2014-07-07 |  | 0 | 0 | 0.01 | 78965.21
14150006 | 2017-01-09 | 2019-08-01 | 0 | 0 | 29134095 | 29426155.55 | 1992 | 1454 | 1899-12-31 | 0 | 0
14150007 | 2015-06-15 | 2015-10-08 | 1573 | 0 | 17478044.2744 | 17520071.53 | 0 | 4328.5 | 0.67171 | 0.26441 | 0.063879
14150008 | 2015-03-01 | 2015-11-12 | 0 | 0 | 2419307.7 | 2360474
14400999 |  |  | 0 | 0 | 0 | 2417990.83 | 0 | 20 | 0.4 | 0.6 | 0
15000004-040, 15050008 | 2018-03-01 | 2019-06-25 | 16758.14 | 29757 | 27328257.9 | 29220571.93 | 3159.93 | 8829 | 0.92315 | 0.076396 | 0.00045305
15000006-040, 15050011 | 2016-11-22 | 2018-06-30 | 792923 | 673928 | 30253384.5637 | 36635553.75 | 21741 | 39088.39 | 0.77557 | 0.21633 | 0.008097
15000007-040, 15030048 | 2017-11-15 | 2019-08-01 | 3717330.1 | 1285621 | 78220221.47 | 77212796.51 | 112107.21 | 114891.44 | 0.90122 | 0.097823 | 0.00095307
15001 | 2002-11-23 |  | 69284 | 0 | 20749086 | 20750359 | 0 | 5621 | 1899-12-31 | 0 | 0
15030001 | 2015-01-01 | 2016-01-01 | 75994.589 | 0 | 4586721.64 | 4535466.89 | 9222.5 | 11145.36 | 0.98152 | 0.017631 | 0.00085237
15030002 | 2014-12-17 | 2015-05-01 | 26 | 0 | 1359521.38 | 1117046.94 | 2334 | 1105 | 0.93394 | 0.057014 | 0.0090498
15030003 | 2014-12-22 | 2015-01-30 | 85.59 | 0 | 197325.36 | 195273.78 | 247 | 255 | 0.99216 | 0.0078431 | 0
15030004 | 2015-01-05 | 2015-03-31 | 3529.2 | 0 | 738382.19 | 716634.85 | 2137 | 2603 | 0.96638 | 0.033615 | 0
15030005 | 2015-02-16 | 2015-03-15 | 410 | 0 | 354605 | 342361.35 | 280 | 224 | 1899-12-31 | 0 | 0
15030006 | 2015-03-15 | 2015-12-01 | 38229 | 41055 | 1382228.08 | 1331666.66 | 2689 | 4177.91 | 0.97164 | 0.028363 | 0
15030007 | 2015-02-02 | 2015-04-01 | 3357 | 0 | 501973 | 432006.87 | 622 | 303.99 | 0.98684 | 0.013158 | 0
15030008 | 2015-05-15 | 2016-06-15 | 234541 | 249112 | 8026043.6 | 8472899.03 | 12870 | 15404.21 | 0.92317 | 0.073064 | 0.0037652
15030009 | 2015-01-01 |  | 9597 | 8 | 211213.36 | 199760.62 | 1385 | 924 | 0.96645 | 0.03355 | 0
15030010 | 2016-06-01 |  | 1 | 0 | 2088931 | 1897920.1
15030011 | 2015-04-20 | 2015-11-01 | 119470 | 90487 | 3654453.06 | 3654442.2 | 11739 | 12516.75 | 0.94463 | 0.055366 | 0
15030012 | 2015-05-01 | 2016-07-01 | 294398 | 117936 | 14235788.76 | 14150037 | 28775 | 30980 | 0.93346 | 0.065833 | 0.00071014
15030013 | 2015-05-18 | 2015-08-14 | 2332.2 | 0 | 1660557.4 | 1557745.52 | 2548 | 2494 | 0.95309 | 0.044908 | 0.0020048
15030014 |  | 2015-12-31 | 2551 | 0 | 717908.32 | 718245.01 | 1116 | 993.5 | 0.99396 | 0.0060393 | 0
15030015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 88168 | 84048.9 | 0 | 1090 | 0.69083 | 0.30917 | 0
15030016 | 2015-03-23 | 2016-02-29 | 9220.8 | 4 | 6100970.464 | 6072672.02 | 8129.4 | 7760.5 | 0.7667 | 0.22273 | 0.010566
15030017 | 2015-04-06 | 2015-06-17 | 7 | 0 | 446197.99 | 421381.69 | 406 | 284 | 0.80282 | 0.19718 | 0
15030018 | 2015-10-01 | 2016-12-01 | 2023 | 0 | 436992 | 425591.72 | 1520 | 2335.5 | 0.99615 | 0.0038536 | 0
15030019 | 2015-04-01 | 2015-06-20 | 523 | 0 | 726745 | 733889.11 | 1078 | 751 | 0.87617 | 0.12383 | 0
15030020 | 2015-03-14 | 2015-08-14 | 2055 | 0 | 3934287.89 | 3865657.17 | 3331 | 2256 | 0.85417 | 0.14583 | 0
15030021 | 2016-02-15 | 2018-01-08 | 529807.78 | 459874 | 87326032.767 | 87054781.16 | 82434.7 | 95920.18 | 0.9254 | 0.073671 | 0.00092785
15030022 | 2015-07-01 | 2015-11-16 | 11018 | 0 | 2226398.69 | 1999036.38 | 3475 | 4646.5 | 0.93339 | 0.063166 | 0.0034435
15030023 | 2016-03-14 | 2016-09-30 | 359322 | 0 | 11134923.69 | 9656275.5 | 12338 | 10417.46 | 0.89532 | 0.10468 | 0
15030024 |  | 2015-07-15 | 0 | 0 | 0.01 | 0
15030025 | 2015-05-04 | 2015-06-30 | 0 | 0 | 121267 | 116506.67 | 754 | 733.92 | 0.93528 | 0.064721 | 0
15030026 | 2015-01-01 |  | 0 | 0 | 0.01 | 3984926.2 | 0 | 33824.3 | 0.90937 | 0.076897 | 0.013733
15030027 | 2015-05-18 | 2015-08-21 | 18148 | 0 | 515801 | 506296.1 | 983 | 1115 | 0.98924 | 0.010762 | 0
15030028 | 2015-05-18 | 2015-12-31 | 512 | 0 | 567509.89 | 496792.97 | 741 | 566.5 | 0.93557 | 0.064431 | 0
15030029 | 2015-07-01 |  | 0 | 0 | 2633880.95 | 2387003.54 | 797 | 1223.57 | 0.66348 | 0.33652 | 0
15030030 | 2015-05-11 | 2015-07-09 | 55.22 | 0 | 215977.22 | 234452.82 | 151 | 462.5 | 1899-12-31 | 0 | 0
15030031 | 2015-08-17 | 2016-12-31 | 852 | 0 | 28260897.77 | 27754469.42 | 3530 | 5461 | 0.88775 | 0.11225 | 0
15030032 | 2015-07-01 | 2016-05-16 | 3 | 0 | 7087922.37 | 7028194.33 | 1656 | 1351.01 | 0.9654 | 0.034604 | 0
15030033 | 2015-05-04 | 2015-10-30 | 101636 | 0 | 1076107.36 | 978892.57 | 912 | 1199 | 0.95538 | 0.044621 | 0
15030034 | 2015-07-01 | 2017-05-31 | 11588 | 4633 | 55908124.9438 | 50559168.56 | 11051 | 9350.84 | 0.87514 | 0.12464 | 0.00021388
15030035 | 2015-06-01 |  | 29714 | 0 | 2156761.09 | 2119485.48 | 2103 | 1453.5 | 0.83798 | 0.14001 | 0.022016
15030036 | 2015-06-22 | 2015-12-01 | 10 | 0 | 403378.5 | 408495.59 | 340 | 657 | 0.96499 | 0.035008 | 0
15030037 | 2015-06-15 |  | 4981 | 0 | 1218320 | 1033680.25 | 1614 | 1230 | 0.87846 | 0.10854 | 0.013008
15030038 | 2015-05-15 | 2015-10-30 | 0 | 0 | 736263 | 753624.05 | 320 | 446.5 | 0.97312 | 0.026876 | 0
15030039 | 2015-08-03 | 2016-11-11 | 319164.8 | 168865 | 12370086.9088 | 12118482.9 | 22524 | 24970.96 | 0.94211 | 0.056125 | 0.001762
15030040 |  |  | 0 | 0 | 0.01 | 0
15030041 | 2015-09-24 | 2016-09-14 | 995.61 | 31206 | 17879305.41 | 17684765.84 | 16163 | 18513.6 | 0.94877 | 0.048478 | 0.0027547
15030042 | 2015-06-30 |  | 0 | 0 | 0 | 442572.19 | 0 | 698 | 0.71633 | 0.28367 | 0
15030043 | 2015-06-30 | 2016-12-31 | 0 | 0 | 0 | 71873.89
15030044 | 2015-08-01 | 2016-03-04 | 37891.35 | 0 | 2843347.8782 | 2679475.84 | 5804 | 4123.5 | 0.76197 | 0.23415 | 0.0038802
15030045 | 2015-08-05 | 2015-12-31 | 12277 | 0 | 1083507.172 | 1027032.58 | 1524 | 1559.5 | 0.97307 | 0.026932 | 0
15030046 | 2015-08-24 |  | 0 | 0 | 4857701 | 3587238.78 | 3109 | 3698 | 0.97891 | 0.021092 | 0
15030047 | 2015-09-01 | 2016-09-01 | 279065 | 248506 | 10229665.33 | 9493672.09 | 26617 | 31384.31 | 0.94789 | 0.044784 | 0.0073285
15030049 |  | 2016-08-01 | 17065 | 11729 | 3727348.93 | 3608301.12 | 3902.5 | 4344.84 | 0.96225 | 0.037746 | 0
15030050 | 2015-09-08 | 2015-11-30 | 0 | 0 | 198753.76 | 198104.6 | 1302 | 1228.51 | 0.87994 | 0.12006 | 0
15030051 | 2015-09-15 | 2015-12-11 | 22 | 0 | 146857 | 120408.79 | 1896 | 1357 | 0.79956 | 0.20044 | 0
15030052 | 2015-10-28 | 2016-03-31 | 45654 | 0 | 4499965.94 | 4291872.51 | 5917 | 8183.71 | 0.95283 | 0.047167 | 0
15030053 | 2015-10-19 | 2015-12-31 | 9259 | 0 | 274952.5 | 225995.83 | 640 | 478.5 | 0.98119 | 0.018809 | 0
15030054 | 2016-12-01 | 2016-09-30 | 2480 | 0 | 174783.01 | 111109.02
15030055 | 2017-04-04 | 2019-08-02 | 866958.23 | 553745 | 27499372.37 | 25723848.91 | 29385.4 | 27109.71 | 0.87617 | 0.12333 | 0.00049798
15030056 | 2015-11-18 | 2015-12-31 | 9010 | 0 | 197672.13 | 172590.73 | 233 | 200 | 0.98 | 0.02 | 0
15030057 | 2015-12-11 | 2016-03-16 | 26691 | 29591 | 1044779.13 | 1082414.5 | 4360 | 4201.65 | 0.99691 | 0.003094 | 0
15030058 | 2016-01-11 | 2016-09-03 | 10441 | 25511 | 1828737.86 | 1814696.92 | 4919 | 6916 | 0.92452 | 0.074176 | 0.0013013
15030997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -4728635
15030999 | 2013-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -125838.08 | 0 | 222 | 1899-12-31 | 0 | 0
15040001 | 2015-02-11 | 2015-03-11 | 378 | 0 | 106193 | 113593.66
15040002 | 2015-09-10 | 2015-05-30 | 0 | 0 | 129411.5 | 71391.98
15040003 | 2015-09-01 | 2015-12-31 | 0 | 0 | 180000 | -134.29 | 0 | 16.5 | 0.9697 | 0.030303 | 0
15040005 | 2015-06-10 | 2015-07-22 | 871.4565 | 0 | 235351.49 | 233910.61
15040006 | 2015-06-08 | 2015-07-04 | 881.5661 | 0 | 227957.56 | 233333.69
15040007 |  |  | 0 | 0 | 0.01 | 0
15040009 | 2015-08-24 | 2016-03-01 | 0 | 0 | 873780.79 | 1307401.75
15040010 | 2015-11-01 | 2016-01-31 | 0 | 0 | 605826.6 | 586997.87
15040011 | 2015-09-30 | 2018-07-31 | 0 | 0 | 900968.29 | 908796.13
15040012 | 2015-09-30 | 2018-07-31 | 0 | 0 | 68219.38 | 66408.74
15040013 | 2016-02-01 | 2016-08-30 | 0 | 0 | 244229.45 | 243843.42
15040014 | 2015-12-11 | 2016-09-16 | 50024 | 0 | 174011883.18 | 172822962.77 | 8883 | 18687.5 | 0.7673 | 0.21292 | 0.019773
15040015 | 2016-09-06 | 2016-02-08 | 0 | 0 | 175714.83 | 198862.63 | 0 | 3 | 1899-12-31 | 0 | 0
15040016 | 2016-09-12 | 2016-10-20 | 0 | 0 | 194800.82 | 214580.23 | 0 | 18 | 1899-12-31 | 0 | 0
15040997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | 85691.18
15040999 | 2013-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -8414.84
15050001 | 2015-02-01 | 2016-04-30 | 51415.0903 | 0 | 12725713.2396 | 12643140.03 | 12042 | 13831.94 | 0.9255 | 0.064994 | 0.009507
15050003 |  | 2019-09-30 | 289 | 0 | 1411225 | 1661995.62 | 125 | 155.5 | 0.97749 | 0.022508 | 0
15050004 | 2015-03-23 | 2017-05-25 | 726099.5 | 553190 | 26097715.9645 | 26265950.55 | 44266.5 | 46273 | 0.86762 | 0.12676 | 0.0056188
15050005 | 2017-05-01 | 2018-12-21 | 123542 | 68088 | 13440489.662 | 13813539.49 | 20868 | 21393.56 | 0.94143 | 0.057961 | 0.00060766
15050006 | 2015-03-16 | 2015-08-31 | 2 | 8 | 142613.87 | 142763.72 | 68 | 32 | 1899-12-31 | 0 | 0
15050007 | 2015-06-01 | 2015-12-01 | 15256.8263 | 0 | 3479928.04 | 3643962.69 | 2408 | 6104.68 | 0.90139 | 0.076417 | 0.022196
15050009 | 2015-05-04 | 2015-08-14 | 1142.15 | 4607 | 608186.37 | 579035.01 | 1309 | 1219.5 | 0.94301 | 0.056991 | 0
15050010 | 2016-04-25 | 2018-08-30 | 23015 | 43148 | 59184515.22 | 59087861.45 | 12808 | 16885.09 | 0.91392 | 0.085845 | 0.0002369
15050012 | 2016-06-01 | 2017-07-31 | -1 | 0 | 357534.14 | 354998.16 | 48 | 413.97 | 1899-12-31 | 0 | 0
15050013 | 2015-08-03 | 2016-02-19 | 3507 | 0 | 674049.68 | 723182.8 | 799.5 | 2230.89 | 0.85365 | 0.13179 | 0.014568
15050014 | 2015-10-02 | 2017-11-16 | 1958079.37 | 1479535 | 112996953.4075 | 112560314.66 | 96452.09 | 99949.17 | 0.81721 | 0.15921 | 0.023582
15050015 | 2015-08-17 | 2015-10-01 | 0 | 0 | 192839.12 | 193595.38 | 0 | 2.5 | 0.8 | 0.2 | 0
15050016 | 2016-12-26 | 2018-12-17 | 798255.1 | 704033 | 78567291.0207 | 79875911.32 | 66496.25 | 69453.03 | 0.92964 | 0.067636 | 0.0027285
15050017 | 2015-09-15 | 2016-03-31 | 0 | 0 | 733243.92 | 1162814.59 | 380 | 691 | 1899-12-31 | 0 | 0
15050018 | 2015-11-02 | 2016-01-15 | 513 | 2 | 782390.77 | 799381.69 | 664 | 1082.15 | 0.93947 | 0.060528 | 0
15050019, 15000008-040, 16050011 | 2018-02-19 | 2019-11-26 | 1616633.9 | 564596 | 49049735.9352 | 50375472.67 | 40404.08 | 52049.66 | 0.82227 | 0.16985 | 0.0078771
15050020 |  | 2017-09-30 | 0 | 0 | 38840 | 51421.52
15050021 | 2016-03-01 | 2017-09-22 | 1636350.55 | 1561021 | 58554466.81 | 61764713.08 | 64874 | 81111.96 | 0.863 | 0.12864 | 0.0083588
15050022 | 2016-01-04 | 2016-04-15 | 0 | 0 | 0 | 114186.6
15050997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -1315981.5
15050999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | 14818.1 | 0 | 16 | 1899-12-31 | 0 | 0
15060001 | 2015-03-01 | 2015-08-01 | 0 | 0 | 0.01 | 0
15060002 | 2015-06-01 | 2018-06-29 | 2013.17 | 0 | 741235.4 | 729903.99 | 959.5 | 5459.5 | 0.91263 | 0.087371 | 0
15060003 | 2015-06-01 | 2015-12-01 | 0 | 0 | 85352 | 89707.66 | 0 | 15.01 | 1899-12-31 | 0 | 0
15060004 | 2015-01-26 | 2017-07-28 | 13329.5 | 20 | 8520566.573 | 8584916.49 | 17322 | 14237.5 | 0.91775 | 0.082248 | 0
15060005 | 2017-07-28 | 2018-06-04 | 336607 | 238207 | 8338253.01 | 7553087.89 | 16556 | 13617 | 0.92296 | 0.077036 | 0
15060006 | 2015-03-23 | 2016-10-13 | 10.5 | 0 | 9064220.92 | 8997642.64 | 4243.5 | 8523.5 | 0.92779 | 0.072212 | 0
15060007 | 2015-03-02 | 2015-11-27 | 3 | 208 | 1325133.05 | 1377531.17 | 0 | 4202.5 | 0.86865 | 0.13135 | 0
15060008 | 2015-04-01 | 2015-04-30 | 0 | 0 | 0.01 | 0
15060009 | 2015-04-15 | 2018-07-31 | 0 | 0 | 791075 | 846500.25 | 0 | 955 | 0.94555 | 0.05445 | 0
15060010 | 2015-04-01 | 2015-08-31 | 320 | 0 | 0 | 0
15060011 | 2015-07-01 | 2015-10-15 | 0 | 0 | 0.01 | 0
15060012 | 2015-11-30 | 2016-03-31 | 1385 | 0 | 515532.04 | 516786.06 | 2481 | 1786.5 | 0.92863 | 0.071369 | 0
15060013 | 2015-11-01 | 2017-09-30 | 1 | 0 | 1427511 | 1539511.1 | 600 | 1286 | 0.92457 | 0.075428 | 0
15060014 | 2015-04-20 | 2018-12-14 | 1422234.2 | 1534288 | 64242516.8133 | 66447466.15 | 292018.61 | 441675.88 | 0.89885 | 0.10115 | 0
15060014-162 | 2015-06-22 | 2018-12-14 | 212048 | 0 | 541963907.59 | 541146657.73 | 187120.5 | 303887.89 | 0.9126 | 0.087402 | 0
15060015 | 2015-06-01 | 2015-12-31 | 1462 | 0 | 1739594 | 1680716.8
15060017 | 2015-10-15 | 2016-11-30 | 815313.65 | 498313 | 13044088.2435 | 13013704.12 | 18135.78 | 16435.5 | 0.85975 | 0.14025 | 0
15060018 | 2015-12-11 | 2017-06-30 | 609898 | 70234 | 23060983.72 | 24816233.86 | 26798 | 38478.5 | 0.90269 | 0.097314 | 0
15060019 | 2015-09-01 | 2016-09-30 | 100 | 0 | 89843 | 109597.49 | 60 | 270 | 0.92222 | 0.077778 | 0
15060020 | 2015-10-15 | 2018-06-30 | 0 | 47 | 5541985 | 6078662.05 | 1600 | 12527 | 0.97773 | 0.022272 | 0
15060021 | 2015-06-22 | 2015-10-12 | 298606 | 2967 | 4045272.35 | 3825824.11 | 9888 | 8550.5 | 0.86802 | 0.13198 | 0
15060022 | 2015-01-01 | 2015-07-31 | 0 | 0 | 34343 | 37406.8
15060023 | 2015-10-01 | 2016-12-31 | 276 | 0 | 16922761.3 | 16666939.23 | 997 | 9256 | 0.93318 | 0.066822 | 0
15060024 | 2015-08-01 | 2018-04-30 | 0 | 0 | 2525949.61 | 2388906.11 | 0 | 3583 | 0.89045 | 0.10955 | 0
15060025 | 2017-02-15 | 2017-08-15 | 10713481.1 | 6305087 | 50372795.2618 | 45035323.82 | 333350 | 312432.47 | 0.87482 | 0.12518 | 0
15060026 | 2015-08-01 | 2019-12-31 | 10474.2 | 28 | 7059715.2 | 7208953.28 | 15774.3 | 39457 | 0.94486 | 0.055136 | 0
15060027 | 2015-08-03 | 2015-12-21 | -1 | 0 | 1738599.7 | 1705878.78 | 2389 | 1876 | 0.9347 | 0.065299 | 0
15060028 | 2016-02-01 | 2019-05-31 | 65586 | 84813 | 129969808.115 | 128031238.15 | 89439 | 155455.5 | 0.89717 | 0.10283 | 0
15060029 | 2015-08-24 | 2016-02-29 | 291956 | 100569 | 7696194.99 | 8058902.09 | 12180 | 19223 | 0.82308 | 0.17692 | 0
15060031 | 2015-08-11 | 2015-10-11 | 0 | 0 | 364652 | 369282.31 | 0 | 16 | 1899-12-31 | 0 | 0
15060032 | 2015-11-01 | 2018-08-16 | 241257.75 | 263049 | 10827564.7154 | 11714685.68 | 47856.55 | 61341 | 0.86471 | 0.13529 | 0
15060032-162 | 2015-11-01 | 2018-08-18 | 0 | 0 | 23168718.44 | 23492823.84 | 2080 | 1729.02 | 0.99682 | 0.003181 | 0
15060033 | 2015-11-15 | 2016-01-31 | 0 | 0 | 88593 | 119888.02
15060034 | 2015-10-01 | 2016-02-01 | 5646 | 8 | 1013717 | 1022168.48 | 1527 | 2067 | 0.95791 | 0.04209 | 0
15060035 | 2015-10-08 | 2016-10-31 | 30 | 0 | 3793657.74 | 3681990.37 | 0 | 8829.25 | 0.90138 | 0.098621 | 0
15060036 | 2015-08-10 | 2016-06-01 | 0 | 0 | 81706.09 | 82362.77
15060038 | 2015-10-01 | 2016-10-13 | 22831 | 117692 | 1482393.6 | 1514389.3 | 2706 | 6032 | 0.87177 | 0.12823 | 0
15060039 | 2015-11-15 | 2017-06-30 | 0 | 0 | 12946672.37 | 13030229.42
15060040 | 2016-01-01 | 2016-02-26 | 98 | 0 | 77195.02 | 76458.61 | 28 | 383.5 | 0.98827 | 0.011734 | 0
15060041 | 2015-11-01 | 2020-03-31 | 994089.5 | 737024 | 40568083.0639 | 41677507.58 | 94919 | 101669.05 | 0.87352 | 0.12648 | 0
15060042, 15060043, 14060010, 15060045, 15060044 | 2015-11-16 | 2017-10-31 | 867686.09 | 889836 | 45777091.1574 | 45125876.07 | 66894 | 69501 | 0.90913 | 0.090869 | 0
15060046 | 2017-11-01 | 2020-03-31 | 1688836.69 | 1420078 | 75260387.2774 | 74193000.8 | 129379.75 | 163559.5 | 0.89908 | 0.10092 | 0
15060047 | 2016-04-01 | 2017-07-01 | 12991 | 0 | 14232064.7717 | 14633211.97 | 746 | 5256 | 0.97879 | 0.021214 | 0
15060997 | 2013-01-01 | 2013-12-31 | 0 | 0 | 0.01 | -2457024.28
15060999 | 2012-01-01 | 2012-12-31 | 2 | 0 | 0.01 | -466.91 | 0 | 9.5 | 0.84211 | 0.15789 | 0
15080001 | 2015-04-06 | 2015-11-02 | 0 | 0 | 3672060.02 | 3624753.24 | 901 | 849.5 | 0.99058 | 0.0094173 | 0
15080002 | 2015-06-01 | 2016-08-12 | 465991 | 291474 | 12503791 | 12685245.73 | 18774 | 23565 | 0.89786 | 0.096202 | 0.005941
15080003 | 2015-03-04 | 2015-12-31 | 0 | 0 | 0.01 | 0
15080004 | 2015-09-21 | 2016-05-31 | 194133 | 210018 | 12548203.4 | 11869930.31 | 13937 | 15169.5 | 0.93711 | 0.062692 | 0.00019777
15080004-064 | 2015-10-01 | 2016-05-31 | 0 | 0 | 3889347.44 | 3889347.63
15080005 | 2016-04-04 | 2017-06-20 | 646142 | 473107 | 40478342.43 | 39113702.74 | 27324 | 26252 | 0.92976 | 0.070242 | 0
15080006 | 2015-03-09 | 2018-01-16 | 1772702.6 | 1054606 | 47252867.17 | 45730092.36 | 46939.5 | 44274.6 | 0.95112 | 0.048674 | 0.00020328
15080007 | 2015-10-19 | 2016-07-07 | 0 | 0 | 4615563 | 4215315.13 | 103 | 592.5 | 0.99831 | 0.0016878 | 0
15080008 | 2015-06-01 | 2016-02-01 | 0 | 0 | 2004673 | 1968218.02 | 0 | 97 | 0.96907 | 0.030928 | 0
15080009 | 2015-07-31 | 2016-01-11 | 17012 | 3682 | 401899.15 | 363856.41 | 1785.5 | 1566.5 | 0.86116 | 0.13884 | 0
15080010 | 2015-08-26 | 2015-10-30 | 7804 | 0 | 406715.82 | 356574.74 | 1114 | 1281 | 0.82162 | 0.17838 | 0
15080013 | 2015-09-18 | 2015-12-18 | 14747 | 0 | 588822.48 | 582882.81 | 1820 | 1780 | 0.97584 | 0.024157 | 0
15080014 |  | 2016-04-29 | 0 | 0 | 213790 | 169568.2
15080015 | 2015-10-01 | 2017-01-27 | 18364 | 6459 | 2004110.54 | 1918186.03 | 2655 | 3821 | 0.88498 | 0.09474 | 0.020283
15080015-064 | 2015-10-05 | 2017-03-31 | 0 | 0 | 15601 | 15601
15080016 | 2015-11-01 | 2016-03-01 | 36674 | 4804 | 1032808 | 952192.57 | 901 | 1326.5 | 0.75123 | 0.16773 | 0.08104
15080016-064 | 2015-11-01 | 2016-03-01 | 0 | 0 | 24970 | 24970
15080017 | 2016-03-15 | 2017-03-31 | 168407 | 105013 | 10702657.22 | 10574302.55 | 9047.5 | 9420 | 0.9172 | 0.074151 | 0.0086518
15080018 | 2015-11-01 | 2016-03-01 | 0 | 120 | 40775 | 35602.43 | 0 | 4 | 1899-12-31 | 0 | 0
15080019 |  | 2017-04-30 | 0 | 0 | 47548 | 37638.24
15080020 | 2016-01-01 | 2018-12-31 | 0 | 0 | 0.01 | -0.01
15080020-063 | 2016-01-01 | 2019-06-30 | 1 | 0 | 1857664 | 1783744.19
15080021 | 2015-12-18 | 2017-12-31 | 28 | 0 | 37508 | 36746.89 | 128 | 299.5 | 0.99165 | 0.0083472 | 0
15080997 | 2015-01-01 | 2015-01-31 | 0 | 0 | -739966 | -1381419.87
15080999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | 14524.9 | 0 | 55 | 0.96364 | 0.036364 | 0
15090001 | 2015-05-01 | 2017-08-31 | 18461 | 0 | 3347909.61 | 2961160.92 | 2247 | 3336.08 | 0.97962 | 0.020383 | 0
15090002 | 2015-02-01 | 2015-06-30 | 0 | 0 | 1017732.5 | 1017155.94 | 0 | 288.69 | 1899-12-31 | 0 | 0
15090003 | 2014-12-01 | 2015-07-31 | 0 | 0 | 76101 | 52046.53 | 475 | 134 | 1899-12-31 | 0 | 0
15090004 | 2015-02-01 | 2016-03-31 | 0 | 0 | 0 | 891.35
15090005 | 2015-01-28 | 2015-07-31 | 4896 | 0 | 5861817.98 | 5026432.95 | 3649 | 4155.9 | 0.66866 | 0.23437 | 0.096971
15090006 | 2015-01-01 | 2016-12-31 | 844.69 | 0 | 1331562 | 1010039.02 | 14 | 1093.32 | 0.80381 | 0.15183 | 0.04436
15090007 | 2015-03-01 | 2015-09-30 | 3509 | 0 | 2753770.16 | 2644246.17 | 1227 | 1090.4 | 0.78861 | 0.16966 | 0.041728
15090008 | 2015-01-01 | 2015-12-31 | 0 | 0 | 26520 | 2075.44
15090009 | 2015-01-31 | 2016-06-30 | 15730 | 0 | 544366 | 564078.17 | 1591 | 1830.73 | 0.99945 | 0.00054623 | 0
15090010 | 2015-03-31 | 2015-10-31 | 0 | 0 | 1705777.69 | 1691925.63 | 252 | 920 | 1899-12-31 | 0 | 0
15090011 | 2015-05-01 | 2018-11-05 | 290917.5 | 89640 | 57600046.379 | 56861634.62 | 32713.7 | 32013.93 | 0.91641 | 0.066534 | 0.017055
15090012 | 2015-08-01 | 2016-02-28 | 30194.23 | 19901 | 4015501.355 | 3878322 | 2935.5 | 3865.17 | 0.9154 | 0.063516 | 0.021086
15090013 | 2015-08-01 | 2017-08-30 | 27257 | 5662 | 2909361.69 | 2852826.89 | 16828 | 4223.26 | 0.88421 | 0.1004 | 0.015391
15090014 | 2015-11-01 | 2017-10-31 | 175965.2 | 168521 | 29253836.6357 | 28455478.63 | 15175.5 | 14673.21 | 0.95522 | 0.038574 | 0.0062018
15090015 | 2015-10-01 | 2016-05-31 | 0 | 0 | 10904487.06 | 10814707.07 | 0 | 674 | 1899-12-31 | 0 | 0
15090016 | 2016-02-01 | 2016-10-31 | 0 | 0 | 6035069.07 | 5915120.74 | 854 | 712 | 1899-12-31 | 0 | 0
15090017 | 2016-01-04 | 2016-05-31 | 0 | 0 | 950058 | 969173.94 | 546 | 614 | 0.98046 | 0.019544 | 0
15090991 | 2015-01-01 | 2015-12-31 | 187159 | 96390 | 0 | -59011.56 | 5716.25 | 10212.9 | 0.98433 | 0.014638 | 0.0010281
15090992 | 2015-01-01 | 2016-12-31 | 0 | 0 | 0.01 | -154263.56 | 0 | 1767 | 0.82286 | 0.11743 | 0.059706
15090997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -1998874.12
15090999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 5000.01 | 8545.84 | 0 | 70.88 | 1899-12-31 | 0 | 0
15110001 |  |  | 0 | 0 | 784711.03 | 782682.54
15110002-151, 15110002, 20110002-151, 20110002 | 2016-01-01 | 2018-11-15 | 0 | 0 | 91182096.547 | 103054505.41 | 0 | 17091.5 | 0.86944 | 0.12937 | 0.0011955
15110003 | 2015-05-28 | 2021-10-31 | 0 | 0 | 33149706.6 | 37745807.93 | 0 | 187731 | 0.835 | 0.16492 | 7.4575e-05
15110003-159 | 2015-05-28 | 2021-10-31 | 0 | 0 | 740779583 | 0
15110005 | 2016-02-25 | 2019-06-01 | 1638 | 0 | 28612520.64 | 28471217.62 | 0 | 463.5 | 0.97303 | 0.026969 | 0
15110006 | 2015-11-09 | 2020-12-08 | 0 | 0 | 101600 | 133927.83
15110006-159 | 2015-11-09 | 2020-12-08 | 0 | 0 | 18168338 | 0
15110007-159 | 2015-05-28 |  | 0 | 0 | 47618831 | 0
15110008-159 | 2015-05-28 | 2021-10-31 | 0 | 0 | 13020699 | 0
15110997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | -16161.5
15110999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | -150836.91
15120001 | 2014-12-31 | 2015-06-30 | 22 | 0 | 14303752 | 13911537.6 | 0 | 7 | 1899-12-31 | 0 | 0
15120999 | 2015-01-01 |  | 0 | 0 | 0 | 2135.41
15141001 | 2015-05-04 | 2015-12-31 | 7768 | 7457 | 45492782.0635 | 44537488.92 | 67838 | 60931.75 | 0.67423 | 0.23739 | 0.088378
15141002 | 2015-06-01 | 2015-12-31 | 3164 | 2084 | 17759387.55 | 18147771.67 | 31995 | 46677.25 | 0.74109 | 0.25891 | 0
15141003 | 2015-06-08 |  | 380749 | 0 | 459310.5404 | 489319.43 | 1360 | 1451 | 0.60924 | 0.24466 | 0.14611
15141004 | 2015-08-01 | 2017-04-30 | 1228610 | 1025366 | 115399840.146 | 107296719 | 205334 | 168863.5 | 0.76137 | 0.23863 | 0
15141005 | 2015-09-01 | 2016-08-31 | 1631 | 168 | 20759426 | 20807148.5 | 13393 | 5560.25 | 0.78333 | 0.21667 | 0
15141006 | 2015-08-03 |  | 1017307 | 0 | 1197557 | 1013487.49 | 2474 | 2075.5 | 0.72175 | 0.21971 | 0.05854
15141007 | 2015-07-27 | 2017-06-30 | 245441 | 243735 | 37405744.61 | 37170835.47 | 60104 | 58130.25 | 0.69456 | 0.28529 | 0.020144
15141008 | 2015-07-27 | 2015-12-31 | 0 | 0 | 561720.5 | 565082.3
15141997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -6197627.41
15141999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | 361360.57 | 0 | 1927.14 | 0.945 | 0.055004 | 0
15141999-110 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | 11133.39
15145001 |  |  | 0 | 0 | 0.01 | 661090.41 | 0 | 18.5 | 1899-12-31 | 0 | 0
15145003 | 2015-02-18 | 2015-10-01 | 43051 | 35843 | 1798685.28 | 1561869.54 | 9482.82 | 7532 | 0.84629 | 0.15371 | 0
15145005 | 2015-06-09 | 2016-03-18 | 834756.53 | 819212 | 12152451.4648 | 9673435.14 | 68994.5 | 55735.5 | 0.98028 | 0.019691 | 2.6913e-05
15145006 | 2015-05-01 | 2017-12-31 | 0 | 0 | 243462.84 | 270760.07 | 0 | 0 | 0 | 0 | 0
15145007 | 2015-05-01 | 2017-12-31 | 12 | 0 | 261796.84 | 246064.71 | 0 | 0 | 0 | 0 | 0
15145008 | 2015-08-01 | 2018-06-30 | 332730 | 328567 | 6376636.4936 | 6769043.63 | 16743 | 19177 | 0.80643 | 0.14092 | 0.052641
15145009 | 2017-08-01 | 2017-12-31 | 77 | 0 | 276678.25 | 367137.28
15145010 | 2015-07-01 | 2016-10-31 | 12981805 | 12715372 | 79722860.9454 | 66660655.16 | 707310.26 | 688722.07 | 0.85245 | 0.14754 | 9.4378e-06
15145011 | 2015-06-08 | 2016-01-22 | 158513.08 | 157082 | 1932901.97 | 1886941.86 | 9924 | 11609.75 | 0.8352 | 0.1648 | 0
15145012 | 2015-07-01 | 2016-08-31 | 6732794 | 6731343 | 37537724.5694 | 34388770.82 | 257363 | 237108.12 | 0.8419 | 0.15487 | 0.003239
15145013 | 2015-07-01 | 2016-08-31 | 6304312 | 5982240 | 29040537.5367 | 26229989.53 | 248887.5 | 184195.27 | 0.85313 | 0.14687 | 0
15145014 | 2015-07-01 | 2016-08-31 | 6257551 | 6180253 | 41603658.075 | 38152896.43 | 237009 | 212717.5 | 0.83019 | 0.16975 | 5.6413e-05
15145015 | 2015-07-01 | 2016-08-31 | 7241418 | 7169047 | 31090428.9693 | 27705033.94 | 258258.55 | 273616.5 | 0.8339 | 0.1661 | 0
15145016 | 2015-08-24 | 2016-01-01 | 0 | 0 | 0.01 | 0
15145017 | 2015-08-03 | 2016-09-30 | 6730922 | 6726311 | 37100086.625 | 35468376.16 | 246750 | 228532.45 | 0.81321 | 0.18673 | 6.126e-05
15145018 | 2015-08-03 | 2016-09-09 | 3833137 | 3813439 | 21814267.727 | 18641392.38 | 138271 | 115812.81 | 0.85476 | 0.14512 | 0.00012088
15145019 | 2015-08-03 | 2016-09-09 | 5662194 | 5661743 | 30398366.7454 | 26886156.96 | 253794 | 226617.3 | 0.82302 | 0.17698 | 0
15145020 | 2015-09-28 | 2015-12-18 | 35263 | 35235 | 432047.49 | 295537.34 | 4966 | 5238.75 | 0.89372 | 0.10628 | 0
15145021 | 2015-10-31 |  | 63 | 0 | 18739 | 22125.78
15145022 | 2015-10-30 | 2017-01-31 | 65 | 0 | 233108.84 | 231583.93
15145023 | 2015-10-30 | 2017-12-31 | 25 | 0 | 283118.84 | 289231.43
15145024 | 2015-10-30 | 2017-12-31 | 460 | 0 | 169797 | 82609.94
15145025 |  |  | 98 | 0 | 18938 | 25494.95
15145026 | 2015-10-30 | 2019-05-31 | 379223 | 378177 | 10537206.09 | 11692645.9 | 32044 | 32370 | 0.79934 | 0.13265 | 0.068018
15145027 | 2015-10-30 | 2017-12-31 | 100 | 0 | 233683 | 241816.76
15145029 | 2015-01-01 | 2017-06-30 | 113 | 0 | 37107 | 30465.34
15145030 | 2015-12-01 | 2016-12-30 | 195812 | 195637 | 3580687.9915 | 5245426.24 | 18989.85 | 27847.75 | 0.95537 | 0.041125 | 0.0035012
15145997 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0.01 | -2308021.62
15145999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | 59689.94
15146001 | 2015-03-30 | 2015-12-31 | 748131 | 747909 | 9286049 | 8920778.41 | 15434 | 21066.5 | 0.77723 | 0.22277 | 0
15146002 | 2015-05-15 | 2015-12-31 | 141 | 0 | 3961175 | 3911326.41
15146003 | 2015-10-12 | 2017-05-26 | 105214 | 104853 | 3994818.27 | 3567963.53 | 8157.18 | 6366.25 | 0.9153 | 0.084704 | 0
15146004 |  | 2016-05-13 | 258090 | 255247 | 4051230.19 | 3734991.51 | 4618 | 4828 | 0.84548 | 0.15452 | 0
15146005 | 2015-09-01 | 2016-08-31 | 0 | 0 | 5108162.86 | 5110237.21
15146006 | 2015-09-01 | 2016-08-31 | 0 | 0 | 11283024.99 | 11277938.87
15146008 | 2015-08-17 | 2017-12-31 | 752438 | 757427 | 36224647.4863 | 33776665.57 | 108779 | 51258 | 0.79607 | 0.20393 | 0
15146009 | 2015-08-17 | 2015-12-18 | 23551 | 23550 | 249056 | 218948.18 | 1829 | 2022 | 0.9273 | 0.0727 | 0
15146010 | 2015-12-01 | 2016-08-31 | 0 | 0 | 1121378 | 1120372.63
15146011 | 2015-12-01 | 2016-08-31 | 0 | 0 | 810916 | 809843.43
15146012 | 2016-01-04 | 2017-03-31 | 464613 | 463442 | 13718744.0325 | 15246553.59 | 22963 | 27237.25 | 0.71667 | 0.28333 | 0
15146013 | 2016-01-04 | 2017-03-31 | 121077 | 120396 | 4943196.68 | 4741585.58 | 7631 | 7372 | 0.7775 | 0.2225 | 0
15146014 | 2016-01-04 | 2016-12-30 | 5867.92 | 5528 | 21380287.8784 | 22586444.69 | 60535 | 63371 | 0.74693 | 0.25307 | 0
15146015 | 2015-11-16 | 2016-12-31 | 123 | 0 | 5269935 | 5035246.62 | 0 | 1101 | 0.77748 | 0.22252 | 0
15146016 |  | 2016-12-31 | 265203 | 254484 | 6313551.22 | 6123386.77 | 9965 | 7355 | 0.7329 | 0.2671 | 0
15146997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -112854.89
15146999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -81128.47
15148001 | 2015-05-04 | 2015-11-16 | 541707 | 518102 | 8147753.2504 | 7992158.22 | 29744.67 | 30429.5 | 0.67702 | 0.30109 | 0.021887
15148002 | 2015-02-23 | 2016-09-01 | 806831.01 | 737823 | 6438732.1225 | 5892269.66 | 88500 | 30348 | 0.80592 | 0.19408 | 0
15148003, 15146007, 15145004 | 2015-03-30 | 2016-11-01 | 12717843 | 12635928 | 83716885.763 | 74909840.07 | 715307.35 | 710846.34 | 0.85427 | 0.14572 | 8.0709e-06
15148004 | 2015-05-18 | 2016-03-31 | 433394 | 412769 | 4486700.01 | 3803669.23 | 18499 | 17758 | 0.75329 | 0.24671 | 0
15148005 | 2015-05-26 | 2016-10-31 | 170643 | 170492 | 3427321.055 | 2592040.92 | 11702 | 9308 | 0.79856 | 0.20117 | 0.00026859
15148006 | 2015-06-03 | 2015-11-27 | 155494 | 152435 | 2771108.79 | 2272562.42 | 11803 | 8518 | 0.71607 | 0.27324 | 0.010683
15148007 | 2015-06-13 | 2017-09-30 | 36846 | 17260 | 283774.2136 | 229742.69 | 1123 | 1255 | 0.87052 | 0.12948 | 0
15148008 | 2015-06-15 | 2016-12-31 | 259299 | 259255 | 2596856.25 | 2063790.17 | 8772 | 7519 | 0.89001 | 0.10999 | 0
15148009 | 2015-05-26 |  | 5918 | 5916 | 177132 | 156308.76 | 866 | 788 | 0.74239 | 0.25761 | 0
15148010 | 2015-06-15 | 2016-08-31 | 0 | 0 | 1838377.39 | 1836874.94
15148011 | 2015-06-15 | 2016-08-31 | 0 | 0 | 1899629.9 | 1904241.18
15148012 | 2015-06-15 | 2016-08-31 | 0 | 0 | 1676584.3 | 1675196.16
15148013 | 2015-06-15 | 2016-08-31 | 0 | 0 | 1987630.53 | 1984145.94
15148014 | 2015-07-06 | 2016-12-17 | 832101.91 | 654137 | 7492984.2911 | 7241548.1 | 88388.4 | 31317 | 0.84103 | 0.15897 | 0
15148015 | 2015-08-03 | 2016-08-31 | 0 | 0 | 4119673.87 | 4116681.24
15148016 | 2015-08-03 | 2016-08-31 | 0 | 0 | 6936740.02 | 6936932.71
15148017 | 2015-08-03 | 2016-08-31 | 0 | 0 | 3564025.56 | 3541533.52
15148018 | 2015-08-31 | 2016-03-31 | 371661 | 354395 | 3791825.8611 | 3153890.16 | 13922.48 | 9855 | 0.79072 | 0.20928 | 0
15148019 | 2015-09-08 | 2016-10-31 | 600485 | 600451 | 7492780.85 | 7224498.76 | 21121 | 23670 | 0.7681 | 0.227 | 0.0049007
15148021, 15110004 | 2015-11-23 | 2017-10-22 | 116266.25 | 123005 | 16284510.984 | 13705272.04 | 68368 | 35379.75 | 0.87876 | 0.12124 | 0
15148022 | 2015-10-26 | 2016-07-01 | 335389 | 345249 | 1185604.7504 | 1034870.69 | 4158 | 5888.25 | 0.82775 | 0.17225 | 0
15148023 | 2015-11-09 | 2016-07-31 | 342228 | 444225 | 4690149 | 4647148.82 | 4923 | 12701.25 | 0.80551 | 0.19449 | 0
15148997 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -1463123.08
15148999 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0.01 | -19577.67
15150001 | 2016-01-04 | 2017-01-31 | 0 | 0 | 10612573.87 | 10595060.75
15150002 |  | 2015-07-15 | 0 | 0 | 99213.45 | 115464.28
15150003 | 2016-05-23 | 2017-08-31 | 0 | 0 | 22475764.633 | 22122083.74 | 0 | 946 | 0.82505 | 0.15381 | 0.021142
15150004 | 2016-01-05 |  | 2812 | 0 | 1171316.63 | 1170794.85 | 5444 | 2518.5 | 0.87354 | 0.12646 | 0
15150004-155 | 2016-01-05 | 2016-07-30 | 2873 | 0 | 13484912.9 | 12312362.75 | 5444 | 2518.5 | 0.87354 | 0.12646 | 0
15400999 |  |  | 0 | 0 | 0 | 98084.67
16000004-040, 16090004 | 2017-09-05 | 2019-01-07 | 3659 | 1093 | 45532958.9401 | 43952392.6 | 3311.5 | 8870.11 | 0.86088 | 0.10462 | 0.034498
16000009-040, 17060008 | 2017-04-10 | 2018-10-19 | 2766319.19 | 1144389 | 57020133.4078 | 59525490.03 | 82733.7 | 121654.65 | 0.8704 | 0.1296 | 0
16001 | 2002-05-01 |  | 363017 | 412611 | 28098114 | 29266457 | 0 | 167598 | 1899-12-31 | 0 | 0
16002 | 2002-07-01 |  | 346875 | 12600085847 | 9342583 | 9365768 | 0 | 22178 | 1899-12-31 | 0 | 0
16003 | 2001-07-01 |  | 317 | 0 | 280866 | 261272 | 0 | 408 | 1899-12-31 | 0 | 0
16004 | 2002-06-30 |  | 476765 | 377732 | 17640166 | 17646132 | 0 | 32893 | 1899-12-31 | 0 | 0
16005 | 2002-11-29 |  | 0 | 0 | 0 | 62547
16006 | 2002-08-30 |  | 0 | 0 | 0 | 267942 | 0 | 0 | 0 | 0 | 0
16007 | 2004-10-31 |  | 0 | 0 | 1490354 | 1490381 | 0 | 135 | 1899-12-31 | 0 | 0
16008 | 2001-12-31 |  | 0 | 0 | 430456 | 450504 | 0 | 6 | 1899-12-31 | 0 | 0
16009 | 2002-02-01 |  | 0 | 0 | 0 | 432545
16010 | 2002-01-01 |  | 25 | 0 | 182728 | 187429
16011 | 2001-07-01 |  | 0 | 0 | 266914 | 269892 | 0 | 480 | 1899-12-31 | 0 | 0
16012 | 2002-07-01 |  | 16 | 0 | 387321 | 416658 | 0 | 2844 | 1899-12-31 | 0 | 0
16013 | 2002-01-14 |  | 0 | 0 | 0 | 7639 | 0 | 91 | 1899-12-31 | 0 | 0
16014 | 2001-12-19 |  | 855 | 0 | 656706 | 919469 | 0 | 2809 | 1899-12-31 | 0 | 0
16015 | 2001-06-30 |  | 0 | 0 | 0 | 62843 | 0 | 1026 | 1899-12-31 | 0 | 0
16016 | 2002-07-02 |  | 0 | 143617 | 4347550 | 4299489 | 4903 | 5804 | 1899-12-31 | 0 | 0
16017 | 2001-12-31 |  | 0 | 0 | 0 | 15071 | 0 | 300 | 1899-12-31 | 0 | 0
16018 |  |  | 0 | 0 | 0 | 78562 | 0 | 549 | 1899-12-31 | 0 | 0
16019 | 2001-12-31 |  | 0 | 0 | 0 | 22914 | 0 | 97 | 1899-12-31 | 0 | 0
16020 |  |  | 8937 | 7753 | 616135 | 617953 | 0 | 2123 | 1899-12-31 | 0 | 0
16021 | 2001-11-01 |  | 21 | 0 | 0 | 230684 | 0 | 671 | 1899-12-31 | 0 | 0
16022 | 2001-11-15 |  | 1950 | 0 | 0 | 238229 | 0 | 544 | 1899-12-31 | 0 | 0
16023 | 2001-11-30 |  | 0 | 32178 | 1018802 | 1022270 | 0 | 3641 | 1899-12-31 | 0 | 0
16024 | 2006-01-29 |  | 627203 | 346691 | 0 | 56510848 | 0 | 90552 | 1899-12-31 | 0 | 0
16025 |  |  | 1299744 | 1728924 | 0 | 13561160 | 0 | 36720 | 1899-12-31 | 0 | 0
16027 | 2002-10-01 |  | 825513 | 727146 | 1 | 14848807 | 0 | 43073 | 1899-12-31 | 0 | 0
16028 |  |  | 0 | 0 | 0 | 307595 | 0 | 166 | 1899-12-31 | 0 | 0
16029 | 2004-05-01 |  | 12178197 | 3502053 | 41732499 | 103954370 | 0 | 377444 | 1899-12-31 | 0 | 0
16030001 | 2016-01-01 | 2017-01-01 | 100 | 0 | 3853531.9956 | 3853500.88 | 7062.33 | 10421.5 | 0.97328 | 0.023461 | 0.0032625
16030002 | 2016-04-01 | 2016-09-01 | 753 | 0 | 1587277.24 | 1666560.71 | 0 | 1038 | 0.88536 | 0.11464 | 0
16030003 | 2016-04-11 | 2016-08-12 | 71977 | 43324 | 3699523.19 | 3868690.51 | 4124 | 5785.62 | 0.90528 | 0.091952 | 0.0027655
16030004 | 2016-03-21 | 2016-09-30 | 349 | 0 | 2030563.86 | 2081252.84 | 2513 | 2113.2 | 0.99314 | 0.0068616 | 0
16030005 | 2016-02-29 |  | 1068 | 0 | 2497877.37 | 2497840.55 | 264 | 200 | 1899-12-31 | 0 | 0
16030006 | 2016-03-06 |  | 0 | 0 | 74382.85 | 77890.25 | 240 | 464 | 0.78879 | 0.2069 | 0.0043103
16030007 | 2016-03-07 | 2016-09-01 | 37088 | 11169 | 7546618 | 7509412.39 | 6978 | 6830.87 | 0.88853 | 0.10774 | 0.0037331
16030008 |  | 2016-07-15 | 24 | 0 | 85683.01 | 95871.32 | 304 | 618 | 1899-12-31 | 0 | 0
16030009 | 2016-05-09 | 2016-09-30 | 29 | 0 | 440085.95 | 418755.47 | 369 | 314.63 | 0.89511 | 0.10489 | 0
16030010 | 2017-06-14 | 2019-02-22 | 3299819.69 | 2659885 | 178582065.541 | 177512793.97 | 156265.79 | 178624.82 | 0.88198 | 0.11341 | 0.0046102
16030011 | 2016-06-13 | 2016-09-14 | 3848 | 0 | 973530.06 | 951277.71 | 1425 | 1300.8 | 0.99385 | 0.0061501 | 0
16030012 | 2016-04-19 |  | 2694 | 0 | 1814810.36 | 1790049.8 | 1476 | 1908 | 0.84434 | 0.15147 | 0.0041929
16030013 | 2016-04-18 | 2018-01-19 | 1496570 | 945050 | 39555182.6296 | 41077926.77 | 88282.5 | 126131.37 | 0.91606 | 0.083706 | 0.00022992
16030014 | 2016-05-09 | 2017-10-01 | 39241 | 202232 | 13295555.43 | 13029898.86 | 17833.5 | 16814.5 | 0.94424 | 0.055161 | 0.00059472
16030015 | 2016-10-01 |  | 0 | 0 | 0.01 | 149262.49 | 0 | 0 | 0 | 0 | 0
16030016 | 2016-03-01 | 2017-03-01 | 1775.8 | 0 | 66121.88 | 67197.91 | 382 | 266 | 0.88346 | 0.11654 | 0
16030017 | 2016-05-09 |  | 0 | 0 | 309966.82 | 243909.8 | 212 | 87 | 1899-12-31 | 0 | 0
16030018 |  |  | 0 | 0 | 0 | 350947.79 | 0 | 2225 | 0.91326 | 0.086742 | 0
16030019 | 2016-06-01 |  | 0 | 0 | 1033470.52 | 1056151.92 | 403 | 935 | 0.91818 | 0.081818 | 0
16030020 | 2016-05-31 | 2017-07-24 | 233049 | 147178 | 9416271.4301 | 8902475.85 | 17527.3 | 12197.39 | 0.89158 | 0.10842 | 0
16030021 | 2016-06-15 |  | 0 | 0 | 18653.13 | 17739.81 | 0 | 8 | 1899-12-31 | 0 | 0
16030022 | 2016-05-16 | 2017-03-10 | 2481 | 0 | 5969131.47 | 6457355.52 | 15975 | 24733.37 | 0.93299 | 0.062163 | 0.0048517
16030022-900 | 2016-05-16 |  | 0 | 0 | 3274211.2 | 3274211.2
16030023 | 2016-08-15 | 2018-03-31 | 295 | 58 | 12459968.2763 | 10856227.25 | 15681 | 12054.62 | 0.92824 | 0.071757 | 0
16030024 | 2016-07-11 | 2017-07-07 | 22783 | 21332 | 880211.16 | 928503.23 | 4813 | 6149 | 0.90649 | 0.093511 | 0
16030025 |  |  | 0 | 0 | 0 | 97595.22 | 0 | 550 | 0.92 | 0.08 | 0
16030026 | 2016-07-15 |  | 5 | 0 | 276295.6 | 298301.43 | 356 | 125 | 0.992 | 0.008 | 0
16030027 | 2016-07-11 | 2017-02-19 | 5442.1 | 0 | 161158.8 | 167911.51 | 895 | 851.5 | 0.89665 | 0.10335 | 0
16030028 | 2016-10-04 | 2017-07-25 | 286232 | 253050 | 7536730.12 | 7075629.51 | 13748 | 13194.91 | 0.94119 | 0.056385 | 0.0024252
16030029 | 2016-07-15 |  | 0 | 0 | 287057.66 | 319017.93 | 24 | 819 | 0.84982 | 0.15018 | 0
16030030 | 2016-10-31 | 2018-05-31 | 0 | 0 | 781502.18 | 733023.11 | 0 | 260 | 1899-12-31 | 0 | 0
16030031 | 2017-05-15 | 2017-10-13 | 0 | 0 | 72951 | 8607.79 | 48 | 62.78 | 0.8885 | 0.1115 | 0
16030032 | 2016-09-15 |  | 787 | 21320 | 11032640.58 | 9517627.82 | 16178 | 12967.61 | 0.93522 | 0.064314 | 0.00046269
16030033 | 2016-09-08 | 2017-08-21 | 1065 | 809 | 14194159.18 | 14293755.16 | 5761 | 6627.5 | 0.85439 | 0.14289 | 0.002716
16030034 | 2016-09-09 | 2018-01-31 | 111011 | 20288 | 6908161.83 | 6529652.74 | 13371 | 12900 | 0.87283 | 0.11795 | 0.0092248
16030035 |  | 2018-03-31 | 0 | 0 | 711691.33 | 703033.52
16030036 | 2016-10-07 | 2017-01-06 | 12 | 0 | 83573.08 | 78758.91 | 0 | 10 | 0.5 | 0.5 | 0
16030037 | 2017-02-01 | 2017-07-01 | 6417 | 0 | 1899265.15 | 1901489.34 | 2338 | 2622.83 | 0.91383 | 0.074728 | 0.011438
16030038 | 2016-12-15 | 2018-05-31 | 284692.71 | 80926 | 22653399.6324 | 22533633.5 | 14953.7 | 15532.12 | 0.94959 | 0.048223 | 0.002189
16030039 | 2016-08-24 |  | 320 | 0 | 47771.78 | 47143.03 | 240 | 220 | 1899-12-31 | 0 | 0
16030040 | 2017-04-03 | 2017-07-24 | 1 | 0 | 887968 | 873865.59 | 830 | 897.5 | 0.83565 | 0.16435 | 0
16030041 | 2016-11-14 | 2017-08-20 | 0 | 0 | 247389 | 245308.86
16030042 | 2016-11-01 | 2018-03-30 | 24 | 0 | 406529.97 | 400533.07 | 297 | 398 | 0.99497 | 0.0050251 | 0
16030043 | 2016-11-23 | 2017-05-15 | 3 | 0 | 805115.84 | 805115.84 | 370 | 240 | 1899-12-31 | 0 | 0
16030044 | 2016-07-05 | 2016-08-31 | 0 | 0 | 1086135.01 | 1089582.87
16030045 | 2017-02-01 | 2017-12-29 | 345391.25 | 71633 | 8697971.27 | 8786377.25 | 11074 | 11457.04 | 0.93449 | 0.060007 | 0.0054988
16030047 |  |  | 0 | 0 | 2291.92 | 4311.88
16030048 | 2016-12-20 |  | 0 | 0 | 23704 | 23652.18 | 0 | 158 | 0.98734 | 0.012658 | 0
16030997 | 2016-01-01 | 2016-12-31 | 0 | 0 | 0.01 | 0
16030999 | 2016-01-01 |  | 0 | 0 | 0.01 | 18899.29 | 0 | 190 | 1899-12-31 | 0 | 0
16031 | 2002-01-15 |  | 413 | 0 | 0 | 318252 | 0 | 742 | 1899-12-31 | 0 | 0
16032 | 2002-11-30 |  | 484 | 0 | 3071293 | 2994459 | 0 | 4592 | 1899-12-31 | 0 | 0
16033 |  |  | 5009869 | 1316581 | 31066923 | 31499547 | 0 | 110021 | 1899-12-31 | 0 | 0
16034 | 2002-04-20 |  | 149168 | 18636 | 0 | 1597211 | 0 | 7746 | 1899-12-31 | 0 | 0
16035 | 2001-12-21 |  | 0 | 0 | 0 | 58830 | 0 | 406 | 1899-12-31 | 0 | 0
16036 | 2004-11-04 |  | 1501815 | 1124998 | 20174858 | 18833608 | 0 | 144528 | 1899-12-31 | 0 | 0
16037 | 2003-01-06 | 2003-01-06 | 0 | 0 | 2172061 | 2178762 | 0 | 8537 | 1899-12-31 | 0 | 0
16040001 | 2016-03-07 | 2016-08-04 | 9910 | 0 | 692205.833 | 747965.65 | 1087 | 1663 | 0.94528 | 0.05472 | 0
16040002 | 2016-03-21 | 2016-10-21 | 16297 | 0 | 1292883.03 | 1404865.37 | 3517 | 3720 | 0.98253 | 0.017473 | 0
16040003 | 2016-06-13 | 2016-07-15 | 0 | 0 | 223637.92 | 231779.7 | 0 | 12 | 1899-12-31 | 0 | 0
16040004 | 2016-04-04 | 2016-05-06 | 0 | 0 | 213934.62 | 216432.71 | 0 | 17 | 1899-12-31 | 0 | 0
16040005 | 2017-01-03 | 2017-02-03 | 0 | 0 | 229682 | 222981.28 | 0 | 2 | 1899-12-31 | 0 | 0
16040006 | 2017-04-03 | 2018-02-01 | 0 | 0 | 325903.3 | 318994.8
16040007 | 2017-02-08 | 2018-05-09 | 0 | 0 | 28214146.5753 | 25871948.68 | 7834.7 | 9685 | 0.9033 | 0.096696 | 0
16040008 | 2016-07-11 | 2017-07-28 | 105295.02 | 104049 | 2445792.3994 | 2507305.65 | 6920 | 7477.5 | 0.93407 | 0.065931 | 0
16040009 |  | 2017-12-31 | 1 | 0 | 447093.14 | 439278.92 | 0 | 0 | 0 | 0 | 0
16040010 | 2017-03-01 | 2017-10-27 | 52 | 0 | 1044655.08 | 1054455 | 697 | 614 | 0.97394 | 0.026059 | 0
16050001 | 2016-05-02 | 2016-11-18 | 1025 | 0 | 5536318.96 | 5143952.51 | 16 | 0 | 0 | 0 | 0
16050002 | 2016-04-04 | 2016-07-05 | 33 | 0 | 158484.02 | 142959.91 | 44 | 0 | 0 | 0 | 0
16050003 | 2016-04-04 | 2016-07-05 | 0 | 0 | 172081.56 | 162023.46
16050005 | 2016-05-27 | 2016-06-07 | 0 | 0 | 12138 | 10422.75 | 118 | 109 | 1899-12-31 | 0 | 0
16050006 | 2016-07-18 | 2017-03-31 | 1152.63 | 0 | 747923.1051 | 741557.79 | 1391.38 | 1536.14 | 0.96647 | 0.023761 | 0.0097647
16050007 | 2016-08-01 | 2016-08-12 | 11 | 0 | 55490 | 54517.27
16050008 | 2016-09-26 | 2016-12-12 | 17 | 0 | 633024.02 | 598653.98 | 0 | 0 | 0 | 0 | 0
16050009 | 2016-09-21 | 2016-10-25 | 12 | 0 | 58723 | 56955.72
16050010 | 2017-03-21 | 2019-10-17 | 374550.72 | 333480 | 51418397.2634 | 52748582.05 | 37391.58 | 83540.99 | 0.81097 | 0.17089 | 0.018135
16060001 | 2018-10-08 | 2020-01-31 | 0 | 0 | 1476316 | 1855900.54 | 2173 | 3861 | 0.97578 | 0.024217 | 0
16060002 | 2016-04-22 | 2016-11-01 | 0 | 0 | 2763415.25 | 2731424.32 | 0 | 1443.5 | 0.89851 | 0.10149 | 0
16060003 | 2017-02-20 | 2019-11-30 | 12273.8 | 33956 | 61534552.9329 | 62295973.58 | 22937.3 | 57187 | 0.89703 | 0.10297 | 0
16060004 | 2016-05-09 | 2016-09-13 | 0 | 0 | 643114.32 | 643459.48 | 0 | 1344.5 | 0.96356 | 0.036445 | 0
16060005 | 2016-02-26 | 2016-12-28 | 77652.75 | 32172 | 8025697.885 | 7737192.92 | 8373.95 | 7827.5 | 0.88061 | 0.11939 | 0
16060006 | 2016-04-01 | 2016-08-31 | 13 | 0 | 2308038.57 | 2292704.34 | 1606.5 | 3262.5 | 0.87847 | 0.12153 | 0
16060007 | 2016-03-01 | 2016-04-15 | 0 | 0 | 21756 | 10021.18
16060008 | 2016-03-01 | 2016-07-31 | 0 | 0 | 10162.5 | 15119.27
16060009 | 2016-08-01 | 2017-06-05 | 0 | 0 | 0.01 | 576833.02 | 0 | 497 | 0.68109 | 0.31891 | 0
16060010 | 2016-07-05 | 2017-10-27 | 1056537 | 435694 | 25527777.27 | 26271805.6 | 36854 | 61831.5 | 0.84569 | 0.15431 | 0
16060011 | 2016-05-09 | 2016-12-17 | 293273 | 128605 | 6071858.592 | 6047598.31 | 7640 | 36195 | 0.93596 | 0.064042 | 0
16060012 | 2017-02-01 | 2018-10-31 | 0 | 0 | 827980 | 893155.25 | 100 | 9 | 1899-12-31 | 0 | 0
16060013 | 2016-08-01 | 2017-12-31 | 0 | 0 | 2336 | 2352.54
16060014 | 2016-08-01 | 2018-04-30 | 500 | 0 | 544409 | 547379.68 | 310 | 2151 | 0.96606 | 0.033938 | 0
16060015 | 2016-04-01 | 2016-08-01 | 0 | 0 | 0.01 | 47422.01
16060016 | 2017-03-01 | 2019-12-31 | 0 | 0 | 0.01 | 0
16060017 | 2016-07-25 | 2016-10-28 | 280 | 0 | 505698.38 | 504198.62 | 569 | 1836.5 | 0.91288 | 0.087122 | 0
16060018 | 2016-07-15 | 2016-09-30 | 0 | 0 | 1139979 | 991341.87 | 0 | 1697.5 | 0.84271 | 0.15729 | 0
16060019 | 2016-04-01 | 2017-07-01 | 0 | 0 | 59999 | 58263.8
16060020 | 2016-10-01 | 2019-06-01 | 5307203.02 | 3762020.33 | 239503448.8864 | 243788120.19 | 287855.59 | 397342.99 | 0.82724 | 0.17276 | 0
16060021 | 2017-01-01 | 2018-02-01 | 1308 | 0 | 90391.39 | 160757.2
16060022 | 2016-09-20 | 2017-07-20 | 161 | 0 | 1955989 | 1820592.12 | 673 | 1116.5 | 0.72145 | 0.27855 | 0
16060023 | 2018-08-20 | 2020-01-31 | 0 | 0 | 250039 | 258024.05
16060024 | 2016-09-26 | 2016-12-31 | 0 | 0 | 32733.38 | 53366.93 | 0 | 260 | 0.78846 | 0.21154 | 0
16060025 | 2017-01-03 | 2018-12-31 | 133427.33 | 305 | 27717200.65 | 26085463.78 | 9322.7 | 18633 | 0.92006 | 0.079939 | 0
16060026 | 2016-09-15 | 2017-01-01 | 0 | 0 | 168060 | 168881.81 | 340 | 473 | 0.95455 | 0.045455 | 0
16060027 | 2016-09-16 | 2016-12-31 | 0 | 0 | 26431 | -1412
16060028 | 2016-07-01 | 2016-12-31 | 0 | 0 | 0.01 | 67849.53
16060030 | 2016-12-15 | 2018-06-30 | 0 | 7 | 780635 | 835305.35 | 312 | 1842 | 0.97883 | 0.021173 | 0
16060031 | 2017-11-01 | 2019-08-31 | 4661 | 43 | 5178630.9044 | 5656846.1 | 7439 | 16187.5 | 0.95212 | 0.047876 | 0
16060032 | 2016-11-07 | 2017-11-01 | 13628 | 1198 | 5435805.1018 | 5540790.68 | 8273 | 10436.5 | 0.77325 | 0.22675 | 0
16060033 | 2016-11-15 | 2019-12-30 | 0 | 0 | 1826462 | 1846967.24 | 2760 | 6720.5 | 0.99055 | 0.0094487 | 0
16060034 | 2016-11-23 | 2016-12-23 | 10 | 0 | 216760.13 | 205038.56 | 364 | 1118.5 | 0.93563 | 0.064372 | 0
16060035 | 2016-12-12 | 2017-10-06 | 0 | 0 | 72125 | 50430.63 | 0 | 687 | 0.97234 | 0.027656 | 0
16080001 | 2016-03-28 | 2016-05-03 | 960 | 974 | 185686 | 164930.27 | 212 | 180.5 | 0.9446 | 0.055402 | 0
16080002 | 2016-01-25 | 2016-04-01 | 12566 | 7638 | 646826 | 599062.31 | 792 | 1138 | 0.77548 | 0.21924 | 0.0052724
16080003 | 2016-07-05 | 2018-07-27 | 508644.5 | 303217 | 18996538.8878 | 18482550.07 | 30209.5 | 32819 | 0.90521 | 0.093117 | 0.0016759
16080004 | 2016-06-01 | 2016-12-02 | 27765 | 51554 | 3084197 | 3064864.54 | 9357 | 9961 | 0.90287 | 0.09477 | 0.0023592
16080005 | 2016-01-04 | 2017-03-31 | 437233 | 249079 | 34630159.0083 | 34282844.6 | 9538.51 | 11279.62 | 0.82437 | 0.13613 | 0.039496
16080006 | 2016-07-25 | 2016-12-09 | 2409 | 0 | 1448603.43 | 1258599.11 | 1733 | 976.15 | 0.93546 | 0.064539 | 0
16080007 | 2016-11-01 | 2017-11-30 | 46669 | 40046 | 11495498.22 | 11302855.23 | 6151 | 6265.5 | 0.9534 | 0.046205 | 0.00039901
16080008 | 2016-09-01 | 2016-12-30 | 0 | 0 | 3495 | 822.53
16080009 | 2016-04-18 | 2016-11-22 | 1782 | 1412 | 6884643 | 6889957.19 | 1397 | 2626.5 | 0.85494 | 0.13269 | 0.012374
16080010 | 2016-08-01 | 2017-09-25 | 67426 | 21780 | 3062490.215 | 2991715.2 | 5151 | 5298.5 | 0.85685 | 0.13976 | 0.0033972
16080011 | 2016-08-01 | 2017-09-25 | 202612 | 87243 | 6471936.29 | 6394402.55 | 10244 | 11110 | 0.90972 | 0.088569 | 0.0017102
16080012 | 2016-06-01 | 2018-07-24 | 3259426.51 | 1896968 | 337490358.9682 | 339038734.98 | 168629.49 | 192033.67 | 0.86984 | 0.12806 | 0.0021064
16080013 | 2016-04-26 | 2016-09-16 | 1 | 0 | 1224512.93 | 1148436.2 | 0 | 210.5 | 0.92874 | 0.038005 | 0.033254
16080014 | 2016-01-01 | 2016-10-03 | 0 | 0 | 791023 | 759175.14 | 0 | 20.15 | 1899-12-31 | 0 | 0
16080016 | 2016-09-27 | 2016-12-31 | 3996 | 3081 | 593876 | 531248.75 | 675 | 329.5 | 0.96813 | 0.031866 | 0
16080017 | 2016-12-17 | 2017-08-18 | 208080.08 | 191583 | 10517273.979 | 10612993.59 | 11644.6 | 10836.5 | 0.89789 | 0.10091 | 0.0011996
16080018 | 2016-08-08 | 2016-09-09 | 67 | 0 | 288352.82 | 275511.77 | 283 | 389.5 | 0.99101 | 0.0089859 | 0
16080019 | 2017-01-03 | 2017-04-14 | 10505 | 17174 | 593187 | 556409.12 | 593 | 900 | 0.82333 | 0.17667 | 0
16080020 | 2016-08-01 | 2016-10-31 | 0 | 0 | 25000 | 13362.56
16080021 | 2016-08-22 | 2019-12-31 | 1246 | 0 | 387503 | 331944.92 | 1372 | 1172.5 | 0.86525 | 0.13475 | 0
16080022 | 2017-04-01 | 2018-12-01 | 341762.76 | 230061 | 23050441.0008 | 22931598.6 | 25363.38 | 29076.25 | 0.89664 | 0.094072 | 0.0092859
16080023 | 2017-01-09 | 2018-11-21 | 492480 | 267094 | 15791605.099 | 15769263.23 | 17589.1 | 21567.25 | 0.92499 | 0.063696 | 0.011313
16080024 | 2016-12-01 | 2017-12-22 | 85568 | 48280 | 2600068.97 | 2591332.67 | 4285 | 3294.5 | 0.91425 | 0.085445 | 0.00030354
16080025 | 2017-05-01 | 2017-08-31 | 21660.46 | 0 | 897243.59 | 850302.57 | 1117.3 | 1175.5 | 0.88898 | 0.11102 | 0
16080026 | 2017-05-19 | 2020-01-31 | 1196779.05 | 536257 | 75240433.055 | 74851368.74 | 83061.89 | 86720.12 | 0.89208 | 0.10159 | 0.0063365
16080028 | 2016-12-28 | 2018-10-01 | 24 | 0 | 56100 | 40366.37 | 383 | 259.37 | 0.91132 | 0.088676 | 0
16090001 | 2016-09-01 | 2017-09-30 | 76316.04 | 38790 | 18431689.8905 | 18179479.37 | 12882 | 14045.2 | 0.90887 | 0.080312 | 0.010822
16090002 | 2016-01-25 | 2017-10-01 | 3455.9 | 227 | 6765903.5 | 5688334.75 | 8573 | 5354.06 | 0.86057 | 0.13709 | 0.0023347
16090003 | 2016-07-01 | 2019-02-01 | 602837.85 | 340051 | 316186531.0793 | 310912710.02 | 108559.5 | 95323.07 | 0.83636 | 0.1302 | 0.033434
16090005 | 2016-04-01 | 2016-12-31 | 0 | 172 | 2674880 | 2986355.57 | 690 | 1591.75 | 0.88409 | 0.10806 | 0.007853
16090006 | 2016-06-01 | 2017-08-31 | 736924.32 | 527236 | 51972399.9988 | 52407320.19 | 30215.55 | 35859.99 | 0.90971 | 0.079511 | 0.010778
16090007, 17090001 | 2016-06-01 | 2018-11-01 | 160406.6 | 115018 | 94923351.2146 | 97886285.3 | 25928 | 21936.89 | 0.89324 | 0.099626 | 0.0071377
16090008 | 2016-08-01 | 2016-12-31 | 0 | 0 | 25000 | 142575.98 | 0 | 593.79 | 0.936 | 0.063996 | 0
16090009 | 2017-03-01 | 2018-08-31 | 372.6 | 47 | 34818630.35 | 34781108.81 | 4264 | 4938.98 | 0.87639 | 0.11389 | 0.0097186
16090010 | 2016-08-01 | 2017-08-31 | 109802.47 | 11954 | 6620797.6938 | 5670611.25 | 7575 | 8666.22 | 0.81491 | 0.17135 | 0.013731
16110001 | 2016-06-28 | 2019-04-30 | 688048 | 486944 | 47489397.34 | 45065788.02 | 127576 | 142849.57 | 0.85453 | 0.14547 | 0
16110002 | 2017-04-22 | 2018-08-06 | 0 | 0 | 867733.17 | 899063.25
16110003 | 2016-10-06 | 2019-11-29 | 5688028.93 | 4519432 | 145573512.6038 | 174830864.43 | 175163.4 | 407973.46 | 0.77998 | 0.21956 | 0.00045224
16110004 | 2017-06-06 | 2019-06-28 | 946 | 0 | 25326570.7 | 28493768.52 | 2600 | 6707 | 0.896 | 0.10176 | 0.0022365
16135001 |  |  | 0 | 0 | 598609 | 367678.17
16135002 | 2016-11-28 | 2017-01-31 | 115 | 0 | 97300 | 89966.44 | 80 | 0 | 0 | 0 | 0
16135003 | 2016-11-28 | 2017-01-31 | 30 | 0 | 103545 | 87045.88
16135004 | 2016-11-28 | 2017-01-31 | 23 | 0 | 24800 | 21118.58 | 10 | 0 | 0 | 0 | 0
16141001 |  | 2016-12-31 | 32450 | 0 | 10245305.2479 | 8259778.66 | 98776 | 119983.25 | 0.74445 | 0.25138 | 0.0041756
16141002 | 2016-02-01 | 2016-10-15 | 634000 | 628983 | 56257968.06 | 54666744.32 | 122711 | 123061 | 0.73571 | 0.26424 | 5.2819e-05
16141003 | 2016-01-25 | 2016-03-31 | 0 | 0 | 19806 | 10431.69 | 100 | 86 | 0.93023 | 0.069767 | 0
16141004 | 2016-01-01 | 2016-12-31 | 506 | 0 | 82123.9991 | 64712.19 | 1058 | 643.5 | 0.79487 | 0.20513 | 0
16141005 | 2016-04-18 | 2016-12-31 | 740703.27 | 702365 | 83805299.0135 | 81624439.68 | 97120 | 115917 | 0.77056 | 0.22944 | 0
16141006 | 2016-04-01 | 2017-06-01 | 543218 | 482892 | 95322247.8416 | 95219367.11 | 126182.5 | 117183 | 0.59987 | 0.35415 | 0.045979
16141007 | 2016-04-16 | 2017-06-01 | 217306 | 174032 | 66091490.1826 | 60678982.74 | 105189.5 | 84195 | 0.6098 | 0.36475 | 0.025447
16141008 | 2016-03-07 | 2017-06-30 | 38 | 0 | 2208726 | 2110505.68
16141009 | 2016-05-02 | 2016-05-26 | 260 | 0 | 281060.47 | 218333.55 | 0 | 245.5 | 0.87373 | 0.12627 | 0
16141010 | 2016-05-16 | 2017-07-28 | 68363 | 64792 | 22644837.47 | 20139349.12 | 29024 | 32103.75 | 0.64063 | 0.29996 | 0.059409
16141011 | 2016-06-06 | 2017-06-06 | 9 | 0 | 694068.3061 | 554446.96 | 8929 | 7406.5 | 0.92378 | 0.076217 | 0
16141012 | 2016-07-11 | 2016-11-06 | 983 | 0 | 87220 | 73496.47 | 304 | 200 | 0.68 | 0.32 | 0
16141013 | 2016-07-14 | 2017-03-31 | 0 | 0 | 48776 | 38098.65
16141014 | 2016-12-12 | 2017-11-30 | 29178 | 15968 | 57332461.42 | 55445035.53 | 70996 | 73508 | 0.84621 | 0.15379 | 0
16141015 | 2016-10-21 | 2017-09-27 | 13622 | 10837 | 33028756.74 | 33818729.15 | 58278 | 75645.5 | 0.68355 | 0.20942 | 0.10703
16141016, 16146021, 16148021 | 2016-04-29 | 2018-12-31 | 2515367 | 2121909 | 253862751.4067 | 251954377.57 | 445143 | 482338.09 | 0.79769 | 0.20231 | 0
16141017 | 2016-11-10 | 2016-12-31 | 211 | 0 | 3178940 | 3316099.01 | 7446 | 9494.5 | 0.74301 | 0.25699 | 0
16141018 | 2017-08-14 | 2019-08-01 | 24653 | 21934 | 104805158.5076 | 103427753.63 | 106726 | 142205.5 | 0.67382 | 0.28504 | 0.041138
16141019 | 2016-12-07 | 2016-12-31 | 0 | 0 | 566809.82 | 556686.17
16141020 | 2016-12-19 | 2017-01-13 | 150 | 0 | 396256 | 317260.27 | 1507 | 1435.5 | 0.84639 | 0.15012 | 0.0034831
16141021 | 2017-04-15 | 2017-11-03 | 0 | 0 | 632977 | 631573.26
16141022 | 2016-11-10 | 2016-12-31 | 3 | 0 | 574224.25 | 513762.02 | 3641 | 1376.5 | 0.8478 | 0.1522 | 0
16141023 | 2016-12-12 | 2017-01-20 | 46 | 0 | 373948.66 | 271400.4 | 1820 | 1468.5 | 0.91794 | 0.082057 | 0
16141024 | 2016-12-17 | 2017-01-15 | 80 | 0 | 646118.445 | 724939.81 | 19238 | 9633.75 | 0.72993 | 0.25787 | 0.012197
16141026 | 2015-01-01 | 2017-12-31 | 0 | 0 | 0.01 | 956378.56
16145001 | 2016-04-21 | 2017-06-30 | 3190267 | 3227395 | 15211282.8289 | 15481159.19 | 80042.42 | 89841.5 | 0.80345 | 0.19655 | 0
16145002 | 2016-04-04 |  | 164141 | 162599 | 4324263.453 | 5541173 | 25781.6 | 34687.25 | 0.93278 | 0.051914 | 0.015308
16145003 | 2016-06-06 | 2017-12-31 | 43 | 0 | 10314.12 | 6385.19
16145004 | 2017-06-01 | 2017-12-31 | 43 | 0 | 10314.12 | 7850.28
16145005 | 2017-06-01 | 2017-12-31 | 43 | 0 | 10314.12 | 8923.74
16145006 | 2017-06-01 | 2017-12-31 | 43 | 0 | 10314.12 | 9440.62
16145007 | 2016-06-06 |  | 43 | 0 | 10314.12 | 7754.47
16145008 | 2016-05-15 | 2017-05-01 | 85883.5 | 83447 | 5120665.15 | 5031238.77 | 49127 | 57721.5 | 0.93278 | 0.067219 | 0
16145010 | 2016-10-17 | 2018-06-30 | 420018 | 419110 | 5616591.4316 | 5872798.51 | 33072 | 33581.45 | 0.85632 | 0.10454 | 0.039144
16145011 | 2016-08-22 | 2017-03-31 | 211740 | 209685 | 3426586.46 | 3496380.36 | 32347 | 21418.25 | 0.81407 | 0.18412 | 0.0018092
16145012 | 2016-05-01 | 2016-08-30 | 10351 | 10223 | 427458.0049 | 222643.09 | 6818 | 4246.5 | 0.91511 | 0.084893 | 0
16145013 | 2016-07-06 |  | 361333 | 356645 | 3319742.68 | 5122921.51 | 18102.5 | 33967.5 | 0.88717 | 0.10675 | 0.0060793
16145014 | 2016-08-02 |  | 10806 | 10806 | 307640.86 | 278096.78 | 2128 | 2612 | 0.92152 | 0.078484 | 0
16145015 | 2016-09-05 |  | 0 | 0 | 0.01 | 0 | 0 | 2067.75 | 0.99299 | 0.0070125 | 0
16145016 | 2016-11-04 | 2017-09-30 | 13112484 | 12893396 | 116539897.0871 | 106216177.88 | 555607.2 | 521262.75 | 0.83775 | 0.16225 | 0
16145019 | 2016-10-03 | 2016-12-31 | 6516 | 7017 | 710622.61 | 612547.1 | 5214.5 | 3841.5 | 0.88299 | 0.11701 | 0
16145020 | 2016-10-24 |  | 14 | 14 | 10435 | 17681.6 | 56 | 97 | 0.75258 | 0.24742 | 0
16145021 | 2016-10-01 | 2017-06-30 | 256787 | 220426 | 9486369.75 | 9500967.48 | 94962.7 | 95832.5 | 0.87778 | 0.12222 | 0
16145022 | 2016-10-01 | 2017-04-30 | 43208 | 2 | 1058501.11 | 1060860.61 | 3331 | 5226 | 0.91007 | 0.089935 | 0
16145023 | 2016-10-10 |  | 5932 | 730 | 23325 | 22111.6 | 208 | 160 | 1899-12-31 | 0 | 0
16145024 | 2017-07-04 | 2017-12-31 | 9 | 0 | 170483 | -151900.64
16145025 | 2016-10-25 | 2017-03-31 | 11 | 0 | 35239 | 32271.64
16145026, 16145027, 16145018, 16145017, 17146003, 17148002, 17148001 | 2016-11-22 | 2018-01-31 | 9215166.4 | 5003148 | 127784963.43 | 123991854.62 | 241448.86 | 267319.79 | 0.86717 | 0.13283 | 0
16146002 | 2016-02-08 | 2016-05-31 | 4692 | 0 | 15801.41 | 13978.16 | 146 | 150 | 0.8 | 0.2 | 0
16146003 | 2016-04-18 | 2017-01-31 | 212 | 0 | 10589663 | 10207785.16 | 0 | 0 | 0 | 0 | 0
16146004 | 2016-04-01 |  | 0 | 0 | 11884682.4 | 0
16146005 | 2016-04-04 | 2016-12-01 | 627748 | 627927 | 16886575.13 | 16525295.01 | 23986 | 28501.75 | 0.77688 | 0.22312 | 0
16146006 |  | 2016-12-02 | 1252188 | 1370 | 27687902.2 | 26741839.29 | 33080 | 31866 | 0.73539 | 0.26461 | 0
16146007 | 2016-04-30 | 2016-08-01 | 4 | 0 | 8181 | 8026.41 | 0 | 0 | 0 | 0 | 0
16146008 | 2016-05-05 | 2016-05-27 | 63 | 0 | 113864 | 41342.01 | 244 | 0 | 0 | 0 | 0
16146009 | 2016-06-15 | 2016-07-15 | 16 | 0 | 35390.45 | 22436.03 | 102 | 104 | 0.73077 | 0.26923 | 0
16146010 | 2016-07-25 | 2017-03-29 | 283776 | 262812 | 2441530.344 | 2346312.35 | 19263 | 14500 | 0.88214 | 0.11786 | 0
16146011 | 2016-07-18 | 2016-07-29 | 10069 | 0 | 41779.8754 | 30776.75 | 341.7 | 364.5 | 0.89849 | 0.10151 | 0
16146012 | 2016-08-26 | 2016-10-19 | 403 | 0 | 63764.79 | 61348.41 | 388 | 313.5 | 0.79745 | 0.20255 | 0
16146013 | 2016-08-01 | 2016-11-30 | 0 | 0 | 62150 | 58223.02
16146014 | 2016-08-15 | 2016-11-30 | 0 | 0 | 3366 | 3367.36
16146014-110 | 2016-08-15 | 2016-11-30 | 0 | 0 | 75737 | 71751.44
16146015 | 2017-01-02 | 2016-11-01 | 0 | 0 | 10914 | 0
16146016 | 2016-10-03 |  | 0 | 0 | 17300 | 0
16146017 | 2016-10-03 | 2016-10-24 | 0 | 0 | 17300 | 18273.06
16146018 | 2017-01-02 | 2017-06-29 | 111250 | 109538 | 18778545.77 | 17650402.5 | 34161.85 | 52206.49 | 0.81996 | 0.18004 | 0
16146019 | 2016-10-01 | 2016-11-22 | 41078 | 41108 | 409972.1 | 411796.73 | 1434 | 2349.25 | 0.88092 | 0.11908 | 0
16146020 | 2016-10-25 | 2017-03-31 | 5566 | 6288 | 173432 | 169616.46 | 745 | 1174 | 0.91525 | 0.084753 | 0
16146022 | 2016-10-31 |  | 31 | 0 | 828961.64 | 734786.67
16148001, 16146001, 15145028 | 2016-01-01 | 2017-10-31 | 5730125 | 4998639 | 34700607.6866 | 34221133.29 | 281986 | 295225.25 | 0.87479 | 0.12521 | 0
16148002 | 2016-02-08 | 2016-12-31 | 2216133 | 2170317 | 10895789.8448 | 8474914.34 | 49441.27 | 38591.5 | 0.77897 | 0.22103 | 0
16148003 | 2016-04-11 | 2017-05-31 | 3012503 | 2301029 | 21569928.41 | 19887440.41 | 143672 | 66259.25 | 0.70521 | 0.28978 | 0.0050144
16148004 | 2016-04-04 | 2016-12-31 | 771343 | 639291 | 12024906.8682 | 11035012.73 | 34382.5 | 35695.5 | 0.70796 | 0.28925 | 0.0027875
16148005 | 2016-03-07 |  | 0 | 0 | 4750 | 0
16148006 | 2016-03-07 | 2016-12-31 | 1045701 | 1045484 | 6451066.69 | 5227795.43 | 27300 | 26176.5 | 0.78132 | 0.21868 | 0
16148007 | 2016-04-11 | 2016-12-31 | 1303317 | 1319789 | 13751361.59 | 11642058.6 | 51579 | 37365 | 0.78563 | 0.21437 | 0
16148008 | 2016-05-16 | 2016-12-31 | 34332 | 10290 | 1806968.62 | 1585096.75 | 3150 | 1470 | 0.89558 | 0.10442 | 0
16148009 | 2016-05-16 |  | 0 | 0 | 4750 | 0
16148010 |  | 2016-12-31 | 3 | 0 | 94483 | 94282.33 | 700 | 0 | 0 | 0 | 0
16148011, 14060015 | 2014-06-01 | 2018-06-29 | 611943.5 | 553097 | 87626659.5288 | 93872855.04 | 37507.64 | 101756.18 | 0.80756 | 0.19244 | 0
16148013 | 2016-07-29 | 2016-08-06 | 1 | 0 | 25263.21 | 20370.53 | 0 | 241.5 | 0.53416 | 0.46584 | 0
16148014 | 2016-08-03 | 2017-05-31 | 43 | 0 | 576441.45 | 428025.37 | 1360 | 1183 | 0.80727 | 0.19273 | 0
16148015 | 2016-09-06 | 2016-12-31 | 12 | 0 | 255184 | 206271.85 | 850 | 897.5 | 0.85237 | 0.14763 | 0
16148016 | 2016-09-26 | 2016-12-31 | 12 | 0 | 316106 | 293348.38 | 850 | 1189.5 | 0.84027 | 0.15973 | 0
16148017 | 2016-11-30 | 2017-09-15 | 1014795 | 571396 | 8400143.4809 | 7743996.73 | 27380 | 30233 | 0.8085 | 0.1915 | 0
16148018 | 2016-10-17 | 2017-09-30 | 694736 | 510577 | 9179639.2741 | 8998860.86 | 26888 | 26345.5 | 0.72143 | 0.2687 | 0.0098689
16148019 | 2016-10-10 | 2017-12-31 | 343688 | 334272 | 4932535.5755 | 4602463.03 | 14878 | 16538.5 | 0.82142 | 0.17858 | 0
16148020 | 2016-10-26 | 2018-03-31 | 1808 | 722 | 345409.91 | 182785.62 | 900 | 360.5 | 0.88904 | 0.11096 | 0
16148022 | 2016-11-16 | 2017-06-30 | 0 | 0 | 64253 | 37462.03
16148023 | 2016-12-05 | 2016-12-31 | 15101 | 7429 | 269700 | 218858.36 | 2298 | 575.5 | 0.76455 | 0.23545 | 0
16148024 | 2016-12-07 | 2017-02-15 | 101334 | 0 | 419600 | 386580.99 | 3806 | 1258 | 0.75238 | 0.24762 | 0
16148025 | 2016-12-01 | 2016-12-31 | 42623 | 35844 | 479793.8 | 392459.6 | 1845 | 1478 | 0.68031 | 0.31969 | 0
16150001 | 2015-12-04 | 2017-06-07 | 0 | 0 | 288480.0944 | 311342.16
16150002 | 2016-03-02 | 2017-12-28 | 0 | 0 | 417149 | 419450.63
16150005 |  | 2016-09-29 | 0 | 0 | 108167.84 | 108354.48
16150999 | 2016-01-01 | 2016-12-31 | 0 | 0 | 0.01 | 0
16999 | 2001-12-31 |  | 0 | 0 | 0 | 97258 | 0 | 183 | 1899-12-31 | 0 | 0
17000001-040, 16030046 | 2017-10-30 | 2019-03-31 | 713621.27 | 325261 | 22743842.4 | 21994416.08 | 24487.5 | 18930.36 | 0.92375 | 0.076253 | 0
17000003-040, 17060025, 17060014, 18060057, 20060016 | 2017-12-01 | 2020-02-28 | 1421066.66 | 635061 | 39787861.9541 | 40388868.19 | 42825.87 | 69759.97 | 0.8962 | 0.1038 | 0
17000004-040, 16050004 | 2016-06-01 | 2017-05-29 | 311396.25 | 291276 | 18810983.9003 | 18242213.85 | 9998.21 | 8738.03 | 0.88584 | 0.11244 | 0.0017166
17001 |  | 2003-06-30 | 383493 | 569152 | 4596846 | 4650460 | 0 | 47734 | 1899-12-31 | 0 | 0
17002 | 2001-12-31 |  | 0 | 0 | 142909 | 257347 | 0 | 0 | 0 | 0 | 0
17003 | 2001-04-02 | 2001-04-02 | 0 | 0 | 279955 | 280461 | 0 | 734 | 1899-12-31 | 0 | 0
17004 | 2001-04-02 | 2001-04-02 | 0 | 0 | 43029 | 42860 | 0 | 65 | 1899-12-31 | 0 | 0
17005 | 2002-01-31 |  | 60943 | 27583 | 3665785 | 3692195 | 0 | 9405 | 1899-12-31 | 0 | 0
17010 | 2004-06-01 | 2004-06-01 | 16110 | 0 | 1177457 | 1258963 | 0 | 3511 | 1899-12-31 | 0 | 0
17012 | 2001-06-25 | 2001-06-25 | 109 | 0 | 471049 | 478884 | 0 | 821 | 1899-12-31 | 0 | 0
17013 | 2006-12-31 | 2004-12-29 | 19484 | 39660 | 82983531 | 83033622 | 0 | 79805 | 1899-12-31 | 0 | 0
17014 | 2001-05-31 |  | 55 | 0 | 0 | 785443 | 0 | 1477 | 1899-12-31 | 0 | 0
17015 | 2001-10-31 | 2001-12-06 | 443 | 0 | 2438794 | 2448940 | 0 | 2428 | 1899-12-31 | 0 | 0
17016 | 2004-01-31 | 2004-03-19 | 20654 | 7192 | 11136325 | 11148445 | 0 | 20095 | 1899-12-31 | 0 | 0
17017 |  |  | 0 | 0 | 5043 | 5209
17018 | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 698606 | 0 | 31 | 1899-12-31 | 0 | 0
17020 |  |  | 0 | 0 | 0 | 7708
17021 | 2001-12-14 |  | 624 | 0 | 36144 | 36874 | 0 | 252 | 1899-12-31 | 0 | 0
17030001 | 2017-01-01 | 2018-12-31 | 0 | 0 | 6063010.79 | 6063010.78 | 0 | 14662.72 | 0.95076 | 0.038806 | 0.010435
17030002 | 2017-01-01 | 2017-12-31 | 0 | 0 | 8369804.12 | 8369645.2 | 0 | 39071.34 | 0.83589 | 0.15304 | 0.011069
17030003 | 2017-03-15 | 2017-11-30 | 6671 | 13251 | 13702488.7825 | 11063274.13 | 21585 | 8851.97 | 0.88867 | 0.1102 | 0.0011297
17030004 | 2017-04-01 | 2017-12-31 | 33270.82 | 0 | 1570806.76 | 1631445.49 | 3043.9 | 3210.5 | 0.99299 | 0.0070083 | 0
17030005 | 2018-08-13 | 2020-08-25 | 1557459.88 | 808432 | 54867481.3374 | 56197100.97 | 78303.15 | 68507.63 | 0.88245 | 0.11622 | 0.0013283
17030006 | 2017-10-16 | 2017-12-29 | 34377 | 25426 | 1368584 | 1335392.14 | 1879 | 2055.67 | 0.99805 | 0.0019458 | 0
17030007 | 2017-01-23 | 2017-03-17 | 8 | 0 | 502925.98 | 490091.26 | 1094 | 693 | 1899-12-31 | 0 | 0
17030008 | 2017-01-09 | 2018-07-31 | 0 | 0 | 1758479 | 1646192.66 | 48 | 526 | 0.96388 | 0.036122 | 0
17030009 | 2017-01-09 | 2018-08-31 | 0 | 0 | 743095.48 | 735554.86 | 1032 | 686.76 | 0.87405 | 0.12595 | 0
17030010 | 2018-05-21 | 2018-11-30 | 65757.03 | 8 | 1932396.62 | 1980370.65 | 3986.7 | 4080 | 0.85502 | 0.14498 | 0
17030011 | 2017-01-09 | 2019-02-28 | 60 | 17030091 | 4087637 | 26751162.63 | 4987 | 33347.67 | 0.91948 | 0.076167 | 0.0043481
17030012 | 2017-02-06 | 2017-12-29 | 6697 | 4905 | 7795922.3458 | 7488659.85 | 10299 | 6210 | 0.96087 | 0.03913 | 0
17030013 | 2017-05-15 | 2017-08-15 | 317203 | 8948 | 6475452.81 | 6561681.67 | 5991.35 | 6534.98 | 0.88653 | 0.10582 | 0.0076511
17030014 | 2017-01-25 |  | 0 | 0 | 29735.19 | 30542.83 | 102 | 102 | 0.92157 | 0.078431 | 0
17030015 | 2017-02-27 | 2017-11-01 | 21484 | 12870 | 5764205.52 | 5756056.09 | 6937 | 6308.62 | 0.90505 | 0.092572 | 0.0023777
17030016 | 2017-05-01 | 2018-07-02 | 255522.61 | 270918 | 8271368.075 | 8680897.73 | 17421.1 | 19421.32 | 0.97603 | 0.023969 | 0
17030017 | 2017-03-27 | 2017-11-01 | 75779 | 0 | 2590193.92 | 2525646.5 | 7463 | 7181 | 0.90621 | 0.091561 | 0.0022281
17030018 | 2017-04-17 | 2017-11-13 | 44188 | 11500 | 1974408.18 | 2007369.27 | 2914.7 | 3504.63 | 0.87759 | 0.10643 | 0.015979
17030019 | 2017-04-27 | 2017-12-31 | 46704 | 21313 | 3201903.95 | 3076052.17 | 5969 | 6372.5 | 0.95975 | 0.032876 | 0.0073754
17030020 | 2018-10-01 | 2019-02-01 | 214898.69 | 174957 | 19051693.75 | 19133459.78 | 30302 | 31030.5 | 0.98574 | 0.014131 | 0.00012891
17030021 |  |  | 0 | 0 | 0.01 | 186868.16 | 0 | 604.5 | 0.86518 | 0.13482 | 0
17030022 | 2017-06-01 | 2017-12-01 | 2 | 0 | 2688070.44 | 2711832.11 | 1296 | 1610.97 | 0.98417 | 0.015829 | 0
17030023 | 2018-04-16 | 2019-06-28 | 254254.04 | 22893 | 6934502.4 | 6994483.88 | 15750.4 | 21796.12 | 0.9532 | 0.043677 | 0.0031198
17030024 |  |  | 0 | 0 | 0.01 | 9667.82 | 0 | 55 | 1899-12-31 | 0 | 0
17030025 | 2017-06-19 | 2018-03-01 | 4417 | 242 | 1338658.3 | 1263157.6 | 1520.7 | 1582.28 | 0.93174 | 0.068256 | 0
17030026 | 2017-08-15 | 2018-05-31 | 341124 | 0 | 8634316.87 | 6990954.09 | 14634 | 7843.06 | 0.92433 | 0.075672 | 0
17030027 | 2017-10-01 | 2018-11-09 | 194407.16 | 118019 | 6353637.43 | 6313936.3 | 16013.9 | 14623.26 | 0.98646 | 0.01354 | 0
17030028 | 2017-10-02 | 2019-08-31 | 11677 | 0 | 1453130.4 | 1322736.16 | 746 | 730 | 0.96986 | 0.030137 | 0
17030029 | 2017-06-05 | 2019-01-01 | 1 | 0 | 468723.9474 | 479363.59 | 1378.66 | 826 | 0.89286 | 0.074455 | 0.032688
17030030 | 2017-08-24 | 2018-12-31 | 129574.5 | 96843 | 30057198.2108 | 30079162.36 | 22444.5 | 15859.38 | 0.91989 | 0.08011 | 0
17030031 | 2017-08-21 | 2019-02-05 | 217 | 0 | 7748785.69 | 7320761.19 | 3177 | 5525 | 0.78932 | 0.18389 | 0.026787
17030032 | 2017-08-01 | 2018-04-30 | 37408 | 4572 | 1735854.67 | 1674300.2 | 3660.5 | 3804 | 0.92035 | 0.079653 | 0
17030033 | 2017-08-16 | 2017-11-15 | 0 | 0 | 1126827.85 | 1119691.88 | 2214 | 2212.86 | 0.56346 | 0.30797 | 0.12857
17030034 | 2017-08-21 | 2018-03-09 | 7060 | 350 | 750331.6 | 687431.66 | 774 | 353.43 | 0.98585 | 0.014147 | 0
17030035 | 2017-09-18 | 2018-01-21 | 0 | 0 | 616278.71 | 574943.33 | 1870 | 2082.66 | 0.98992 | 0.010083 | 0
17030036 | 2017-11-15 | 2018-08-31 | 172451.74 | 47794 | 6094922.4815 | 5353880.02 | 12293.5 | 10179.09 | 0.96738 | 0.032616 | 0
17030037 | 2017-08-28 | 2017-12-31 | 2 | 0 | 175625.16 | 188814.5 | 826 | 1004.5 | 0.99353 | 0.0064709 | 0
17030038 | 2018-08-06 | 2019-04-05 | 28450 | 0 | 2978153.24 | 2915690.29 | 5089 | 6121.49 | 0.93204 | 0.065997 | 0.0019603
17030039 | 2017-07-03 | 2017-09-30 | 0 | 0 | 374478.04 | 358477.34 | 1148 | 1185.82 | 0.93886 | 0.061139 | 0
17030040 | 2018-03-01 | 2020-10-01 | 12899 | 11742 | 3166193.52 | 3150811.33 | 3266 | 4903 | 0.95391 | 0.046094 | 0
17030041 | 2017-10-02 | 2018-10-12 | 69 | 0 | 232323.76 | 215315.06 | 484 | 711.5 | 0.52284 | 0.39283 | 0.084329
17030042 | 2017-10-09 | 2018-12-31 | 707 | 3469 | 1123006.03 | 1096332.67 | 2954 | 2509.71 | 0.90457 | 0.093039 | 0.0023907
17030043 | 2017-10-16 | 2019-02-15 | 2649148 | 2162379 | 23671121.047 | 23571685.92 | 90428.28 | 92794.93 | 0.89223 | 0.10714 | 0.00062503
17030044 | 2017-10-16 | 2018-06-01 | 19 | 0 | 2076805.84 | 2032027.9 | 1035 | 4104.5 | 0.94543 | 0.049214 | 0.00536
17030045 | 2017-10-16 | 2018-03-30 | 311413.32 | 0 | 9658188.66 | 9411237.91 | 18216.2 | 18310.5 | 0.79837 | 0.17733 | 0.024303
17030046 | 2017-10-02 | 2018-01-02 | 0 | 0 | 467061.39 | 506388.43 | 4492 | 5189.46 | 0.91994 | 0.080064 | 0
17030047 | 2017-09-11 | 2017-11-06 | 0 | 0 | 545613.15 | 536838.85 | 64 | 65 | 0.98462 | 0.015385 | 0
17030048 | 2017-08-01 | 2019-07-31 | 25881.75 | 5997 | 9325170.1805 | 9491293.93 | 3298.1 | 9597.5 | 0.80135 | 0.18661 | 0.012034
17030049 |  |  | 597235.4 | 110394 | 25703038.2293 | 24111745.03 | 25034.9 | 22052 | 0.96211 | 0.037525 | 0.00036278
17030050 | 2018-12-01 | 2022-03-31 | 0 | 0 | 33242.73 | 28417.61
17030051 | 2018-06-01 | 2019-10-31 | 1183431.42 | 947717 | 25615420.6819 | 25699242.21 | 57716.14 | 51552.98 | 0.92264 | 0.077131 | 0.00023277
17030052 | 2018-04-01 | 2018-10-01 | 602386.26 | 18496 | 14732632.3405 | 12130890.29 | 24615.59 | 13373.13 | 0.93737 | 0.062626 | 0
17040001 | 2017-02-06 | 2018-05-09 | 0 | 0 | 3396481.91 | 2941843.15
17040002 | 2017-03-13 | 2018-04-06 | 0 | 42 | 3090170.05 | 3503185.72 | 4786 | 4610 | 0.83861 | 0.16139 | 0
17040003 | 2017-03-06 | 2018-09-24 | 92263 | 31313 | 5669268.7612 | 6752075.79 | 13826 | 20034.5 | 0.95857 | 0.041429 | 0
17040004 | 2017-05-01 | 2018-07-31 | 2378 | 0 | 3476635.54 | 3562675.9 | 2297 | 5381.5 | 0.88869 | 0.11131 | 0
17040005 |  | 2017-12-31 | 0 | 0 | 0 | 54.59
17040006 | 2017-02-20 | 2017-06-12 | 0 | 0 | 1308220.42 | 1377272.96 | 0 | 25 | 1899-12-31 | 0 | 0
17040007 | 2017-04-03 | 2017-10-30 | 0 | 0 | 737765.67 | 737019.1
17040008 | 2017-04-03 | 2018-12-10 | 153 | 88 | 1435592.992 | 1698806.37 | 3754 | 5149 | 0.96106 | 0.03894 | 0
17040009 | 2017-11-06 | 2019-04-30 | 0 | 0 | 0.01 | 33832.98
17040010 | 2018-01-15 | 2019-08-30 | 0 | 0 | 83335656.12 | 92532681.45 | 8775 | 13640 | 0.83006 | 0.16994 | 0
17040011 | 2017-12-18 | 2018-09-28 | 6 | 0 | 21292082.7548 | 21390597.89 | 6244 | 7551 | 0.94605 | 0.053953 | 0
17040012 | 2017-07-21 |  | 0 | 0 | 10393 | 12240.53
17040013 | 2017-09-15 | 2018-06-30 | 1837 | 0 | 2167697 | 2405792.25 | 2029 | 3457 | 0.83222 | 0.16778 | 0
17040014 | 2017-11-13 | 2018-01-18 | 1361 | 0 | 254522 | 244096.26 | 964 | 393 | 0.96819 | 0.031807 | 0
17040015 | 2017-11-17 | 2018-02-02 | 800 | 0 | 734371.76 | 709437.88 | 71 | 0 | 0 | 0 | 0
17040016 | 2017-12-18 | 2018-01-29 | 0 | 0 | 88313.98 | 84091.23
17040017 | 2018-02-02 | 2018-01-19 | 0 | 0 | 2058322.57 | 2383570.35 | 0 | 526 | 0.97338 | 0.026616 | 0
17040018 | 2018-04-13 | 2019-02-20 | 174 | 0 | 13800934.81 | 14265999.35 | 0 | 1682.5 | 0.57058 | 0.35929 | 0.070134
17040019 | 2017-09-01 | 2018-04-30 | 0 | 0 | 28617.38 | 28426.27
17040020 | 2018-03-26 | 2019-01-15 | 2 | 21 | 43605607.35 | 45195701.11 | 6964 | 6945.5 | 0.71471 | 0.28529 | 0
17050001 | 2017-07-24 | 2018-03-28 | 44164 | 35652 | 25591819.42 | 26304413.1 | 2130 | 4267.14 | 0.9686 | 0.031403 | 0
17050002 | 2017-02-06 | 2017-08-18 | 25 | 0 | 2140362.97 | 2134965.8 | 82 | 0 | 0 | 0 | 0
17050003 | 2017-02-15 |  | 0 | 0 | 551509 | 563224.15 | 184 | 100 | 1899-12-31 | 0 | 0
17050004 | 2017-06-01 |  | 46 | 0 | 202677.04 | 232785.87 | 0 | 80 | 1899-12-31 | 0 | 0
17050005 | 2017-09-01 | 2019-01-11 | 56 | 0 | 380965.43 | 386027.12 | 56 | 48 | 1899-12-31 | 0 | 0
17050006 | 2018-04-23 | 2019-06-27 | 657223.51 | 256496 | 30764763.4727 | 29575694.05 | 20562.5 | 15450.26 | 0.9701 | 0.029644 | 0.0002589
17050007 | 2017-08-15 | 2020-06-05 | 163806.52 | 29567 | 272790290.9213 | 286795512.57 | 39365.5 | 92320.49 | 0.9103 | 0.086844 | 0.0028596
17050009 | 2017-12-04 | 2018-12-18 | 174 | 0 | 31958 | 19298.35 | 102 | 40 | 1899-12-31 | 0 | 0
17050010 | 2017-12-26 | 2018-06-18 | 23047 | 2658 | 787369.07 | 578702.43 | 3320 | 1625 | 0.92738 | 0 | 0.072615
17050011 | 2017-12-06 | 2018-08-31 | 84774.69 | 54699 | 9051667.335 | 9184177.34 | 6261.13 | 4753.41 | 0.9169 | 0.081415 | 0.001683
17050012 | 2017-06-12 | 2018-12-31 | 2933 | 0 | 17813236.295 | 17598440.14 | 0 | 161.5 | 0.97523 | 0.024768 | 0
17050013 | 2017-07-19 | 2018-02-15 | 4223.2 | 1417 | 352411.54 | 346977.54 | 847 | 613.76 | 0.97393 | 0.026069 | 0
17050014 | 2017-07-01 | 2017-12-04 | 3376.2 | 2615 | 685239.8364 | 640240.57 | 1052.72 | 983.83 | 0.9075 | 0.092496 | 0
17050015 | 2017-08-24 | 2017-10-31 | 96.9 | 8 | 58773.83 | 49943.19 | 150.3 | 136 | 0.86765 | 0.13235 | 0
17050016 | 2017-01-01 | 2017-07-01 | 127 | 0 | 12466.31 | 79007.45 | 64 | 86 | 1899-12-31 | 0 | 0
17050017 | 2018-04-15 | 2019-12-31 | 47 | 0 | 30383569.916 | 30324183.95 | 46 | 480 | 1899-12-31 | 0 | 0
17050018 | 2017-10-31 | 2017-12-31 | 9 | 4 | 41675.46 | 41756.89 | 136 | 134 | 0.85075 | 0.14925 | 0
17050019 | 2017-11-01 | 2020-12-01 | 0 | 0 | 0 | 35771.88
17050020 | 2017-07-01 | 2018-03-30 | 0 | 0 | 140264.98 | 138830.13
17050021, 17050008 | 2018-01-02 | 2020-05-29 | 674741.89 | 535845 | 83768995.3241 | 106907536.05 | 72953.24 | 104783.45 | 0.91106 | 0.084871 | 0.0040674
17060001 | 2017-01-26 | 2017-03-31 | 3 | 0 | 763619.33 | 749702.06 | 0 | 1552.5 | 0.78261 | 0.21739 | 0
17060002 | 2017-03-01 | 2018-05-01 | 38947.5 | 25101 | 1356034.17 | 1694826.44 | 4334 | 7509.5 | 0.84773 | 0.15227 | 0
17060003 | 2017-03-01 | 2018-03-01 | 163444 | 6701 | 2331461.9 | 2507170.48 | 6808 | 7819.5 | 0.853 | 0.147 | 0
17060004 | 2017-02-22 | 2017-09-01 | 0 | 0 | 1807556 | 1586099.72 | 0 | 1357 | 0.82646 | 0.17354 | 0
17060005 | 2017-05-01 | 2018-05-01 | 52698 | 28088 | 3413327.1 | 3506399.11 | 9465 | 12317.5 | 0.85338 | 0.14662 | 0
17060009 | 2017-04-03 | 2017-07-01 | 0 | 0 | 468817 | 422704.68 | 0 | 692 | 0.69798 | 0.30202 | 0
17060010 | 2017-04-01 | 2017-06-30 | 0 | 0 | 35269 | 35436.71 | 0 | 329 | 0.60486 | 0.39514 | 0
17060011 | 2017-04-06 | 2018-10-31 | 0 | 0 | 340814 | 339949.79 | 80 | 895.5 | 0.92351 | 0.076494 | 0
17060012 | 2017-04-17 | 2017-07-01 | 20 | 304 | 595466.25 | 753556.83 | 0 | 4055.5 | 0.87178 | 0.12822 | 0
17060013 | 2018-06-01 | 2020-06-19 | 394046.4 | 34320.5 | 37437703.0225 | 42339900.54 | 5844.5 | 38515.8 | 0.91663 | 0.083368 | 0
17060015 | 2017-10-01 | 2018-04-01 | 99029 | 18875 | 8805198.39 | 8665635.04 | 16054.97 | 21893.5 | 0.85708 | 0.14292 | 0
17060016 | 2017-07-10 | 2017-08-01 | 16 | 0 | 15224 | 15363.18 | 16 | 20 | 0.825 | 0.175 | 0
17060017 | 2017-06-01 | 2017-11-30 | 5 | 0 | 583597 | 522296.9 | 0 | 749 | 0.58478 | 0.41522 | 0
17060018 | 2017-07-12 | 2017-11-29 | 682 | 0 | 329597.85 | 333351.97 | 744 | 723 | 0.87344 | 0.12656 | 0
17060019 | 2017-06-26 | 2017-11-29 | 2915 | 2410 | 1747162.44 | 1748968.11 | 2936 | 2768.5 | 0.93083 | 0.069171 | 0
17060020 | 2017-09-01 | 2018-10-31 | 11648 | 8106 | 4919691.4432 | 4915113.49 | 3656.18 | 4018.5 | 0.88516 | 0.11484 | 0
17060021 | 2017-07-24 | 2017-11-30 | 415 | 0 | 80358 | 83552.78 | 415 | 25 | 1899-12-31 | 0 | 0
17060022 | 2018-04-16 | 2019-11-04 | 1862475.26 | 1430007 | 45224270.6383 | 45653872.6 | 72521.98 | 85419.97 | 0.87077 | 0.12923 | 0
17060023 | 2017-09-20 | 2018-01-12 | 146 | 0 | 113778 | 100812.97 | 0 | 8.5 | 0.94118 | 0.058824 | 0
17060024 | 2017-09-01 | 2020-12-31 | 224 | 0 | 362995.7 | 261181.33 | 0 | 0 | 0 | 0 | 0
17060026 | 2017-10-01 | 2018-06-01 | 58 | 0 | 11655.89 | 1506.83
17060027 | 2017-07-10 | 2018-03-01 | 2769 | 4472 | 9852749.97 | 9405410.79 | 6981 | 7434 | 0.87154 | 0.12846 | 0
17060028 | 2017-10-01 | 2018-05-04 | 292021 | 41578 | 3515173.11 | 4004416.3 | 7295 | 13327 | 0.8512 | 0.1488 | 0
17060029 | 2017-11-15 | 2018-12-31 | 357943 | 1549204 | 29316324.93 | 27199304.53 | 27406.5 | 39561.5 | 0.83211 | 0.16789 | 0
17060030 | 2017-08-25 | 2018-06-30 | 0 | 0 | 199651 | 189148.97 | 60 | 127.5 | 0.96863 | 0.031373 | 0
17060031 | 2017-08-21 | 2017-11-17 | 9 | 0 | 371509.62 | 382518.93 | 1008 | 1189 | 0.93272 | 0.067283 | 0
17060032 | 2017-08-21 | 2017-08-31 | 0 | 0 | 15117.01 | 15064.7 | 0 | 12 | 1899-12-31 | 0 | 0
17060033 | 2017-09-12 | 2018-10-31 | 0 | 0 | 599735 | 661639.15 | 450 | 2217 | 0.98241 | 0.017591 | 0
17060034, 20060007 | 2016-08-01 | 2019-11-22 | 948035.5 | 576094 | 28917205.7398 | 30248843.35 | 39953 | 50203 | 0.95249 | 0.047511 | 0
17060035 | 2017-09-01 | 2017-09-30 | 0 | 0 | 129011 | 129370.08
17060036 | 2017-12-01 | 2019-08-30 | 391798.02 | 312439 | 43023104.4323 | 46346253.91 | 48099.8 | 61946 | 0.8238 | 0.17615 | 4.8429e-05
17060037 | 2017-11-06 | 2017-11-24 | 52 | 0 | 10100.64 | 5854.69 | 32 | 40 | 1899-12-31 | 0 | 0
17060038 | 2017-12-04 | 2018-02-01 | 0 | 0 | 218879 | 220519.76
17060039 | 2017-11-29 | 2018-05-01 | 0 | 0 | 19675 | 18187.67
17060040 | 2018-01-03 | 2018-05-01 | 0 | 0 | 0.01 | 2602.59
17060041 | 2018-01-22 | 2018-11-26 | 808 | 35 | 846011.4 | 844825.06 | 1714 | 1926.5 | 0.90112 | 0.098884 | 0
17060042 | 2017-12-01 | 2018-05-01 | 0 | 0 | 83581 | 61105.78
17060043 | 2018-01-03 | 2018-05-31 | 1415 | 1395 | 429157.57 | 435117.87 | 1295 | 1398.5 | 0.92528 | 0.074723 | 0
17060044 | 2017-01-01 | 2017-12-31 | 0 | 0 | 0.01 | 58942.32
17080001 | 2017-03-01 | 2017-05-05 | 24355 | 22692 | 298648.6 | 284944.27 | 628.5 | 574 | 1899-12-31 | 0 | 0
17080002 | 2017-04-10 | 2017-09-08 | 8969.69 | 840 | 554416.18 | 521171.36 | 1982.9 | 1957 | 0.99745 | 0.0025549 | 0
17080003 | 2017-08-01 | 2017-11-02 | 6944 | 0 | 371207.98 | 337520.3 | 479 | 124 | 1899-12-31 | 0 | 0
17080004 | 2016-11-18 | 2017-12-29 | 0 | 0 | 5608 | 6403.48
17080005 | 2017-06-20 | 2017-10-13 | 3510.5 | 0 | 716124.55 | 679732.48 | 204.5 | 337 | 0.96736 | 0.032641 | 0
17080006 | 2017-06-13 | 2017-12-29 | 26293.45 | 6181 | 7774982.49 | 7558018.92 | 1481.6 | 874.75 | 0.98742 | 0.012575 | 0
17080007 | 2018-09-01 | 2020-12-31 | 6549485.06 | 2867375 | 241401451.2122 | 241661661.04 | 149269.78 | 189431.34 | 0.92904 | 0.069614 | 0.0013461
17080008 | 2017-05-12 | 2017-07-31 | 6343 | 6245 | 166363 | 159899.78 | 524 | 510 | 0.98235 | 0.017647 | 0
17080009 | 2018-04-10 | 2019-08-02 | 570456.02 | 468835 | 23927573.102 | 24314034.65 | 26819.38 | 30756.12 | 0.94585 | 0.053843 | 0.00030888
17080010 | 2018-01-02 | 2018-05-15 | 13976.5 | 1762 | 793960.14 | 747115.26 | 1253 | 321 | 0.74299 | 0.20717 | 0.049844
17080011 | 2017-07-17 | 2017-12-31 | 0 | 0 | 131004 | 105510.4 | 80 | 123 | 0.97561 | 0.02439 | 0
17080012 | 2017-10-23 | 2018-07-06 | 18652 | 32 | 1257497.7 | 1175250.6 | 2533.9 | 2794 | 0.89961 | 0.097888 | 0.0025054
17080013 | 2018-01-08 | 2018-09-14 | 100643.5 | 66461 | 6376561.645 | 6188127.07 | 5637.9 | 6887.67 | 0.88596 | 0.10591 | 0.0081305
17080014 | 2018-07-11 | 2019-01-24 | 130289.41 | 67909 | 5597012.67 | 5513608.14 | 7618.6 | 7416.84 | 0.95739 | 0.042471 | 0.00013483
17080015 | 2017-08-14 | 2019-05-17 | 626 | 66 | 1099720.0008 | 838790.86 | 4759 | 3495 | 0.88426 | 0.099285 | 0.016452
17080016 | 2018-01-02 | 2018-05-09 | 8705.51 | 1822 | 777546.71 | 760430.07 | 549.2 | 1272.5 | 0.90766 | 0.092338 | 0
17080017 | 2018-01-18 | 2019-08-31 | 27651.91 | 0 | 4302381.99 | 4223022.26 | 5248.9 | 4644.5 | 0.90386 | 0.092798 | 0.0033373
17080019 | 2018-07-20 | 2019-01-31 | 8810 | 5101 | 507584.64 | 495820.1 | 531 | 488 | 0.89857 | 0.10143 | 0
17080020 | 2018-05-15 | 2019-02-28 | 13509.5 | 9227 | 947724.37 | 937306.13 | 1179.6 | 1035 | 0.77101 | 0.20193 | 0.027053
17080021 | 2018-03-23 | 2019-03-28 | 43572 | 32317 | 1522340.17 | 1464477.56 | 2434.4 | 2020.5 | 0.89631 | 0.10022 | 0.0034645
17080022 | 2017-11-10 | 2018-10-01 | 79773.53 | 53992 | 5049230.26 | 5044588.59 | 7048.6 | 7162.5 | 0.87888 | 0.10513 | 0.015986
17080023 | 2017-11-20 | 2019-09-02 | 853 | 0 | 912885.05 | 854662.5 | 694 | 201.5 | 0.90074 | 0.039702 | 0.059553
17080024 | 2018-03-19 | 2021-03-22 | 1754786.06 | 539804 | 46283943.32 | 46061599.78 | 67628.12 | 81031.11 | 0.84744 | 0.13649 | 0.016068
17080025 | 2017-11-15 | 2018-08-10 | 217833.65 | 201024 | 3564198.26 | 3514323.95 | 7886 | 7568.5 | 0.8939 | 0.10517 | 0.00092489
17080026 | 2019-05-01 | 2021-06-01 | 2086 | 0 | 300000 | 421118.13
17080028, 16080027 | 2017-10-01 | 2019-07-01 | 519363.48 | 306082 | 16483667.078 | 17349537.1 | 17085.7 | 24094.81 | 0.45867 | 0.53793 | 0.0033933
17080029 | 2018-07-09 | 2019-03-31 | 14468.5 | 8314 | 1429425.97 | 1349994.59 | 1306.8 | 1728 | 0.80382 | 0.18171 | 0.014468
17090002 | 2017-06-01 | 2017-12-29 | 12732 | 3783 | 4867732 | 4798247.36 | 5430 | 6966.74 | 0.72261 | 0.17153 | 0.10586
17090003 | 2017-07-01 | 2018-05-31 | 51191 | 35754 | 27277150.6249 | 25548485.96 | 28381.5 | 30751.59 | 0.82842 | 0.12965 | 0.041933
17090004 | 2017-02-03 | 2017-09-01 | 0 | 0 | 1250222.79 | 1207397.71 | 0 | 0 | 0 | 0 | 0
17090005 | 2017-02-03 | 2017-09-01 | 50104 | 237 | 3658782.77 | 3514129.89 | 3212 | 2656.25 | 0.90974 | 0.085365 | 0.0048941
17090006 | 2017-02-03 | 2018-02-01 | 0 | 0 | 182129 | 213128.79
17090007 | 2017-06-01 | 2017-11-07 | 1897 | 2576 | 617838.6051 | 540028.92 | 2776 | 1285.84 | 0.79196 | 0.14193 | 0.066105
17090010 | 2017-08-01 | 2019-03-31 | 0 | 1008 | 5537108 | 5452614.02 | 0 | 2154.36 | 0.96333 | 0.03667 | 0
17090011 | 2017-09-01 | 2018-03-01 | 608 | 0 | 632863 | 649803.75 | 40 | 15.04 | 1899-12-31 | 0 | 0
17110001 | 2017-05-17 | 2017-08-21 | 0 | 0 | 272987 | 287161.73
17110002 | 2017-09-08 | 2021-04-26 | 0 | 0 | 58698852.92 | 58428861.07 | 0 | 794.5 | 0.91126 | 0.088735 | 0
17110003 | 2017-05-01 | 2017-05-15 | 0 | 0 | 81456.33 | 82331.01
17110004 | 2017-07-10 | 2017-12-13 | 0 | 0 | 595354.65 | 521932.61
17110005 | 2017-06-26 | 2018-01-16 | 0 | 0 | 1052065.83 | 995051.83 | 0 | 140.23 | 1899-12-31 | 0 | 0
17110006 | 2017-08-02 | 2018-01-17 | 0 | 0 | 649034.24 | 538470.08
17110007 | 2017-06-29 | 2019-08-31 | 0 | 0 | 22648672.73 | 21725521.74 | 4600 | 7034.85 | 0.99879 | 0.0012083 | 0
17110008 | 2017-11-27 | 2019-05-31 | 0 | 0 | 2583972.57 | 2452676.45 | 0 | 933.1 | 0.98928 | 0.010717 | 0
17110009 | 2017-10-15 | 2023-04-12 | 95951.5 | 0 | 141118520.89 | 115443924.9 | 0 | 7368 | 0.80449 | 0.19286 | 0.0026466
17110010 | 2018-03-12 | 2020-12-22 | 0 | 0 | 26558987.1168 | 25716489.37 | 0 | 505 | 0.80099 | 0.19901 | 0
17110011 | 2018-08-01 | 2019-07-09 | 1799 | 0 | 1807963 | 1693342.11
17110012 | 2018-08-20 | 2019-05-10 | 0 | 0 | 466058.67 | 515349.16
17110013 | 2018-04-16 | 2020-04-19 | 619 | 0 | 42828727.28 | 42816711.58
17110014 | 2018-05-29 | 2019-04-30 | 0 | 0 | 366211.58 | 353856.87
17110015 | 2017-11-01 | 2019-03-15 | 0 | 0 | 183502 | 175022.48
17110016 | 2019-05-06 | 2019-07-31 | 0 | 0 | 101787.85 | 89483.74
17110017 | 2017-11-01 | 2018-12-21 | 564 | 0 | 11902679.69 | 11110589.59 | 0 | 982.5 | 0.74911 | 0.25089 | 0
17110018 | 2018-01-02 | 2018-07-31 | 734 | 0 | 234567.92 | 225289.88
17110019 | 2018-07-25 | 2019-12-26 | 9001 | 0 | 7032852.9051 | 6891871
17110020 | 2018-03-08 | 2019-05-09 | 3870 | 0 | 1821106.93 | 1690794.99
17110021 | 2018-04-23 | 2018-05-31 | 0 | 0 | 76964 | 77991.45
17110022 | 2018-04-23 | 2018-07-11 | 0 | 0 | 112323 | 113191.03
17110023 | 2017-11-01 | 2019-03-15 | 0 | 0 | 800918 | 783567.66
17110024 | 2017-11-01 | 2019-03-15 | 0 | 0 | 212752 | 198766.43
17141001 | 2017-01-01 | 2017-12-31 | 64775 | 0 | 12789482.5303 | 12789482.53 | 393279 | 170418 | 0.74768 | 0.25045 | 0.0018777
17141002 | 2017-04-15 | 2017-11-03 | 0 | 0 | 37914 | 38159.03
17141003 | 2017-08-01 | 2018-03-01 | 40 | 0 | 5170240.5 | 5143794.66
17141004 | 2017-06-01 | 2017-12-09 | 7277 | 5391 | 47417413.2216 | 46700711.81 | 88280 | 87065.3 | 0.57897 | 0.29803 | 0.123
17141005 | 2017-02-20 | 2017-12-31 | 55 | 0 | 255994.7105 | 164851.3 | 4799 | 2383.49 | 0.67674 | 0.32326 | 0
17141006 | 2017-01-23 | 2017-06-30 | 734418 | 0 | 1288473.986 | 1316111.51 | 5734 | 3278.51 | 0.82004 | 0.17127 | 0.008693
17141007 | 2017-04-26 | 2017-12-31 | 8614 | 0 | 2498397.585 | 3581367.63 | 68017 | 59086.25 | 0.75788 | 0.23888 | 0.003241
17141008 | 2017-08-01 | 2017-12-15 | 4204 | 3058 | 17107134.704 | 16832383.57 | 52852 | 64773 | 0.47083 | 0.43325 | 0.09592
17141009 | 2017-07-15 | 2017-12-15 | 3670 | 2435 | 19839711.12 | 19556942.57 | 48942 | 78415.53 | 0.58733 | 0.17593 | 0.23674
17141010 | 2017-08-01 | 2017-12-15 | 5045 | 4903 | 14583988.79 | 15486697.22 | 48200 | 62179.5 | 0.51297 | 0.38893 | 0.098103
17141011 | 2017-08-01 | 2017-12-15 | 143 | 37 | 92457.07 | 86070.15 | 0 | 268 | 0.92164 | 0.078358 | 0
17141012 | 2017-08-01 | 2019-10-31 | 45 | 0 | 1113916.12 | 851297.48 | 466 | 691 | 0.8437 | 0.1563 | 0
17141013, 18148024, 19146004 | 2017-09-05 | 2020-10-17 | 1755155 | 624514 | 175706608.4707 | 167786400.08 | 293069.5 | 284994 | 0.70455 | 0.28312 | 0.012326
17141014 | 2017-08-14 | 2017-12-15 | 1663 | 1555 | 12352771.7 | 11208031.16 | 37070 | 32994.5 | 0.68952 | 0.27952 | 0.03096
17141015 | 2017-08-14 | 2017-12-15 | 1620 | 1609 | 12196024.4308 | 11249979.08 | 33649.7 | 34346.25 | 0.71819 | 0.21519 | 0.066623
17141016, 17146018, 17148014 | 2017-08-21 | 2019-06-30 | 2114103 | 1758624 | 80041769.0789 | 90957513.41 | 164701 | 222802.23 | 0.80872 | 0.19117 | 0.0001051
17141017 | 2017-09-05 | 2017-10-31 | 1349.5 | 0 | 206994.1405 | 214381.32 | 0 | 1350.5 | 0.75861 | 0.15846 | 0.082932
17141018 | 2017-09-06 | 2017-09-18 | 208360 | 0 | 232105.62 | 194083.89 | 0 | 964.5 | 0.66563 | 0.33437 | 0
17141019 | 2017-09-11 | 2017-12-01 | 1 | 0 | 323265.64 | 264390.67
17141020 | 2017-09-18 | 2017-11-17 | 1357 | 0 | 147108.21 | 133858.48 | 1440 | 1519.5 | 0.89207 | 0.10793 | 0
17141021 | 2017-10-06 | 2017-10-20 | 554 | 0 | 140954 | 152499.51 | 0 | 867.5 | 0.71297 | 0.28703 | 0
17141022, 17148020 | 2017-11-11 | 2018-12-01 | 49411 | 6303 | 86011093.35 | 90313099.19 | 119720 | 153205.63 | 0.76842 | 0.22542 | 0.0061622
17141023, 17146028, 17148018 | 2017-11-06 | 2018-12-31 | 6326625 | 8419863 | 143499118.1613 | 146216325.06 | 303103 | 326402.65 | 0.75703 | 0.23933 | 0.0036383
17141025 | 2018-08-06 | 2019-11-18 | 6498 | 6181 | 65929837.473 | 69859197.64 | 95662 | 118013.3 | 0.67464 | 0.30228 | 0.023082
17141026, 18146020, 19148025 | 2019-06-03 | 2020-12-01 | 9438309.54 | 999353 | 154959353.3372 | 146043355.95 | 202936.49 | 170714.1 | 0.77477 | 0.22004 | 0.0051954
17141027 | 2017-11-27 | 2018-04-02 | 2191561 | 0 | 5211524 | 5518573.47 | 3040 | 6739 | 0.6679 | 0.27163 | 0.060469
17141028 | 2017-11-27 | 2017-12-13 | 14 | 0 | 1532577.9 | 1386754.76
17141029 | 2017-11-27 | 2017-12-02 | 24530 | 0 | 271963.28 | 350050.03 | 446 | 782 | 0.76662 | 0.23338 | 0
17141030 | 2018-01-02 | 2018-02-26 | 599 | 503 | 2010911.34 | 1968628.08 | 7774 | 7833.5 | 0.60516 | 0.23023 | 0.16461
17141031 | 2017-12-04 | 2017-12-18 | 0 | 0 | 34137 | 38376.54 | 40 | 250.5 | 0.998 | 0.001996 | 0
17141032 | 2018-04-23 | 2018-09-15 | 7457 | 5068 | 56860227.4705 | 55416142.29 | 83945 | 89715.5 | 0.58996 | 0.36624 | 0.043805
17145002 | 2017-02-17 | 2020-01-17 | 36729 | 10254 | 4261806.004 | 4243034.52 | 41007 | 34780.75 | 0.91971 | 0.080289 | 0
17145003 | 2017-07-24 | 2018-12-31 | 22506190 | 22312567 | 318586500.35 | 306242313.05 | 646353 | 731176.86 | 0.91445 | 0.08177 | 0.0037803
17145004, 17146012, 17148006 | 2017-05-01 | 2017-10-19 | 8137860 | 7405891 | 36153409.69 | 37749227.16 | 291522 | 335908.32 | 0.80075 | 0.19925 | 0
17145005 | 2017-04-10 | 2017-05-31 | 13 | 0 | 76056.42 | 43879.51 | 0 | 190.5 | 0.78352 | 0.21648 | 0
17145006 | 2017-07-17 | 2017-12-31 | 0 | 0 | 2200 | 1124.25
17145007, 17148005 | 2017-03-27 | 2018-12-31 | 15376682.4 | 15096285 | 124399904.3669 | 113393802.79 | 548444.12 | 524076.56 | 0.84133 | 0.15867 | 0
17145008 | 2017-04-20 |  | 26 | 12 | 31884.91 | 42940.26 | 350 | 331 | 0.84592 | 0.15408 | 0
17145009 | 2017-05-15 | 2017-12-31 | 2 | 0 | 18591 | 6708.63 | 90 | 34.5 | 1899-12-31 | 0 | 0
17145010 | 2017-05-30 | 2018-06-30 | 254951 | 231028 | 9789051.82 | 10252761.72 | 29352 | 27673 | 0.803 | 0.15466 | 0.042334
17145011, 17148008 | 2017-06-01 | 2018-06-30 | 208895 | 205188 | 10219524.76 | 9613461.96 | 28863 | 27197 | 0.80936 | 0.1651 | 0.02554
17145012 | 2017-06-14 |  | 953224 | 1051926 | 5372105.7717 | 5800616.31 | 44691.76 | 53504.59 | 0.82284 | 0.17716 | 0
17145013, 17146026, 17148015 | 2017-10-13 | 2018-04-01 | 2323262 | 2148047 | 22802377.02 | 22190739.29 | 94481 | 90477 | 0.81848 | 0.18152 | 0
17145014 | 2017-12-04 | 2018-09-14 | 86 | 0 | 210326 | 177251.6
17145015 | 2017-09-25 | 2018-02-09 | 203 | 196 | 23227 | 29086.31 | 194 | 105.5 | 0.98578 | 0.014218 | 0
17145016 | 2017-08-21 | 2020-01-01 | 5594 | 608 | 1347265 | 860825.9 | 8518 | 7125 | 0.9167 | 0.083298 | 0
17145017 | 2017-10-23 | 2018-01-14 | 33182 | 32334 | 930847 | 815545.92 | 15156 | 10175.5 | 0.9204 | 0.079603 | 0
17145018, 18148014 | 2018-06-25 | 2019-03-01 | 1925151 | 1812239 | 17710657.17 | 20497022.56 | 85624 | 113581.99 | 0.81275 | 0.18707 | 0.00018351
17146001 | 2017-03-01 | 2017-12-31 | 18 | 0 | 595408 | 472771.67
17146002 | 2017-03-01 | 2017-12-31 | 8 | 0 | 35910 | 23856.02
17146004 | 2017-02-10 | 2017-05-01 | 9316 | 0 | 47966.53 | 35389.06 | 480 | 623.41 | 0.63347 | 0.36653 | 0
17146005 | 2017-03-13 | 2017-05-31 | 104 | 0 | 38478 | 37359.2 | 360 | 320.5 | 0.74883 | 0.25117 | 0
17146006 | 2017-06-19 | 2017-11-21 | 369321 | 295812 | 10313594.63 | 10023056.17 | 11431 | 12597 | 0.84842 | 0.15158 | 0
17146007 | 2017-05-15 | 2017-06-15 | 617 | 0 | 257225.17 | 255375.18 | 867 | 694 | 0.92075 | 0.038905 | 0.040346
17146008 | 2017-02-27 | 2017-05-01 | 4 | 0 | 21739 | 17948.96
17146009 | 2017-03-01 | 2017-05-01 | 5 | 0 | 21739 | 18142.77
17146010 | 2017-09-21 | 2018-10-31 | 181 | 0 | 9512455.01 | 9490404.92
17146011 | 2017-08-01 | 2017-11-23 | 75918 | 65701 | 6351397.106 | 6055482.02 | 10358 | 9177.5 | 0.707 | 0.293 | 0
17146013 | 2017-10-30 | 2018-07-31 | 169030 | 195431 | 5655358.4398 | 6148084.5 | 26106.6 | 20294.15 | 0.77896 | 0.22104 | 0
17146014 | 2017-06-01 | 2017-07-28 | 0 | 0 | 11718 | 7160.62
17146015 | 2017-09-05 | 2017-11-30 | 73 | 0 | 436224.3199 | 322071.92 | 966 | 1132 | 0.65945 | 0.34055 | 0
17146016 | 2017-09-05 | 2017-11-30 | 8 | 0 | 23903 | 11833.41 | 240 | 0 | 0 | 0 | 0
17146017 | 2017-09-20 | 2017-10-06 | 0 | 0 | 8122.18 | 7106.81
17146019 | 2017-12-01 | 2018-12-01 | 12876 | 350 | 178650 | 171418.78 | 406 | 130 | 0.79615 | 0.20385 | 0
17146020 | 2018-01-08 | 2018-04-30 | 18928 | 1464 | 3866155.2 | 4782840.15 | 3640 | 5300 | 0.83123 | 0.16877 | 0
17146021 | 2017-07-17 | 2019-12-13 | 2903 | 0 | 21803082.61 | 22585965.82
17146022 | 2017-06-18 | 2021-04-30 | 2881634 | 571604 | 49114524.541 | 53858765.99 | 150638.05 | 180730.8 | 0.76231 | 0.23769 | 0
17146023 | 2017-12-11 | 2017-12-31 | 3504 | 0 | 21447.98 | 18470.26 | 97 | 0 | 0 | 0 | 0
17146024 | 2017-12-11 | 2017-12-31 | 3202 | 0 | 18270.5 | 14995.47 | 103 | 0 | 0 | 0 | 0
17146027 | 2017-11-27 | 2017-11-27 | 0 | 0 | 15170 | 106.88
17146029 | 2018-01-08 | 2018-03-31 | 60 | 0 | 311817.55 | 283966.68 | 1168 | 607 | 0.98847 | 0.011532 | 0
17148003 | 2016-12-22 | 2016-12-31 | 387 | 0 | 94203 | 32203.18 | 692 | 0 | 0 | 0 | 0
17148004 | 2017-05-05 | 2018-06-01 | 311279 | 308174 | 7818748.4666 | 7791228.25 | 33704 | 27730 | 0.76531 | 0.23047 | 0.0042193
17148007 | 2017-05-01 | 2017-07-01 | 30 | 0 | 493820 | 435546.13 | 960 | 1104.5 | 0.7569 | 0.2431 | 0
17148009 | 2017-07-01 | 2017-10-18 | 38676.02 | 28663 | 681251.973 | 574225.68 | 2608 | 2067 | 0.83116 | 0.16884 | 0
17148010 | 2017-08-15 |  | 502733 | 445098 | 5902497.66 | 6386036.31 | 18424 | 24742.5 | 0.80546 | 0.19046 | 0.004082
17148011 | 2017-08-14 |  | 54010 | 144 | 2587332.3734 | 2624003.42 | 9657.12 | 10408.5 | 0.71706 | 0.28078 | 0.0021617
17148012 | 2017-08-14 |  | 117661 | 126681 | 3689986.9932 | 3425349.66 | 13198.5 | 11978.5 | 0.72893 | 0.26907 | 0.0020036
17148013 | 2017-08-14 |  | 13396 | 7113 | 1896627.2971 | 1900596.08 | 6540.24 | 8832.5 | 0.71112 | 0.28259 | 0.0062836
17148016 | 2017-09-01 | 2017-12-31 | 431 | 424 | 1231687.02 | 1179806.66 | 7516 | 7484 | 0.66762 | 0.31447 | 0.017905
17148017 | 2017-09-01 | 2017-12-31 | 409 | 135 | 1051656.8638 | 1051171.21 | 7011 | 7360 | 0.67473 | 0.32065 | 0.0046196
17148019 | 2017-11-28 |  | 11 | 0 | 1245174.8 | 1225205.93 | 3470 | 2443.5 | 0.54082 | 0.38142 | 0.077757
17150002 | 2017-04-01 | 2018-08-31 | 0 | 0 | 3443624.02 | 2679276.15
17150003 | 2018-03-01 | 2019-04-23 | 334920.86 | 0 | 81630437.0862 | 88649756.3 | 54729.7 | 76952.5 | 0.98089 | 0.017907 | 0.001202
17150004 | 2017-03-01 | 2020-07-31 | 0 | 239800 | 65046496.35 | 64507956.33 | 0 | 256237.99 | 0.81936 | 0.14102 | 0.039619
17150004-163 | 2017-11-01 | 2020-07-20 | 18438 | 0 | 1474028005.2644 | 1480541033.34 | 0 | 0 | 0 | 0 | 0
17150005 | 2017-05-15 | 2018-08-31 | 0 | 0 | 5742710.52 | 5065832.36 | 0 | 312.83 | 1899-12-31 | 0 | 0
17150006 |  |  | 0 | 0 | 0 | 1678.22
17150007 | 2017-06-19 | 2017-09-02 | 688 | 0 | 602981.7 | 583161.3 | 388 | 241.5 | 0.89027 | 0.095238 | 0.014493
17150009 | 2017-07-20 | 2018-09-30 | 0 | 0 | 851400.04 | 845422.35 | 16 | 0 | 0 | 0 | 0
17150010 |  |  | 91 | 0 | 1857012.49 | 1828959.81 | 90 | 210 | 0.95238 | 0.047619 | 0
17150011 | 2017-10-01 | 2020-03-31 | 0 | 0 | 48550 | 8615.56
17150012 | 2017-12-06 | 2018-11-03 | 209 | 0 | 2173848.71 | 2168599.59
17999 | 2001-12-31 |  | 0 | 0 | 0 | 21805
18000004-040, 18040004, 18040011 | 2017-09-18 | 2019-04-26 | 0 | 0 | 16053735.77 | 16172811.06 | 0 | 4 | 1899-12-31 | 0 | 0
18000014-040, 19090002, 19090012, 19090011 | 2019-06-03 | 2020-09-30 | 484038.59 | 169636 | 40507279.32 | 41101704.09 | 14360.7 | 15135.38 | 0.89738 | 0.098223 | 0.0043943
18030001 | 2018-01-01 | 2018-12-31 | 0 | 0 | 1517640.42 | 1534850.34 | 0 | 4629.5 | 0.93347 | 0.062426 | 0.0041041
18030002 | 2018-01-01 | 2018-12-31 | 0 | 25 | 11292062.15 | 11282412.55 | 0 | 57655.57 | 0.8915 | 0.10338 | 0.0051166
18030003, 19030044 | 2018-06-18 | 2020-08-31 | 468249.5 | 71656 | 21813456.7559 | 22265623.36 | 89743.97 | 88309.5 | 0.92323 | 0.074504 | 0.0022633
18030005 | 2018-01-11 | 2018-04-15 | 3575 | 5381 | 1603231.97 | 1339716.53 | 1817 | 1456 | 0.97734 | 0.022665 | 0
18030006 | 2018-09-01 |  | 320729.6 | 545 | 4570823.74 | 4480780.66 | 7296.9 | 6560.47 | 0.96525 | 0.034754 | 0
18030007 | 2018-02-15 | 2021-07-15 | 0 | 0 | 2711670.4461 | 2638732.63
18030008 | 2018-01-02 | 2019-01-21 | 17 | 133235 | 12439742.103 | 12026944.18 | 16600.5 | 15900 | 0.92575 | 0.073742 | 0.00050314
18030009 | 2018-02-19 | 2018-05-04 | 0 | 0 | 4969357.6965 | 4273622.61 | 2935 | 2235.85 | 0.95885 | 0.03757 | 0.0035781
18030010 | 2018-06-01 | 2019-01-15 | 45809.13 | 28518 | 2985413.1787 | 3009583.87 | 2969.55 | 3379.82 | 0.98387 | 0.016125 | 0
18030011 | 2018-08-01 | 2019-06-07 | 45329.3 | 13859 | 6566227.7 | 6588035.73 | 4351.3 | 5082.02 | 0.9936 | 0.0063951 | 0
18030012 | 2018-06-11 | 2019-09-02 | 177890 | 101184 | 2436648.75 | 2471663.29 | 7904.1 | 6204.68 | 0.77299 | 0.22024 | 0.0067691
18030013 | 2019-05-01 | 2019-09-01 | 31760.1 | 19396 | 2767329.93 | 2750641.66 | 4019.7 | 4273 | 0.90428 | 0.081676 | 0.014042
18030014 | 2018-09-01 | 2018-12-31 | 206314.99 | 51940 | 7223842.9701 | 7236012.65 | 7810.3 | 9096.5 | 0.98917 | 0.010828 | 0
18030015 | 2018-05-13 | 2018-12-31 | 15952 | 16151 | 364155 | 378365.18 | 3129 | 1691.5 | 0.90216 | 0.097842 | 0
18030016, 18030004 | 2018-01-08 | 2018-08-31 | 299569.5 | 108832 | 11821516.6065 | 11900841.46 | 11209 | 10936.24 | 0.8887 | 0.10727 | 0.004038
18030018 | 2018-05-14 | 2018-08-17 | 4 | 0 | 1729923.1 | 1449518.04 | 2848 | 3613.74 | 0.97869 | 0.021308 | 0
18030019 | 2018-05-01 | 2018-11-01 | 29854.59 | 0 | 1876237.9998 | 1908261.51 | 2158.05 | 2162.75 | 0.99861 | 0.0013871 | 0
18030020 | 2018-05-07 | 2018-06-30 | 9251 | 0 | 65013 | 63310.87 | 447 | 425.5 | 0.91187 | 0.088132 | 0
18030021 |  | 2018-05-11 | 0 | 0 | 0.01 | 286501.85 | 0 | 2277 | 0.98463 | 0.015371 | 0
18030022 | 2018-05-21 | 2018-08-10 | 17531 | 0 | 210458 | 198599.75 | 892 | 569.19 | 0.98067 | 0.019326 | 0
18030023 | 2018-05-28 | 2018-11-01 | 2091 | 2 | 683697.83 | 649139.24 | 3828 | 2848 | 0.93346 | 0.066538 | 0
18030024 | 2018-07-03 | 2018-09-15 | 177 | 0 | 69621.14 | 68485.71 | 199 | 119 | 0.9916 | 0.0084034 | 0
18030025 | 2018-05-07 | 2019-12-31 | -3684.5 | 40 | 2812012.372 | 2889613.51 | 3737.07 | 5222.97 | 0.91346 | 0.082424 | 0.0041164
18030026 | 2018-05-21 | 2018-08-24 | 18360 | 12110 | 1071741.3 | 1128207.11 | 2835 | 2933.89 | 0.98722 | 0.012782 | 0
18030027 | 2018-06-29 | 2018-07-14 | 103 | 0 | 197224.1 | 189500.07 | 311 | 198.5 | 0.72544 | 0.13098 | 0.14358
18030028 | 2017-12-26 | 2018-02-02 | 0 | 0 | 174754.65 | 173503.22 | 180 | 56 | 1899-12-31 | 0 | 0
18030029 | 2018-06-11 | 2018-10-31 | 4 | 0 | 524870 | 496585.13 | 607 | 452 | 0.94912 | 0.050885 | 0
18030030 | 2018-08-31 | 2018-10-19 | 94539.39 | 46340 | 2447248.93 | 2421365.32 | 4415.4 | 4227 | 0.90892 | 0.090608 | 0.00047315
18030031 | 2018-07-20 | 2019-03-15 | 16874.3 | 0 | 4661570.4856 | 4639271.35 | 933.87 | 1092.5 | 0.99451 | 0.005492 | 0
18030032 | 2018-07-31 | 2018-09-01 | 6444 | 0 | 353500.414 | 321655.31 | 1145.87 | 1959.23 | 0.89736 | 0.098554 | 0.0040832
18030033 | 2018-08-01 | 2019-10-21 | 63891.5 | 66400 | 11020199.925 | 11212337.36 | 25198 | 29883.1 | 0.8926 | 0.099504 | 0.0078974
18030034 | 2018-08-08 | 2018-12-31 | 87.4 | 0 | 359536.53 | 361523.91 | 699 | 584 | 0.98031 | 0.019692 | 0
18030035 | 2018-07-31 | 2018-09-01 | 0 | 0 | 24963 | 16040.12 | 106 | 37 | 0.72973 | 0.27027 | 0
18030036 | 2018-08-13 | 2018-12-28 | 1713 | 0 | 3078984.73 | 2987570.45 | 2059 | 3448.03 | 0.99536 | 0.0046403 | 0
18030037 | 2018-07-23 | 2018-11-12 | 0 | 11 | 698024.34 | 616846.88 | 2567 | 2226.5 | 0.90523 | 0.092971 | 0.0017965
18030038 | 2018-09-05 | 2018-12-31 | 2 | 0 | 244830.87 | 232632.39 | 557 | 661 | 0.96596 | 0.034039 | 0
18030039 | 2019-02-19 | 2019-06-04 | 6681.76 | 1942 | 980786.05 | 871967.32 | 338.8 | 152 | 0.89474 | 0.10526 | 0
18030040 | 2017-12-15 |  | 0 | 0 | 407036.84 | 405571.85 | 95.92 | 0 | 0 | 0 | 0
18030041 | 2018-09-17 | 2018-05-25 | 0 | 0 | 342186 | 334411.4 | 40 | 62.5 | 1899-12-31 | 0 | 0
18030042 | 2018-09-27 | 2019-06-24 | 0 | 0 | 1687141.59 | 1739829.95
18030043 | 2018-10-08 | 2019-03-31 | 142966.24 | 31330 | 5256898 | 5256907.43 | 8095.4 | 10850.11 | 0.8259 | 0.13032 | 0.043778
18030044 | 2018-10-12 | 2019-02-18 | 51581.75 | 10 | 2526602.24 | 2533841.37 | 4342 | 6089.25 | 0.81036 | 0.18865 | 0.00098534
18030045 | 2018-10-08 | 2019-06-01 | 50944.77 | 5779 | 9237090.44 | 9165883.92 | 3501.8 | 4363 | 0.96814 | 0.0314 | 0.0004584
18030046 |  |  | 0 | 0 | 0.01 | 0
18030047 | 2018-10-15 | 2019-07-01 | 12389 | 10333 | 3345113.89 | 3326833.9 | 3141 | 3418.5 | 0.9042 | 0.094047 | 0.0017552
18030048 | 2018-10-29 | 2019-11-21 | 2324475.86 | 2332581 | 78522078.7635 | 78797731.23 | 103685.3 | 93047 | 0.89955 | 0.098685 | 0.0017679
18030049 | 2018-12-17 | 2019-06-03 | 14441.5 | 2925 | 2879798.7 | 2634554 | 1255.9 | 627.5 | 0.93386 | 0.066135 | 0
18030050 | 2019-04-01 |  | 58311 | 2168 | 1583893.92 | 1631481.55 | 2076.9 | 2539 | 0.99823 | 0.0017724 | 0
18030051 |  |  | 0 | 0 | 88158.7 | 102782.16
18030052 | 2018-11-12 | 2019-03-01 | 0 | 0 | 743096.88 | 720488.73 | 744.5 | 721 | 1899-12-31 | 0 | 0
18030053 | 2018-09-03 | 2019-01-29 | 0 | 0 | 383670.68 | 382950.59 | 2120 | 1551.5 | 0.92556 | 0.074444 | 0
18030054 | 2018-12-05 | 2019-06-30 | 385 | 0 | 5736028.3672 | 5751710.62 | 5460 | 6696 | 0.96386 | 0.036141 | 0
18030055 | 2019-01-07 | 2019-05-24 | 12 | 0 | 557175.35 | 556487.73 | 1943 | 2410.25 | 0.961 | 0.020745 | 0.018255
18030056 | 2018-12-09 | 2019-03-28 | 313893 | 0 | 1711471.0125 | 1732973.02 | 5603.41 | 4787 | 0.68164 | 0.27303 | 0.045331
18030057 | 2019-06-03 | 2019-08-30 | 341 | 0 | 744228.09 | 659655.81 | 419.6 | 321 | 0.99065 | 0.0093458 | 0
18030058 | 2019-02-01 | 2019-06-01 | 0 | 0 | 166078.1 | 182272.34 | 60 | 72 | 1899-12-31 | 0 | 0
18040001 | 2018-03-19 | 2018-07-16 | 53973 | 0 | 1177972.13 | 1453823.58 | 1616 | 4613.5 | 0.92294 | 0.077056 | 0
18040003 | 2018-12-15 | 2020-02-01 | 0 | 0 | 0.01 | 34117.45
18040005 | 2018-02-19 | 2018-05-18 | 30 | 0 | 2699634.2798 | 2665492.44 | 0 | 333 | 0.98649 | 0.013514 | 0
18040006 | 2018-07-03 | 2020-10-30 | 0 | 0 | 0.01 | 0
18040007 | 2018-05-01 | 2020-04-30 | 0 | 0 | 0.01 | 1694.86
18040008 | 2018-10-01 | 2019-02-11 | 0 | 0 | 639981.1 | 592414.76 | 0 | 8 | 1899-12-31 | 0 | 0
18040009 | 2018-03-19 | 2019-09-30 | 67319 | 15964 | 7815000.64 | 9645390.93 | 9317 | 19464.5 | 0.87739 | 0.12261 | 0
18040010 |  |  | 0 | 0 | 648016.02 | 749517.12
18040010-173 |  |  | 0 | 0 | 924329 | 803747.06
18040012 | 2018-10-15 | 2020-07-31 | 18419 | 8211 | 49089220.87 | 48315277.2 | 13316.3311 | 18327.05 | 0.85827 | 0.14173 | 0
18040013 | 2018-11-05 | 2018-11-17 | 666 | 0 | 73900.9 | 93525.72 | 389 | 584 | 0.71233 | 0.28767 | 0
18040014 | 2018-10-22 | 2019-01-23 | 0 | 0 | 7379128.892 | 7285997.44 | 396.5 | 1528.5 | 0.89696 | 0.10304 | 0
18040015 | 2018-10-18 | 2019-01-31 | 0 | 0 | 60000 | 4924.07
18040016 | 2018-10-25 | 2019-01-31 | 0 | 0 | 45662 | 1376.3
18040017 | 2018-12-10 | 2019-04-30 | 0 | 0 | 1743982.71 | 1613357.77 | 536 | 685 | 0.74745 | 0.25255 | 0
18050001 | 2018-03-09 | 2018-05-31 | 2165.6 | 2068 | 588733.98 | 616484.79 | 576.4 | 873 | 0.97709 | 0.02291 | 0
18050002 | 2018-06-17 | 2018-09-28 | 11727.99 | 839 | 2888104.97 | 2901972.42 | 1579 | 2487.5 | 0.94995 | 0.049447 | 0.00060302
18050003 |  |  | 0 | 0 | 87750 | 208877.56
18050005 | 2018-01-09 | 2019-02-28 | 0 | 0 | 342743.99 | 645189.49
18050006 | 2018-02-22 | 2019-11-30 | 198029.07 | 57760 | 7390721.867 | 16470271.18 | 24814.8 | 70523.76 | 0.92537 | 0.066531 | 0.0081037
18050007 | 2019-06-04 | 2020-10-20 | 150138.36 | 1982 | 68037369.1607 | 71177072.99 | 2768 | 3667.79 | 0.82483 | 0.16958 | 0.0055892
18050008 | 2019-01-15 | 2020-04-11 | 277100.73 | 82838.5 | 54378167.4462 | 58188100.27 | 25842.9 | 46538.22 | 0.85059 | 0.13654 | 0.012871
18050009 | 2018-09-15 | 2018-12-15 | 0 | 0 | 4620 | 7892.1
18050010 |  |  | 0 | 0 | 1921633 | -2801.09 | 48 | 66.5 | 1899-12-31 | 0 | 0
18050011 | 2018-01-01 | 2018-12-31 | 20 | 0 | 3114.8 | 802.09
18050012 | 2017-10-18 |  | 20 | 0 | 3234.04 | 450.69
18050013 | 2020-01-01 |  | 0 | 0 | 1429378.75 | 1097834.27
18050014 | 2018-11-01 |  | 2105 | 0 | 275000 | 522930.18 | 0 | 56 | 1899-12-31 | 0 | 0
18050015 | 2018-03-01 | 2018-06-29 | 2079.1 | 223 | 588034.02 | 620797.43 | 1323.5 | 1922 | 0.90635 | 0.08949 | 0.0041623
18050016 | 2018-03-03 | 2018-03-03 | 398 | 0 | 18695.46 | 26206.9 | 25 | 9 | 0 | 1899-12-31 | 0
18050017, 18050004 | 2018-01-01 | 2018-08-26 | 41745.71 | 11756 | 17393441.5655 | 16012359.46 | 5677.4 | 5358 | 0.95624 | 0.039196 | 0.004561
18050018 | 2018-10-01 | 2019-07-31 | 39095.35 | 8227 | 2929653.35 | 2431358.46 | 6032.4 | 3993.16 | 0.99549 | 0.0037564 | 0.00075128
18050019 | 2018-08-20 | 2018-10-12 | 8286 | 1975 | 362452.73 | 359627.42 | 974 | 843 | 0.95255 | 0.04745 | 0
18050020 | 2018-05-01 | 2018-06-15 | 1562 | 769 | 177075.19 | 177196.48 | 470 | 448 | 0.9375 | 0.053571 | 0.0089286
18050021 | 2018-05-15 | 2018-08-01 | 3270 | 339 | 300634.47 | 301096.65 | 531 | 610.5 | 0.8534 | 0.11876 | 0.027846
18050022 | 2018-04-15 | 2018-12-31 | 12505.5 | 6136 | 276938.14 | 289814.24 | 470 | 1016.5 | 0.71372 | 0.2184 | 0.06788
18050023 | 2018-10-01 | 2019-03-31 | 0 | 0 | 4620 | 4994.75
18050024 | 2018-06-01 | 2019-03-01 | 4409 | 36286 | 2779134.285 | 2796891.58 | 4152.4 | 3561.86 | 0.89921 | 0.088577 | 0.012213
18050025 | 2018-07-18 | 2019-12-31 | 477.91 | 364 | 418812.88 | 388926.37 | 232 | 561.02 | 0.77006 | 0.1123 | 0.11764
18050026 | 2018-06-07 | 2018-12-31 | 236255 | 40909 | 2903983.425 | 2901845.45 | 8591 | 6285.5 | 0.95617 | 0.041126 | 0.0027046
18050027 | 2019-09-03 | 2021-03-01 | 356646.69 | 249227 | 38914390.2316 | 28262206.37 | 24901.7 | 19584.25 | 0.94409 | 0.0553 | 0.00061274
18050028 | 2018-05-01 | 2018-07-31 | 0 | 0 | 226800 | 291808.84
18050029 |  |  | 76616.49 | 61858 | 27608625.695 | 25709230.19 | 12585.8 | 10482.39 | 0.94076 | 0.057716 | 0.0015264
18050030 | 2020-12-01 | 2022-12-01 | 3988 | 0 | 2259348.47 | 2414651.17 | 0 | 260 | 1899-12-31 | 0 | 0
18050031 | 2018-08-01 | 2019-08-01 | 5896.3 | 1986 | 4342409.85 | 4350045.05 | 3192.18 | 1629.89 | 0.91886 | 0.073164 | 0.007976
18050032 | 2018-07-18 | 2018-08-14 | 9758.37 | 128 | 339639.88 | 297201.34 | 693.2 | 497 | 0.94769 | 0.052314 | 0
18050033 |  |  | 421575.71 | 0 | 73950228.39 | 2497116.67 | 23357.8 | 440.5 | 0.99319 | 0.0068104 | 0
18050034 | 2019-05-01 | 2020-05-01 | 51629.82 | 0 | 20721311.79 | 20650667.56 | 2180.4 | 4531.96 | 0.98831 | 0.011695 | 0
18050035 | 2019-03-01 | 2019-11-01 | 6734.86 | 26 | 1263936.1854 | 1189492.95 | 433.82 | 442.12 | 0.94006 | 0.053153 | 0.0067855
18050036 | 2018-10-09 | 2018-10-15 | 11314.5 | 141 | 112399.83 | 109126.27 | 190.3 | 150.5 | 0.96013 | 0.039867 | 0
18050037 | 2019-05-01 | 2019-12-31 | 13275 | 6 | 1104552.49 | 1105936.2 | 652.6 | 1363.25 | 0.91253 | 0.081606 | 0.0058683
18050038 | 2019-03-01 | 2020-07-31 | 704650.65 | 675443 | 44511072.2449 | 44455907.89 | 16991.6 | 23573.73 | 0.92489 | 0.071077 | 0.0040299
18050039 | 2018-11-01 | 2019-10-31 | 833891.85 | 500512 | 3207352.6295 | 3307023.54 | 17887.9 | 16126.37 | 0.92608 | 0.066413 | 0.0075032
18050040 | 2018-11-26 | 2018-12-21 | 2887.62 | 0 | 73954.69 | 70242.07 | 301.57 | 248 | 1899-12-31 | 0 | 0
18050041 |  |  | 0 | 0 | 112572.95 | 101407.79
18050042 | 2018-12-10 | 2021-04-01 | 4750703.81 | 3446885 | 841948897.9186 | 843073902.61 | 446258.59 | 533641.02 | 0.79945 | 0.17775 | 0.022804
18050050 | 2018-11-09 | 2019-02-28 | 20275.7 | 2049 | 1709091.8709 | 1642469.38 | 1954.6 | 2314 | 0.89909 | 0.053803 | 0.047105
18050051 | 2019-03-22 | 2019-09-04 | 32683.5 | 2347 | 1619806.8982 | 1696869.95 | 2354.71 | 3523.78 | 0.916 | 0.063852 | 0.020149
18050052 | 2018-12-01 | 2019-01-31 | 11219.5 | 0 | 560368.22 | 496222.48 | 1031.4 | 540.74 | 0.96301 | 0.036986 | 0
18050053 | 2018-12-01 | 2019-04-12 | 30404 | 0 | 789623.1643 | 767195.84 | 1518 | 1377.09 | 0.96551 | 0.034493 | 0
18050054 | 2019-01-01 |  | 68745.62 | 0 | 3566310.96 | 2983613.15 | 48 | 0 | 0 | 0 | 0
18050056 | 2019-05-31 |  | 239077.3 | 124582 | 11040334.05 | 10395518.17 | 16666.25 | 13784 | 0.84805 | 0.13247 | 0.019479
18050057 | 2019-01-02 | 2019-06-30 | 47813.3 | 551 | 3862698.3432 | 3753949.24 | 9356.21 | 7580.6 | 0.95891 | 0.02579 | 0.015302
18060001 | 2020-01-01 | 2022-08-01 | 0 | 0 | 0 | -2624
18060002 | 2019-01-01 | 2020-06-30 | 0 | 0 | 0.01 | 3608.61
18060003 | 2018-01-03 | 2018-06-18 | 1798 | 2649 | 1163411.9525 | 1184103.83 | 2850 | 2724 | 0.89611 | 0.10389 | 0
18060004 | 2018-01-29 | 2018-09-28 | 70627.64 | 6919 | 11643214.5 | 11150812.01 | 5924.02 | 6556.5 | 0.93991 | 0.060093 | 0
18060005 | 2018-06-01 | 2021-06-01 | 0 | 0 | 286928.27 | 331268.26 | 0 | 130 | 1899-12-31 | 0 | 0
18060006 | 2019-03-04 | 2019-11-04 | 0 | 0 | 0.01 | 31110.21
18060007 | 2018-01-02 | 2019-12-30 | 287 | 33 | 696632 | 677189.32 | 1280 | 4515 | 0.96955 | 0.030454 | 0
18060008 | 2018-02-07 | 2020-12-31 | 0 | 0 | 0.01 | 26.73
18060009 | 2018-03-12 | 2018-04-06 | 22 | 0 | 520926 | 518635.46 | 278 | 80.5 | 1899-12-31 | 0 | 0
18060010, 17060007, 17060006, 16060029 | 2017-03-01 | 2019-07-01 | 1407533.8 | 708687 | 60044064.1259 | 57756805.75 | 84178.5 | 102892.5 | 0.90154 | 0.098463 | 0
18060011 | 2018-04-23 | 2018-10-01 | 1443 | 1742 | 737579.77 | 735664.72 | 1301 | 1727 | 0.89867 | 0.10133 | 0
18060012 | 2018-05-01 | 2018-07-31 | 1197 | 355 | 137555.26 | 137490.26 | 550 | 364 | 0.89423 | 0.10577 | 0
18060013 | 2018-05-01 | 2018-09-30 | 871 | 641 | 276092.06 | 276137.42 | 776 | 678 | 0.92552 | 0.074484 | 0
18060014 | 2018-03-01 | 2019-12-31 | 117 | 498 | 333836.04 | 362754.31 | 234 | 2214.23 | 0.84848 | 0.15152 | 0
18060015 | 2018-03-19 | 2018-06-01 | 472 | 1297 | 507788.56 | 513409.72 | 432 | 2185.5 | 0.92885 | 0.071151 | 0
18060016 | 2018-04-23 | 2018-07-09 | 1221.5 | 1178 | 474646.27 | 480860.37 | 1021.5 | 1206 | 0.88101 | 0.11899 | 0
18060017 | 2018-03-23 | 2018-12-31 | 1460 | 1944 | 673899.76 | 685153.12 | 1884 | 1943.5 | 0.84178 | 0.15822 | 0
18060018 | 2018-03-26 | 2018-07-01 | 87 | 0 | 13396 | 15223.62 | 82 | 65 | 0.63846 | 0.36154 | 0
18060019 | 2018-04-01 | 2018-10-01 | 110 | 0 | 55000 | 80569.42
18060020 | 2018-04-16 | 2018-10-31 | 2 | 0 | 898332 | 864808.36 | 0 | 959.5 | 0.93851 | 0.06149 | 0
18060021 | 2018-05-01 | 2019-05-01 | 924 | 830 | 289429 | 353672 | 1166 | 2605 | 0.93858 | 0.06142 | 0
18060022 | 2018-04-03 | 2019-02-28 | 39 | 58 | 88370.07 | 88423.36 | 60 | 57.5 | 0.58261 | 0.41739 | 0
18060023 | 2018-05-01 | 2018-08-17 | 60 | 80 | 40125 | 40593.8 | 76 | 89 | 0.82584 | 0.17416 | 0
18060024 | 2018-06-01 | 2019-02-28 | 631.35 | 358 | 233366.45 | 232497.69 | 347 | 392 | 0.87245 | 0.12755 | 0
18060025 | 2018-11-01 | 2020-02-21 | 493569.66 | 252058 | 23888440.27 | 23904463.6 | 23581.7 | 28631 | 0.91528 | 0.084716 | 0
18060026 | 2018-10-01 | 2019-04-01 | 3385.75 | 2432 | 6508029.89 | 6784857.75 | 4730 | 18484 | 0.85263 | 0.14737 | 0
18060027 | 2018-05-08 | 2018-06-08 | 0 | 0 | 8985 | 8844.29 | 0 | 28 | 0.89286 | 0.10714 | 0
18060028 | 2018-05-01 | 2020-12-31 | 1 | 0 | 730648 | 593363.1 | 0 | 323.5 | 0.94745 | 0.05255 | 0
18060029 | 2018-06-01 | 2018-11-30 | 1026 | 1398 | 1289562.94 | 1284063.69 | 1354 | 1556 | 0.90167 | 0.098329 | 0
18060030 | 2018-09-01 | 2019-07-19 | 393900.16 | 176923 | 12918200.3647 | 13357559.11 | 22092.47 | 34957.5 | 0.89456 | 0.10544 | 0
18060031 | 2018-06-25 | 2019-08-30 | 10631 | 0 | 4730168.82 | 4526862.77 | 1112.3 | 5138 | 0.96341 | 0.03659 | 0
18060032 | 2018-08-13 | 2019-04-26 | 21414.7 | 19011 | 1624730.8192 | 1736918.25 | 12729.07 | 5454 | 0.86478 | 0.13522 | 0
18060033 | 2018-10-01 | 2019-06-01 | 487109.51 | 252327 | 8949960.6409 | 12481922.3 | 20611 | 41889.5 | 0.80753 | 0.19247 | 0
18060034 | 2018-08-01 | 2019-06-28 | 141 | 0 | 419452.45 | 394983.05 | 32 | 220 | 0.97273 | 0.027273 | 0
18060035 | 2018-10-01 | 2019-12-31 | 179545 | 33793 | 24468365.4698 | 24456902.26 | 11000.1 | 15419.5 | 0.89387 | 0.10613 | 0
18060036 | 2018-07-18 | 2019-02-05 | 8233 | 15332 | 1201513.799 | 1709704.48 | 3366 | 8180 | 0.86516 | 0.13484 | 0
18060037 | 2018-07-20 | 2019-02-05 | 4977 | 1710 | 6735772.2598 | 6749039.24 | 4370 | 8773 | 0.84088 | 0.15912 | 0
18060038 | 2018-08-24 | 2019-01-16 | -3 | 1187 | 415050 | 421812.18 | 1314 | 1187 | 0.87826 | 0.12174 | 0
18060039 | 2019-01-14 | 2019-12-20 | 132397.5 | 4614 | 4338493.97 | 4396260.12 | 5398.8 | 14049.27 | 0.89558 | 0.10442 | 0
18060040 | 2018-10-04 | 2019-07-25 | 97577 | 4 | 7727203.1872 | 7698295.68 | 1359.5 | 224 | 0.77679 | 0.22321 | 0
18060041 | 2018-09-01 | 2019-08-01 | 0 | 0 | 0.01 | 0
18060042 | 2018-11-09 | 2019-02-28 | 865 | 931 | 276059.45 | 276114.86 | 1174 | 949 | 0.90674 | 0.093256 | 0
18060043 | 2018-11-01 | 2018-12-31 | -2 | 465 | 356612.39 | 357499.75 | 555 | 485 | 0.79485 | 0.20515 | 0
18060044 | 2018-10-05 | 2018-12-31 | 1 | 10 | 4417905.92 | 4696593.61 | 4600 | 11242.5 | 0.9779 | 0.022104 | 0
18060045 | 2018-10-05 | 2018-12-01 | 716.37 | 16 | 25506.47 | 18993.02 | 68 | 32 | 0.75 | 0.25 | 0
18060046 | 2018-11-01 | 2019-06-30 | 150 | 0 | 348558 | 352555.2 | 1600 | 3119.5 | 0.9774 | 0.0226 | 0
18060048 | 2019-01-28 | 2021-01-28 | 3981537 | 59887 | 7912251.185 | 9212986.49 | 10391 | 20851.5 | 0.8502 | 0.14965 | 0.00014387
18060049 | 2019-03-01 | 2019-10-01 | 20118 | 28246 | 1954644.6296 | 2069199.22 | 4727.1 | 3967 | 0.84321 | 0.15679 | 0
18060050 | 2019-06-01 | 2020-03-30 | 0 | 0 | 115531.25 | 242258.74
18060051 | 2019-08-01 | 2020-09-30 | 0 | 0 | 0.01 | 826320.31
18060052 | 2019-01-14 | 2019-07-12 | 51299 | 24826 | 2720447.6 | 2774866.66 | 1900.8 | 3050 | 0.88066 | 0.11934 | 0
18060053 | 2019-01-14 | 2019-06-21 | 54563 | 97665 | 1775303.45 | 1808145.37 | 2664.4 | 7137.5 | 0.9317 | 0.068301 | 0
18060054 | 2019-01-14 | 2019-06-14 | 45803 | 13572 | 1430842.95 | 1474626.95 | 2325 | 3301.5 | 0.84492 | 0.15508 | 0
18060055 | 2018-10-29 | 2019-04-01 | 0 | 0 | 3109508 | 3018951.41 | 6530 | 10141.55 | 0.80703 | 0.19297 | 0
18060058 | 2019-02-07 | 2020-04-16 | 468118.52 | 0 | 29693544.55 | 116547.33 | 20520.3 | 0 | 0 | 0 | 0
18060059 | 2018-12-17 | 2019-05-31 | 235798.04 | 98701 | 1472360.49 | 1810960.01 | 9711 | 14324.33 | 0.82643 | 0.17357 | 0
18060060 | 2019-02-11 | 2019-11-26 | 1812.14 | 1968 | 993877.28 | 1006465.9 | 2517.39 | 3185.5 | 0.91446 | 0.085544 | 0
18060061 | 2019-02-18 | 2019-04-30 | 868 | 222 | 136149.7 | 136680.28 | 639 | 221 | 0.74887 | 0.25113 | 0
18060062 | 2018-11-15 | 2019-08-01 | 0 | 0 | 0.01 | 147239.97
18060063 | 2018-12-26 | 2019-04-01 | 5 | 0 | 457845.27 | 390079.9 | 689 | 954 | 0.89413 | 0.10587 | 0
18080001 | 2018-05-04 | 2019-08-22 | 822132.37 | 543836 | 29622287.7602 | 29659942.13 | 37603.91 | 46101.61 | 0.90293 | 0.094769 | 0.0022993
18080002 | 2018-01-27 | 2019-03-31 | 72.5 | 2 | 6381827.18 | 6451875.6 | 5085.28 | 5387.28 | 0.88723 | 0.10413 | 0.0086314
18080003 | 2018-03-23 | 2018-06-11 | 5468.85 | 729 | 299250.84 | 321441.14 | 473 | 422 | 0.94905 | 0.050948 | 0
18080004 | 2018-07-20 | 2019-04-30 | 14673 | 11471 | 899790.38 | 835743.15 | 873.5 | 1047 | 0.84909 | 0.1404 | 0.010506
18080006 | 2018-07-03 | 2018-10-24 | 22858 | 11014 | 675370.57 | 598345.48 | 1322.3 | 1029 | 0.95335 | 0.046647 | 0
18080007 | 2018-07-09 | 2019-04-11 | 68633 | 48790 | 2967723.77 | 2978729.15 | 2914.9 | 3937 | 0.77889 | 0.19749 | 0.023622
18080008, 19080004 | 2019-06-01 | 2022-02-01 | 3553036.89 | 2252566 | 157047443.8807 | 157598026.22 | 137235.84 | 159838.37 | 0.9339 | 0.065828 | 0.00027376
18080009 | 2018-06-11 | 2018-09-24 | 788 | 460 | 537824.35 | 739957.11 | 36 | 235.91 | 0.96223 | 0.037769 | 0
18080010 | 2018-06-07 | 2022-03-31 | 0 | 4 | 0.01 | -3.74 | 0 | 0 | 0 | 0 | 0
18080010-063 | 2018-06-07 | 2022-03-31 | 0 | 0 | 736829 | 772106.19
18080011 | 2018-07-01 | 2021-12-31 | 0 | 0 | 0.01 | 115.1
18080011-063 | 2018-08-01 | 2021-12-31 | 0 | 0 | 2025737 | 1518308.76
18080012 | 2018-12-17 | 2019-07-20 | 69456 | 0 | 6856768.25 | 7253753.08 | 2188.2 | 3057.71 | 0.95356 | 0.034176 | 0.012264
18080013 | 2019-01-02 |  | 73728 | 44224 | 2145265.98 | 1999286.68 | 1979.7 | 2096 | 0.90625 | 0.090649 | 0.0031011
18080014 | 2018-07-31 | 2019-02-28 | 0 | 54 | 59025 | 62205.05 | 306 | 267 | 0.94944 | 0.050562 | 0
18080015 | 2020-01-01 | 2019-07-31 | 0 | 0 | 344835 | 277767.8
18080016 | 2018-09-17 | 2020-03-31 | 14627.91 | 58024 | 5527447.2352 | 4998905.42 | 7360.4 | 4139.23 | 0.93501 | 0.063176 | 0.0018119
18080017 | 2018-09-25 | 2018-10-03 | 0 | 0 | 0.01 | 0
18080018 | 2018-11-27 | 2018-11-30 | 0 | 0 | 4475 | 3997.53 | 30 | 23 | 1899-12-31 | 0 | 0
18080019 | 2018-10-22 | 2019-06-17 | 1374 | 0 | 2345046.55 | 2339924.11
18080020 | 2019-02-21 | 2019-06-21 | 11615.6 | 7819 | 801278.6 | 805206.72 | 1098.3 | 1072.5 | 0.9049 | 0.078788 | 0.016317
18080021 | 2019-03-27 | 2019-06-06 | 17989 | 8114 | 1466343.23 | 1505285.45 | 2009.35 | 2081 | 0.89164 | 0.10596 | 0.0024027
18080022 | 2018-10-29 | 2019-04-29 | 18113.74 | 5637 | 1056524.5382 | 1011792.45 | 1130.1 | 1578.5 | 0.90751 | 0.062084 | 0.030409
18080023 | 2019-04-03 | 2019-06-17 | 34007.37 | 24010 | 1599644.64 | 1589808.1 | 2548.3 | 3089.12 | 0.9359 | 0.064096 | 0
18080024 | 2018-12-10 | 2019-06-28 | 63731 | 43733 | 1208009.08 | 1164594.48 | 2161.7 | 2243.91 | 0.88435 | 0.11297 | 0.0026739
18080025 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0.01 | 26062.61
18080026 |  | 2019-03-31 | 0 | 0 | 0.01 | 0
18080027 | 2019-02-18 | 2019-07-30 | 68177 | 86566 | 4354164.75 | 1.5334e-09 | 3975.1 | 5166.15 | 0.8766 | 0.11237 | 0.011033
18080028 |  | 2019-03-12 | 0 | 0 | 27621.6 | 23427.08
18090002 | 2019-02-04 | 2019-09-30 | 224752.5 | 121374 | 25940397.6072 | 26777833.84 | 22828 | 23953.78 | 0.90758 | 0.087178 | 0.0052393
18090003 | 2017-11-01 | 2019-03-31 | 198 | 45 | 9814244 | 9755485.83 | 2044 | 2656.5 | 0.96198 | 0.036138 | 0.0018822
18090004 | 2018-07-01 | 2019-09-30 | 21748 | 17015 | 19229564.88 | 15695157.35 | 22658 | 23835.76 | 0.89673 | 0.088921 | 0.014348
18090005, 17090008 | 2017-05-01 | 2018-11-06 | 310383 | 5550359 | 111294144.78 | 112557824.56 | 17538 | 28524.61 | 0.82186 | 0.14267 | 0.035478
18090006 | 2018-03-01 | 2019-03-31 | 7 | 0 | 308511 | 296495.53 | 0 | 40 | 1899-12-31 | 0 | 0
18090007 | 2018-06-01 | 2018-10-31 | 6428.78 | 17 | 742871.6399 | 747445.73 | 503 | 715 | 0.72727 | 0.22168 | 0.051049
18090008 | 2018-06-20 | 2019-04-30 | 328 | 674 | 5222332 | 4988979.29 | 9900 | 9817.91 | 0.90711 | 0.068701 | 0.02419
18090009 | 2018-09-24 | 2019-03-23 | 203 | 43 | 2726951.9 | 2627601.06 | 1436 | 1236.5 | 0.94662 | 0.051355 | 0.0020218
18090010 | 2018-10-29 | 2019-04-12 | 416 | 126 | 5102903.12 | 5108737.91 | 2873 | 3554.08 | 0.9419 | 0.052194 | 0.0059087
18090011 | 2018-11-19 | 2019-04-30 | 10415 | 0 | 160910 | 126481.12 | 550.6 | 539.25 | 0.89986 | 0.076032 | 0.024108
18090012 | 2018-06-20 | 2019-03-31 | 1865 | 46 | 588892.85 | 594846.48 | 733.1 | 651.5 | 0.93707 | 0.062932 | 0
18090013 | 2019-05-15 | 2019-09-30 | 47431.15 | 13504 | 1305726.61 | 1218672.56 | 1612.84 | 1580.61 | 0.88169 | 0.0949 | 0.023409
18090014 | 2019-08-01 | 2020-07-31 | 0 | 0 | 24750 | 24816.42
18090015 | 2019-08-01 | 2020-05-31 | 209922.01 | 39254 | 15217524.77 | 15169887.83 | 10201.4 | 10718.5 | 0.88613 | 0.1099 | 0.0039651
18090016 | 2019-01-03 | 2019-06-30 | 457.46 | 0 | 240605.35 | 207410.9 | 434 | 396 | 0.61616 | 0.15404 | 0.2298
18090017 | 2018-10-23 | 2019-08-31 | 6682.52 | 0 | 232411.11 | 234204.57 | 417.68 | 361.95 | 0.85633 | 0.055256 | 0.08841
18090991, 18090001, 17090009 | 2017-05-01 | 2020-12-31 | 785276.12 | 513188 | 78501602.5837 | 80338107.96 | 48299.27 | 64683.69 | 0.91275 | 0.06313 | 0.02412
18110001 | 2018-01-02 | 2018-10-03 | 15934 | 0 | 3855776.87 | 3575414.27
18110002 | 2018-01-09 | 2018-01-31 | 0 | 0 | 15156 | 15161.64 | 37 | 35.99 | 0.66657 | 0.33343 | 0
18110003 | 2018-06-01 | 2019-07-22 | 88 | 0 | 5509273.65 | 5360445.1
18110004 | 2018-12-01 | 2020-05-02 | 0 | 0 | 21650499.83 | 20621570.97 | 0 | 3352 | 1899-12-31 | 0 | 0
18110005 | 2018-08-06 | 2019-01-09 | 0 | 0 | 668201.15 | 658009.44
18110006 | 2018-10-01 | 2019-02-15 | 57 | 0 | 1193712.18 | 1149059.95
18110007 | 2018-07-20 | 2020-10-05 | 0 | 0 | 57687784.84 | 59112914.91 | 0 | 2004 | 1899-12-31 | 0 | 0
18110008 | 2018-09-06 | 2019-11-04 | 0 | 0 | 117477.98 | 1952610.87
18110009 | 2019-05-09 | 2020-02-10 | 0 | 0 | 4882603.24 | 5405997.72 | 0 | 0 | 0 | 0 | 0
18110010 | 2018-10-29 | 2019-04-05 | 0 | 0 | 717610.11 | 694622.45
18110011 | 2019-04-29 | 2019-05-24 | 0 | 0 | 161658 | 163672.75
18110012 | 2019-01-02 | 2022-03-19 | 217 | 0 | 104162229.41 | 77861693.85 | 4880 | 2270 | 0.99604 | 0.0039648 | 0
18110013 | 2018-11-12 | 2019-06-14 | 0 | 0 | 702640.27 | 952891.45
18110014 | 2019-03-01 | 2019-08-25 | 0 | 0 | 703760.3 | 653348.07
18110015 | 2019-05-20 | 2019-11-27 | 0 | 0 | 1987453.94 | 1965710.47 | 0 | 138 | 1899-12-31 | 0 | 0
18110016 | 2019-04-01 | 2019-08-06 | 0 | 0 | 1151707.27 | 1175832.25 | 0 | 2 | 1899-12-31 | 0 | 0
18110017 | 2019-03-01 | 2019-08-14 | 0 | 0 | 1184449.65 | 1180666.93
18110018 | 2019-02-04 | 2019-06-30 | 0 | 0 | 700836.97 | 663756.41
18110019 | 2019-08-05 | 2020-09-03 | 0 | 0 | 946316.2493 | 902971.31
18110020 | 2019-01-14 | 2019-10-12 | 0 | 0 | 209940 | 203847.46
18110021 | 2019-02-04 | 2019-10-12 | 0 | 0 | 450222.15 | 444374.96
18110022 | 2019-01-14 | 2019-10-12 | 0 | 0 | 438589 | 440487.52
18110023 | 2018-11-29 | 2019-02-28 | 0 | 0 | 270000 | 273445.73
18110024 | 2018-10-29 | 2019-04-27 | 0 | 0 | 1823767.93 | 1798061.76
18110025 | 2018-10-15 | 2019-11-15 | 0 | 0 | 3227659.44 | 3179110.23
18110026 | 2018-10-15 | 2019-11-15 | 0 | 0 | 878979 | 889435.64
18126001 | 2018-07-03 | 2021-04-21 | 1054958.3 | 935052 | 651059982.3058 | 640336992.31 | 87314.78 | 153710.2 | 0.66826 | 0.33174 | 0
18126002 |  | 2020-09-17 | 2520 | 0 | 1460502 | 1495886.24
18141001 | 2018-02-01 | 2018-12-31 | 0 | 0 | 19141.67 | 14091.26
18141002 | 2018-06-01 | 2019-06-30 | 2754 | 2363 | 29877257.26 | 31165810.19 | 40927 | 65765.25 | 0.67107 | 0.2736 | 0.055333
18141006 | 2018-03-19 | 2018-07-01 | 0 | 0 | 70240 | 69561.59
18141007, 18148015 | 2018-06-11 | 2019-04-26 | 7986 | 2353 | 39372957.8487 | 32553643.16 | 140875.5 | 132448.3 | 0.69148 | 0.28035 | 0.028177
18141009 | 2018-05-01 | 2018-12-31 | 0 | 0 | 21087.15 | 10912.37
18141010, 18148010 | 2018-07-30 | 2019-06-29 | 560426 | 320551 | 37651872.8915 | 41785975.57 | 73489 | 101811.75 | 0.64251 | 0.32309 | 0.034395
18141011, 18148016 | 2018-06-05 | 2019-05-15 | 8149 | 1795 | 22934273.24 | 22320007.7 | 80403.76 | 97457.68 | 0.82115 | 0.17885 | 0
18141013 | 2019-04-01 | 2020-11-01 | 11051 | 12494 | 136193192.3912 | 146007131.41 | 260284.5 | 321035.25 | 0.7838 | 0.21599 | 0.00020247
18141014 | 2018-09-10 | 2019-09-01 | 503 | 243 | 2993794.13 | 2536592.95 | 9140 | 9972.09 | 0.77195 | 0.22805 | 0
18141015 | 2018-09-10 | 2019-09-01 | 1059 | 972 | 13807519.54 | 12307350.73 | 42711 | 48198.3 | 0.77401 | 0.22599 | 0
18141016 | 2018-10-12 | 2019-02-01 | 977 | 785 | 8926195.95 | 6121734.27 | 21844 | 21681.5 | 0.72807 | 0.26419 | 0.007737
18141018 | 2018-10-08 |  | 1578 | 1462 | 27282501.06 | 31509397.45 | 109340 | 179088.13 | 0.78805 | 0.21195 | 0
18141019 | 2018-10-15 | 2019-07-31 | 1268 | 926 | 20333500.67 | 16840478.69 | 65295 | 67255.51 | 0.65997 | 0.30276 | 0.037276
18141020 | 2019-04-01 | 2020-04-01 | 0 | 0 | 1048700 | 876029.31
18145001 | 2018-01-22 | 2018-02-28 | 5 | 0 | 65044 | 60671.37
18145005 | 2018-04-01 | 2019-03-08 | 65639 | 136182 | 5439340.81 | 5388419.42 | 0 | 26506.32 | 0.93038 | 0.069323 | 0.00030181
18145006 | 2018-04-23 | 2018-06-01 | 114 | 0 | 15249.19 | 13478.32 | 96 | 52 | 1899-12-31 | 0 | 0
18145008 | 2018-06-25 | 2019-12-31 | 8044264 | 9094356 | 122299437 | 124076779.11 | 531290 | 594505.31 | 0.86947 | 0.13053 | 0
18145009 | 2018-09-20 |  | 0 | 0 | 0.01 | 328.03
18145010 | 2018-09-20 |  | 1058 | 0 | 245312 | 247029.14 | 656 | 505 | 0.84356 | 0.15644 | 0
18145011 | 2019-03-19 |  | 38853631.78 | 18237641 | 301858678.0797 | 359631497.99 | 1300228.21 | 1941169.9 | 0.85356 | 0.14643 | 1.0303e-05
18145012 | 2018-02-27 |  | 3564635 | 5309873 | 57796986.017 | 67950769.21 | 241554.05 | 548641.28 | 0.85095 | 0.14902 | 3.0986e-05
18145013 | 2018-04-22 | 2020-02-04 | 5869277 | 8276895 | 57784700.14 | 69591027.98 | 233845 | 514634.39 | 0.86886 | 0.13114 | 0
18145014 | 2019-04-01 |  | 10626768.8 | 3940059 | 41031573.182 | 50125076.69 | 205072.4 | 395166.85 | 0.82174 | 0.17823 | 3.7959e-05
18145016, 19148008 | 2019-08-15 |  | 7664376.1 | 2892534 | 52301327.23 | 52169524.04 | 193693.2 | 226179.5 | 0.79448 | 0.20552 | 0
18146001 | 2018-02-20 | 2018-05-25 | 127446 | 126778 | 1560607.1 | 1601358.22 | 5932 | 6155 | 0.70333 | 0.29667 | 0
18146002 | 2018-03-26 | 2018-12-31 | 1004861 | 371597 | 16578749.23 | 16173405.67 | 13254 | 16996.75 | 0.793 | 0.207 | 0
18146003 | 2018-02-26 | 2018-05-25 | 5 | 173 | 48589.05 | 62973.54 | 0 | 173.5 | 0.69164 | 0.30836 | 0
18146005 | 2018-03-22 | 2018-06-22 | 109600.8 | 120072 | 591723.7389 | 759423.94 | 2989 | 5934.5 | 0.84363 | 0.15637 | 0
18146006 | 2018-08-06 | 2019-12-31 | 1499 | 0 | 19486890.22 | 18798198.89
18146007 | 2018-04-09 | 2018-04-15 | 0 | 0 | 34506.34 | 19147.41 | 0 | 124 | 0.64516 | 0.35484 | 0
18146008, 18148008, 18145004 | 2018-06-18 | 2018-12-15 | 5222887 | 5586056 | 50345277.73 | 52497470.32 | 175173.36 | 256794.36 | 0.77559 | 0.22438 | 2.5175e-05
18146011 | 2018-08-01 | 2018-12-14 | 22372 | 25751 | 3050937.68 | 3327438.42 | 3624 | 5774.75 | 0.74975 | 0.25025 | 0
18146012, 16080015 | 2017-03-06 | 2020-09-01 | 2634439.85 | 1097477 | 73212197.3612 | 71108791.77 | 89972.41 | 89000.09 | 0.92469 | 0.073466 | 0.0018483
18146013 | 2018-07-02 | 2019-03-15 | 59800 | 51992 | 2487767.72 | 2954632.97 | 4565 | 13391 | 0.89527 | 0.10473 | 0
18146014 | 2018-06-25 | 2020-01-10 | 179631 | 166790 | 8137904.53 | 8219947.82 | 8203 | 8670.6 | 0.83368 | 0.16632 | 0
18146015 | 2018-08-02 | 2020-05-30 | 333931.08 | 335487 | 6183833.003 | 6086143.31 | 15000.56 | 7940.5 | 0.77495 | 0.22505 | 0
18146016 | 2019-05-20 | 2020-11-01 | 1371645 | 1231223 | 52317676.343 | 50736472.57 | 40957 | 79960.5 | 0.84515 | 0.15472 | 0.00012506
18146017, 18141017 | 2019-04-01 | 2021-06-30 | 734504 | 741681 | 100098095.232 | 104334305.83 | 106016 | 169063.3 | 0.81514 | 0.18469 | 0.0001764
18146018 | 2019-03-01 | 2019-10-31 | 1046 | 398 | 498475.51 | 508794.59 | 2234 | 1292 | 0.85899 | 0.14101 | 0
18146019 | 2018-05-17 | 2020-01-14 | 4728 | 5114 | 9790711.2 | 10689204.65 | 10 | 5479.92 | 0.90611 | 0.079016 | 0.014872
18146022 | 2018-11-05 | 2018-12-31 | 17 | 1 | 503433.17 | 382353.95 | 370 | 2427.5 | 0.78062 | 0.21938 | 0
18146023, 19148018 | 2019-06-03 | 2020-01-31 | 2665810.29 | 854580 | 24860182.77 | 22715396.49 | 21848.38 | 24657.5 | 0.77898 | 0.22102 | 0
18146024, 19148005 | 2019-05-01 | 2019-12-31 | 779816 | 995410 | 25881478.67 | 24987854.66 | 24865 | 36472 | 0.72264 | 0.27736 | 0
18146025 | 2019-03-01 | 2019-11-01 | 417106 | 457003 | 21490733.21 | 22212014.5 | 14169 | 26184.92 | 0.79495 | 0.20505 | 0
18146026 | 2019-07-01 | 2019-05-01 | 97549 | 93890 | 2620134.07 | 2910335.17 | 10968 | 16151.5 | 0.71502 | 0.28498 | 0
18148001 | 2018-01-09 |  | 0 | 0 | 182170.95 | 173090.75 | 165 | 0 | 0 | 0 | 0
18148002 | 2018-04-02 | 2018-12-01 | 1237059 | 940274 | 14407678.616 | 14788980.14 | 84516 | 72171.5 | 0.76039 | 0.23539 | 0.0042191
18148003 | 2018-01-25 |  | 328991 | 493154 | 9253759.999 | 8742226.77 | 31194 | 32720.78 | 0.66122 | 0.33387 | 0.0049051
18148004, 18141005 | 2018-04-02 | 2019-06-30 | 755192 | 1295463 | 76462593.2 | 92337856.97 | 132369 | 229638.95 | 0.64267 | 0.25584 | 0.10149
18148005 | 2018-03-20 |  | 0 | 0 | 37636 | 27955.7
18148007, 18141003 | 2018-04-26 | 2018-10-31 | 5430.5 | 53488 | 12027242.6252 | 11438666.62 | 39609 | 40538.5 | 0.6592 | 0.325 | 0.0158
18148009, 18146010, 18141008 | 2018-07-16 | 2018-12-31 | 615811 | 496516 | 43094123.5662 | 45288165.19 | 58917.5 | 87946.75 | 0.6958 | 0.27866 | 0.025541
18148011, 17141024, 18146004 | 2018-04-10 | 2019-12-17 | 1548050 | 829340 | 124770832.05 | 127866193.32 | 173234.24 | 235873.75 | 0.78345 | 0.21655 | 0
18148012 | 2018-06-11 |  | 34803 | 0 | 617685 | 645407.63 | 1561 | 3098 | 0.84038 | 0.15962 | 0
18148013 | 2018-07-31 | 2020-05-01 | 646021 | 453439 | 12617660.72 | 15169675.5 | 31268 | 56549.94 | 0.72704 | 0.26766 | 0.0052962
18148017 | 2018-11-07 |  | 380633 | 268059 | 3971026.9633 | 3974717.98 | 30963 | 17638.5 | 0.79776 | 0.20224 | 0
18148018 | 2018-10-01 | 2019-07-15 | 62106.92 | 27 | 3595246.068 | 3243067.17 | 16310 | 19176 | 0.76222 | 0.23778 | 0
18148019 | 2018-10-10 |  | 25796.1 | 66 | 2885517.1479 | 2499907.38 | 11969 | 9748 | 0.81755 | 0.18245 | 0
18148020, 18146021, 18141012 | 2018-10-15 | 2020-04-21 | 932196 | 629347 | 82317048.6474 | 86038950.47 | 125753.5 | 148599.14 | 0.76472 | 0.23524 | 4.4878e-05
18148021 | 2018-07-01 | 2018-11-30 | 0 | 0 | 56954.05 | 57389.61
18148022 | 2019-02-07 |  | 392575 | 369971 | 11293157.212 | 11120143.88 | 27925 | 50651.08 | 0.81662 | 0.18327 | 0.00010859
18148023 | 2019-01-17 |  | 326510 | 157965 | 3346521.02 | 3488770.83 | 9950 | 14615 | 0.8168 | 0.1832 | 0
18150001 | 2018-03-08 | 2021-07-31 | 1330950.62 | 1277642 | 110010384.6157 | 109128213.66 | 81372.1 | 70865 | 0.85246 | 0.14748 | 5.6445e-05
18150001-152 | 2017-01-01 |  | 0 | 0 | 120727281 | 0
18150002 |  |  | 0 | 0 | 190621 | 168018.96
18150004-168, 18150004 | 2019-01-03 | 2020-01-30 | 24458 | 0 | 21225331.88 | 21006106.2 | 2302.1 | 1979.75 | 0.43041 | 0.56959 | 0
18150006 | 2018-05-14 | 2022-12-31 | 0 | 0 | 0.01 | -4.5475e-13
18150006-172 |  |  | 0 | 0 | 0.01 | 0
18150007 | 2018-08-06 | 2018-04-01 | 0 | 0 | 4158775.0441 | 4149691.11
18150008 |  | 2021-03-01 | 0 | 0 | 23458451.23 | 21616087.68
18150008-169 |  |  | 92295 | 0 | 271238809.6167 | 261730943.82 | 153676.65 | 67301.75 | 0.94852 | 0.051485 | 0
18150009 | 2018-12-01 | 2019-08-01 | 0 | 0 | 1334535.94 | 843049.28
18150009-152 | 2018-12-01 |  | 0 | 0 | 20560716 | 0
18801 | 2001-05-31 |  | 0 | 0 | 167966 | 190931 | 0 | 884 | 1899-12-31 | 0 | 0
18802 | 2001-12-31 |  | 0 | 0 | 14862 | 14862 | 0 | 88 | 1899-12-31 | 0 | 0
18803 | 2001-12-31 |  | 0 | 0 | 55492 | 58416 | 0 | 33 | 1899-12-31 | 0 | 0
18804 | 2001-12-31 |  | 0 | 0 | 0 | 3222 | 0 | 4 | 1899-12-31 | 0 | 0
18805 |  | 2001-11-15 | 110060 | 107796 | 6791769 | 6803509 | 0 | 5073 | 1899-12-31 | 0 | 0
18806 | 2001-12-01 | 2001-10-12 | 112312 | 51910 | 11413621 | 11407031 | 0 | 11555 | 1899-12-31 | 0 | 0
18807 | 2001-11-16 | 2001-09-28 | 773243 | 2806 | 2759073 | 2762007 | 0 | 3608 | 1899-12-31 | 0 | 0
18808 | 2001-05-25 |  | 0 | 0 | 250335 | 262046 | 0 | 1048 | 1899-12-31 | 0 | 0
18809 | 2002-06-01 | 2001-05-24 | 204 | 0 | 5778285 | 5786677 | 0 | 5067 | 1899-12-31 | 0 | 0
18810 | 2001-09-20 | 2001-09-20 | 301 | 177 | 670195 | 792433 | 0 | 5241 | 1899-12-31 | 0 | 0
18811 | 2001-09-01 | 2001-09-01 | 5406 | 3337 | 381592 | 384111 | 0 | 748 | 1899-12-31 | 0 | 0
18813 | 2001-11-19 |  | 371 | 280 | 1454462 | 1455998 | 0 | 8408 | 1899-12-31 | 0 | 0
18814 | 2001-12-31 |  | 41475 | 37244 | 7025326 | 7029855 | 0 | 30037 | 1899-12-31 | 0 | 0
18815 | 2001-10-10 |  | 271 | 0 | 19676 | 19785 | 0 | 246 | 1899-12-31 | 0 | 0
18816 | 2002-11-30 |  | 0 | 0 | 63529 | 63528 | 0 | 166 | 1899-12-31 | 0 | 0
18817 | 2002-11-30 |  | 0 | 0 | 0 | 648 | 0 | 0 | 0 | 0 | 0
18818 | 2002-06-01 |  | 0 | 0 | 3114471 | 3111317 | 0 | 54 | 1899-12-31 | 0 | 0
18819 | 2003-12-15 | 2003-10-31 | 3422358 | 60949 | 18012075 | 18012744 | 0 | 65664 | 1899-12-31 | 0 | 0
18899 | 2001-12-31 |  | 0 | 0 | 0 | 157013 | 0 | 212 | 1899-12-31 | 0 | 0
19000004-040, 19060011, 19060050 | 2019-10-01 | 2021-07-30 | 1425129.76 | 901624 | 63571196.2096 | 60986420.22 | 82353.96 | 86787 | 0.77586 | 0.22414 | 0
19030001 | 2019-01-01 | 2019-12-31 | 0 | 0 | 1183843.94 | 1195962.18 | 0 | 3955.5 | 0.9234 | 0.059158 | 0.017444
19030002 | 2019-01-01 | 2019-12-31 | 0 | 0 | 5931787.07 | 5931786.98 | 0 | 28840.13 | 0.91432 | 0.079819 | 0.0058599
19030003 | 2018-12-18 | 2019-01-30 | 0 | 0 | 57490.57 | 58670.45 | 120 | 122.67 | 1899-12-31 | 0 | 0
19030004 | 2019-01-14 | 2019-04-01 | 0 | 0 | 1153212.51 | 1091074.17 | 1169 | 1360.5 | 0.99081 | 0.0091878 | 0
19030007 | 2019-04-01 | 2019-08-23 | 56190.15 | 44002 | 3080257.51 | 3115299.79 | 4892.7 | 4294.5 | 0.99173 | 0.0064035 | 0.0018628
19030008 | 2019-06-07 | 2021-03-26 | 285346.52 | 158967 | 12809997.99 | 13215131.1 | 21088.7 | 24339.47 | 0.98205 | 0.017954 | 0
19030009 | 2018-12-26 | 2019-03-15 | 162 | 0 | 153627 | 124661.48 | 90 | 60 | 0.96667 | 0.033333 | 0
19030010 | 2018-12-26 | 2019-07-31 | 9988.6 | 0 | 2850440 | 2774861.37 | 7605.6 | 5283 | 0.95694 | 0.041548 | 0.0015143
19030011 | 2018-11-19 | 2019-04-12 | 0 | 0 | 465273.48 | 438167.06 | 1919 | 2242.5 | 0.93712 | 0.062876 | 0
19030012 | 2019-10-01 | 2020-04-01 | 304175 | 81018 | 14667001.55 | 14705950.41 | 11380.6 | 15200 | 0.92957 | 0.069901 | 0.00052632
19030013 | 2019-05-01 | 2019-12-31 | 672 | 176 | 293976.8603 | 338402.5 | 1412 | -1976.67 | 1899-12-31 00:55 | -0.034907 | -0.0035413
19030014 | 2019-02-04 | 2019-04-30 | 1 | 0 | 22446.11 | 23268.41 | 93.5 | 88.5 | 1899-12-31 | 0 | 0
19030015 | 2019-06-03 | 2020-08-11 | 329537.79 | 151810 | 7878956.5 | 8008407.3 | 20134.8 | 23567.67 | 0.96538 | 0.034454 | 0.00016972
19030016 | 2019-06-01 | 2020-08-01 | 618522.4 | 49852 | 73830787.48 | 73280737.43 | 17569.6 | 18158.25 | 0.7458 | 0.24665 | 0.0075448
19030017 | 2019-04-29 | 2020-08-28 | 244252.26 | 71670 | 24308389.436 | 24540639.65 | 27721.1 | 25587.5 | 0.94818 | 0.050806 | 0.0010161
19030018 | 2019-02-01 | 2019-02-08 | 0 | 0 | 248246.7 | 248183.54 | 1491.12 | 1509.12 | 0.99172 | 0.008283 | 0
19030019 | 2019-03-25 |  | 465679.69 | 255850 | 29126742.19 | 23708234.37 | 46461.6 | 37041.5 | 0.76219 | 0.23698 | 0.0008369
19030020 |  |  | 1 | 0 | 580589.39 | 570438.74 | 1008 | 972.25 | 0.97814 | 0.021857 | 0
19030023 | 2019-09-20 | 2019-12-09 | 6500 | 0 | 1642487.08 | 1494179.26 | 477.7 | 575.5 | 0.98089 | 0.019114 | 0
19030024 | 2019-08-28 | 2019-11-22 | 3769 | 0 | 487657.41 | 480722.05 | 370.9 | 376 | 0.98936 | 0.010638 | 0
19030025 | 2019-04-08 |  | 12866.73 | 0 | 626547.91 | 594479.42 | 1792 | 2011.91 | 0.94682 | 0.049704 | 0.0034793
19030026 | 2019-05-06 | 2019-08-16 | 23 | 55 | 1628183.68 | 1587808.57 | 1642 | 2212.5 | 0.98373 | 0.016271 | 0
19030027 | 2020-02-01 | 2022-02-28 | 0 | 0 | 45162 | 29437.12
19030028 | 2019-05-13 | 2019-09-03 | 144 | 0 | 1966531.44 | 1994000.38 | 1622 | 1073 | 0.94408 | 0.055918 | 0
19030029 | 2019-06-20 | 2019-07-20 | 0 | 0 | 87035.11 | 84375.88 | 56 | 56.5 | 0.99115 | 0.0088496 | 0
19030030 |  |  | 0 | 0 | 5144.07 | 2555.54 | 0 | 2 | 1899-12-31 | 0 | 0
19030031 |  |  | 166138.73 | 162096 | 18068311.0773 | 18541618.88 | 13610.46 | 18975.03 | 0.93845 | 0.057312 | 0.0042424
19030032 |  |  | 1685.44 | 7744 | 154428.93 | 198867.86 | 1057 | 1480 | 0.98885 | 0.011149 | 0
19030033 |  |  | 5936.3 | 46463 | 2375901.465 | 2599923.32 | 8021.85 | 20326.5 | 0.97245 | 0.02755 | 0
19030034 |  |  | 0 | 0 | 310282.82 | 284135.24 | 1178 | 1072 | 0.9958 | 0.0041978 | 0
19030035 |  |  | 37271.98 | 538 | 2563800.62 | 2676798.78 | 1745.8 | 1807.5 | 0.99059 | 0.0094053 | 0
19030036 |  |  | 2331.5 | 0 | 787037.48 | 806418.83 | 1606 | 2580.12 | 0.98256 | 0.017441 | 0
19030037 |  |  | 0 | 0 | 1835650.57 | 1689610.63 | 1299 | 946 | 0.9593 | 0.040698 | 0
19030041 |  |  | 57442 | 24500 | 1436814.4 | 1203465.54 | 5739 | 3875.5 | 0.96839 | 0.031609 | 0
19030042 |  |  | 2700 | 0 | 773327.59 | 642898.62 | 228 | -2258.56 | 1899-12-31 | 0 | 0
19030043 |  |  | 100 | 0 | 12264 | 10163.94 | 96 | 87 | 0.65517 | 0.34483 | 0
19030045 |  |  | 0 | 0 | 228629.01 | 189786.27 | 712 | 633.51 | 0.96054 | 0.039463 | 0
19030046 |  |  | 0 | 0 | 3865381.46 | 3901247.53 | 4393 | 3205 | 0.94399 | 0.05351 | 0.0024961
19030047 |  |  | 840474.7 | 486589 | 41771089.0525 | 42837255.71 | 36681.16 | 39465.5 | 0.85618 | 0.13418 | 0.0096413
19030048 |  |  | 26 | 1367 | 2577737.29 | 2522789.04 | 3431 | 2923.5 | 0.97896 | 0.021036 | 0
19030049 |  |  | 447 | 0 | 860803.8 | 851608.72 | 1555 | 1805.5 | 0.78704 | 0.21296 | 0
19030050 |  |  | 11610 | 2 | 1940696.9956 | 1816438.99 | 2730 | 6404.25 | 0.8476 | 0.11243 | 0.039973
19030051 |  |  | -171 | 0 | 263845.4 | 227920.29 | 760 | 529.1 | 0.7165 | 0.2835 | 0
19030052 |  |  | 19535.81 | 0 | 1328799.34 | 1313217.8 | 1918.4 | 2076 | 0.86729 | 0.11681 | 0.015896
19030053 |  |  | 140914.33 | 18252 | 7816003.71 | 7816377.5 | 3763.5 | -4472.5 | 1899-12-31 00:16 | -0.011179 | 0
19030054 |  |  | 0 | 0 | 79746.31 | 80222.53 | 0 | 197 | 0.99746 | 0.0025381 | 0
19030055 |  |  | 0 | 0 | 0.01 | 1727.08
19030056 |  |  | 0 | 0 | 9858 | 7910.64
19030057 |  |  | 0 | 143 | 270725.01 | 215908.15 | 752 | 277.5 | 0.92793 | 0.072072 | 0
19030058 |  |  | 49 | 0 | 475310.57 | 433110.94 | 714 | 792.3 | 0.97791 | 0.022088 | 0
19030059 |  |  | 95 | 0 | 656000.81 | 669274.32 | 1939 | 2418 | 0.99711 | 0.002895 | 0
19030060 |  |  | 13917.75 | 0 | 338244.75 | 363611.97 | 279 | 444.5 | 0.88751 | 0.058493 | 0.053993
19030061 |  |  | 0 | 0 | 824534.07 | 710092.68 | 769 | 629.5 | 0.94599 | 0.054011 | 0
19030062 |  |  | 0 | 0 | 142152.87 | 112400.96 | 348 | 126 | 1899-12-31 | 0 | 0
19030063 |  |  | 13194 | 0 | 25268403.42 | 15722369.4 | 3796 | 3315 | 0.99879 | 0.0012066 | 0
19030064 |  |  | 3 | 0 | 163426.34 | 137844.43 | 6662 | 516 | 0.94961 | 0.050388 | 0
19030065 |  |  | 81.3 | 0 | 16010.97 | 23402.08 | 3.5 | 205.5 | 0.99757 | 0.0024331 | 0
19030066 |  |  | 199 | 0 | 51803.62 | 49823.46 | 199 | 175.5 | 0.82906 | 0.10256 | 0.068376
19030067 |  |  | 0 | 0 | 174525.475 | 187272.2 | 473.5 | 469 | 0.9968 | 0.0031983 | 0
19030068 |  |  | 0 | 0 | 15421.11 | 14807.12 | 0 | 58 | 1899-12-31 | 0 | 0
19030069 |  |  | 24789 | 0 | 1200437.96 | 1179091.57 | 2101 | 2467.5 | 0.96089 | 0.039108 | 0
19040001 | 2019-02-01 | 2019-04-30 | 0 | 0 | 2052182.52 | 2109691.89 | 16 | 2070 | 0.92705 | 0.072947 | 0
19040003 | 2019-01-14 |  | 0 | 0 | 0 | 0
19040004 | 2019-04-19 | 2020-10-31 | 866886.6 | 0 | 52557329.8 | 54088575.7 | 7855.6 | 9981.78 | 0.83705 | 0.16295 | 0
19040005 | 2019-05-13 |  | 15134 | 0 | 675373.22 | 676989.95 | 325 | 198 | 0.56566 | 0.43434 | 0
19040006 | 2019-04-22 | 2019-06-13 | 28483 | 0 | 860313.15 | 646017.31 | 406 | 1797.5 | 0.92712 | 0.072879 | 0
19040009 |  |  | 39277 | 0 | 4780233.33 | 4483800.27 | 252.7 | 2734.5 | 0.76906 | 0.23094 | 0
19040010 |  |  | 51744 | 28065 | 3012194.3 | 2951514.39 | 378 | 469.5 | 0.94675 | 0.053248 | 0
19040011, 19000009-040, 19040008 |  |  | 411681 | 0 | 42652161.53 | 41527318.84 | 7402.7 | 9248.5 | 0.92183 | 0.078175 | 0
19040012 |  |  | 0 | 0 | 101391.28 | 51871.39
19040013 |  |  | 0 | 0 | 19337.28 | 23241.98 | 0 | 35 | 0 | 1899-12-31 | 0
19040014 |  |  | 132338 | 132323 | 290311.7 | 290311.7 | 1649.9 | 1031 | 0.84481 | 0.15519 | 0
19040015 |  |  | 9376.35 | 9204 | 169215.44 | 191138.5 | 495.34 | 804.5 | 0.75078 | 0.24922 | 0
19050001 | 2019-07-03 |  | 1087.02 | 0 | 437069.7 | 425648.34 | 188.14 | 14.5 | 0.96552 | 0.034483 | 0
19050002 |  |  | 0 | 0 | 137465 | 335958.62
19050003 | 2019-04-01 | 2020-06-30 | 136839.13 | 4524 | 17740173.8161 | 17597139.51 | 9500.18 | 8387.74 | 0.93031 | 0.046973 | 0.022712
19050004 | 2019-06-01 | 2019-11-30 | 28881 | 2539 | 2754581.2704 | 2704985.13 | 2127.9 | 1334.5 | 0.82578 | 0.15961 | 0.014612
19050005 |  |  | 37439 | 27647 | 4247299.99 | 5055867.73 | 2415.5 | 4868.5 | 0.91168 | 0.088323 | 0
19050006 |  |  | 28091.83 | 512 | 2164348.51 | 2182750.8 | 1865.7 | 1430.5 | 0.92415 | 0.075848 | 0
19050008 |  |  | 63389.44 | 0 | 72755363.94 | 3168457.52 | 15160.9 | 204.5 | 0.98289 | 0.017115 | 0
19050009 |  |  | 1072945.67 | 140650.24 | 96311699.8813 | 28941755.3 | 38701.07 | 26975.6 | 0.89166 | 0.1062 | 0.0021408
19050010 |  |  | 251285.87 | 251420.5 | 32289406.89 | 29723115.06 | 14129.1 | 14750.93 | 0.90753 | 0.0883 | 0.0041692
19050011 |  |  | 0 | 0 | 86168.42 | 77314.79
19050012 |  |  | 27 | 0 | 435303.2 | 113067.32
19050050 |  |  | 2516.25 | 0 | 276180.1139 | 263242.9 | 343.83 | 310.14 | 0.87909 | 0.12091 | 0
19050051 |  |  | 0 | 0 | 17519.65 | 17323.64
19055001, 19040007 |  |  | 317062.18 | 140956 | 47394067.5277 | 46808661.16 | 32102.32 | 33376 | 0.96944 | 0.030561 | 0
19055002 |  |  | 0 | 0 | 25179 | 27381.66
19055003 |  |  | 0 | 1 | 0.01 | -1.819e-11 | 0 | 1258.5 | 0.9265 | 0.063965 | 0.0095352
19055004 |  |  | 0 | 0 | 15550.28 | 27085.81
19055005 |  |  | 0 | 0 | 8478.2 | 26433.69
19055006 |  |  | 0 | 0 | 9677.63 | 37206.59
19055007 |  |  | 0 | 0 | 14025.08 | 19965.18
19055008 |  |  | 7 | 0 | 38862.7068 | 30814.83
19055009 |  |  | 7905.27 | 62 | 4349423.72 | 4243450.79 | 3349.08 | 3035 | 0.91351 | 0.06458 | 0.021911
19055010 |  |  | 1023.5 | 0 | 600386 | 510388.04 | 12 | 936 | 1899-12-31 | 0 | 0
19055011 |  |  | 13 | 0 | 18630.335 | 17407.17 | 83.5 | 80 | 0.75 | 0.25 | 0
19055012 |  |  | 0 | 0 | 8101.13 | 7733.51
19055013 |  |  | 0 | 0 | 52803.62 | 98542.34
19055014 |  |  | 0 | 0 | 0.01 | 99724.76
19055015 |  |  | 10 | 1917 | 989464.84 | 1000865.51 | 1312 | 1726.07 | 0.98957 | 0.010428 | 0
19055016 |  |  | 66119.54 | 20740 | 7126171.0652 | 7125196.57 | 3135.7 | 4444.22 | 0.99707 | 0.0029251 | 0
19055017 |  |  | 91099 | 60838 | 18163149.8269 | 19493310.15 | 17511.43 | 25566.5 | 0.91835 | 0.081087 | 0.00056715
19055018 |  |  | 10 | 0 | 2126.33 | 7171.97
19055019 |  |  | 10 | 0 | 14126.88 | 14811.24
19055020 |  |  | 16645.57 | 0 | 371528.25 | 396692.18 | 397.5 | 962 | 0.921 | 0.079002 | 0
19055021 |  |  | 25 | 0 | 1434196.01 | 1282385.57
19055022 |  |  | 0 | 0 | 0.01 | 0
19055023 |  |  | 10 | 0 | 2482.32 | 179.99
19055024 |  |  | 86 | 0 | 217233.4 | 217295.4 | 718 | 671.5 | 0.94639 | 0.035741 | 0.01787
19055025 |  |  | 0 | 0 | 65000 | 75001.66 | 0 | 64 | 1899-12-31 | 0 | 0
19055026 |  |  | 593794.97 | 324119.72 | 53872853 | 54754503.18 | 30200.08 | 27665.07 | 0.91516 | 0.084154 | 0.00068679
19055027 |  |  | 1 | 3 | 12391 | 9730.81 | 86 | 79.5 | 0.85535 | 0.14465 | 0
19055028 |  |  | 0 | 0 | 5683.64 | 8390.76
19060001 | 2019-01-04 | 2020-01-31 | 0 | 0 | 14581 | 8189.67
19060004 | 2019-02-01 | 2019-05-31 | 806 | 131 | 114074.67 | 115357.82 | 659 | 263 | 0.89544 | 0.10456 | 0
19060005 | 2019-01-01 | 2019-02-01 | 0 | 0 | 15000 | 723.88
19060006 | 2019-01-18 | 2019-05-13 | 3 | 0 | 72800.3 | 54854.86 | 255 | 468 | 0.9594 | 0.040598 | 0
19060007 | 2019-04-01 | 2019-12-31 | 1 | 0 | 577344.9974 | 605189.41 | 482 | 215 | 0.99302 | 0.0069767 | 0
19060008 | 2019-01-21 | 2019-05-01 | 23 | 60 | 11602.45 | 17612.03 | 59 | 67 | 0.9403 | 0.059701 | 0
19060009 | 2019-01-28 | 2019-12-31 | 623 | 164 | 296952.6886 | 304539.71 | 376 | 1486.5 | 0.89842 | 0.10158 | 0
19060010 | 2019-04-01 | 2020-01-13 | 640445.45 | 136268 | 13066982.97 | 16418354.06 | 49488 | 78835.25 | 0.76092 | 0.23908 | 0
19060012 | 2019-02-18 | 2019-12-31 | 20890.82 | 381 | 2581422.57 | 2784058.73 | 1615.6 | 5406 | 0.85146 | 0.14854 | 0
19060013 | 2019-01-01 | 2019-11-01 | 0 | 0 | 1047603.87 | 1362052.02
19060014 | 2019-03-01 | 2019-05-31 | 0 | 0 | 3623 | 4740.61 | 0 | 48 | 0.875 | 0.125 | 0
19060016 | 2019-01-01 | 2019-12-01 | 0 | 0 | 550796.11 | 550833.01
19060017 | 2019-04-01 | 2019-05-31 | 4774 | 0 | 188595.302 | 189569.48 | 1939.9 | 493 | 0.94726 | 0.052738 | 0
19060018 | 2019-04-09 | 2019-08-30 | 0 | 0 | 0.01 | 0
19060019 | 2019-04-22 | 2020-12-07 | 161115 | 10769 | 5696911.17 | 5833592.67 | 14595.1 | 14192 | 0.93458 | 0.065424 | 0
19060020 | 2019-08-01 | 2020-05-01 | 0 | 0 | 373718 | 391969.66
19060021 |  |  | 208 | 966 | 545405.22 | 534210.78 | 1093 | 1144 | 0.89248 | 0.10752 | 0
19060022 |  | 2020-03-20 | 951312.66 | 619504 | 37503685.44 | 37496766.89 | 40684.6 | 43022.75 | 0.79526 | 0.20474 | 0
19060023 |  | 2020-07-30 | 0 | 0 | 989999.7 | 982037.74 | 3750 | 4389 | 0.96389 | 0.036113 | 0
19060024 |  | 2019-08-30 | 0 | 1080 | 2634323.61 | 2756130.24 | 366.4 | 4101.5 | 0.8136 | 0.1864 | 0
19060025 | 2019-04-15 | 2019-09-01 | 0 | 0 | 1716388.6 | 1719292.77
19060026 | 2019-01-01 | 2019-11-01 | 0 | 0 | 113845 | 113683.93 | 0 | 0 | 0 | 0 | 0
19060027 | 2019-04-15 | 2019-09-01 | 0 | 0 | 0 | -4019.17
19060028 |  |  | 645 | 485 | 139267 | 137480.09 | 496 | 580 | 0.8319 | 0.1681 | 0
19060029 | 2019-06-01 | 2020-10-28 | 390843.08 | 508776 | 11411748.85 | 16364311.16 | 29700 | 56951 | 0.7804 | 0.2196 | 0
19060030 |  | 2019-11-22 | 28482.12 | 3000 | 1965241.06 | 2063237.22 | 2238.8 | 5802.5 | 0.89798 | 0.10202 | 0
19060031 | 2019-06-01 | 2019-10-23 | 22211.76 | 1098 | 921833.42 | 952097.42 | 1556 | 2835 | 0.83228 | 0.16772 | 0
19060032 | 2019-05-13 |  | 805066.67 | 504514 | 9328049.1802 | 9525803.24 | 31067.3 | 39861.5 | 0.90601 | 0.093988 | 0
19060033 | 2019-06-01 |  | 680666 | 538230 | 7678608.05 | 9922862.33 | 30212 | 33318.25 | 0.73358 | 0.26642 | 0
19060034 |  |  | 726 | 38 | 47971.89 | 55450.63 | 386 | 915 | 0.93825 | 0.061749 | 0
19060035 | 2019-06-03 |  | 45194.23 | 6095 | 408984.1836 | 592613.79 | 1992.6 | 6347.25 | 0.90464 | 0.095356 | 0
19060036 | 2019-05-28 |  | 680 | 1698 | 379634.9519 | 363623.85 | 2431 | 2033 | 0.88342 | 0.11658 | 0
19060037 | 2019-06-11 |  | 10344.5 | 733 | 1119652.13 | 1143292.4 | 3602.9 | 4558 | 0.82624 | 0.17376 | 0
19060039 |  |  | 0 | 0 | 993427.08 | 1006897.9
19060040 |  |  | 0 | 0 | 288787.56 | 292278.41
19060041 |  |  | 0 | 0 | 1250487.21 | 1203634.48
19060042 |  |  | 0 | 0 | 258288.13 | 218163.75
19060043 |  |  | 0 | 0 | 1056671.35 | 1052695.36
19060044 |  |  | 0 | 0 | 449931 | 434233.29 | 0 | 0 | 0 | 0 | 0
19060045 |  |  | 6374.75 | 197 | 645233.33 | 647319.16 | 1962.25 | 2495 | 0.80261 | 0.19739 | 0
19060046 |  |  | 83036.51 | 33978 | 6724028.6001 | 7057229.1 | 7715 | 13973.75 | 0.93332 | 0.066679 | 0
19060047 |  |  | 14104 | 0 | 7378488.554 | 7798534.7 | 2692.7 | 6669.5 | 0.87518 | 0.12482 | 0
19060048 |  |  | 413792.08 | 274634 | 23041045.9973 | 21329306.63 | 10977.74 | 15396 | 0.92167 | 0.078332 | 0
19060049 |  |  | 0 | 17 | 31708.98 | 29552.42 | 90 | 62.5 | 0.848 | 0.152 | 0
19060051 |  |  | 571 | 0 | 87336.73 | 87174.88 | 284 | 11.5 | 1899-12-31 | 0 | 0
19060052 |  |  | 7634.3 | 48 | 194753.43 | 195313.34 | 547.3 | 837 | 0.91756 | 0.082437 | 0
19060053 |  |  | 19270.9 | 813.01 | 2872294.45 | 3035264.14 | 3434.4 | 5341 | 0.86791 | 0.13209 | 0
19060054 |  |  | 18 | 0 | 630303.94 | 722041.46 | 0 | 382.5 | 0.96863 | 0.031373 | 0
19060055 |  |  | 7 | 0 | 35811.53 | 87131.89
19060056 |  |  | 407978.68 | 385712 | 27867060.6733 | 25199542.43 | 18696.82 | 21154.5 | 0.84041 | 0.15959 | 0
19060057 |  |  | 150 | 0 | 196358 | 224627.26 | 190 | 1005.5 | 0.96917 | 0.03083 | 0
19060058 |  |  | 0 | 0 | 155451 | 136983.91 | 0 | 0 | 0 | 0 | 0
19060059 |  |  | 16 | 897 | 117912 | 104174.05 | 1068 | 991.5 | 0.86737 | 0.13263 | 0
19060060 |  |  | 40 | 0 | 10084.04 | 11550 | 24 | 11 | 0.81818 | 0.18182 | 0
19060061 |  |  | 274 | 20 | 3746503.24 | 3779296.61 | 141 | 506 | 0.91798 | 0.082016 | 0
19060062 |  |  | 1186.2 | 0 | 188217.95 | 195479.25 | 577.2 | 681.5 | 0.92443 | 0.075569 | 0
19060063 |  |  | 42205.76 | 32930 | 1359904.93 | 1371069.51 | 1347.37 | 3804.5 | 0.96885 | 0.031147 | 0
19060064 |  |  | 518 | 316 | 107239 | 107688.91 | 469 | 377 | 0.70027 | 0.29973 | 0
19060065 |  |  | 20486.98 | 8745 | 447251.4 | 453264.77 | 681.76 | 785 | 0.98217 | 0.017834 | 0
19060066 |  |  | 102 | 8 | 163741.01 | 158065.27 | 250 | 223.5 | 0.74944 | 0.25056 | 0
19060067 |  |  | 1643 | 0 | 263938.35 | 271346.75 | 294 | 297 | 0.96633 | 0.03367 | 0
19060068 |  |  | 87525.86 | 68225 | 2344338.0664 | 2235089.69 | 2546.23 | 5471 | 0.92332 | 0.076677 | 0
19060069 |  |  | 3008 | 0 | 505079.7 | 543292.25 | 0 | 129.5 | 1899-12-31 | 0 | 0
19060070 |  |  | 20 | 29 | 44534.96 | 45402.4 | 14 | 446.5 | 0.94401 | 0.055991 | 0
19060071 |  |  | 415.4 | 3 | 7377.48 | 8906.69 | 108 | 135.5 | 0.80812 | 0.19188 | 0
19060072 |  |  | 0 | 0 | 117753 | 107949.02
19080001 | 2019-08-19 |  | 59108.29 | 29143 | 2411723.6 | 2442581.47 | 4503.7 | 5281 | 0.91924 | 0.076974 | 0.0037872
19080002 | 2019-01-21 | 2019-05-01 | 399 | 0 | 2844848.48 | 2925976.3 | 255 | 244 | 0.85041 | 0.14959 | 0
19080003 | 2019-04-08 | 2020-04-01 | 11 | 0 | 1026419.09 | 873427.94
19080005 | 2019-04-24 |  | -629 | 0 | 134814 | 133707.23 | 222 | 284 | 0.99648 | 0.0035211 | 0
19080006 |  |  | 798 | 0 | 389652.51 | 432638.98
19080007 |  |  | 0 | 0 | 780332.76 | 752558.71 | 336 | 320.5 | 0.97816 | 0.021841 | 0
19080008 |  |  | 932338.65 | 480130 | 33721466.0641 | 33553251.03 | 31572.55 | 37454.76 | 0.94706 | 0.05221 | 0.00073422
19080009 |  |  | 272800.48 | 84647 | 54236408.285 | 50134415.87 | 22824.2 | 18407.32 | 0.93005 | 0.069619 | 0.00032596
19080010 |  |  | 1754202.8 | 0 | 22381147.4609 | 7482637.39 | 51528.25 | 6140.75 | 0.92863 | 0.071368 | 0
19080010-142 |  |  | 3257817.75 | 0 | 247499802.01 | 54945585.08 | 179963.65 | 34311.75 | 0.9314 | 0.068599 | 0
19080011 |  |  | 116775.18 | 4461 | 25850702.64 | 24448211.59 | 7086.7 | 5946.44 | 0.9424 | 0.056084 | 0.0015135
19080012 |  |  | 379095.06 | 201052 | 30104819.1441 | 28841788.63 | 25501.13 | 22997.89 | 0.92444 | 0.072257 | 0.0033047
19080013 |  |  | 139 | 0 | 543664 | 474232.58 | 889 | 1050.5 | 0.87387 | 0.12613 | 0
19080014 |  |  | 14731.43 | 5459 | 665251.35 | 655560.2 | 1364.4 | 1616.96 | 0.87878 | 0.11256 | 0.0086582
19090001 | 2019-07-01 | 2023-08-01 | 404891 | 8487 | 62164929.9174 | 59937279.78 | 13485.14 | 15106.5 | 0.82978 | 0.1556 | 0.014629
19090003 | 2019-04-01 | 2020-03-31 | 1003 | 0 | 3699934.8662 | 3581834.83
19090004 |  |  | 48241.31 | 26084 | 2037118.27 | 1982613.9 | 1256.8 | 2064.82 | 0.94624 | 0.049399 | 0.0043587
19090005 |  |  | 131 | 72 | 406575.337 | 383782.71 | 586.2 | 367 | 0.73569 | 0.17711 | 0.087193
19090006 |  |  | 9253.09 | 8 | 2426682.7 | 2368572.29 | 1991.5 | 2052.18 | 0.96126 | 0.034841 | 0.0038983
19090007 |  |  | 15746.66 | 0 | 7654407.12 | 7392185.3 | 937.6 | 1144.5 | 0.76715 | 0.18174 | 0.051114
19090008 |  |  | 211476 | 27223 | 2849752.81 | 3198251.8 | 5076.8 | 3165.93 | 0.92482 | 0.07028 | 0.0048959
19090009 |  |  | 36357 | 68749 | -1.1096e-10 | -2.0009e-11 | 10940.2 | 16207.5 | 0.9603 | 0.039704 | 0
19090010 |  |  | 2 | 0 | 99206 | 92121.42
19090013 |  |  | 939 | 4 | 852998.52 | 800318.26 | 716.4 | 618 | 0.98382 | 0.016181 | 0
19090014 |  |  | 0 | 0 | 0 | 187322.42
19090015 |  |  | 240 | 0 | 5212945.88 | 5075152.99 | 477 | 2452.21 | 0.96554 | 0.029361 | 0.0050974
19090016 |  |  | 0 | 0 | 171600 | 170759.62
19090017 |  |  | 0 | 0 | 10644 | 8364.5 | 0 | 97 | 0.56701 | 0.43299 | 0
19090018 |  |  | 0 | 0 | 133111 | 116203.75
19090019 |  |  | 14989.54 | 2 | 3529523 | 3326029.69 | 12548.01 | 4826.5 | 0.85787 | 0.095307 | 0.046825
19090020 |  |  | 1717 | 2302 | 9548207.72 | 9409335.95 | 1600 | 2740.5 | 0.93596 | 0.060755 | 0.0032841
19090021 |  |  | 35410 | 3530 | 2497110.18 | 2505412.74 | 1717.1 | 2046.81 | 0.85245 | 0.13142 | 0.016123
19090991 | 2019-01-01 | 2020-12-31 | 1921 | 2990 | 226487 | 617038.24 | 1044 | 3479.45 | 0.99396 | 0.0060354 | 0
19110001, 20060028, 20060006 | 2019-06-01 | 2021-03-11 | 154639.11 | 226979 | 35185328.1704 | 37484339.04 | 13670.9 | 15082 | 0.31052 | 0.022809 | 0
19110002 | 2019-01-22 |  | 0 | 0 | 480502.98 | 476462.67
19110003 | 2019-01-01 | 2019-08-09 | 0 | 0 | 1397721 | 2.3283e-10
19110004 | 2019-07-23 |  | 0 | 0 | 6368367.24 | 6163361.79
19110005 |  |  | 0 | 0 | 11647008.7092 | 11323043.26 | 0 | 204.38 | 1899-12-31 | 0 | 0
19110006 |  |  | 0 | 0 | 29756 | 25057.29
19110007 |  |  | 0 | 0 | 9533937.67 | 8969127.07 | 0 | 6562.8 | 0.96518 | 0.034817 | 0
19110008 |  |  | 0 | 0 | 1695708.01 | 1713953.87
19110009 |  |  | 1069 | 0 | 1712771.19 | 1715331.6
19110010 |  |  | 31 | 0 | 559684.13 | 539831.79 | 720 | 499 | 0.96192 | 0.038076 | 0
19110011 |  |  | 0 | 0 | 1519681.85 | 1552119.32
19110012 |  |  | 0 | 0 | 534882.45 | 533882.49
19110013 |  |  | 0 | 0 | 476396 | 474224.18
19110014 |  |  | 0 | 0 | 175944 | 175192.86
19110015 |  |  | 0 | 0 | 30740 | 30685.87
19110016 |  |  | 0 | 0 | 2088584.92 | 2090174.68
19126001 |  |  | 1558763 | 465739.4 | 371701186.5858 | 343485684.59 | 226102.38 | 202813.27 | 0.83506 | 0.16491 | 2.4653e-05
19141001 | 2019-01-16 | 2019-06-01 | 201 | 0 | 6142681.54 | 4745100.21 | 11000 | 16249.41 | 0.80128 | 0.19872 | 0
19141006 | 2019-04-01 |  | 985 | 653 | 41536655.3954 | 42469063.22 | 15115 | 23045.83 | 0.74068 | 0.25555 | 0.0037751
19141007 | 2019-04-08 |  | 1892 | 1319 | 21862755.19 | 20546946.85 | 64943 | 85423.35 | 0.83075 | 0.16925 | 0
19141008 | 2019-05-06 |  | 7865.03 | 1418 | 10847149.8772 | 12120383.82 | 25890 | 68228.75 | 0.80837 | 0.19163 | 0
19141009, 19148016 | 2019-06-24 |  | 11187440.35 | 387937 | 57172390.8 | 58448999.91 | 103336.36 | 114954.25 | 0.70953 | 0.25764 | 0.032838
19141013, 19146012, 19148017 | 2019-07-24 | 2020-06-29 | 11913662.35 | 1926435 | 110873217.068 | 117011342.13 | 227415.26 | 201771.28 | 0.81365 | 0.18625 | 0.00010027
19141014 |  |  | 0 | 0 | 142339.56 | 158060.5 | 0 | 3910.5 | 0.7375 | 0.2625 | 0
19141015, 19148011 | 2019-08-01 | 2020-11-09 | 1390735.84 | 1268271 | 140868699.7759 | 125260461.37 | 303389.13 | 203006 | 0.69007 | 0.30689 | 0.0030363
19141016 | 2019-04-01 | 2019-10-31 | 2007 | 1868 | 22677279.86 | 22181079.18 | 64928 | 88060.79 | 0.79217 | 0.20506 | 0.0027708
19141017, 19148023, 19146019 | 2019-07-01 |  | 17427360.32 | 1349530 | 159178653.5599 | 152741126.98 | 318844.58 | 294204.46 | 0.7935 | 0.2065 | 0
19141018 | 2020-04-06 | 2020-12-01 | 0 | 0 | 91100 | 72401.66
19141019 |  |  | 0 | 0 | 85133.31 | 97415.36
19141020 |  |  | 1239 | 1057 | 21240119.377 | 18119714.63 | 66402 | 69963 | 0.66071 | 0.29835 | 0.040936
19141021 |  |  | 3348 | 3320 | 27615741.0926 | 21741182.91 | 102553.7 | 87519.5 | 0.83972 | 0.16028 | 0
19141025 |  |  | 100 | 74 | 2860752.72 | 2072798.84 | 7890 | 8506 | 0.88755 | 0.11245 | 0
19141026 |  |  | 924 | 561 | 16892294.89 | 15241772.22 | 55711.5 | 54307.4 | 0.65636 | 0.27996 | 0.063684
19141028 |  |  | 0 | 0 | 2901231.78 | 1599588.68 | 0 | 10475.5 | 0.62541 | 0.25459 | 0.11999
19141029 |  |  | 11 | 4 | 102305.66 | 81696.08 | 6936 | 970 | 0.98711 | 0.012887 | 0
19145002, 19148010 | 2019-06-07 | 2019-12-31 | 7687668 | 1130118 | 22974852.33 | 22095579.78 | 90270 | 74350 | 0.81408 | 0.18592 | 0
19145003 | 2019-04-29 | 2019-09-06 | 23889 | 45190 | 1133919 | 1155307.69 | 8490 | 5605.5 | 0.81277 | 0.18723 | 0
19145004 | 2019-04-15 | 2019-08-02 | 142668 | 124605 | 2079297.81 | 1356520.36 | 33561 | 27333 | 0.88935 | 0.11065 | 0
19145005, 19146017, 20148007 | 2019-07-29 | 2020-06-05 | 6422338.82 | 2904647 | 65745033.45 | 71067106.72 | 234862.8 | 304977.75 | 0.89456 | 0.10544 | 0
19145007 | 2019-10-07 |  | 764 | 0 | 464146 | 329118.1 | 0 | 136.5 | 0.87912 | 0.12088 | 0
19145008, 19148024, 19146021 | 2019-04-15 | 2019-06-28 | 14115009.36 | 9080360 | 151545459.126 | 141551340.77 | 604064.28 | 536802.8 | 0.83742 | 0.16258 | 0
19145009 |  |  | 201 | 0 | 175448.3 | 93834.28
19145010 |  |  | 0 | 0 | 120897 | 61128.04
19145011 |  |  | 295 | 0 | 223137 | 216096.36 | 600 | 475.5 | 0.73756 | 0.26244 | 0
19145012, 20148009 |  |  | 5033277.45 | 3456486 | 42766304.59 | 48007603 | 216054.77 | 282221 | 0.86125 | 0.13875 | 0
19145013 |  |  | 0 | 0 | 82114.98 | 46874.07
19145014 |  |  | 3279971.59 | 3665057 | 58085762.41 | 63973749.54 | 237783.19 | 307536.68 | 0.8484 | 0.1516 | 0
19146001, 18141021, 19148002 | 2019-01-01 | 2020-06-26 | 4408079 | 2638775 | 154938088.5216 | 167694438.85 | 268070 | 345315.81 | 0.76863 | 0.23137 | 0
19146002 | 2019-01-21 | 2019-09-30 | 27312 | 14831 | 2132339.94 | 1952621.8 | 6459 | 6334.75 | 0.74447 | 0.25553 | 0
19146003, 19148003, 19145001 | 2019-01-14 | 2020-10-31 | 5489628.79 | 9563141 | 93871906.79 | 97323476.45 | 390504.27 | 425477.83 | 0.83042 | 0.16957 | 3.269e-06
19146005 | 2019-07-15 | 2019-10-15 | 94750 | 4579 | 1370711 | 1070694.75 | 10496 | 3434 | 0.82266 | 0.17734 | 0
19146006, 19141003, 19148013 | 2019-06-17 | 2020-10-01 | 4254735.62 | 592142 | 78863914.8076 | 80696835.16 | 179332.89 | 204255.75 | 0.82878 | 0.17122 | 0
19146007, 19148006, 19141002 | 2019-04-01 | 2019-11-23 | 1479412.07 | 458388 | 122901848.5238 | 115232288.15 | 176586.9 | 186459.25 | 0.70181 | 0.29437 | 0.0038215
19146008, 19141005, 19148020, 19146023, 19141024 | 2019-09-15 | 2020-08-01 | 8871808.68 | 927836 | 165014011.2716 | 159974791.5 | 204646.18 | 252287.77 | 0.82898 | 0.17102 | 0
19146009, 19141004, 19148019, 19146022, 19141022 | 2019-09-15 | 2020-06-01 | 8735346.17 | 800027 | 129062645.7346 | 124874802.01 | 443767.4 | 221863.13 | 0.79005 | 0.20995 | 0
19146010, 19141010, 19148015 | 2019-08-15 | 2020-06-09 | 8644853.4 | 431356 | 101678425.3796 | 103872596.09 | 164633.66 | 169893.5 | 0.72536 | 0.27068 | 0.0039634
19146011, 19141012, 19148009 | 2019-07-01 | 2019-11-18 | 3753651.08 | 264085 | 52433001.745 | 51529431.18 | 67155.52 | 86012.79 | 0.69218 | 0.289 | 0.018815
19146013 | 2020-03-01 | 2020-08-31 | 360838.11 | 255306 | 12485275.45 | 6221918.39 | 12680.7 | 3195 | 0.80235 | 0.19765 | 0
19146014 | 2019-04-01 | 2019-12-20 | 176562 | 22265 | 2575676.29 | 2574732.41 | 3004 | 5860 | 0.78242 | 0.21758 | 0
19146016 | 2019-07-08 | 2020-07-24 | 292464.06 | 229691 | 20736968.63 | 18007760.03 | 38673.11 | 39370.5 | 0.80504 | 0.19496 | 0
19146018 |  |  | 0 | 0 | 52999 | 11178.86
19146020 |  |  | 0 | 0 | 59383 | 38675.71
19146025 |  |  | 1002 | 2070 | 33138305.36 | 31564205.53 | 14842.42 | 25140.5 | 0.82454 | 0.17546 | 0
19148001 | 2019-03-18 | 2019-11-30 | 1174897 | 725358 | 17298436.15 | 18145102.16 | 73310 | 71736.5 | 0.7623 | 0.23448 | 0.0032201
19148004 | 2019-04-29 |  | 38432 | 14895 | 3482590.0852 | 3424152.57 | 20410 | 10501.5 | 0.83164 | 0.16836 | 0
19148007, 18145015 | 2019-04-22 |  | 3557414 | 3675800 | 50854750.75 | 60010869.19 | 225411.25 | 345435.2 | 0.78251 | 0.21749 | 0
19148012, 19146015, 19141011 | 2019-05-01 | 2020-09-01 | 21779060.63 | 2906178 | 217101666.77 | 213962039.96 | 465509.97 | 395517.66 | 0.77193 | 0.22807 | 0
19148014 |  |  | 18 | 332 | 2892275.6762 | 2620479.13 | 8781.5 | 10596.5 | 0.71559 | 0.27837 | 0.0060397
19148021, 19141027 |  |  | 21923487.66 | 2254731 | 135694867.4889 | 124042453.1 | 249648.04 | 188733.38 | 0.75444 | 0.24556 | 0
19148022, 19141023 |  |  | 13495808.04 | 784868 | 130534527.8488 | 104579126.58 | 150913.19 | 149623.48 | 0.7777 | 0.2164 | 0.0059001
19150001 |  |  | 0 | 0 | 1015000 | 521203.05
19150001-172 |  |  | 0 | 0 | 818284.98 | 1076955.99
19150002 |  |  | 0 | 266 | 59960055.21 | 48328399.81 | 0 | 0 | 0 | 0 | 0
19150002-164 |  |  | 5229427.56 | 0 | 484540873.8602 | 486561788 | 632534.38 | 698570.75 | 1899-12-31 | 0 | 0
19150002-ETH |  |  | 0 | 0 | 72185058 | 0
19150002-LOW |  |  | 0 | 0 | 19543600 | 0
19150002-STE |  |  | 0 | 0 | 58633641 | 0
19150004 |  |  | 675 | 0 | 37200138.7906 | 35488928.49 | 436 | 1052 | 0.86692 | 0.13308 | 0
19150005 |  |  | 0 | 0 | 109089 | 14993.57
19150006 |  |  | 0 | 0 | 856815.634 | 792904.98
19156001 |  |  | 0 | 0 | 42.78 | 15465646.54
19157001 |  |  | 0 | 0 | 2.08 | 7991830.8 | 0 | 201574.6 | 0.73348 | 0.26623 | 0.00029518
19157002 |  |  | 0 | 0 | 0.01 | 2660552.33 | 0 | 53580.5 | 0.69219 | 0.30781 | 0
19157003 |  |  | 0 | 0 | 0 | 168095.29 | 0 | 1681 | 0.88995 | 0.11005 | 0
19157004 |  |  | 0 | 0 | 0.03 | 5099160.71 | 0 | 115202.5 | 0.74809 | 0.25191 | 0
19157005 |  |  | 0 | 0 | 0.04 | 2962229.83 | 0 | 68787.52 | 0.84987 | 0.15013 | 0
19157006 |  |  | 0 | 0 | 57637.01 | 24483.74 | 272 | 273 | 0.87912 | 0.12088 | 0
19157007 |  |  | 0 | 0 | 0.02 | 614524.73 | 0 | 13468 | 0.75739 | 0.23935 | 0.003267
19157008 |  |  | 0 | 0 | 0 | 20953.12 | 0 | 262.5 | 0.62095 | 0.37905 | 0
19157009 |  |  | 0 | 0 | 0 | 18226.43 | 0 | 530.5 | 0.72667 | 0.27333 | 0
19157010 |  |  | 0 | 0 | 0 | 9369.28 | 0 | 182 | 0.92308 | 0.076923 | 0
19157011 |  |  | 0 | 0 | 0 | 74537.97 | 0 | 704.5 | 0.63591 | 0.36409 | 0
19157012 | 2019-04-15 |  | 0 | 0 | 433132.0001 | 246774.49 | 2043 | 1377 | 0.69862 | 0.30138 | 0
19157013 |  |  | 0 | 0 | 0 | 75334.56 | 0 | 835 | 0.61796 | 0.38204 | 0
19157014 |  |  | 0 | 0 | 0.02 | 545867.54 | 0 | 9657 | 0.729 | 0.271 | 0
19157015 |  |  | 0 | 0 | 0.01 | 42347.7 | 0 | 317.5 | 0.88346 | 0.11654 | 0
19157016 | 2019-05-21 | 2019-05-25 | 0 | 0 | 46562 | 41408.2 | 320 | 698 | 0.67622 | 0.32378 | 0
19157017 |  |  | 0 | 0 | 377875 | 233003.86 | 1320 | 1461.5 | 0.69141 | 0.30859 | 0
19157018 |  |  | 267 | 0 | 688095.02 | 705412.53 | 4145 | 7516.5 | 0.64079 | 0.34205 | 0.017162
19157019 |  |  | 0 | 0 | 0.02 | 308799.81 | 0 | 6458 | 0.86242 | 0.13758 | 0
19157020 |  |  | 0 | 0 | 374529 | 211178.28 | 1320 | 1806.5 | 0.64821 | 0.35179 | 0
19157021 |  |  | 0 | 0 | 0.01 | 34183.95 | 0 | 501 | 0.79541 | 0.20459 | 0
19157022 |  |  | 180 | 0 | 243336 | 280097.87 | 1920 | 5313 | 0.80679 | 0.19321 | 0
19157997 |  |  | 0 | 0 | 0.05 | 21723481.54 | 0 | 109617.92 | 0.93928 | 0.060725 | 0
1999 | 2000-12-31 |  | 0 | 0 | 0 | 327608 | 0 | 1118 | 1899-12-31 | 0 | 0
20030001 |  |  | 0 | 0 | 1826490.57 | 1945158.19 | 0 | 5453 | 0.95186 | 0.048139 | 0
20030002 |  |  | 141355 | 2 | 3648025.8434 | 3964892.18 | 24581.2 | 23682.71 | 0.91112 | 0.086941 | 0.0019423
20030004 |  |  | 139.03 | 0 | 807288.62 | 726746.28 | 1570 | 1362 | 0.79001 | 0.20999 | 0
20030005 |  |  | 0 | 0 | 433434.2 | 431469.26
20030006 |  |  | 359549.07 | 206305 | 10538171.24 | 9620081.54 | 23987.18 | 20923.87 | 0.98024 | 0.019332 | 0.00043013
20030007 |  |  | 0 | 0 | 339528.56 | 361760.36 | 652 | -35119.46 | 1899-12-31 00:01 | -0.00075457 | 0
20030008 |  |  | 0 | 0 | 585308 | 525300.45 | 412 | 334 | 0.98802 | 0.011976 | 0
20030009 |  |  | 0 | 0 | 12193.02 | 12910.59 | 52 | 52 | 1899-12-31 | 0 | 0
20030010 |  |  | 0 | 0 | 45502.07 | 41310.98 | 1595 | 75 | 0.85333 | 0.14667 | 0
20030011 |  |  | 1779.4 | 0 | 1519304.48 | 1480976.83 | 2598 | -5949 | 1899-12-31 02:06 | -0.079425 | -0.0080686
20030012 |  |  | 36 | 0 | 1287956.9984 | 1243021.86 | 5951.38 | 5192.91 | 0.95224 | 0.046217 | 0.0015406
20030013 |  |  | 120 | 1000 | 21716975.89 | 19662555.26 | 7497 | 8304.5 | 0.98585 | 0.013186 | 0.00096333
20030014 |  |  | 46294.78 | 4 | 3782590.66 | 3771709.91 | 7278 | 8190 | 0.97607 | 0.023932 | 0
20030015 |  |  | 0 | 0 | 212675.58 | 206956.79 | 48 | 40 | 1899-12-31 | 0 | 0
20030016 |  |  | 51509.58 | 13995 | 10377590.33 | 10371853.5 | 3293.2 | 2886 | 0.80198 | 0.19456 | 0.003465
20030017 |  |  | 0 | 0 | 157037 | 157768.71 | 280 | 352 | 1899-12-31 | 0 | 0
20030018 |  |  | 0 | 0 | 153549.16 | 164344.81 | 316 | 231 | 0.91342 | 0.08658 | 0
20030019 |  |  | 0 | 0 | 317514.49 | 323136.58 | 263 | 516 | 0.99419 | 0.005814 | 0
20030020 |  |  | 3803714.24 | 1960647.2 | 44064770.6545 | 40156905.54 | 114541.87 | 111192.31 | 0.91547 | 0.083295 | 0.0012343
20030021 |  |  | 83592.58 | 23040 | 4904930.65 | 4903638.14 | 6482.5 | 6586 | 0.97844 | 0.021561 | 0
20030022 |  |  | 3377 | 0 | 265096.32 | 273630.28 | 792 | 987.5 | 0.99494 | 0.0050633 | 0
20030023 |  |  | -2025 | 0 | 77411.41 | 55291.34 | 2145 | 94 | 0.95745 | 0.042553 | 0
20030024 |  |  | 4 | 0 | 376475.87 | 374402.38 | 460 | 449.5 | 0.84872 | 0.13793 | 0.013348
20030025 |  |  | 0 | 0 | 1622923 | 1559331.07 | 2002 | 1594 | 0.99435 | 0.0056462 | 0
20030026 |  |  | 32 | 0 | 551089.93 | 549491.64 | 150 | 150.27 | 0.76709 | 0.23291 | 0
20030027 |  |  | 4767 | 2359 | 650995.87 | 646250.74 | 793.2 | -1267.38 | 1899-12-31 00:09 | -0.0059177 | 0
20030028 |  |  | 40822.18 | 8557 | 766945.8 | 638451.21 | 2935.5 | 1440 | 0.96771 | 0.032292 | 0
20030029 |  |  | 0 | 0 | 4086996.92 | 4066264.1 | 8054 | 6624 | 0.9375 | 0.0625 | 0
20030030 |  |  | 0 | 0 | 23229 | 23411.03 | 45 | 77 | 0.8961 | 0.1039 | 0
20030031 |  |  | 0 | 0 | 97965 | 96248.14 | 146 | 146.5 | 0.98635 | 0.013652 | 0
20030032 |  |  | 15076 | 0 | 3278429.5361 | 3275617.26 | 5961.83 | 6118.56 | 0.96813 | 0.03187 | 0
20030033 |  |  | 0 | 0 | 185156.77 | 189415.8 | 0 | 80 | 1899-12-31 | 0 | 0
20030034 |  |  | 131.61 | 0 | 208062.96 | 199308.23 | 600.5 | 652.33 | 0.90112 | 0.062085 | 0.036791
20030035 |  |  | 310299 | 0 | 1283995.68 | 1308361.39 | 3574.7 | 3077.5 | 0.8866 | 0.1134 | 0
20030036 |  |  | 61 | 0 | 695828.77 | 688871.26 | 998 | 1571.58 | 0.9491 | 0.025452 | 0.025452
20030037 |  |  | 115175.33 | 39502 | 3092281.74 | 3147948.98 | 4337.6 | 6473.5 | 0.73314 | 0.23967 | 0.027188
20030038 |  |  | 418611.35 | 114495 | 17130164.12 | 17378621.85 | 21314.4 | 27934.2105 | 0.83008 | 0.16355 | 0.0063721
20030039 |  |  | 70 | 0 | 561948.36 | 564418.8 | 1142.5 | 1048.5 | 0.87172 | 0.12828 | 0
20030040 |  |  | 0 | 0 | 0.01 | 149442.63 | 0 | 3338.48 | 0.9654 | 0.033398 | 0.0011982
20030041 |  |  | 1424 | 17259 | 96586 | 121694.26 | 538 | 834 | 0.91067 | 0.089329 | 0
20030042 |  |  | 9 | 0 | 20293 | 30332.41 | 164 | 220.5 | 0.97052 | 0.029478 | 0
20030043 |  |  | 0 | 0 | 0.01 | 65814.78 | 0 | 502.5 | 0.99502 | 0.0049751 | 0
20030044 |  |  | 12395.07 | 0 | 513192.7612 | 509512.5 | 681.93 | 872.04 | 0.98624 | 0.013761 | 0
20030045 |  |  | 77 | 0 | 278372.2 | 270320.97 | 76 | 72 | 1899-12-31 | 0 | 0
20030046 |  |  | 40 | 0 | 153226.57 | 153431.95 | 68 | 31 | 1899-12-31 | 0 | 0
20030047 |  |  | 119 | 0 | 1041931.105 | 1010097.89 | 2878 | 2310.5 | 0.9578 | 0.0062757 | 0.035923
20030048 |  |  | 0 | 0 | 374425 | 555783.74 | 0 | 90 | 1899-12-31 | 0 | 0
20030049 |  |  | -7500.21 | 0 | 846533.55 | 1227409.23 | 4914 | 6624 | 0.99487 | 0.0051329 | 0
20030050 |  |  | 204 | 0 | 1420852.97 | 1347896.39 | 396 | 20 | 1899-12-31 | 0 | 0
20030051 |  |  | 0 | 0 | 756265.5 | 752484.25 | 62 | 59.5 | 1899-12-31 | 0 | 0
20030052 |  |  | 11436 | 7510 | 2461155.19 | 2476569 | 3379 | 2999.5 | 0.83314 | 0.16586 | 0.0010002
20030053 |  |  | 691 | 10 | 243823.29 | 242010.15 | 1229 | 1548 | 0.99354 | 0.0064599 | 0
20030054 |  |  | 7 | 0 | 148558.09 | 135202.88 | 625 | 403.5 | 0.98389 | 0.016109 | 0
20030055 |  |  | 4 | 0 | 93557.46 | 75714.06 | 1527 | 563.67 | 0.8563 | 0.1437 | 0
20030056 |  |  | 0 | 0 | 573653.8 | 550953.1 | 1199 | 989 | 0.96411 | 0.035895 | 0
20030057 |  |  | 29 | 0 | 1239828.78 | 1339532.93 | 4322 | 4385 | 0.98187 | 0.015621 | 0.0025086
20030058 |  |  | 101693 | 73698 | 7035682.23 | 6865132.37 | 7832 | 9475 | 0.94232 | 0.056412 | 0.0012665
20030059 |  |  | 0 | 0 | 72150 | 194441.41
20030060 |  |  | 0 | 0 | 1348654 | 1160878.79 | 0 | 9 | 1899-12-31 | 0 | 0
20030061 |  |  | 80 | 0 | 6276071.7706 | 6157160.36 | 3014 | 3752 | 0.98587 | 0.014126 | 0
20030062 |  |  | 517792.48 | 386925 | 15523002.945 | 14759618.83 | 26448 | 26394.04 | 0.98189 | 0.01811 | 0
20030063 |  |  | 0 | 0 | 154030.25 | 131247.18 | 754 | 907 | 0.81147 | 0.18412 | 0.0044101
20030064 |  |  | 2440 | 0 | 1017267.47 | 1076443.44 | 1441 | 1312 | 0.54345 | 0.34451 | 0.11204
20030065 |  |  | 583 | 0 | 128229.31 | 146487.32 | 346 | 405.56 | 0.57713 | 0.33657 | 0.0863
20030066 |  |  | 2056 | 0 | 2926031.46 | 2094389.19 | 5066.61 | 4376 | 0.85832 | 0.13483 | 0.0068556
20030067 |  |  | 64 | 0 | 120381.76 | 125027.63 | 248 | 357 | 1899-12-31 | 0 | 0
20030068 |  |  | 2 | 0 | 602866.82 | 613399.02 | 532 | 442.5 | 0.99774 | 0.0022599 | 0
20030069 |  |  | 20 | 0 | 347181.79 | 296501.96 | 2675 | 2212.5 | 0.99729 | 0.0027119 | 0
20030070 |  |  | 467608.89 | 101134 | 14081854.8475 | 13672413.41 | 29713.21 | 31657.83 | 0.96684 | 0.032151 | 0.0010108
20030071 |  |  | 91842.29 | 48760 | 4462359.87 | 4617320.64 | 10877.3 | 10906.5 | 0.87783 | 0.11851 | 0.0036675
20030072 |  |  | 3617 | 8 | 1234624.032 | 1242268.57 | 3498 | 2495.64 | 0.99138 | 0.008615 | 0
20030073 |  |  | 2 | 0 | 130941 | 97206.09 | 148 | 24.5 | 0.87755 | 0.12245 | 0
20030074 |  |  | 339109.71 | 25689 | 13798261.5 | 14331653.6 | 28409.1 | 33657.6 | 0.97149 | 0.024767 | 0.0037436
20030075 |  |  | 288222.18 | 89868 | 10986950.0166 | 11103097.86 | 17345.9 | 17727.05 | 0.98367 | 0.012269 | 0.0040616
20030076 |  |  | 0 | 0 | 15419.26 | 15216.46 | 72 | 62.5 | 1899-12-31 | 0 | 0
20030077 |  |  | 3 | 0 | 471943.34 | 376904.37
20030078 |  |  | 0 | 0 | 612270.75 | 591316.92
20030079 |  |  | 0 | 0 | 545094 | 582649.18
20040001 |  |  | 2 | 0 | 14439.46 | 14645.25 | 160 | 169.5 | 0.941 | 0.058997 | 0
20040002 |  |  | 4793524.58 | 123075 | 117336071.78 | 111117966.11 | 47289.4 | 49949.35 | 0.87487 | 0.12513 | 0
20040003 |  |  | 0 | 0 | 25087.18 | 24637.01 | 0 | 107.5 | 1899-12-31 | 0 | 0
20040004 |  |  | 27910 | 10910 | 3433225.11 | 3235182.93 | 1579.7 | 2170 | 0.93272 | 0.067281 | 0
20040005 |  |  | 0 | 0 | 0.01 | 0
20040006 |  |  | 16 | 0 | 11119.08 | 10400.38 | 16 | 44.5 | 1899-12-31 | 0 | 0
20040007 |  |  | 27447.62 | 3502 | 3451381.9072 | 3248499.99 | 1172.1 | 994.5 | 0.96883 | 0.031171 | 0
20040008 |  |  | 2647 | 2616 | 53339.34 | 56670.82 | 273.1 | 302.5 | 0.8 | 0.2 | 0
20040009 |  |  | 2048 | 0 | 52281.48 | 49663.62 | 215.7 | 305 | 0.88197 | 0.11803 | 0
20040010 |  |  | 2572 | 2540 | 64168.85 | 56968.38 | 319.9 | 279 | 0.98566 | 0.014337 | 0
20050001 |  |  | 34931.3 | 2440 | 7014752.8576 | 7145040.4 | 2530.1 | 4431 | 0.91571 | 0.08023 | 0.0040623
20050002 |  |  | 4302 | 509 | 451496.772 | 440220.7 | 452.2 | 604.74 | 0.8582 | 0.10376 | 0.038033
20050003 |  |  | 0 | 0 | 12141.06 | 8745.85
20050004 |  |  | 284 | 0 | 553260.17 | 523244.61 | 282.4 | 307.81 | 1899-12-31 | 0 | 0
20050005 |  |  | 31 | 495 | 1306111.45 | 1301925.73 | 960 | 715 | 0.97483 | 0.025175 | 0
20050006 |  |  | 5746 | 0 | 26601901.97 | 19126341.11 | 7531.5 | 5485.1 | 0.94613 | 0.053505 | 0.00036462
20050007 |  |  | 32969.5 | 32 | 42016452.39 | 12883303.76 | 7939.4 | 1717 | 0.96593 | 0.029412 | 0.0046593
20050008 |  |  | 21 | 0 | 303001.52 | 284289.65 | 8 | 4 | 0 | 1899-12-31 | 0
20050009 |  |  | 0 | 2 | 416668.62 | 378954.69 | 0 | 5 | 1899-12-31 | 0 | 0
20050010 |  |  | 1392 | 1 | 19647142.83 | 20134910.92 | 254 | 24 | 1899-12-31 | 0 | 0
20050011 |  |  | 0 | 0 | 43228.32 | 49891.52
20050012 |  |  | 1103397.77 | 21724.96 | 23388914.9 | 4813468.56 | 19664 | 7840.5 | 0.94866 | 0.046808 | 0.0045278
20050013 |  |  | 0 | 0 | 507127.75 | 546825.97
20050014 |  |  | 3165.1 | 430 | 1048236.1 | 1039431.21 | 568.2 | 746.76 | 0.61065 | 0.36457 | 0.024774
20050015 |  |  | 55 | 0 | 11553677.6471 | 11177565.44
20050050 |  |  | 1008.13 | 483 | 626237.3545 | 641456.84 | 708.13 | 728 | 0.95536 | 0.022665 | 0.021978
20050051 |  |  | 2319 | 0 | 4368.72 | 5874.33 | 0 | 0 | 0 | 0 | 0
20050052 |  |  | 1232 | 0 | 384987.95 | 394749.53 | 701.8 | 725.95 | 0.98898 | 0.01102 | 0
20050053 |  |  | 39.5 | 0 | 518237.35 | 480019.79 | 34.3 | 0 | 0 | 0 | 0
20055001 |  |  | 13 | 0 | 23929.54 | 10616.51
20055002 |  |  | 13 | 0 | 5518.62 | 8096.33
20055003 |  |  | 8 | 0 | 983.33 | 565.78
20055004 |  |  | 8 | 0 | 883.05 | 542.31
20055005 |  |  | 1 | 0 | 73604.47 | 73910.9 | 0 | 140.5 | 0.86477 | 0.13523 | 0
20055006 |  |  | 0 | 0 | 9000 | 1167.96
20055007 |  |  | 677 | 0 | 426686.0445 | 434363.04 | 885 | 843.58 | 0.99763 | 0.0023708 | 0
20055008 |  |  | 25 | 0 | 229967.22 | 223157.63 | 31 | 0 | 0 | 0 | 0
20055009 |  |  | 25 | 0 | 119242.57 | 102041.39 | 256 | 411.5 | 0.98177 | 0.018226 | 0
20055010 |  |  | 493629.22 | 5084.59 | 87844527.26 | 42565862.54 | 6039.2 | 929 | 0.94887 | 0.05113 | 0
20055011 |  |  | 19 | 0 | 28927.74 | 28738.26 | 80 | 44 | 1899-12-31 | 0 | 0
20055012 |  |  | 15 | 0 | 12147.14 | 12754.59 | 24 | 8 | 1899-12-31 | 0 | 0
20055013 |  |  | 61 | 56 | 98038.19 | 93604.77 | 208 | 176.85 | 1899-12-31 | 0 | 0
20055014 |  |  | 1925 | 0 | 162491.21 | 170070.84 | 345 | 438 | 0.98858 | 0.011416 | 0
20055015 |  |  | 65 | 10 | 392165.63 | 357355.93 | 753 | 1167 | 0.94173 | 0.058269 | 0
20055016 |  |  | 15 | 0 | 10776.55 | 10352.24 | 24 | 0 | 0 | 0 | 0
20055017 |  |  | 87 | 0 | 48199.75 | 48914.59 | 152 | 133 | 0.3609 | 0.6391 | 0
20055019 |  |  | 145.8 | 0 | 115836.33 | 112835.3 | 505 | 427 | 0.99063 | 0.0093677 | 0
20055020 |  |  | 26523.65 | 1605 | 2969457.23 | 3086484.95 | 3848.5 | 4048.07 | 0.89168 | 0.1019 | 0.0064228
20055021 |  |  | 63 | 0 | 28877.99 | 30010.64 | 138 | 149 | 0.96644 | 0.033557 | 0
20055022 |  |  | 9 | 0 | 11250.38 | 9171.45 | 16 | 0 | 0 | 0 | 0
20055024 |  |  | 22314.89 | 0 | 29395131.52 | 5452996 | 3796.5 | 2024.43 | 0.93406 | 0.065698 | 0.00024698
20055025 |  |  | 10 | 0 | 6506.98 | 7187.9 | 16 | 8 | 1899-12-31 | 0 | 0
20060001 |  |  | 82 | 26 | 13344.54 | 14634.47 | 153.4 | 259.5 | 0.87091 | 0.12909 | 0
20060002 |  |  | 15 | 0 | 45768 | 45333.83
20060003 |  |  | 6 | 44 | 6443.27 | 6930.43 | 0 | 38 | 0.55263 | 0.44737 | 0
20060004 |  |  | 1454.5 | 556 | 2026435.57 | 2015753.86 | 2821.7 | 2449 | 0.9904 | 0.0095958 | 0
20060005 |  |  | 35984.5 | 1457 | 1035284.1 | 1077176.39 | 1145 | 1635.5 | 0.91562 | 0.084378 | 0
20060008 |  |  | 0 | 0 | 0.01 | 1106.51
20060009 |  |  | 4 | 0 | 599664.84 | 575833.5 | 3 | 165.5 | 0.89124 | 0.10876 | 0
20060010 |  |  | 13438.7 | 4502 | 1051254.87 | 376922.45 | 1221.77 | 1274 | 0.92268 | 0.077316 | 0
20060011 |  |  | 0 | 0 | 0.01 | 0
20060012 |  |  | 0 | 0 | 0.01 | 41919.44
20060013 |  |  | 109413.85 | 56191 | 3398990.4079 | 3320578.47 | 6790 | 7279.5 | 0.96751 | 0.032488 | 0
20060014 |  |  | 65346.95 | 28642 | 1883033.06 | 1894931.08 | 2128.43 | 4602.5 | 0.95611 | 0.043889 | 0
20060015 |  |  | 0 | 0 | 227128 | 223011.59
20060017 |  |  | 797 | 0 | 65187.397 | 59164.4 | 6 | 0 | 0 | 0 | 0
20060019 |  |  | 12 | 90 | 183753.99 | 187170.9 | 258 | 106 | 1899-12-31 | 0 | 0
20060020 |  |  | 14496.5 | 61 | 1656074.13 | 1674504.87 | 2462.7 | 710.5 | 0.90148 | 0.098522 | 0
20060021 |  |  | 91319.71 | 0 | 6652916.18 | 6720007.99 | 3850.6 | 1444 | 0.76697 | 0.23303 | 0
20060022 |  |  | 937373.48 | 733186.35 | 39356686.5865 | 38749934.57 | 59365.6 | 31197.25 | 0.83749 | 0.16251 | 0
20060023 |  |  | 3 | 0 | 228785.56 | 299510.95
20060024 |  |  | 14 | 116 | 291357.59 | 277406.44 | 1286 | 596 | 0.90017 | 0.099832 | 0
20060025 |  |  | 378 | 164 | 641149 | -1.6303e-10 | 1584 | 4416 | 0.98404 | 0.015965 | 0
20060026 |  |  | 3179.23 | 455 | 141118.24 | 143739.89 | 294.7 | 472 | 0.94915 | 0.050847 | 0
20060027 |  |  | 5811.02 | 3492 | 1132548.45 | 1047772.14 | 3095.85 | 2414.25 | 0.80936 | 0.19064 | 0
20060029 |  |  | 0 | 0 | 32153 | 31102.51
20060030 |  |  | 5752.96 | 1604 | 396591.0268 | 352310.65 | 1498.28 | 703.5 | 0.87207 | 0.12793 | 0
20060031 |  |  | 0 | 0 | 39361.2 | 39404.47
20060032 |  |  | 1703956.79 | 834323.62 | 38239452.15 | 36528971.87 | 28691.97 | 32855.78 | 0.82694 | 0.17306 | 0
20060033 |  |  | 1298.7 | 858 | 543962.72 | 557841.04 | 790.6 | 901 | 0.91676 | 0.083241 | 0
20060034 |  |  | 0 | 0 | 34000 | 38384.72
20060035 |  |  | 0 | 0 | 0.01 | 0
20060036 |  |  | 849.5 | 0 | 99491.51 | 106414.22 | 217.8 | 136 | 0.82721 | 0.17279 | 0
20060037 |  |  | 3291.56 | 365 | 187035.04 | 193610.83 | 348.96 | 745 | 0.9557 | 0.044295 | 0
20060038 |  |  | 695.64 | 351 | 366372.1675 | 448937.93 | 589.2 | 512 | 0.84668 | 0.15332 | 0
20060039 |  |  | 111010.4 | 21 | 3825876.99 | 3786891.65 | 3376.5 | 4658.5 | 0.9195 | 0.080498 | 0
20060040 |  |  | 975.17 | 0 | 127680.9 | 151744.86 | 90 | 0 | 0 | 0 | 0
20060041 |  |  | 33 | 0 | 117358.42 | 123176.3
20060043 |  |  | 317 | 0 | 36453.83 | 48042.7 | 308 | 356.5 | 0.8906 | 0.1094 | 0
20060044 |  |  | 12898 | 1516 | 5941440.484 | 6043227.45 | 2969.7 | 6336.5 | 0.80533 | 0.19467 | 0
20060045 |  |  | 28 | 28.01 | 75396.14 | 56415.35 | 42 | 168 | 0.82143 | 0.17857 | 0
20060046 |  |  | 56 | 74 | 221970.04 | 220389.62 | 200 | 66 | 1899-12-31 | 0 | 0
20060047 |  |  | 108 | 26 | 73088.29 | 72567.8 | 88 | 26 | 0.96154 | 0.038462 | 0
20060048 |  |  | 126 | 30 | 234913.87 | 231947.8 | 120 | 30 | 1899-12-31 | 0 | 0
20060049 |  |  | 61477.23 | 36693 | 1883646.87 | 1868713.81 | 7641.4 | 7655 | 0.87159 | 0.12841 | 0
20060050 |  |  | 60074.89 | 19237 | 593609.743 | 628873.04 | 1931.39 | 2660.5 | 0.86262 | 0.13738 | 0
20060052 |  |  | 68131 | 49175.5 | 22826206.6724 | 20110024.21 | 5620 | 17395.04 | 0.89728 | 0.10272 | 0
20060053 |  |  | 1190.25 | 515 | 156261.79 | 208528.47 | 612.9 | 627.5 | 0.8239 | 0.1761 | 0
20060054 |  |  | 128.75 | 62 | 161713.74 | 160959.05 | 108 | 108 | 1899-12-31 | 0 | 0
20060055 |  |  | 58 | 0 | 17683.52 | 10528.01 | 0 | 27 | 1899-12-31 | 0 | 0
20060057 |  |  | 305 | 0 | 175506 | 190472.01 | 305 | 1236 | 0.92435 | 0.075647 | 0
20060059 |  |  | 133 | 8 | 384617.665 | 403442.42 | 2247.1 | 2497 | 0.97317 | 0.026832 | 0
20060060 |  |  | 16 | 0 | 70935.2 | 78106.29
20060061 |  |  | 0 | 16 | 60419545 | 2389825.52 | 0 | 24 | 1899-12-31 | 0 | 0
20060062 |  |  | 15 | 397 | 151032.43 | 158010.17 | 602 | 495 | 0.95152 | 0.048485 | 0
20080001 |  |  | 13827.06 | 5039 | 895972.5 | 993356.8 | 2742 | 3154.5 | 0.80377 | 0.095736 | 0.10049
20080002 |  |  | 201823.76 | 5355 | 16762355.23 | 697993.08 | 15596.61 | 863 | 0.99768 | 0.0023175 | 0
20080003 |  |  | 25313 | 1464 | 1077024.43 | 1113684.42 | 2437.9 | 4104 | 0.9135 | 0.055921 | 0.03058
20080004 |  |  | 8686.83 | 93 | 699634.4 | 687176.23 | 1538.1 | 1516.08 | 0.94459 | 0.055076 | 0.0003298
20080005 |  |  | 0 | 0 | 0.01 | 0
20080006 |  |  | 13343.32 | 7373 | 1673054.53 | 1729626.43 | 1722.1 | 3445.2 | 0.93829 | 0.058516 | 0.0031928
20080007 |  |  | 0 | 0 | 3396 | 3416.48
20080008 |  |  | 5990.33 | 2539 | 217201.64 | 187145.08 | 304.6 | 374 | 0.99599 | 0.0040107 | 0
20080009 |  |  | 229.5 | 0 | 4695286.03 | 4563492.43 | 277.5 | 32.5 | 0.92308 | 0.076923 | 0
20080010 |  |  | 65 | 0 | 19993.3 | 23284.9 | 40 | 89 | 0.93258 | 0.067416 | 0
20080011 |  |  | 3 | 0 | 126272 | 115778.05
20080012 |  |  | 204 | 0 | 601873.26 | 633288.16 | 0 | 30.67 | 1899-12-31 | 0 | 0
20080013 |  |  | 3 | 0 | 11145.44 | 10372.76
20080014 |  |  | 456.27 | 0 | 12176.28 | 11933.89 | 63.6 | 120 | 0.9625 | 0.0375 | 0
20090001 |  |  | 0 | 20 | 0 | 55.49 | 0 | 0 | 0 | 0 | 0
20090002 |  |  | 304 | 0 | 201236 | 204431.18 | 0 | 20 | 1899-12-31 | 0 | 0
20090003 |  |  | 155637.57 | 8.5 | 9050509.75 | 8907815.57 | 2767.8 | 3289 | 0.82533 | 0.15369 | 0.020979
20090004 |  |  | 5682.8 | 209 | 17247458.93 | 17081202.25 | 4224 | 4615.5 | 0.83295 | 0.14635 | 0.020691
20090005 |  |  | 48 | 146.5 | 2763551 | 2578027.49 | 329.5 | 602.5 | 0.89295 | 0.10705 | 0
20090006 |  |  | 479.5 | 0 | 421068.05 | 422158.47 | 294 | 167 | 0.91018 | 0.053892 | 0.035928
20090007 |  |  | 16670 | 209 | 17787126.07 | 16246289.59 | 8204 | 7058 | 0.8088 | 0.11625 | 0.07495
20090008 |  |  | 570.5 | 0 | 7307028 | 2240576.06 | 10460 | 3 | 1899-12-31 | 0 | 0
20090009 |  |  | 3028 | 156 | 22769795.33 | 22485966.48 | 1384.1 | 4360.5 | 0.94611 | 0.052632 | 0.0012613
20090991 |  |  | 121 | 52 | 0 | 129499.29 | 212 | 1421.86 | 0.99332 | 0.0035165 | 0.0031649
20090992 |  |  | 0 | 0 | 0 | 68859.64 | 0 | 237 | 0.86076 | 0.13924 | 0
20110001 |  |  | 3925 | 0 | 6985160.368 | 6985490.17
20110003 |  |  | 502 | 0 | 290930.02 | 225394.45
20110004 |  |  | 0 | 8 | 27612978.77 | 25992933.45 | 0 | 23839.88 | 0.75751 | 0.23171 | 0.01078
20110004-144 |  |  | 0 | 0 | 536777413 | 0
20110005 |  |  | 0 | 0 | 35706 | 30670.13
20110006 |  |  | 154501 | 0 | 88530366.35 | 70690450.76 | 12040 | 4854 | 1899-12-31 | 0 | 0
20110007 |  |  | 8182 | 0 | 26910039.738 | 26680736.07 | 63 | 7924.05 | 0.87115 | 0.12885 | 0
20110008 |  |  | 263 | 0 | 25654008.45 | 13784139.99 | 0 | 62 | 0.64516 | 0.35484 | 0
20110009 |  |  | 17130 | 0 | 15423545.3758 | 14474864.82 | 0 | 36 | 1899-12-31 | 0 | 0
20110010 |  |  | 46283 | 0 | 13363460.5 | 11974851.54 | 0 | 16.7 | 1899-12-31 | 0 | 0
20110011 |  |  | 37 | 0 | 18650974.58 | 12624874.14 | 0 | 3380.89 | 0.96066 | 0.039339 | 0
20110012 |  |  | 12 | 0 | 1887827.9999 | 687052.62
20110013 |  |  | 2069 | 0 | 788425.82 | 775770.82 | 0 | 525 | 0.99048 | 0.0095238 | 0
20110014 |  |  | 579 | 0 | 544692.29 | 471401.53
20110015 |  |  | 129 | 0 | 16338382.18 | 16054421 | 0 | 1050 | 0.98286 | 0.017143 | 0
20110016 |  |  | 88 | 0 | 3410441.56 | 3409448.5
20120001 |  |  | 11 | 0 | 1351814 | 1349206.05
20120002 |  |  | 1122 | 0 | 267542 | 198978.45
20120003 |  |  | 0 | 0 | 421834 | 315955.88
20126001 |  |  | 557 | 160 | 9902581.82 | 10070523.77 | 144 | 1320.5 | 0.84854 | 0.15146 | 0
20126002 |  |  | 3002553.2 | 458745.62 | 642714803.6686 | 555767799.29 | 253676.23 | 261130.37 | 0.82335 | 0.17665 | 0
20126004 |  |  | 1192210.03 | 827920 | 722631143.1765 | 705265919.49 | 216228 | 212599.05 | 0.83123 | 0.12412 | 0.044652
20141001 |  |  | 1601.68 | 734 | 16294067.102 | 10931550.62 | 38410 | 31350 | 0.81325 | 0.18675 | 0
20141003 |  |  | 2984 | 1285 | 23227823.88 | 18687352.52 | 78840 | 81256.58 | 0.79767 | 0.20233 | 0
20141004 |  |  | 11456.68 | 4726 | 101827957.5718 | 91177666.12 | 159155.5 | 115278.5 | 0.78232 | 0.2103 | 0.0073778
20141005 |  |  | 6 | 0 | 599210.14 | 595006.6
20141006 |  |  | 0 | 0 | 758962.5 | 671012.09
20141007 |  |  | 0 | 0 | 340349 | 259112.45
20141008 |  |  | 4 | 0 | 860359 | 477135.83 | 0 | 145 | 1899-12-31 | 0 | 0
20141009 |  |  | 0 | 0 | 154035.67 | 147415.4
20141010 |  |  | 3944 | 2555 | 39353923.7198 | 34076940.33 | 81081 | 82518 | 0.74202 | 0.25798 | 0
20141011 |  |  | 1772 | 1295 | 38618613.98 | 36561723.04 | 47420 | 43481.5 | 0.75678 | 0.19998 | 0.043237
20141013 |  |  | 6128 | 6172 | 52718623.0132 | 52828054.31 | 69002.09 | 86343.35 | 0.79342 | 0.20658 | 0
20145001 |  |  | 12961792.56 | 8790948.73 | 236866438.17 | 232598848.77 | 1054810.02 | 1131922.42 | 0.86357 | 0.13642 | 4.859e-06
20145002 |  |  | 260 | 0 | 194265 | 187905.75 | 160 | 276 | 0.86957 | 0.13043 | 0
20145005 |  |  | 585 | 0 | 4302346.04 | 2639820.77 | 386 | 384.5 | 0.72432 | 0.27568 | 0
20145006 |  |  | 3023127.7112 | 2724497.39 | 65503365.33 | 66327681.08 | 261326.74 | 317287.34 | 0.86186 | 0.13814 | 0
20145007 |  |  | 16817754.46 | 14360299.08 | 836870271.29 | 732549556.05 | 2155844.61 | 2180545.52 | 0.84457 | 0.14547 | 0.0099592
20145008 |  |  | 1387 | 0 | 7796037 | 2896120.54 | 600 | 238 | 0.79832 | 0.20168 | 0
20146001 |  |  | 280328.92 | 254705 | 12552025.93 | 12608755.32 | 14280.67 | 16347 | 0.76292 | 0.23708 | 0
20146002 |  |  | 144337.16 | 161307 | 4381781.6 | 4018678.95 | 4863.47 | 7406.5 | 0.78114 | 0.21886 | 0
20146003 |  |  | 391370 | 377076 | 8799109.08 | 8357171.43 | 11845.34 | 9745.5 | 0.90709 | 0.092909 | 0
20146004 |  |  | 618915.97 | 613472 | 21073600 | 20035902.71 | 23565.84 | 21477 | 0.82172 | 0.17828 | 0
20146005 |  |  | 957 | 0 | 7237514.25 | 29182.66
20146006 |  |  | 191200.8 | 191448.8 | 7563984 | 7364813.64 | 7972.25 | 12907 | 0.89015 | 0.10985 | 0
20146007 |  |  | 0 | 0 | 1399065 | 945979.39
20146008 |  |  | 94420.46 | 86813 | 6208916.76 | 6163106.29 | 4928.69 | 4746 | 0.87853 | 0.12147 | 0
20146009 |  |  | 240 | 0 | 1444815 | 1039331.91
20146010 |  |  | 33537.56 | 1652 | 3792652.05 | 3815632.05 | 5737 | 7309.5 | 0.80409 | 0.19591 | 0
20148001, 19141030, 19146024 |  |  | 14598028.33 | 1391520 | 109134736.56 | 102650213.85 | 93289.98 | 100903.78 | 0.84764 | 0.15236 | 0
20148002 |  |  | 2820797.62 | 168415 | 2714599.4 | 2545533.42 | 5346.24 | 3740 | 0.82128 | 0.17872 | 0
20148003 |  |  | 20407680.84 | 820131 | 17455480.41 | 15635223.41 | 62797.97 | 61934 | 0.82134 | 0.17507 | 0.0035925
20148004 |  |  | 3218196.04 | 110 | 3626246.63 | 2859388.13 | 10617.97 | 4493 | 0.78511 | 0.21489 | 0
20148005, 20141002 |  |  | 2227827.9 | 83104 | 29121841.8102 | 19531006.1 | 43019.82 | 30385 | 0.8151 | 0.16616 | 0.018741
20148006, 19145015 |  |  | 7106667.56 | 3066073 | 54977897.1103 | 49977093.47 | 228442.73 | 171296.92 | 0.84369 | 0.15631 | 0
20148008 |  |  | 3160519.77 | 55484 | 3733933.2905 | 2443741.13 | 16314.26 | 10327 | 0.79592 | 0.20408 | 0
20148010 |  |  | 0 | 0 | 510659.81 | 308318.12 | 0 | 1442.5 | 0.80104 | 0.19896 | 0
20148011 |  |  | 12169845.69 | 285334 | 10141490.15 | 9559503.62 | 19988.65 | 21607 | 0.85221 | 0.14779 | 0
20148012 |  |  | 2 | 0 | 416689.61 | 334037.05 | 0 | 891 | 0.86532 | 0.13468 | 0
20148013 |  |  | 2725795.59 | 140509 | 4449524.56 | 3018492.52 | 17135.17 | 12312.27 | 0.80012 | 0.19988 | 0
20148014, 20141012, 20146011 |  |  | 937420.08 | 604944 | 93880425.0787 | 91235324.46 | 159862.69 | 154895.58 | 0.78566 | 0.21434 | 0
20149001 |  |  | 242 | 0 | 228183 | 166861.37
20149004 |  |  | 235542 | 260391 | 54914777.3554 | 63745201.61 | 31673.31 | 103437.71 | 0.71048 | 0.19523 | 0.094295
20149005 |  |  | 399427.17 | 301645 | 15365690.86 | 15664912.05 | 33992.56 | 43381.5 | 0.7842 | 0.2158 | 0
20149006 |  |  | 622662.68 | 354518 | 27398591.31 | 26371911.31 | 46380.14 | 43824.25 | 0.86 | 0.14 | 0
20149007 |  |  | 182272.28 | 25449 | 10778930.9568 | 10230105 | 14131.96 | 24237 | 0.76076 | 0.23924 | 0
20150001 |  |  | 0 | 0 | 1 | 1078098.42
20150003 |  |  | 0 | 0 | 115208 | 130924.12
20150004 |  |  | 0 | 0 | 0.02 | 578583.72
20150004-110 |  |  | 0 | 0 | 1069573.98 | 756106.4
20150005 |  |  | 1227 | 0 | 1975172.73 | 1930091.65
20150006 |  |  | 1 | 0 | 12957558.8358 | 12093720.93 | 16435 | 0 | 0 | 0 | 0
20150007 |  |  | 0 | 0 | 606593.712 | 666102.89
20157001 |  |  | 0 | 0 | 0.02 | 1265815.32 | 0 | 26618 | 0.73941 | 0.26059 | 0
20157002 |  |  | 0 | 0 | 0 | 33799.72 | 0 | 246.5 | 0.87424 | 0.12576 | 0
20157003 |  |  | 0 | 0 | 0 | 425109.95 | 0 | 681 | 0.74082 | 0.25918 | 0
20157004 |  |  | 0 | 0 | 1394858 | 1015024.51 | 0 | 11514 | 0.88844 | 0.11156 | 0
20157005 |  |  | 0 | 0 | 557310 | 247296.17 | 0 | 2520 | 0.9 | 0.1 | 0
20157006 |  |  | 0 | 0 | 0.03 | 716002.2 | 0 | 13937.5 | 0.70952 | 0.29048 | 0
20157007 |  |  | 0 | 0 | 0.01 | 269908.16 | 0 | 1699.5 | 0.70815 | 0.29185 | 0
20157008 |  |  | 0 | 0 | 0 | 116674.15 | 0 | 1966.5 | 0.67302 | 0.32698 | 0
20157009 |  |  | 0 | 0 | 0.01 | 24245.61 | 0 | 189 | 0.86243 | 0.13757 | 0
20157010 |  |  | 0 | 0 | 0 | 636563.75 | 0 | 17453 | 0.7324 | 0.2676 | 0
20157011 |  |  | 0 | 0 | 0 | 27244.67 | 0 | 239.5 | 0.77244 | 0.22756 | 0
20157012 |  |  | 0 | 0 | 0 | 579306.08 | 0 | 1135.5 | 0.76266 | 0.23734 | 0
21001 | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 796772 | 0 | 7753 | 1899-12-31 | 0 | 0
21002 | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 42279 | 0 | 630 | 1899-12-31 | 0 | 0
21003 | 2002-12-31 | 2003-12-31 | 964 | 0 | 6201368 | 6206174 | 0 | 11062 | 1899-12-31 | 0 | 0
21004 | 2003-12-20 |  | 0 | 0 | 699038 | 685608 | 0 | 358 | 1899-12-31 | 0 | 0
21007 | 2002-09-01 | 2002-08-20 | 2362 | 0 | 416036 | 416346 | 0 | 1243 | 1899-12-31 | 0 | 0
21008 | 2002-12-31 |  | 0 | 0 | 0 | 6956 | 0 | 102 | 1899-12-31 | 0 | 0
21009 | 2002-12-31 |  | 0 | 0 | 9087 | 36245 | 0 | 310 | 1899-12-31 | 0 | 0
21010 | 2002-03-31 | 2002-03-31 | 5 | 0 | 5310 | 5672 | 0 | 40 | 1899-12-31 | 0 | 0
21011 | 2002-07-01 | 2002-08-27 | 106629 | 44573 | 4472022 | 5313301 | 0 | 13231 | 1899-12-31 | 0 | 0
21012 | 2002-03-30 |  | 2043 | 0 | 25839 | 128585 | 0 | 157 | 1899-12-31 | 0 | 0
21013 | 2002-09-11 |  | 113224 | 113315 | 2078379 | 2224771 | 0 | 11470 | 1899-12-31 | 0 | 0
21014 | 2003-11-01 | 2003-07-01 | 229676 | 218130 | 6006022 | 6008075 | 0 | 17821 | 1899-12-31 | 0 | 0
21015 | 2002-02-28 | 2002-02-28 | 0 | 0 | 0 | 1583 | 0 | 0 | 0 | 0 | 0
21016 | 2002-12-31 |  | 0 | 0 | 0 | 18163 | 0 | 5 | 1899-12-31 | 0 | 0
21017 | 2002-04-30 |  | 0 | 0 | 21460 | 21478 | 0 | 142 | 1899-12-31 | 0 | 0
21018 | 2004-08-01 |  | 1000715 | 2360430 | 174430351 | 174516331 | 0 | 203716 | 1899-12-31 | 0 | 0
21019 | 2002-04-29 |  | 0 | 1324 | 0 | 11705 | 0 | 196 | 1899-12-31 | 0 | 0
21020 | 2004-05-31 | 2004-07-01 | 213931 | 287004 | 12754593 | 12732663 | 0 | 45814 | 1899-12-31 | 0 | 0
21021 | 2003-07-11 | 2003-08-08 | 1633293 | 925167 | 10256630 | 10843513 | 0 | 35451 | 1899-12-31 | 0 | 0
21022 | 2002-09-20 | 2002-09-25 | 1819 | 0 | 167056 | 259910 | 0 | 1799 | 1899-12-31 | 0 | 0
21023 | 2003-06-01 | 2002-11-27 | 25657 | 25611 | 831372 | 1293351 | 0 | 4395 | 1899-12-31 | 0 | 0
21024 | 2005-11-05 | 2005-09-02 | 163479 | 119905 | 8760201 | 9083594 | 0 | 19899 | 1899-12-31 | 0 | 0
21025 | 2002-09-30 | 2002-09-30 | 89 | 0 | 433040 | 432981 | 0 | 0 | 0 | 0 | 0
21026 | 2003-11-01 | 2003-10-12 | 10002747816 | 2467135 | 0 | 20418080 | 0 | 95271 | 1899-12-31 | 0 | 0
21027 | 2002-10-31 |  | 0 | 0 | 0 | 11193 | 0 | 121 | 1899-12-31 | 0 | 0
21028 |  |  | 1650494 | 1431854 | 34807648 | 32809650 | 0 | 84166 | 1899-12-31 | 0 | 0
21029 | 2003-10-30 |  | 129527 | 87770 | 1868019 | 1876591 | 0 | 4599 | 1899-12-31 | 0 | 0
21030 | 2004-12-31 | 2005-01-14 | 679171 | 829740 | 43362002 | 44034787 | 0 | 126524 | 1899-12-31 | 0 | 0
21030001 |  |  | 778 | 0 | 3093971.36 | 3742040.32 | 0 | 7598 | 0.94123 | 0.042709 | 0.016057
21030002 |  |  | 3519 | 0 | 5105415.26 | 4554673.58 | 23028.5 | 20023.25 | 0.8513 | 0.14416 | 0.0045447
21030003 |  |  | 52 | 0 | 880892.4 | 854171.41 | 0 | 1805.5 | 0.97757 | 0.018001 | 0.0044309
21030004 |  |  | 0 | 0 | 965658.26 | 54536.87
21030005 |  |  | 1 | 0 | 447196 | 430408.85 | 898 | 1515.55 | 1899-12-31 | 0 | 0
21030006 |  |  | 714 | 0 | 3033497.35 | 3014841.02 | 789 | 1090.5 | 0.55938 | 0.35167 | 0.08895
21030007 |  |  | 7381 | 0 | 774283.82 | 1179589.1 | 1123.8 | 2520 | 0.975 | 0.025 | 0
21030008 |  |  | 15 | 0 | 304482.72 | 320305.42 | 1002 | 1065.5 | 0.97278 | 0.027217 | 0
21030009 |  |  | 938 | 0 | 292820.16 | 284531.7 | 905 | 619 | 0.85703 | 0.13489 | 0.0080775
21030010 |  |  | 0 | 0 | 261226 | 214711.48 | 100 | 0 | 0 | 0 | 0
21030011 |  |  | 69 | 0 | 1445541.71 | 1432009.85 | 3646 | 3192.5 | 0.98105 | 0.018951 | 0
21030012 |  |  | 12 | 0 | 1327210.11 | 1124630.35 | 1912 | 1510 | 0.98874 | 0.011258 | 0
21030013 |  |  | 180 | 0 | 98644.47 | 85401.91 | 265 | 267 | 1899-12-31 | 0 | 0
21030014 |  |  | 24 | 0 | 4375232.19 | 4402212.27 | 24 | 0 | 0 | 0 | 0
21030015 |  |  | 0 | 0 | 172153.1 | 175793.51 | 30 | 8 | 1899-12-31 | 0 | 0
21030016 |  |  | 186189 | 61920 | 29973964.513 | 27754637.27 | 32659.3 | 31054.5 | 0.9213 | 0.0787 | 0
21030017 |  |  | 6 | 0 | 4156040.3269 | 4096181.84 | 1810.18 | 2161 | 0.78852 | 0.21148 | 0
21030018 |  |  | 0 | 0 | 2513015.587 | 2607033.92 | 8 | 225 | 0.81778 | 0.18222 | 0
21030019 |  |  | 145139 | 14113 | 16661900.17 | 16510642.66 | 5889 | 4040.22 | 0.81085 | 0.18841 | 0.00074253
21030020 |  |  | 71843.5 | 0 | 89533047.3292 | 59123786.05 | 13223 | 15830.25 | 0.76992 | 0.22326 | 0.0068224
21030021 |  |  | 8 | 0 | 934569.71 | 960615.67 | 3028 | 1631.5 | 0.8434 | 0.1566 | 0
21030022 |  |  | 5 | 0 | 768602.6525 | 818833.36 | 2347 | 2284.15 | 0.9965 | 0.0035024 | 0
21030023 |  |  | 503.28 | 8 | 3617880.2955 | 3645156.89 | 5507.16 | 5118.5 | 0.85845 | 0.14155 | 0
21030024 |  |  | 246 | 0 | 1069174.4714 | 1096508.55 | 2613.64 | 2076.33 | 0.9516 | 0.048403 | 0
21030025 |  |  | 372 | 0 | 316885.58 | 278351.86 | 1601 | 1310.5 | 0.92217 | 0.062572 | 0.015261
21030026 |  |  | 0 | 0 | 299214 | 240474.13 | 612 | 306 | 0.77451 | 0.22549 | 0
21030027 |  |  | 614 | 24 | 1002360.96 | 988431.85 | 905 | 1424 | 0.96875 | 0.03125 | 0
21030028 |  |  | 1 | 0 | 73669 | 66655.96 | 15 | 0 | 0 | 0 | 0
21030029 |  |  | 13 | 0 | 551513.77 | 552491.44
21030030 |  |  | 4109 | 0 | 505321.23 | 471745.61 | 4489 | 2361.18 | 0.89285 | 0.10715 | 0
21030031 |  |  | 35191.72 | 12457 | 830924.88 | 977395.63 | 1711.4 | 1706 | 0.8391 | 0.15182 | 0.0090856
21030032 |  |  | 13 | 0 | 539386.45 | 541130.94
21030033 |  |  | 105832.66 | 47438 | 8670418.1 | 8752313.02 | 5765.72 | 5619.5 | 0.87001 | 0.12999 | 0
21030034 |  |  | 27 | 0 | 2486112.1 | 2318185.5 | 432 | 1079.5 | 0.89532 | 0.10468 | 0
21030035 |  |  | 214260 | 56837.97 | 46921894.09 | 48330684.46 | 9969.3 | 19686 | 0.94798 | 0.050188 | 0.0018287
21030036 |  |  | 4 | 0 | 401560.28 | 172409.76 | 727 | 865 | 0.99711 | 0.0028902 | 0
21030037 |  |  | 50 | 0 | 217867.52 | 192859.49 | 424 | 344.59 | 0.95502 | 0.044981 | 0
21030038 |  |  | 256 | 0 | 158745.1 | 127788.36 | 132 | 101 | 0.9604 | 0.039604 | 0
21030039 |  |  | 406802.96 | 0 | 20059851.27 | 967701.27 | 18665.09 | 0 | 0 | 0 | 0
21030040 |  |  | 26 | 0 | 1250860.9 | 1212289.48 | 5495 | 4881.2 | 0.95438 | 0.039478 | 0.006146
21030041 |  |  | 36815 | 14763 | 6842499.85 | 6833947.95 | 7018.1 | 8351.95 | 0.84986 | 0.1426 | 0.0075431
21030042 |  |  | 0 | 0 | 136659 | 127978.39 | 280 | 269.5 | 1899-12-31 | 0 | 0
21030043 |  |  | 74034.78 | 0 | 6134762.814 | 6038545.81 | 5997.8 | 8474.6 | 0.97369 | 0.02537 | 0.000944
21030044 |  |  | 304 | 0 | 139675 | 348987.96
21030045 |  |  | 973.06 | 0 | 129279.33 | 108259.85 | 173.6 | 141.5 | 0.93286 | 0.067138 | 0
21030046 |  |  | 5 | 0 | 513483.73 | 504081.07 | 1028 | 999 | 0.76577 | 0.23223 | 0.002002
21030047 |  |  | 0 | 0 | 1326110.21 | 396790 | 4488 | 1532 | 0.9641 | 0.030026 | 0.0058747
21030048 |  |  | 615453.41 | 120498 | 15244392.06 | 6441676.85 | 36070.12 | 20553.5 | 0.96859 | 0.031406 | 0
21030049 |  |  | 57 | 0 | 414460.29 | 411200.81 | 1437 | 1259.5 | 0.8813 | 0.11711 | 0.0015879
21030050 |  |  | 91931.32 | 39579 | 8116026.84 | 4256853.67 | 3783.3 | 4698.5 | 0.84878 | 0.15122 | 0
21030051 |  |  | 23800 | 0 | 985434.58 | 992366.21 | 1321.8 | 1001.5 | 0.97154 | 0.028457 | 0
21030052 |  |  | 6 | 0 | 305010.95 | 305229.35 | 1123 | 973.5 | 0.93272 | 0.067283 | 0
21030053 |  |  | 0 | 0 | 249438.46 | 185192.93 | 0 | 11 | 0.27273 | 0.72727 | 0
21030054 |  |  | 157751.41 | 54812 | 11658216.82 | 9778811.4 | 5733.5 | 8054.5 | 0.93172 | 0.067043 | 0.0012415
21030055 |  |  | 501 | 0 | 3321290.5 | 2476409.64 | 10999 | 5880.45 | 0.73361 | 0.26316 | 0.003231
21030056 |  |  | 37 | 0 | 1300502 | 985084.5 | 580 | 4436.05 | 0.72769 | 0.27231 | 0
21031 | 2002-09-30 |  | 0 | 0 | 10393 | 10967 | 0 | 48 | 1899-12-31 | 0 | 0
21032 | 2004-04-07 | 2004-05-13 | 0 | 0 | 713631 | 715572 | 0 | 3580 | 1899-12-31 | 0 | 0
21035 | 2004-10-01 |  | 3406282 | 2271715 | 43636884 | 43635397 | 0 | 94425 | 1899-12-31 | 0 | 0
21036 | 2002-10-31 |  | 0 | 0 | 0 | 3381 | 0 | 45 | 1899-12-31 | 0 | 0
21038 | 2003-06-30 | 2003-09-22 | 41993 | 0 | 406597 | 412605 | 0 | 2429 | 1899-12-31 | 0 | 0
21040 | 2003-12-31 | 2003-12-31 | 0 | 0 | 10256 | 11630 | 0 | 94 | 1899-12-31 | 0 | 0
21040001 |  |  | 1 | 0 | 35311.99 | 17199.63 | 0 | 166.5 | 0.91892 | 0.081081 | 0
21040002 |  |  | 220 | 7 | 540688.15 | 528122.3 | 247.6 | 209.75 | 0.94279 | 0.057211 | 0
21040003 |  |  | 191410 | 52756 | 257668584.48 | 121853471.54 | 37731 | 16920.5 | 0.85849 | 0.14151 | 0
21040004 |  |  | 7 | 0 | 47890.49 | 45265.74 | 21 | 0 | 0 | 0 | 0
21040005 |  |  | 349.5 | 0 | 79819.17 | 78285.97 | 307.3 | 322.5 | 0.75659 | 0.24341 | 0
21040006 |  |  | 220 | 784 | 545634.27 | 519784.87 | 285.3 | 232.75 | 0.98711 | 0.012889 | 0
21040008 |  |  | 1956 | 0 | 90075.5 | 68132.66 | 347.8 | 303 | 0.85479 | 0.14521 | 0
21040009 |  |  | 206 | 1241 | 567943.42 | 542285.18 | 299.9 | 226.5 | 0.93157 | 0.068433 | 0
21040010 |  |  | 21433.4 | 0 | 4353344.68 | 287106.13 | 829.3 | 2051 | 0.85202 | 0.14798 | 0
21040011 |  |  | 1545 | 0 | 26693.39 | 15487.89 | 147.4 | 66 | 0.35606 | 0.64394 | 0
21040012 |  |  | 18 | 0 | 834577.23 | 263570.58
21040013 |  |  | 652195.44 | 83 | 51806855.05 | 11299437.25 | 4849.6 | 112 | 1899-12-31 | 0 | 0
21041 | 2003-01-10 |  | 1424 | 1116 | 135234 | 136601 | 0 | 1118 | 1899-12-31 | 0 | 0
21050001 |  |  | 0 | 0 | 0.06 | 16519.01
21050002 |  |  | 0 | 1364 | 3190657.83 | 1592637.29 | 0 | 2744.29 | 0.96447 | 0.02988 | 0.0056481
21050003 |  |  | 0 | 208 | 440492.76 | 440441.59 | 0 | 397.89 | 0.83161 | 0.14074 | 0.027646
21050004 |  |  | 469.9 | 221 | 439146.5675 | 426083.11 | 924.5 | 1102 | 0.96824 | 0.028131 | 0.0036298
21050005 |  |  | 4178.8 | 2994.5 | 10312545.27 | 9459826.88 | 4168.3 | 9278.77 | 0.95872 | 0.03411 | 0.0071669
21050006 |  |  | 833 | 6737 | 188278.3 | 190011.81 | 400.83 | 487 | 0.98871 | 0.011294 | 0
21050007 |  |  | 973 | 44 | 5028016.49 | 1968980.16 | 2.1 | 51.5 | 0.82524 | 0.16505 | 0.0097087
21050008 |  |  | 0 | 0 | 1352.12 | 1500.07
21050009 |  |  | 5326.3 | 0 | 5866842.84 | 2095822.1 | 299.9 | 185 | 0.97297 | 0.027027 | 0
21050010 |  |  | 0 | 0 | 2385533.32 | 2186010.89 | 40 | 40 | 1899-12-31 | 0 | 0
21050011 |  |  | 98 | 0 | 13964630.58 | 4698820.62
21050012 |  |  | 5428785.75 | 1578 | 211971447.01 | 16428527.12 | 132886.63 | 3283 | 0.95507 | 0.039141 | 0.0057874
21050013 |  |  | 0 | 0 | 4378661.24 | 2615068.11
21050050 |  |  | 12.5 | 0 | 60220.15 | 70591.84 | 13 | 158 | 0.90823 | 0.091772 | 0
21050051 |  |  | 311 | 16 | 2626368.4917 | 1752850.14 | 341 | 400 | 0.89875 | 0.10125 | 0
21055001 |  |  | 294429.64 | 185616.5 | 59415006.7956 | 41333333.69 | 15998 | 10279.25 | 0.93159 | 0.067247 | 0.0011674
21055002 |  |  | 27 | 0 | 143747.53 | 133649.18 | 284 | 375.02 | 0.92534 | 0.058664 | 0.015999
21055003 |  |  | 237 | 8 | 143943 | 146872.27 | 416 | 464 | 1899-12-31 | 0 | 0
21055004 |  |  | 294 | 0 | 71631164.89 | 11871938.13
21055005 |  |  | 42 | 0 | 1824809.53 | 1511108.64
21055008 |  |  | 3 | 0 | 62939.36 | 62501.68 | 23 | 260.62 | 0.91942 | 0.080577 | 0
21055009 |  |  | 7 | 0 | 2014.18 | 1289.92 | 0 | 5 | 1899-12-31 | 0 | 0
21055010 |  |  | 8056.01 | 0 | 870579.8253 | 702481.64 | 438.3 | 734.3 | 0.98638 | 0.013618 | 0
21055011 |  |  | 2872.98 | 0 | 677327.05 | 627319.96 | 324.8 | 295 | 0.97627 | 0.023729 | 0
21055012 |  |  | 9 | 0 | 6986.26 | 8132.07 | 12 | 21 | 1899-12-31 | 0 | 0
21055013 |  |  | -1039.52 | 0 | 329955.14 | 324700.93 | 446 | 79 | 0.73418 | 0.24051 | 0.025316
21055014 |  |  | 24 | 0 | 17810.86 | 18899.21 | 36 | 48 | 1899-12-31 | 0 | 0
21055015 |  |  | 14 | 0 | 5305.09 | 5519.49 | 6 | 32 | 1899-12-31 | 0 | 0
21055016 |  |  | 33424.39 | 0 | 3898541.25 | 3689631.24 | 867 | 1075.85 | 0.97862 | 0.01766 | 0.003718
21055017 |  |  | 23 | 0 | 75820.76 | 76374.69 | 136 | 155.98 | 0.91024 | 0.019233 | 0.070522
21055018 |  |  | 9 | 0 | 839399.49 | 840670.83 | 814 | 514 | 0.97276 | 0.023346 | 0.0038911
21055019 |  |  | 13 | 0 | 11791.26 | 10626.65 | 16 | 0 | 0 | 0 | 0
21055020 |  |  | 13 | 0 | 62609.45 | 65925.17 | 100 | 48 | 1899-12-31 | 0 | 0
21055021 |  |  | 0 | 0 | 0.01 | 0
21055022 |  |  | 29 | 0 | 332311.06 | 334737.93 | 596 | 422 | 1899-12-31 | 0 | 0
21055023 |  |  | 38.25 | 0 | 7438.55 | 7565.71 | 44 | 24 | 1899-12-31 | 0 | 0
21055024 |  |  | 30 | 0 | 119688.87 | 111601.4 | 52 | 97 | 0.86598 | 0.10309 | 0.030928
21055025 |  |  | 19 | 0 | 34032.72 | 48473.15 | 0 | 0 | 0 | 0 | 0
21055026 |  |  | 9200.5 | 0 | 387480.3 | 336730.91 | 378.1 | 219 | 1899-12-31 | 0 | 0
21055027 |  |  | 12 | 0 | 5541.2 | 5623.07 | 6 | 0 | 0 | 0 | 0
21055028 |  |  | 10 | 0 | 2283.71 | 2789.84 | 2 | 0 | 0 | 0 | 0
21055029 |  |  | 1 | 0 | 6476.86 | 6757.98 | 16 | 0 | 0 | 0 | 0
21055030 |  |  | 6472.59 | 0 | 1375843.21 | 303080.92 | 1294.74 | 739.1 | 0.99865 | 0.001353 | 0
21055031 |  |  | 11 | 0 | 9206.69 | 9089.84 | 16 | 0 | 0 | 0 | 0
21055032 |  |  | 155 | 0 | 43873.35 | 40276.89 | 136 | 204 | 1899-12-31 | 0 | 0
21055033 |  |  | 75631.13 | 7785 | 11852266.4 | 11637698.62 | 5300.2 | 4280.65 | 0.96099 | 0.035742 | 0.0032705
21055034 |  |  | 361 | 0 | 196474.47 | 30764.61 | 440 | 36 | 1899-12-31 | 0 | 0
21055035 |  |  | 37 | 0 | 14833.85 | 16369.54 | 97 | 110 | 1899-12-31 | 0 | 0
21055036 |  |  | 0 | 0 | 3862.26 | 3601.09
21055037 |  |  | 0 | 0 | 0.01 | 0
21055038 |  |  | 15 | 0 | 10382.7 | 12044.95
21055039 |  |  | 5031.18 | 0 | 1342685.48 | 1169011.52 | 526.8 | 1071.5 | 0.92814 | 0.05693 | 0.014932
21055040 |  |  | 12 | 0 | 3527.61 | 4279.64 | 12 | 0 | 0 | 0 | 0
21055043 |  |  | -308 | 0 | 156771.316 | 149426.7 | 962 | 805.96 | 1899-12-31 | 0 | 0
21055044 |  |  | 0 | 0 | 636100.01 | 578587.79
21055045 |  |  | 19 | 0 | 217710.11 | 230077.87 | 196 | 304 | 1899-12-31 | 0 | 0
21055046 |  |  | 6 | 0 | 59910.78 | 61557.83
21055047 |  |  | 14 | 0 | 309780.78 | 344336.4
21055048 |  |  | 4 | 0 | 156606.07 | 153956.67
21055049 |  |  | 11 | 0 | 48738.09 | 814.68
21055050 |  |  | 17 | 0 | 13069.63 | 13605.69
21055051 |  |  | 6484.04 | 0 | 455541.46 | 402860.35 | 928.2 | 1076.6 | 0.99443 | 0.0055731 | 0
21055052 |  |  | 12 | 0 | 4217.29 | 4874.94 | 4 | 0 | 0 | 0 | 0
21060001 |  |  | 0 | 0 | 25000 | 107981.35 | 0 | 0 | 0 | 0 | 0
21060003 |  |  | 136 | 15 | 42921.16 | 42576.17 | 55 | 36 | 0.97222 | 0.027778 | 0
21060004 |  |  | 18 | 565.01 | 220151.65 | 241157.4 | 274.2 | 721.5 | 0.92238 | 0.077616 | 0
21060005 |  |  | 159 | 15 | 19883.81 | 19957.38 | 46 | 32 | 0.96875 | 0.03125 | 0
21060006 |  |  | 1132.5 | 0 | 411069.03 | 425144.92 | 381.2 | 0 | 0 | 0 | 0
21060006, 21060002, 20060056, 19060003, 19060002, 18060056, 19060015, 20060018, | 2019-01-01 | 2019-12-01 | 34 | 0 | 6965860.17 | 7137277.74 | 0 | 0 | 0 | 0 | 0
21060007 |  |  | 2858.55 | 0 | 688556.32 | 717909.41 | 347.6 | 0 | 0 | 0 | 0
21060008 |  |  | 110188 | 41788.25 | 2811289.9086 | 2884669.35 | 4370.92 | 5429.5 | 0.95267 | 0.047334 | 0
21060009 |  |  | 0 | 0 | 0.01 | 0
21060010 |  |  | 190 | 0 | 1613950.38 | 1612235.99 | 190 | 66 | 1899-12-31 | 0 | 0
21060011 |  |  | 5889.91 | 0 | 257970.15 | 270409.83 | 241.2 | 0 | 0 | 0 | 0
21060012 |  |  | 3360 | 1493.4 | 16367611.45 | 17282503.05 | 2221 | 10374.55 | 0.88014 | 0.11986 | 0
21060013 |  |  | 0 | 0 | 76402 | 109429.81
21060014 |  |  | 1 | 7 | 1676423.85 | 693573.01 | 230 | 295 | 0.81356 | 0.18644 | 0
21060015 |  |  | 18.85 | 24 | 19910.06 | 20076.15 | 129 | 70.5 | 0.9078 | 0.092199 | 0
21060016 |  |  | 2314 | 0 | 2001598.69 | 2062900.54 | 708.1 | 0 | 0 | 0 | 0
21060017 |  |  | 7.5 | 0 | 16693.46 | 16394.66
21060018 |  |  | 493 | 183 | 275030.19 | 254322.07 | 131 | 98 | 0.98469 | 0.015306 | 0
21060020 |  |  | 1141.21 | 0 | 1249183.1804 | 1131353.15 | 40 | 0 | 0 | 0 | 0
21060021 |  |  | 0 | 41 | 197055.01 | 185830.09 | 412 | 266 | 0.99624 | 0.0037594 | 0
21060022 |  |  | 0 | 0 | 20072 | 20071.97
21060023 |  |  | 0 | 1 | 1383873.19 | 1183830.51 | 0 | 143 | 0.95105 | 0.048951 | 0
21060024 |  |  | 0 | 0 | 0.01 | 8548.03
21060025 |  |  | 0 | 0 | 5558.41 | 6326.98
21060026 |  |  | 462024.31 | 334799.75 | 18648227.365 | 18918663.84 | 19317.3 | 27959.53 | 0.93572 | 0.064281 | 0
21060027 |  |  | 1022.17 | 0 | 272353.06 | 270277.18
21060028 |  |  | 1132.27 | 0 | 392598.34 | 410811.72 | 106.6 | 0 | 0 | 0 | 0
21060029 |  |  | 0 | 0 | 0.01 | 3722.98
21060030 |  |  | 27018 | 608.26 | 1382945.59 | 1410244.1 | 115 | 1272 | 0.91195 | 0.08805 | 0
21060031 |  |  | 330.6 | 0 | 52823.62 | 52405.09 | 325.4 | 69 | 1899-12-31 | 0 | 0
21060032 |  |  | 38 | 49 | 11540.88 | 11433.4 | 83 | 72 | 0.875 | 0.125 | 0
21060033 |  |  | 92884.97 | 59460 | 501909 | 0 | 1810.97 | 0 | 0 | 0 | 0
21060034 |  |  | 50128.58 | 49943 | 14629833.234 | 12432192.39 | 9941.1 | 8978 | 0.87105 | 0.12895 | 0
21060035 |  |  | 117089 | 75954.97 | 5957945.3267 | 5661634.67 | 5739.99 | 11795 | 0.9621 | 0.037897 | 0
21060036 |  |  | 1093.67 | 0 | 132677.95 | 135343.03
21060037 |  |  | 0 | 0 | 0.01 | 70707.26
21060038 |  |  | 817.6 | 0 | 660661.65 | 676302.2
21060039 |  |  | 1020.21 | 0 | 90422.44 | 90043.14
21060040 |  |  | 6190.39 | 5876 | 404339.31 | 406582.04 | 1394.2 | 2203 | 0.93917 | 0.060826 | 0
21060041 |  |  | 132193.34 | 79189 | 714533.3117 | 793314.27 | 1810.97 | 1839.5 | 0.71922 | 0.28078 | 0
21060042 |  |  | 85 | 95 | 25054.73 | 25902.6 | 108 | 150 | 0.86667 | 0.13333 | 0
21060043 |  |  | 0 | 0 | 0.01 | 62023.73
21060044 |  |  | 1703 | 91 | 28939.1 | 32126.81 | 440.8 | 253 | 0.9249 | 0.075099 | 0
21060045 |  |  | 11471 | 37.5 | 6449194.41 | 6414181.87 | 4900.3 | 3888.91 | 0.91627 | 0.083733 | 0
21060046 |  |  | 0 | 3595 | 1298683 | 1246658.31 | 3161 | 3764.5 | 0.98619 | 0.013813 | 0
21060047, 20060058, 18000015-040, 18060047, 20060042 | 2019-06-01 | 2020-03-30 | 454430.81 | 210401 | 11166795.3706 | 11444213.16 | 18226.64 | 17464.5 | 0.91977 | 0.080233 | 0
21060048 |  |  | 0 | 914 | 515830 | 525001.44 | 1505 | 2025 | 1899-12-31 | 0 | 0
21060049 |  |  | 4 | 214 | 820705.11 | 1156955.18 | 222 | 3364.71 | 0.9251 | 0.074904 | 0
21060050 |  |  | 19129.13 | 6648 | 827677.57 | 810024.3 | 314.5 | 3416.5 | 0.87999 | 0.12001 | 0
21060051 |  |  | 7241.5 | 199.41 | 272330.64 | 285193.29 | 1052.8 | 1454.5 | 0.91509 | 0.084909 | 0
21060052 |  |  | 1343.5 | 1798.99 | 1278046 | 953958.15 | 3888.3 | 2769 | 0.85609 | 0.14391 | 0
21060053 |  |  | 26726 | 1768.83 | 1204750.2285 | 1217582.53 | 4011.29 | 4462.59 | 0.87877 | 0.12123 | 0
21060055 |  |  | 70291 | 44340.1 | 7551226.35 | 6857298.97 | 10403.61 | 15239.45 | 0.79421 | 0.20579 | 0
21060056 |  |  | 78 | 16 | 598016.12 | 580921.19 | 347 | 180 | 0.825 | 0.175 | 0
21060057 |  |  | 261 | 74.2 | 76525.49 | 74124.8 | 214.45 | 338.5 | 0.88035 | 0.11965 | 0
21060059 |  |  | 0 | 0 | 0.01 | 0
21060060 |  |  | 1778946.96 | 745910 | 120918244.0504 | 39880276.65 | 51149.72 | 23353 | 0.74025 | 0.25975 | 0
21060061 |  |  | 788051.3 | 145 | 65750616.09 | 4778134.9 | 38298.9 | 953 | 0.90031 | 0.099685 | 0
21060062 |  |  | 0 | 134 | 306472 | 307316.58 | 873 | 214 | 1899-12-31 | 0 | 0
21060063 |  |  | 1366 | 199.26 | 297373.7 | 283122.34 | 1234.7 | 368.5 | 0.75305 | 0.24695 | 0
21060064 |  |  | 509432.8 | 302200.5 | 25733405.54 | 18191955.47 | 15181.38 | 7356.2 | 0.81427 | 0.18573 | 0
21060065 |  |  | 7447.5 | 5071.5 | 1780234.387 | 1698977.45 | 7562.5 | 11419.5 | 0.97189 | 0.02811 | 0
21060066 |  |  | 294 | 707.85 | 2185730.3552 | 2183983.67 | 3206 | 5564.22 | 0.84679 | 0.15321 | 0
21060067 |  |  | 480868 | 0 | 36502649.62 | 33221964.33 | 737 | 1508.25 | 0.93486 | 0.065142 | 0
21080001 |  |  | 844 | 575 | 874379.93 | 451826.51 | 96 | 133 | 0.98496 | 0.015038 | 0
21080002 |  |  | 19 | 0 | 1357307.48 | 1016449.78 | 2448 | 3043.98 | 0.9412 | 0.057819 | 0.00098555
21080003 |  |  | 82890 | 0 | 93978580.96 | 88223984.19 | 0 | 2243.5 | 0.86561 | 0.13439 | 0
21080004 |  |  | 9881.16 | 5974 | 556964.92 | 553310.58 | 1405.4 | 1507.5 | 0.98541 | 0.014594 | 0
21080005 |  |  | 0 | 0 | 10000 | 9991.72
21080006 |  |  | 328608.5 | 5584 | 78591777.2602 | 51279707.92 | 18212.04 | 8644.48 | 0.88912 | 0.10943 | 0.001446
21080007 |  |  | 39037.61 | 11761 | 2431298 | 2097083.69 | 3108.8 | 1977.5 | 0.96789 | 0.032111 | 0
21080008 |  |  | 0 | 0 | 19800 | 3667.62
21080009 |  |  | 2883936.47 | 1492184.76 | 88187650.43 | 81043608.81 | 76900.7 | 71137.04 | 0.95233 | 0.046709 | 0.00096293
21080010 |  |  | 13 | 1 | 112155 | 121549.9 | 700 | 676 | 0.97633 | 0.023669 | 0
21080011 |  |  | 736877 | 56 | 18545006.8 | 8787473.96 | 24690.1 | 10343 | 0.98458 | 0.015034 | 0.00038673
21080012 |  |  | 4125.3 | 0 | 113021.81 | 113894.92 | 304.6 | 258 | 1899-12-31 | 0 | 0
21080013 |  |  | 102223 | 5394 | 5653850.7 | 5096856.38 | 7434.3 | 9104 | 0.91482 | 0.07958 | 0.0056019
21080014 |  |  | 0 | 0 | 64488 | 31862.34
21080015 |  |  | 804.45 | 0 | 41918.96 | 25195.18 | 280.7 | 227 | 1899-12-31 | 0 | 0
21080016 |  |  | 1275910.07 | 226604.5 | 58778015.418 | 20216895.81 | 43483.72 | 21071.25 | 0.89245 | 0.10717 | 0.00037966
21080017 |  |  | 90710 | 13019 | 5844470.28 | 1672524.89 | 4879.5 | 2430.5 | 0.94651 | 0.052253 | 0.0012343
21080018 |  |  | 0 | 0 | 0.01 | 13139.71
21080018-063 |  |  | 2 | 0 | 265979.95 | 201103.95
21080019 |  |  | 40586.63 | 3619.5 | 13891384.42 | 2468612.36 | 7417.1 | 1859 | 0.9688 | 0.030931 | 0.00026896
21090001 |  |  | 231222.27 | 59592 | 12499905.5408 | 11369946.5 | 6603.58 | 5190 | 0.92938 | 0.068112 | 0.0025048
21090002 |  |  | 59391.39 | 0 | 1714223.85 | 2075388.8 | 5 | 4867.5 | 0.96497 | 0.029687 | 0.0053416
21090003 |  |  | 699 | 0 | 4012824.1362 | 3357422.36 | 4280.17 | 9855.5 | 0.8515 | 0.10086 | 0.047638
21090004 |  |  | 50176 | 1 | 2016518.2 | 1799244.21 | 1500.88 | 1220.5 | 0.89553 | 0.093404 | 0.011061
21090005 |  |  | 0 | 0 | 68763 | 100781.15 | 0 | 21 | 0 | 0.19048 | 0.80952
21090991 |  |  | 1189 | 738 | 0 | 447911.22 | 106 | 4141.5 | 0.99276 | 0.0062779 | 0.00096583
21110001 |  |  | 0 | 0 | 35019 | 32547.94
21110001-174 |  |  | 0 | 0 | 189062 | 181166.84
21110002 |  |  | 0 | 0 | 297 | 462.5
21110002-174 |  |  | 0 | 0 | 12939 | 12072.26
21110003 |  |  | 0 | 0 | 390000.01 | 2210868.12 | 0 | 7420 | 0.91388 | 0.086119 | 0
21110003-159 |  |  | 0 | 0 | 53237697 | 0
21110004 |  |  | 0 | 0 | 524060 | 485586.27 | 0 | 1100 | 1899-12-31 | 0 | 0
21110004-174 |  |  | 0 | 0 | 3046382 | 2997885.3
21110005 |  |  | 117643 | 0 | 62961278.015 | 19661576.47 | 0 | 2067.5 | 0.99903 | 0.00096735 | 0
21110006 |  |  | 0 | 0 | 21575 | 29706.78
21110006-174 |  |  | 0 | 0 | 276003 | 272960.64
21110007 |  |  | 36 | 0 | 319423 | 301269.37
21110008 |  |  | 5822 | 0 | 644249.09 | 490565.63
21110009 |  |  | 0 | 0 | 5572 | 1484.45
21110009-174 |  |  | 0 | 0 | 128796 | 117205.11
21110010 |  |  | 0 | 0 | 1060138 | 679918.31 | 0 | 1640 | 1899-12-31 | 0 | 0
21110010-174 |  |  | 0 | 0 | 18842330 | 8795209.09
21120001 |  |  | 10 | 0 | 172745 | 111836.05
21120002 |  |  | 0 | 0 | 171389.09 | 80158.63
21120003 |  |  | 3598017.15 | 667849.26 | 1392024809.63 | 566043337.71 | 431420.68 | 122536.83 | 0.872 | 0.10032 | 0.027679
21120004 |  |  | 2816 | 0 | 1921084.75 | 815375.6
21120005 |  |  | 0 | 0 | 490000 | 443573.08
21120006 |  |  | 219152.32 | 0 | 315027854.09 | 116381374.38 | 4870.1 | 6861.5 | 0.78445 | 0.19828 | 0.01727
21120007 |  |  | 2 | 0 | 1396863.8 | 1164672.71
21120008 |  |  | 0 | 0 | 520960 | 403456.7
21126001 |  |  | 9 | 0 | 2557258 | 2193414.58
21141001, 21148003 |  |  | 31973.41 | 37421 | 19194458.32 | 17919170.17 | 58625.9 | 58924.5 | 0.74649 | 0.24818 | 0.0053285
21141002 |  |  | 7139.2 | 2518 | 94772963.3005 | 90024634.33 | 125801 | 98243.36 | 0.73479 | 0.23907 | 0.026135
21141003 |  |  | 13177.59 | 1000 | 32408252.64 | 34044809.75 | 82767 | 135903.7 | 0.66334 | 0.24968 | 0.086981
21141004 |  |  | 9993.65 | 1247 | 27559923.623 | 27843531.39 | 37526 | 38317.4 | 0.66521 | 0.30986 | 0.024936
21141005 |  |  | 0 | 0 | 110235.66 | 65378.78
21141006 |  |  | 4551.82 | 2440 | 56511014.5996 | 55422028.51 | 75386 | 79370.72 | 0.67318 | 0.31592 | 0.010898
21141007 |  |  | 1906 | 1124 | 30554240.8314 | 31855389.71 | 76459 | 129251.65 | 0.64434 | 0.29693 | 0.058723
21141008 |  |  | 1455 | 1129 | 29310464.8895 | 30212099.21 | 79185 | 124274 | 0.67119 | 0.30293 | 0.025878
21141009 |  |  | 4373.73 | 1460 | 39950179.91 | 35314338.69 | 46555 | 39241.6 | 0.77981 | 0.20402 | 0.016175
21141010 |  |  | 21153.09 | 5178 | 89634628.31 | 80195025.73 | 119062 | 113317.5 | 0.8274 | 0.1726 | 0
21141011 |  |  | 17528.86 | 923 | 41101725.5214 | 31882276.57 | 88655.5 | 75951.5 | 0.76348 | 0.23652 | 0
21141012 |  |  | 3583.4 | 2538 | 53152898.06 | 47808476.96 | 56703 | 49428.5 | 0.73795 | 0.26107 | 0.0009711
21141013 |  |  | 0 | 0 | 659490 | 529372.09
21141014 |  |  | 18550.9 | 2420.5 | 99886068.5624 | 87379423.33 | 138084 | 74026.25 | 0.88943 | 0.11057 | 0
21141015 |  |  | 0 | 0 | 5242221 | 4379108.27
21141016 |  |  | 2628.32 | 1318 | 28468629 | 18600726.48 | 63006 | 115200.34 | 0.82721 | 0.13753 | 0.035259
21141017 |  |  | 18317.15 | 3210 | 41512364.25 | 40574956.18 | 68272 | 62092.92 | 0.75065 | 0.24932 | 3.221e-05
21141018 |  |  | 22460.1 | 4927.5 | 76615614.294 | 75483978.23 | 115720 | 110115.93 | 0.75343 | 0.24657 | 0
21141019 |  |  | 4805.73 | 1790 | 43128440.08 | 40660102.37 | 109745 | 139882.8 | 0.63134 | 0.31974 | 0.048918
21141020 |  |  | 4 | 4 | 42490.68 | 22706.32 | 152 | 168 | 0.61905 | 0.38095 | 0
21141021 |  |  | 4001.21 | 0 | 114748898.68 | 20810726.9 | 171070 | 2715.5 | 0.86301 | 0.13699 | 0
21141022 |  |  | 0 | 0 | 0 | 0 | 0 | -65565.84 | 0.92861 | 0.052767 | 0.018621
21145001 |  |  | 172 | 0 | 1551545 | 918416.34 | 500 | 836.5 | 0.82679 | 0.17321 | 0
21145002 |  |  | 88 | 0 | 1464672 | 851672.85 | 500 | 937 | 0.87081 | 0.12919 | 0
21145003 |  |  | 46 | 0 | 137694 | 137603.75 | 40 | 390 | 0.82821 | 0.17179 | 0
21145004 |  |  | 3178185.63 | 1960390 | 59979283.03 | 57272031.31 | 184310.59 | 137300.02 | 0.83701 | 0.16299 | 7.2833e-06
21145005 |  |  | 5596 | 0 | 227722.5 | 235446.51 | 2632 | 3613 | 0.6525 | 0.3475 | 0
21145006 |  |  | 6545913.72 | 708656.5 | 160412656.74 | 104588729.51 | 436141.84 | 132974 | 0.90024 | 0.099764 | 0
21145007 |  |  | 8191324.11 | 0 | 123728184.94 | 15132961.65 | 368094.35 | 302.5 | 0.80992 | 0.19008 | 0
21145008 |  |  | 93 | 0 | 819067.02 | 825418.62 | 520 | 1327.5 | 0.70847 | 0.29153 | 0
21146002 |  |  | 242762.4 | 193052 | 12841360.04 | 13790645.27 | 8787.74 | 27933 | 0.77589 | 0.22411 | 0
21146003 |  |  | 47 | 0 | 17486.68 | 10597.34 | 76 | 40 | 1899-12-31 | 0 | 0
21146004 |  |  | 49 | 0 | 31739.97 | 18614.32 | 60 | 80 | 0.875 | 0.125 | 0
21146005 |  |  | 482351.1 | 281886.44 | 23654245.29 | 21379265.37 | 17920.03 | 23133 | 0.87094 | 0.12906 | 0
21146006 |  |  | 133697.45 | 108517 | 14927046.77 | 12605004.16 | 5643.23 | 5465 | 0.8694 | 0.12987 | 0.00073193
21146007 |  |  | 893 | 0 | 6812447.56 | 930490.27
21146008 |  |  | 0 | 0 | 213750 | 150387.26
21146009 |  |  | 0 | 0 | 180805 | 125327
21146010 |  |  | 0 | 0 | 148598.04 | 121435.63 | 48 | 374 | 0.95588 | 0.044118 | 0
21146011 |  |  | 148 | 0 | 12767998.57 | 8233352.24 | 0 | 308.5 | 0.90762 | 0.092382 | 0
21146012 |  |  | 69437.23 | 0 | 3678908.76 | 3513138.8 | 3192.24 | 4083.5 | 0.96743 | 0.03257 | 0
21146013 |  |  | 202521.91 | 180328 | 14998579.64 | 14083754.44 | 7774.76 | 6856.5 | 0.75381 | 0.24619 | 0
21146014 |  |  | 0 | 0 | 113210 | 93432.78 | 0 | 16 | 1899-12-31 | 0 | 0
21146015 |  |  | 4986.46 | 0 | 3885513.93 | 3418734.82
21146016 |  |  | 439018.72 | 84100 | 16866588.6175 | 15497017.57 | 27379.76 | 36011 | 0.78284 | 0.21716 | 0
21146017 |  |  | 55761.6 | 0 | 2475236.18 | 2559581.66 | 4022.08 | 7756.09 | 0.8416 | 0.1584 | 0
21146018 |  |  | 0 | 0 | 934804 | 847115.21
21146019 |  |  | 612933.38 | 174705 | 30232878.89 | 27469416.25 | 79722.12 | 81763.77 | 0.80962 | 0.19038 | 0
21146020 |  |  | 88164.03 | 0 | 14788148.34 | 627886.52 | 26106.48 | 0 | 0 | 0 | 0
21146021 |  |  | 569177.61 | 538803 | 32565763.87 | 29748069.83 | 16642.09 | 25726.5 | 0.78384 | 0.21616 | 0
21146022 |  |  | 198064.17 | 97362 | 6666937.33 | 4602138.87 | 6187.92 | 3960 | 0.9351 | 0.064899 | 0
21146023 |  |  | 103429.26 | 41591 | 5135474.89 | 2050589.97 | 3916.33 | 1092 | 0.8402 | 0.1598 | 0
21146024 |  |  | 490358.86 | 4 | 26369996 | 23387280.97 | 78890.84 | 78380.8 | 0.75682 | 0.24318 | 0
21146025 |  |  | 0 | 0 | 180805 | 140432.86
21146026 |  |  | 0 | 0 | 58995 | 46716.13
21148001 |  |  | 3148525.35 | 173445 | 3286433.86 | 2761468.89 | 8019.8 | 5351.5 | 0.84509 | 0.15491 | 0
21148002 |  |  | 7161369.6 | 501299 | 9706820.48 | 11503246.03 | 29694.71 | 49859.5 | 0.80429 | 0.19571 | 0
21148005 |  |  | 809966.44 | 816231 | 17288938.52 | 14519868.32 | 60845.78 | 51949.5 | 0.83736 | 0.16104 | 0.0015977
21148006 |  |  | 5045033 | 340839 | 5777493.1646 | 6204060.39 | 18812.26 | 19413.5 | 0.77008 | 0.22981 | 0.00010302
21148007 |  |  | 4650563 | 72632 | 4439146.14 | 3611841.8 | 19259.96 | 15241.5 | 0.79293 | 0.20149 | 0.0055769
21148008 |  |  | 12642566.16 | 221787 | 14045325.86 | 15510797.43 | 40300.5 | 53340.8 | 0.68237 | 0.30625 | 0.01138
21148009 |  |  | 2246318.32 | 20882.69 | 2060474.4542 | 1394311.77 | 6166.78 | 4420 | 0.744 | 0.24717 | 0.0088235
21148010 |  |  | 5297409.79 | 1750 | 6572756.2408 | 4825090.39 | 19440.57 | 14905.5 | 0.78213 | 0.20113 | 0.016739
21148011 |  |  | 18245742.83 | 166546.25 | 22911594.3217 | 20185545.05 | 43821.49 | 72012.5 | 0.70987 | 0.27677 | 0.013359
21148012 |  |  | 2030296.42 | 15338 | 5969002.85 | 5021551.62 | 5663.75 | 11053.75 | 0.70352 | 0.28128 | 0.015198
21148013 |  |  | 2396970.85 | 130 | 5180391.68 | 4244971 | 6280.85 | 12326.31 | 0.74893 | 0.24442 | 0.0066524
21148014 |  |  | 2281370.85 | 87 | 2645740.29 | 2261825.78 | 6875.13 | 9408 | 0.69935 | 0.29438 | 0.0062713
21148015 |  |  | 12308824.17 | 1671260 | 14819898.8468 | 14112373.56 | 53130.65 | 58306.33 | 0.75738 | 0.24262 | 0
21148016 |  |  | 5835882.2 | 40095 | 7403314.08 | 6544641.57 | 20344.46 | 23259.5 | 0.76633 | 0.23287 | 0.00079537
21148017 |  |  | 938461.5 | 0 | 1115023.64 | 936284.15 | 794.36 | 622 | 0.72347 | 0.27653 | 0
21148018 |  |  | 4931871.08 | 5084686.75 | 38521111.1245 | 29763847.03 | 113517.87 | 112345 | 0.75945 | 0.24055 | 0
21149001 |  |  | 45097.16 | 41144 | 3407815.16 | 3254909.92 | 2015.31 | 2560.5 | 0.89143 | 0.10857 | 0
21149002 |  |  | 0 | 113 | 748117.4 | 497921.29 | 0 | 123 | 1899-12-31 | 0 | 0
21149003 |  |  | 342253.64 | 270802.12 | 60448661.8404 | 57040100.64 | 49526.89 | 63227.77 | 0.82906 | 0.1634 | 0.0075442
21150001 |  |  | 0 | 0 | 15000 | 2001.47
21150002 |  |  | 0 | 0 | 9380.01 | 9166.72
21150003 |  |  | 0 | 0 | 103378.54 | 66448.55
21150004 |  |  | 0 | 0 | 342145 | 311937.08
21150004-164 |  |  | 0 | 0 | 803780 | 519825.2
21150005 |  |  | 0 | 0 | 1504402 | 1253909.74
21150006 |  |  | 0 | 0 | 0.01 | 0
21150007 |  |  | 0 | 0 | 52285134.53 | 30009661.28 | 0 | 607.5 | 0.65844 | 0.34156 | 0
21157001 |  |  | 0 | 0 | 0 | 331870.93 | 0 | 6437.46 | 0.78346 | 0.21654 | 0
21157002 |  |  | 0 | 0 | 0 | 4772.97 | 0 | 90.5 | 0.9116 | 0.088398 | 0
21157003 |  |  | 0 | 0 | 0 | 288046.56 | 0 | 1594 | 0.92346 | 0.076537 | 0
21157004 |  |  | 0 | 0 | 0 | 803782.75 | 0 | 2531 | 0.7987 | 0.2013 | 0
21157005 |  |  | 0 | 0 | 0 | 11293.34 | 0 | 133.5 | 0.97004 | 0.029963 | 0
21157006 |  |  | 0 | 0 | 0 | 68025.9 | 0 | 995 | 0.9392 | 0.060804 | 0
21157007 |  |  | 0 | 0 | 0 | 13635.83 | 0 | 301 | 0.61462 | 0.38538 | 0
21157008 |  |  | 0 | 0 | 0 | 70987.89
21157009 |  |  | 0 | 0 | 0 | 53619.82
21203 | 2004-03-14 | 2004-03-14 | 0 | 0 | 10050580 | 9901859 | 0 | 8730 | 1899-12-31 | 0 | 0
21901 | 2002-12-31 |  | 0 | 0 | 0 | 27568 | 0 | 0 | 0 | 0 | 0
21999 | 2002-12-31 |  | 0 | 0 | 0 | 195510 | 0 | 469 | 1899-12-31 | 0 | 0
22030001 |  |  | 0 | 0 | 0.01 | 3555051.24 | 0 | 11282.5 | 0.96756 | 0.029072 | 0.003368
22030002 |  |  | 5698.5 | 0 | 2459481.59 | 2336136.78 | 12897 | 11478.75 | 0.87568 | 0.1014 | 0.022912
22030003 |  |  | 22 | 0 | 875396.9332 | 485002.47 | 1383 | 892 | 0.94619 | 0.053812 | 0
22030004 |  |  | 1 | 0 | 376463.58 | 443882.57 | 207 | 871.5 | 0.95295 | 0.047045 | 0
22030005 |  |  | 0 | 0 | 1136093 | 2335.2 | 3590 | 2 | 1899-12-31 | 0 | 0
22030006 |  |  | 136444.5 | 2361.5 | 3204818.67 | 3056905.43 | 7994.91 | 7208.48 | 0.95721 | 0.042794 | 0
22030007 |  |  | 3 | 0 | 2166235.47 | 2061933.17 | 1217 | 968.62 | 0.97149 | 0.020256 | 0.0082592
22030008 |  |  | 0 | 0 | 1933517 | 896542.03 | 2871 | 1998 | 0.97573 | 0.0042543 | 0.02002
22030009 |  |  | 6198.59 | 0 | 817322.3792 | 598044.02 | 1719 | 895 | 0.98939 | 0.010615 | 0
22030010 |  |  | 29900.94 | 0 | 2158245.44 | 2230812.32 | 2927.6 | 4940 | 0.96235 | 0.030364 | 0.0072874
22030011 |  |  | 0 | 0 | 197582.71 | 174033.59 | 549 | 330.5 | 0.91679 | 0.083207 | 0
22030012 |  |  | 64096.79 | 0 | 2329867.17 | 2070937.69 | 2822.2 | 3020 | 0.90563 | 0.094371 | 0
22030013 |  |  | 1239.09 | 0 | 285966.55 | 273886.6 | 245 | 310.5 | 1899-12-31 | 0 | 0
22030014 |  |  | 0 | 0 | 2274582.59 | 1624673.36 | 4686 | 4058.5 | 0.98916 | 0.010841 | 0
22030015 |  |  | 112843.66 | 0 | 4535044.617 | 4800527.37 | 6697.68 | 8873.48 | 0.86922 | 0.12999 | 0.00078887
22030016 |  |  | 299245.28 | 0 | 11724961.32 | 3953612.88 | 19972.4 | 6065 | 0.96702 | 0.032976 | 0
22030017 |  |  | 0 | 0 | 325825.73 | 415910.86 | 312 | 419.5 | 0.95828 | 0.032181 | 0.0095352
22030018 |  |  | 129097.72 | 2 | 3767880.43 | 2842408.56 | 5913.17 | 3320 | 0.98012 | 0.01747 | 0.0024096
22030019 |  |  | 0 | 0 | 718748 | 587491.58 | 2549 | 2664 | 0.98911 | 0.010886 | 0
22030020 |  |  | 352 | 6 | 524167.0324 | 479775.53 | 2427 | 2412 | 0.93408 | 0.06592 | 0
22030021 |  |  | 0 | 0 | 136000.01 | 489683.56
22030022 |  |  | 201796.92 | 0 | 7160533.01 | 5565694.89 | 12268.1 | 9486.88 | 0.73332 | 0.26668 | 0
22030023 |  |  | 98666.9 | 29751 | 4483585.31 | 4719262.69 | 5477 | 7831 | 0.99598 | 0.0040225 | 0
22030024 |  |  | 0 | 0 | 831286 | 295402.56 | 125 | 96 | 1899-12-31 | 0 | 0
22030025 |  |  | 45525.72 | 0 | 4886423.884 | 4176292.2 | 5311 | 6366.5 | 0.92743 | 0.063457 | 0.0091102
22030026 |  |  | 5 | 0 | 545879.64 | 457076.58 | 1033 | 811 | 0.96917 | 0.030826 | 0
22030027 |  |  | 20084.03 | 0 | 2294196.97 | 2247418.5 | 2977.48 | 3342 | 0.87208 | 0.12792 | 0
22030028 |  |  | 22579.34 | 788.3 | 3562821.64 | 2236343.49 | 2165.4 | 1997 | 0.94642 | 0.05358 | 0
22030029 |  |  | 119070.43 | 42306.2 | 7414425.49 | 4855530.02 | 4688.7 | 4060 | 0.95517 | 0.044828 | 0
22030030 |  |  | 0 | 0 | 464716 | 455921.76 | 0 | 120 | 1899-12-31 | 0 | 0
22030031 |  |  | 5143 | 0 | 159638.03 | 122829.31 | 292 | 287 | 0.98432 | 0.015679 | 0
22030032 |  |  | 30610.6 | 0 | 1345622.88 | 1237357.76 | 3030.5 | 2265 | 0.94305 | 0.051656 | 0.005298
22030033 |  |  | 0 | 0 | 0.01 | 368120.47
22030034 |  |  | 6606 | 0 | 1127168.19 | 579261.4 | 1409.8 | 1096.5 | 0.96626 | 0.011856 | 0.021888
22030035 |  |  | 229241.75 | 2874 | 47045229.73 | 13827627.34 | 19203.4 | 1460.5 | 0.98973 | 0.01027 | 0
22030036 |  |  | 158720.71 | 0 | 43536549.92 | 3054250.6 | 12459.8 | 892 | 0.95964 | 0.040359 | 0
22030037 |  |  | 0 | 0 | 344101 | 276957.34 | 988 | 1102 | 0.96824 | 0.03176 | 0
22030039 |  |  | 21369.42 | 1221 | 1592287.55 | 1590255.41 | 637.8 | 923.5 | 0.99242 | 0.0075799 | 0
22030040 |  |  | 1 | 0 | 2276702.71 | 495765.35 | 16 | 328 | 1899-12-31 | 0 | 0
22030041 |  |  | 0 | 0 | 726228 | 283389.16
22030042 |  |  | 0 | 0 | 162714 | 170081.38 | 957 | 1121.5 | 0.96255 | 0.030317 | 0.0071333
22030043 |  |  | 8378.85 | 0 | 163859.84 | 110593.89 | 595.1 | 419.5 | 0.97259 | 0.027414 | 0
22030044 |  |  | 78033.7 | 0 | 3606940.03 | 3565360.83 | 858.1 | 1460.5 | 0.9911 | 0.0089011 | 0
22030045 |  |  | 134436.15 | 0 | 12872679.17 | 750872.2 | 3357.8 | 0 | 0 | 0 | 0
22030046 |  |  | 0 | 0 | 0.01 | 103500.41 | 0 | 520.9196 | 0.66022 | 0.28027 | 0.05951
22030047 |  |  | 213 | 0 | 665328.23 | 586489.86 | 714 | 388 | 1899-12-31 | 0 | 0
22030048 |  |  | 0 | 1 | 10000000 | 848283.84 | 0 | 3543.5 | 0.96811 | 0.028503 | 0.0033865
22030050 |  |  | 1 | 0 | 9320 | 9848.75 | 0 | 16 | 1899-12-31 | 0 | 0
22030051 |  |  | 5361.99 | 0 | 648804.89 | 316675.72 | 497.5 | 117.5 | 1899-12-31 | 0 | 0
22030052 |  |  | 0 | 0 | 0.01 | 23308.68
22030053 |  |  | 0 | 0 | 0.01 | 0
22030054 |  |  | 0 | 0 | 0.01 | 0
22030055 |  |  | 0 | 0 | 0.01 | 0
22030056 |  |  | 0 | 0 | 0.01 | 0
22030099 |  |  | 0 | 0 | 0.01 | 0
22040001 |  |  | 7 | 0 | 3344588.58 | 2640955.3
22040002 |  |  | 20162 | 15868 | 392021.3 | 404231.65 | 1124 | 1111.5 | 0.94242 | 0.05758 | 0
22040003 |  |  | 12149 | 0 | 208504.11 | 84522.93 | 726 | 46 | 0.91304 | 0.086957 | 0
22040004 |  |  | 0 | 0 | 0.02 | 47607.99
22040005 |  |  | 8 | 0 | 69604.28 | 33182.6
22040006 |  |  | 4647 | 10 | 507165.39 | 401322.12 | 0 | 94 | 1899-12-31 | 0 | 0
22040007 |  |  | 7136 | 79753 | 683041.94 | 387187.47 | 1524.7 | 2644 | 0.93835 | 0.061649 | 0
22040009 |  |  | 436.65 | 0 | 11681312.81 | 298380.52 | 866 | 0 | 0 | 0 | 0
22040011 |  |  | 16 | 0 | 1313676.54 | 28152.45
22040012 |  |  | 20 | 0 | 38338.81 | 25819.86 | 325 | 283 | 0.96113 | 0.038869 | 0
22040013 |  |  | 12952 | 2053 | 292568 | 140197.86 | 580.4 | 665.5 | 0.92637 | 0.073629 | 0
22040014 |  |  | 16551 | 3152 | 396912.34 | 35622.35 | 905 | 215 | 0.99535 | 0.0046512 | 0
22040015 |  |  | 26 | 0 | 1058843 | 5058.94
22040017 |  |  | 0 | 0 | 0 | 403.78
22050001 |  |  | 0 | 0 | 0.09 | 239598.01
22050002 |  |  | 38260.79 | 5324.07 | 14647378.66 | 8810382.16 | 4703.8 | 2514.6 | 0.92699 | 0.071622 | 0.0013919
22050003 |  |  | 27124.29 | 28532.65 | 649810.87 | 539088.33 | 528.9 | 560.5 | 0.99643 | 0.0035682 | 0
22050004 |  |  | 2 | 24 | 302489.65 | 310349.93 | 116 | 69 | 0.69565 | 0.30435 | 0
22050005 |  |  | 30.29 | 0 | 1079051.19 | 558791.4
22050006 |  |  | 0 | 0 | 78488.18 | 58664.77
22050007 |  |  | 15625.5 | 0 | 5389879.4 | 141119.03 | 1162.7 | 0 | 0 | 0 | 0
22055001 |  |  | 43 | 0 | 3460152.24 | 1622207.54 | 166.21 | 117.37 | 1899-12-31 | 0 | 0
22055002 |  |  | 11829.96 | 0 | 1015726.58 | 476108.76 | 1132.3 | 889.5 | 0.91962 | 0.080382 | 0
22055003 |  |  | 10 | 0 | 2559 | 2270.6
22055004 |  |  | 9 | 0 | 2170.11 | 2404.42
22055005 |  |  | 15 | 0 | 18422.35 | 18658.77
22055006 |  |  | 10 | 0 | 297397.82 | 160325.98
22055007 |  |  | 24 | 0 | 128219.47 | 104320.31 | 172 | 97.33 | 1899-12-31 | 0 | 0
22055008 |  |  | 30 | 0 | 1870401.42 | 1649266.08 | 633.9 | 1074.17 | 0.96974 | 0.030256 | 0
22055009 |  |  | 0 | 0 | 0.02 | 0
22055010 |  |  | 25 | 0 | 2113309.38 | 1632423.41
22055012 |  |  | 39133.29 | 20756 | 1092547.3792 | 1157884.17 | 1603.03 | 2411.5 | 0.95957 | 0.040431 | 0
22055013 |  |  | 22 | 0 | 5992451.54 | 777247.89
22055014 |  |  | 41865.65 | 28653 | 4061759.05 | 3494178.18 | 3548.9 | 2910.5 | 0.96427 | 0.031781 | 0.0039512
22055015 |  |  | 36043.52 | 0 | 5479419.55 | 521959.18 | 1168.7 | 0 | 0 | 0 | 0
22055016 |  |  | 4004.71 | 1667 | 2457406.72 | 1893446.56 | 1213.4 | 625.35 | 1899-12-31 | 0 | 0
22055017 |  |  | 42 | 0 | 5175037.46 | 307958.99
22055018 |  |  | 114798.23 | 14934 | 7090685.25 | 2152686.67 | 7364.7 | 2528.43 | 0.97429 | 0.025708 | 0
22055019 |  |  | 10 | 0 | 4865 | 10100.57 | 8 | 0 | 0 | 0 | 0
22055020 |  |  | 17 | 0 | 798953 | 295059.66
22055021 |  |  | 13 | 0 | 16085.18 | 6585.71 | 24 | 0 | 0 | 0 | 0
22055022 |  |  | 0 | 0 | 0 | -3.99
22055024 |  |  | 27 | 0 | 797478.34 | 297394.49 | 457 | 18 | 1899-12-31 | 0 | 0
22055025 |  |  | 27 | 0 | 222293.97 | 77574.46 | 376 | 46 | 1899-12-31 | 0 | 0
22055026 |  |  | 31 | 0 | 897386.84 | 193430.78 | 569 | 16 | 1899-12-31 | 0 | 0
22055027 |  |  | 14153.72 | 192 | 2094566.23 | 197332.31 | 854 | 0 | 0 | 0 | 0
22055028 |  |  | 14 | 0 | 18435.98 | 369.14 | 88 | 3.9 | 1899-12-31 | 0 | 0
22055029 |  |  | 12 | 0 | 7626 | 9374.75
22055030 |  |  | 12 | 0 | 14792.81 | 12791.98
22055031 |  |  | 23 | 0 | 199080.79 | 30640.89 | 40 | 0 | 0 | 0 | 0
22055032 |  |  | 12 | 0 | 58855.36 | 669.42
22055033 |  |  | 21 | 0 | 1342215.89 | 21925.71
22055034 |  |  | 14 | 0 | 7394.4 | 0
22055035 |  |  | 0 | 0 | 0.01 | 25751
22055036 |  |  | 15 | 0 | 41621.97 | 29246.07
22055037 |  |  | 17 | 0 | 13792.95 | 5670.32 | 4 | 0 | 0 | 0 | 0
22055038 |  |  | 0 | 0 | 0.01 | 0
22055039 |  |  | 0 | 0 | 0.01 | 0
22055040 |  |  | 0 | 0 | 0.01 | 0
22055041 |  |  | 0 | 0 | 0.02 | 10800
22055042 |  |  | 0 | 0 | 0.01 | 0
22055043 |  |  | 0 | 0 | 0.01 | 0
22060001 |  |  | 19 | 40 | 80534.13 | 85310.3 | 59 | 40 | 1899-12-31 | 0 | 0
22060002 |  |  | 242.5 | 0 | 131683.97 | 136279.04 | 112 | 0 | 0 | 0 | 0
22060003 |  |  | 8436 | 542.19 | 413338.74 | 394953.19 | 662.2 | 1250.11 | 0.91561 | 0.084393 | 0
22060004 |  |  | 71 | 0 | 33323.04 | 33286.19
22060005 |  |  | 9 | 0 | 7601951.2 | 1325501.76 | 0 | 56 | 1899-12-31 | 0 | 0
22060006 |  |  | 79570.67 | 527 | 13222136.33 | 3354010.26 | 432.6 | 548.5 | 0.93528 | 0.064722 | 0
22060007 |  |  | 179915.62 | 5789.5 | 5507171.37 | 3886211.88 | 5482.5 | 2457.75 | 0.91924 | 0.080765 | 0
22060008 |  |  | 17354 | 75.24 | 1562892.4 | 1502039.58 | 1093.8 | 2355.5 | 0.8391 | 0.1609 | 0
22060009 |  |  | 1951.5 | 270 | 601945.29 | 598582.47 | 267.2 | 636.5 | 0.91909 | 0.080911 | 0
22060010 |  |  | 11.5 | 0 | 196798.87 | 177308.97
22060011 |  |  | 0 | 0 | 0.02 | 46219.01
22060012 |  |  | 18245 | 15733.85 | 1859237.43 | 1159721.07 | 1629 | 1460 | 0.96541 | 0.034589 | 0
22060013 |  |  | 2272 | 1864.48 | 1567136.39 | 1125245.56 | 2538.9 | 2906.5 | 0.86633 | 0.13367 | 0
22060014 |  |  | 7 | 0 | 205078 | 69676.82
22060015 |  |  | 0 | 0 | 0.01 | 217818.4
22060016 |  |  | 0 | 0 | 0.01 | 387184.59
22060017 |  |  | 14319 | 0 | 2510691.78 | 490918.23 | 830.2 | 0 | 0 | 0 | 0
22060018 |  |  | 15514.5 | 0 | 1301980.76 | 1262518.72 | 290 | 1127.5 | 0.8133 | 0.1867 | 0
22060019 |  |  | 30 | 0 | 83050.27 | 69413.2
22060020 |  |  | 1049 | 0 | 370750.38 | 263407.19
22060021 |  |  | 300 | 0 | 14282.53 | 18280.66 | 152 | 0 | 0 | 0 | 0
22060022 |  |  | 382 | 18.6 | 62739.21 | 60291.38 | 154 | 51 | 1899-12-31 | 0 | 0
22060023 |  |  | 7.25 | 0 | 418463.89 | 54748.94
22060024 |  |  | 0 | 0 | 0.02 | 92169.86
22060025 |  |  | 4 | 0 | 29377.01 | 19275.07
22060026 |  |  | 11 | 0 | 0.01 | 1599.68
22060027 |  |  | 10149 | 1917.5 | 715576.23 | 594887.14 | 2010.3 | 1376.5 | 0.81511 | 0.18489 | 0
22060028 |  |  | 0 | 0 | 0.01 | 9600
22060029 |  |  | 0 | 0 | 0.01 | 5790
22060030 |  |  | 13092.5 | 0 | 710017.53 | 11160.11
22060031 |  |  | 0 | 21 | 477234 | 27727.73 | 1780 | 37 | 1899-12-31 | 0 | 0
22060032 |  |  | 7031 | 0 | 228040.02 | 16812.3
22060033 |  |  | 4507 | 0 | 209913.88 | 61707.09 | 294.5 | 0 | 0 | 0 | 0
22060034 |  |  | 0 | 0 | 4388511.02 | 81298.32
22060035 |  |  | 295 | 0 | 295536.8 | 84038.17
22060036 |  |  | 485.48 | 66 | 377902.2 | 313046.72 | 219.9 | 47 | 0.97872 | 0.021277 | 0
22060037 |  |  | 6226 | 0 | 96315.44 | 1599.25 | 105 | 0 | 0 | 0 | 0
22060038 |  |  | 0 | 0 | 0.01 | 6679.62
22060039 |  |  | 0 | 0 | 0.01 | 0
22060040 |  |  | 0 | 16 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0
22065001 |  |  | 0 | 0 | 0.01 | 418885.06
22065002 |  |  | 0 | 0 | 200000 | 389061.36
22065003 |  |  | 0 | 0 | 7000 | 6116.01
22065004 |  |  | 0 | 0 | 0.01 | 14617.89 | 0 | 94 | 0.94681 | 0.053191 | 0
22065005 |  |  | 0 | 0 | 0.01 | 76480.84
22080001 |  |  | 132 | 0 | 19344 | 14785.13
22080002 |  |  | 0 | 0 | 0.01 | 22439.95 | 0 | 8 | 1899-12-31 | 0 | 0
22080003 |  |  | 89800 | 3186 | 2549427.61 | 1924263.74 | 5053.6 | 4730.8 | 0.95142 | 0.048153 | 0.00042276
22080004 |  |  | 0 | 0 | 0.01 | 3375.75
22080005 |  |  | 69320.98 | 24799 | 5296929.77 | 4851414.88 | 5297.1 | 6685.5 | 0.97023 | 0.027373 | 0.0023932
22080006 |  |  | 40 | 0 | 327505.69 | 625 | 400 | 0 | 0 | 0 | 0
22080007 |  |  | 14178 | 0 | 241970.96 | 253960.86 | 628.6 | 911 | 1899-12-31 | 0 | 0
22080008 |  |  | 0 | 0 | 25470 | 21165.7 | 60 | 40 | 1899-12-31 | 0 | 0
22080009 |  |  | 0 | 0 | 0.01 | 104789.6
22080010 |  |  | 0 | 0 | 0.01 | 176223.32
22080011 |  |  | 4 | 0 | 131195.22 | 108072.28 | 136 | 29 | 0.034483 | 0.96552 | 0
22080012 |  |  | 1113.1 | 650 | 281353.77 | 258340.64 | 345.4 | 137 | 0.9708 | 0.029197 | 0
22080013 |  |  | 0 | 0 | 0.01 | 15074.12
22080013-063 |  |  | 5 | 0 | 594939.27 | 16784.89
22080014 |  |  | 0 | 0 | 0.01 | 13657
22080015 |  |  | 0 | 0 | 0.01 | 3178.9 | 0 | 40 | 1899-12-31 | 0 | 0
22080016 |  |  | 0 | 0 | 0.01 | 0
22080017 |  |  | 0 | 0 | 0.01 | 179
22080018 |  |  | 0 | 0 | 0.01 | 6656
22090001 |  |  | 13883 | 2976 | 21329649.1 | 17012983.45 | 3888 | 4497.5 | 0.94697 | 0.052362 | 0.00066704
22090002 |  |  | 54631 | 0 | 6411135 | 5073683.67 | 3095.1 | 1789.5 | 0.95138 | 0.048617 | 0
22090003 |  |  | 240 | 0 | 520685 | 384323.79 | 0 | 162 | 0.93827 | 0.061728 | 0
22090004 |  |  | 1810 | 0 | 1694397 | 451047.34
22090005 |  |  | 5212.8 | 0 | 4607608 | 1734599.4 | 4840.8 | 2448.5 | 0.89014 | 0.071064 | 0.038799
22090006 |  |  | 39575 | 0 | 24134498.69 | 2004434.36 | 3569.3 | 730 | 0.95411 | 0.043151 | 0.0027397
22110001 |  |  | 0 | 0 | 110.01 | 763.55
22110001-174 |  |  | 0 | 0 | 31875 | 30250.14
22110002 |  |  | 0 | 0 | 127537 | 29979.04
22110002-174 |  |  | 0 | 0 | 2002971 | 1891057.09
22110003 |  |  | 0 | 0 | 259778 | 0
22110004 |  |  | 0 | 0 | 3253679.8116 | 3284636.38 | 0 | 536.5 | 0.81174 | 0.16962 | 0.018639
22110005 |  |  | 0 | 0 | 35667 | 32105.79
22110006 |  |  | 163 | 0 | 9935126.08 | 119590.25
22110007 |  |  | 118 | 0 | 21447210.51 | 13340349.49 | 0 | 362 | 0.93923 | 0.060773 | 0
22110008 |  |  | 250404 | 0 | 91448691 | 6554147.21
22110009 |  |  | 139443 | 0 | 63872156.6 | 3308399.1
22110010 |  |  | 0 | 0 | 1923144 | 155341.61
22110011 |  |  | 306 | 0 | 18144559 | 238366.46
22120001 |  |  | 0 | 0 | 4822591.44 | 3757541.88
22120002 |  |  | 0 | 5436 | 286566941 | 30395260.75 | 0 | 8055.5 | 0.75483 | 0.24517 | 0
22120003 |  |  | 244 | 7 | 1328394.9108 | 782160.88 | 204.9 | 411 | 0.91484 | 0.085158 | 0
22120004 |  |  | 0 | 0 | 78985 | 20298.06
22120005 |  |  | 0 | 0 | 243586.8 | 185307.01
22120006 |  |  | 0 | 0 | 84583.9 | 25937.24
22120007 |  |  | 0 | 0 | 0 | 7612.01
22120008 |  |  | 0 | 0 | 0 | 52645.98
22120009 |  |  | 0 | 0 | 0 | 29129.05 | 0 | 395 | 0.99494 | 0.0050633 | 0
22120010 |  |  | 0 | 0 | 172825 | 1257.56
22141001 |  |  | 0 | 0 | 660250 | 350328.7
22141003 |  |  | 0 | 0 | 14569082.28 | 116219.63 | 0 | 30 | 0.66667 | 0.33333 | 0
22141004 |  |  | 0 | 0 | 256765 | 143284.96
22141005 |  |  | 0 | 0 | 194750 | 163194.11
22141006 |  |  | 0 | 0 | 800634 | 691492.54
22141007 |  |  | 2714.45 | 488 | 19925561.34 | 12654275.5 | 49401 | 37552.7 | 0.74315 | 0.16655 | 0.0903
22141009 |  |  | 0 | 0 | 271700 | 25275
22141010 |  |  | 0 | 0 | 1156420 | 670998.17
22141011 |  |  | 661.33 | 0 | 1208764.5 | 825723.4 | 1620 | 195 | 0.70513 | 0.29487 | 0
22141012 |  |  | 0 | 0 | 24479678.59 | 84418.37
22141013 |  |  | 0 | 0 | 2053817 | 113572.92
22141015 |  |  | 0 | 0 | 31632361.99 | 233715.45
22141016 |  |  | 0 | 0 | 151937 | 2542.15
22141017 |  |  | 0 | 0 | 35030.68 | 6224.71 | 152 | 0 | 0 | 0 | 0
22141018 |  |  | 154 | 73 | 6564697.3 | 1653989.54 | 4410 | 3308.5 | 0.86882 | 0.13118 | 0
22141019 |  |  | 0 | 0 | 48426665.15 | 25
22141021 |  |  | 0 | 0 | 72950887 | 1790.08
22141023 |  |  | 9 | 0 | 498586.5 | 439258.18 | 3902.5 | 5981.5 | 0.81744 | 0.18256 | 0
22145001 |  |  | 123 | 0 | 640290.51 | 482871.55 | 104 | 0 | 0 | 0 | 0
22145002 |  |  | 123 | 0 | 610222.51 | 362202.47 | 104 | 0 | 0 | 0 | 0
22145003 |  |  | 122 | 0 | 651140.01 | 382117.22 | 104 | 0 | 0 | 0 | 0
22145004 |  |  | 111 | 0 | 594498.51 | 401234.31 | 104 | 0 | 0 | 0 | 0
22145005 |  |  | 123 | 0 | 588526.01 | 296381.19 | 104 | 0 | 0 | 0 | 0
22145006 |  |  | 123 | 0 | 672378.51 | 286846.57 | 104 | 0 | 0 | 0 | 0
22145007 |  |  | 20 | 0 | 12359081 | 6730219.02 | 479 | 555 | 0.84955 | 0.15045 | 0
22145008 |  |  | 6 | 0 | 6572253 | 1941504.7
22145009 |  |  | 6 | 0 | 974812 | 307202.01
22145010 |  |  | 0 | 0 | 71566.01 | 34644.48 | 0 | 0 | 0 | 0 | 0
22145011 |  |  | 1200 | 0 | 81500 | 50135.66 | 1100 | 960 | 0.83333 | 0.16667 | 0
22145012 |  |  | 6 | 0 | 9771265 | 70262.87
22145013 |  |  | 6 | 0 | 9108967 | 69203.64
22145014 |  |  | 6 | 0 | 10249694 | 76436.3
22146001 |  |  | 484331.96 | 0 | 31796250.01 | 2514029.82 | 30362.44 | 0 | 0 | 0 | 0
22146002 |  |  | 0 | 0 | 2539540 | 283709.83
22146003 |  |  | 0 | 0 | 128745.8 | 98632.6 | 0 | 901 | 0.78468 | 0.21532 | 0
22146004 |  |  | 0 | 0 | 2438869.07 | 1820890.78
22146005 |  |  | 0 | 0 | 906271 | 5992.46
22146007 |  |  | 682 | 0 | 8992726 | 2000.38
22146008 |  |  | 21 | 0 | 222851.95 | 49588.12 | 0 | 292.5 | 0.77607 | 0.22393 | 0
22146009 |  |  | 0 | 0 | 496926.42 | 193550.12 | 0 | 888.5 | 0.78391 | 0.21609 | 0
22148001 |  |  | 10925884 | 466641.25 | 11708644.94 | 10965138.82 | 52037.93 | 35550.47 | 0.77199 | 0.22801 | 0
22148002 |  |  | 8554749.82 | 0 | 8258988.64 | 7209975.31 | 35706.31 | 34100 | 0.72176 | 0.27824 | 0
22148003 |  |  | 960581.5 | 12881.55 | 1150288.69 | 904440.73 | 3478.53 | 2547.5 | 0.66045 | 0.33955 | 0
22148004 |  |  | 5363797.35 | 28162 | 4019733.96 | 2831285.26 | 8752.6 | 11031 | 0.7561 | 0.20633 | 0.037576
22148005 |  |  | 1202056.3 | 489795 | 19862193.2044 | 12032353.45 | 57462.51 | 41933.88 | 0.80564 | 0.19317 | 0.0011924
22148006 |  |  | 3746108.31 | 156705 | 3859565.9928 | 2169509.28 | 12198.12 | 6267 | 0.73544 | 0.26456 | 0
22148007 |  |  | 2855682.39 | 197706.7 | 3064918.87 | 2257403.96 | 10240.81 | 6835.32 | 0.71328 | 0.28672 | 0
22148009 |  |  | 9131862.95 | 618.5 | 8826411.16 | 5934455.84 | 24750.71 | 25224 | 0.70025 | 0.2971 | 0.0026562
22148010 |  |  | 923997.36 | 612204.69 | 18172502.56 | 15125907.41 | 254316.37 | 57699.16 | 0.79547 | 0.20002 | 0.0045061
22148011 |  |  | 14464146.64 | 797815.05 | 17466737.09 | 14970975.54 | 54147.3 | 49920.61 | 0.77552 | 0.22443 | 5.008e-05
22148012 |  |  | 738240.5 | 57506 | 1046305.34 | 942088.45 | 3047.05 | 2103.5 | 0.67126 | 0.32874 | 0
22148013 |  |  | 1479576.62 | 69146 | 742050.54 | 532112.97 | 2755.21 | 2383 | 0.61078 | 0.38922 | 0
22148014 |  |  | 159064 | 51328 | 4690117.5 | 1571032.67 | 6700 | 6773 | 0.7758 | 0.2242 | 0
22148016 |  |  | 12968413 | 130199 | 20672199.9 | 2281218.27 | 68410.97 | 10189.5 | 0.82016 | 0.17984 | 0
22148018 |  |  | 3434963.31 | 19717 | 3911128.3 | 2577518.54 | 10897.91 | 10197.98 | 0.90886 | 0.091144 | 0
22148019 |  |  | 12590694.52 | 14778 | 12443508.09 | 2110933.51 | 36818.66 | 8289.02 | 0.82684 | 0.17316 | 0
22148020 |  |  | 100 | 0 | 70870 | 70592.02 | 0 | 480 | 0.83333 | 0.16667 | 0
22148021 |  |  | 2 | 0 | 121899 | 115880.27 | 0 | 962.5 | 0.86442 | 0.13558 | 0
22148022 |  |  | 8184487 | 152 | 3047468.34 | 983640.35 | 4851.12 | 3278 | 0.82672 | 0.17328 | 0
22148023 |  |  | 1000553.97 | 14594.4 | 1509149.65 | 51223.46 | 2604.84 | 636.5 | 0.80754 | 0.19246 | 0
22148024 |  |  | 575238.23 | 53754.9 | 470290.29 | 195149.88 | 1491.24 | 908.5 | 0.71326 | 0.28674 | 0
22149001 |  |  | 1693 | 0 | 832769 | 559055.46
22149002 |  |  | 394273.14 | 0 | 22892009.16 | 2513727.83 | 37438.74 | 409 | 0.94866 | 0 | 0.051345
22149003 |  |  | 0 | 0 | 909640.02 | 637593.02
22149004 |  |  | 305949.47 | 0 | 14312536.68 | 1256513.09 | 33663.05 | 32 | 0.375 | 0.625 | 0
22149005 |  |  | 0 | 0 | 5280406.49 | 1908773.82
22149006 |  |  | 0 | 0 | 4909796.15 | 1760786.31
22149007 |  |  | 0 | 0 | 16470081.6 | 232037.85
22149008 |  |  | 0 | 0 | 14978142 | 2346751.84
22150001 |  |  | 0 | 0 | 710589.4 | 608821.26
22150002 |  |  | 0 | 0 | 2814652 | 862767.68 | 0 | 0 | 0 | 0 | 0
22150003 |  |  | 0 | 0 | 143206 | 50950.99
22150004 |  |  | 0 | 0 | 32105600 | 15060799.55
22150004-143 |  |  | 121150 | 0 | 511828604.38 | 81102500.87 | 32581 | 10685.5 | 0.88031 | 0.11132 | 0.0083758
22150005 |  |  | 0 | 0 | 0.01 | 0
22150005-143 |  |  | 96230 | 0 | 294383075.14 | 46127129.39 | 85557.66 | 0 | 0 | 0 | 0
22150006 |  |  | 0 | 0 | 0.01 | 4495.7
22150006-143 |  |  | 1 | 0 | 27170957 | 8775414.03 | 0 | 3813.5 | 0.89078 | 0.098597 | 0.01062
22150007 |  |  | 0 | 0 | 0.01 | 0
22150007-143 |  |  | 495187 | 0 | 24711782 | 1100156.66 | 3937 | 0 | 0 | 0 | 0
22150008 |  |  | 0 | 0 | 0.02 | 150377.88
22150009 |  |  | 0 | 0 | 0.01 | 340835.89
22150010 |  |  | 0 | 0 | 130000 | 126333.25
(blank)
18000001-040, 18040002, 19040002 | 2019-01-01 | 2020-07-21 | 572359.67 | 3982 | 45245324.92 | 46410696.68 | 12758.2 | 16430 | 0.8266 | 0.1734 | 0
19030021, 19030022, 19030006, 19030005, 19030040, 19030039, 19030038 | 2019-01-01 | 2019-07-31 | 5558 | 0 | 10963173.03 | 10871575.91 | 9314 | 12228.83 | 0.94154 | 0.058462 | 0
18146009, 18148006, 18141004 | 2018-05-21 | 2018-12-29 | 1098198 | 1092144 | 120703583.4731 | 122454020.61 | 181135.12 | 229979.1 | 0.66724 | 0.30771 | 0.025054
Grand Total | 2000-12-31 | 2023-08-01 | 11171740128.1079 | 13147340493.69 | 41732760757.7221 | 34487885237.26 | 48366958.2911 | 54330524.2801 | 0.83539 | 0.11023 | 0.0058258

## 2022
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Chicago Operations | 22090001 | QTS - 4.5MW F Block |  |  | 0 | 13883 | 2976 | 21329649.1 | 17012983.45 | 3888 | 4497.5 | 94.7% | 5.236% | 0.0667%
Chicago Operations | 22090003 | Loyola - Chicago Small Proj 22 |  |  | 0 | 240 | 0 | 520685 | 384323.79 | 0 | 162 | 93.83% | 6.173% | 0%
Chicago Operations | 22090004 | Allstate-Hudson Infrastructure |  |  | 4000 | 1810 | 0 | 1694397 | 451047.34
Chicago Operations | 22090005 | Lurie-9Enable/19Pharm/Biorepo |  |  | 10000 | 5212.8 | 0 | 4607608 | 1734599.4 | 4840.8 | 2448.5 | 89.01% | 7.106% | 3.88%
Chicago Operations | 22090002 | Wheaton - McAlister Reno |  |  | 19200 | 54631 | 0 | 6411135 | 5073683.67 | 3095.1 | 1789.5 | 95.14% | 4.862% | 0%
Chicago Operations | 22090006 | Esperanza Health Center |  |  | 45000 | 39575 | 0 | 24134498.69 | 2004434.36 | 3569.3 | 730 | 95.41% | 4.315% | 0.274%
Civil Group Operations | 22148001 | Chevelon Butte Wind - Civil |  |  | 0 | 10925884 | 466641.25 | 11708644.94 | 10965138.82 | 52037.93 | 35550.47 | 77.2% | 22.8% | 0%
Civil Group Operations | 22148002 | Appaloosa Wind - Civil |  |  | 0 | 8554749.82 | 0 | 8258988.64 | 7209975.31 | 35706.31 | 34100 | 72.18% | 27.82% | 0%
Civil Group Operations | 22148003 | Stampede Storage - Civil |  |  | 0 | 960581.5 | 12881.55 | 1150288.69 | 904440.73 | 3478.53 | 2547.5 | 66.05% | 33.95% | 0%
Civil Group Operations | 22148004 | Laurel Mtn AES Repower - Civil |  |  | 0 | 5363797.35 | 28162 | 4019733.96 | 2831285.26 | 8752.6 | 11031 | 75.61% | 20.63% | 3.758%
Civil Group Operations | 22148005 | Inertia Wind - Civil |  |  | 0 | 1202056.3 | 489795 | 19862193.2044 | 12032353.45 | 57462.51 | 41933.88 | 80.56% | 19.32% | 0.1192%
Civil Group Operations | 22148006 | King Mountain Power - Civil |  |  | 0 | 3746108.31 | 156705 | 3859565.9928 | 2169509.28 | 12198.12 | 6267 | 73.54% | 26.46% | 0%
Civil Group Operations | 22148007 | Wolf Hollow Power - Civil |  |  | 0 | 2855682.39 | 197706.7 | 3064918.87 | 2257403.96 | 10240.81 | 6835.32 | 71.33% | 28.67% | 0%
Civil Group Operations | 22148009 | Eclipse & ML Repower - Civil |  |  | 0 | 9131862.95 | 618.5 | 8826411.16 | 5934455.84 | 24750.71 | 25224 | 70.02% | 29.71% | 0.2656%
Civil Group Operations | 22148010 | Chokecherry Sierra Madre 2022 |  |  | 0 | 923997.36 | 612204.69 | 18172502.56 | 15125907.41 | 254316.37 | 57699.16 | 79.55% | 20% | 0.4506%
Civil Group Operations | 22148011 | Texas Solar Nova I - Civil |  |  | 0 | 14464146.64 | 797815.05 | 17466737.09 | 14970975.54 | 54147.3 | 49920.61 | 77.55% | 22.44% | 0.005008%
Civil Group Operations | 22148012 | Fort Stockton Power - Civil |  |  | 0 | 738240.5 | 57506 | 1046305.34 | 942088.45 | 3047.05 | 2103.5 | 67.13% | 32.87% | 0%
Civil Group Operations | 22148013 | Abilene Power - Civil |  |  | 0 | 1479576.62 | 69146 | 742050.54 | 532112.97 | 2755.21 | 2383 | 61.08% | 38.92% | 0%
Civil Group Operations | 22148014 | ELS UNO State Street - Civil |  |  | 0 | 159064 | 51328 | 4690117.5 | 1571032.67 | 6700 | 6773 | 77.58% | 22.42% | 0%
Civil Group Operations | 22148016 | White Rock Wind - Civil |  |  | 0 | 12968413 | 130199 | 20672199.9 | 2281218.27 | 68410.97 | 10189.5 | 82.02% | 17.98% | 0%
Civil Group Operations | 22148018 | Grand Meadow Repower - Civil |  |  | 0 | 3434963.31 | 19717 | 3911128.3 | 2577518.54 | 10897.91 | 10197.98 | 90.89% | 9.114% | 0%
Civil Group Operations | 22148019 | Texas Solar Nova II - Civil |  |  | 0 | 12590694.52 | 14778 | 12443508.09 | 2110933.51 | 36818.66 | 8289.02 | 82.68% | 17.32% | 0%
Civil Group Operations | 22148020 | Nobles ADLS Repower - Civil |  |  | 0 | 100 | 0 | 70870 | 70592.02 | 0 | 480 | 83.33% | 16.67% | 0%
Civil Group Operations | 22148021 | Nobles V136 Repower - Civil |  |  | 0 | 2 | 0 | 121899 | 115880.27 | 0 | 962.5 | 86.44% | 13.56% | 0%
Civil Group Operations | 22148022 | Pyron Repower - Civil |  |  | 0 | 8184487 | 152 | 3047468.34 | 983640.35 | 4851.12 | 3278 | 82.67% | 17.33% | 0%
Civil Group Operations | 22148023 | UNO1A Substation - Civil |  |  | 0 | 1000553.97 | 14594.4 | 1509149.65 | 51223.46 | 2604.84 | 636.5 | 80.75% | 19.25% | 0%
Civil Group Operations | 22148024 | Revolution Storage - Civil |  |  | 0 | 575238.23 | 53754.9 | 470290.29 | 195149.88 | 1491.24 | 908.5 | 71.33% | 28.67% | 0%
Data Center Operations | 22120001 | Meta - 2022 Program Services |  |  | 0 | 0 | 0 | 4822591.44 | 3757541.88
Data Center Operations | 22120003 | Meta - EAG Retrofits 2022 SMA |  |  | 0 | 244 | 7 | 1328394.9108 | 782160.88 | 204.9 | 411 | 91.48% | 8.516% | 0%
Data Center Operations | 22120004 | Google - UNO 2 Master Planning |  |  | 0 | 0 | 0 | 78985 | 20298.06
Data Center Operations | 22120005 | Meta - Retrofits PMA 2022 |  |  | 0 | 0 | 0 | 243586.8 | 185307.01
Data Center Operations | 22120006 | Google EWD Campus Planning |  |  | 0 | 0 | 0 | 84583.9 | 25937.24
Data Center Operations | 22120007 | Google - Bluesky Expansion |  |  | 0 | 0 | 0 | 0 | 7612.01
Data Center Operations | 22120009 | Google UNO1A-Offsite Formwork |  |  | 0 | 0 | 0 | 0 | 29129.05 | 0 | 395 | 99.49% | 0.5063% | 0%
Data Center Operations | 22120008 | Google - UNO Building 2 |  |  | 350000 | 0 | 0 | 0 | 52645.98
Data Center Operations | 22120002 | Meta - UCO |  |  | 2500000 | 0 | 5436 | 286566941 | 30395260.75 | 0 | 8055.5 | 75.48% | 24.52% | 0%
DCS-G+ Operations | 22120010 | Google - NBF1A YAWN |  |  | 300000 | 0 | 0 | 172825 | 1257.56
Denver Operations | 22060001 | SCL-LMC Irrigation Repairs |  |  | 0 | 19 | 40 | 80534.13 | 85310.3 | 59 | 40 | 100% | 0% | 0%
Denver Operations | 22060002 | SCL-LMC W Pines Cooling |  |  | 0 | 242.5 | 0 | 131683.97 | 136279.04 | 112 | 0 | 0% | 0% | 0%
Denver Operations | 22060004 | SCL-LMC Water Heater |  |  | 0 | 71 | 0 | 33323.04 | 33286.19
Denver Operations | 22060005 | MDI-3043 Walnut |  |  | 0 | 9 | 0 | 7601951.2 | 1325501.76 | 0 | 56 | 100% | 0% | 0%
Denver Operations | 22060007 | MC Truck Dock Repairs |  |  | 0 | 179915.62 | 5789.5 | 5507171.37 | 3886211.88 | 5482.5 | 2457.75 | 91.92% | 8.076% | 0%
Denver Operations | 22060008 | NJH - MIDC Remodel |  |  | 0 | 17354 | 75.24 | 1562892.4 | 1502039.58 | 1093.8 | 2355.5 | 83.91% | 16.09% | 0%
Denver Operations | 22060010 | SCL-SJB Electrical Coord |  |  | 0 | 11.5 | 0 | 196798.87 | 177308.97
Denver Operations | 22060012 | Woodward - Small Projects 2022 |  |  | 0 | 18245 | 15733.85 | 1859237.43 | 1159721.07 | 1629 | 1460 | 96.54% | 3.459% | 0%
Denver Operations | 22060013 | SCL - SJH LinAcc Remodel |  |  | 0 | 2272 | 1864.48 | 1567136.39 | 1125245.56 | 2538.9 | 2906.5 | 86.63% | 13.37% | 0%
Denver Operations | 22060014 | PA-07 Stockpile |  |  | 0 | 7 | 0 | 205078 | 69676.82
Denver Operations | 22060018 | NJH-Morgridge Academy |  |  | 0 | 15514.5 | 0 | 1301980.76 | 1262518.72 | 290 | 1127.5 | 81.33% | 18.67% | 0%
Denver Operations | 22060019 | SCL-SJB Smoke Detector |  |  | 0 | 30 | 0 | 83050.27 | 69413.2
Denver Operations | 22060020 | SCL-SJB Life Safety Remed |  |  | 0 | 1049 | 0 | 370750.38 | 263407.19
Denver Operations | 22060021 | SCL-LMC W Pines Waste |  |  | 0 | 300 | 0 | 14282.53 | 18280.66 | 152 | 0 | 0% | 0% | 0%
Denver Operations | 22060022 | SCL-LMC W Pines Load Bank |  |  | 0 | 382 | 18.6 | 62739.21 | 60291.38 | 154 | 51 | 100% | 0% | 0%
Denver Operations | 22060025 | SCL-SJB Small Capital 2022 |  |  | 0 | 4 | 0 | 29377.01 | 19275.07
Denver Operations | 22060026 | SCL-SJB OPEX Projects |  |  | 0 | 11 | 0 | 0.01 | 1599.68
Denver Operations | 22060027 | NJH-MRI/CT Project |  |  | 0 | 10149 | 1917.5 | 715576.23 | 594887.14 | 2010.3 | 1376.5 | 81.51% | 18.49% | 0%
Denver Operations | 22060029 | MHUW Renovations |  |  | 0 | 0 | 0 | 0.01 | 5790
Denver Operations | 22060030 | SCL-SJB RMAP Lab |  |  | 0 | 13092.5 | 0 | 710017.53 | 11160.11
Denver Operations | 22060031 | Park Creek-Filing 59 "IFDA MH" |  |  | 0 | 0 | 21 | 477234 | 27727.73 | 1780 | 37 | 100% | 0% | 0%
Denver Operations | 22060032 | SCL-SJB NUC Med Exhaust |  |  | 0 | 7031 | 0 | 228040.02 | 16812.3
Denver Operations | 22060034 | Denver Broncos Scoreboard |  |  | 0 | 0 | 0 | 4388511.02 | 81298.32
Denver Operations | 22060035 | SCL-SJB Patient Lifts |  |  | 0 | 295 | 0 | 295536.8 | 84038.17
Denver Operations | 22060037 | SCL-SJB PPBR Panel Replacement |  |  | 0 | 6226 | 0 | 96315.44 | 1599.25 | 105 | 0 | 0% | 0% | 0%
Denver Operations | 22060009 | CoorsTek NT154 |  |  | 1000 | 1951.5 | 270 | 601945.29 | 598582.47 | 267.2 | 636.5 | 91.91% | 8.091% | 0%
Denver Operations | 22060023 | SCL-SJB MRI Chiller |  |  | 1000 | 7.25 | 0 | 418463.89 | 54748.94
Denver Operations | 22060033 | NJH-Level 3 Imaging Recep |  |  | 1000 | 4507 | 0 | 209913.88 | 61707.09 | 294.5 | 0 | 0% | 0% | 0%
Denver Operations | 22060036 | InterMtn - LMC - Emerg Repair |  |  | 1000 | 485.48 | 66 | 377902.2 | 313046.72 | 219.9 | 47 | 97.87% | 2.128% | 0%
Denver Operations | 22060003 | DHHA-OBGYN |  |  | 4901 | 8436 | 542.19 | 413338.74 | 394953.19 | 662.2 | 1250.11 | 91.56% | 8.439% | 0%
Denver Operations | 22060017 | SCLH MGFR Airport & Alameda |  |  | 10000 | 14319 | 0 | 2510691.78 | 490918.23 | 830.2 | 0 | 0% | 0% | 0%
Denver Operations | 22060028 | Cleo Parker Expansion |  |  | 22000 | 0 | 0 | 0.01 | 9600
Denver Operations | 22060038 | Xcel Aurora Service Center |  |  | 32500 | 0 | 0 | 0.01 | 6679.62
Denver Operations | 22060006 | Pearl East Campus |  |  | 40000 | 79570.67 | 527 | 13222136.33 | 3354010.26 | 432.6 | 548.5 | 93.53% | 6.472% | 0%
Denver Operations | 22060011 | Arista C2 Office Building |  |  | 81000 | 0 | 0 | 0.02 | 46219.01
Denver Operations | 22060015 | HighPoint-Whole Foods |  |  | 140000 | 0 | 0 | 0.01 | 217818.4
Denver Operations | 22060024 | OneFlight International |  |  | 175000 | 0 | 0 | 0.02 | 92169.86
Denver Operations | 22060040 | Highpoint Ind Bldg 3 - Grading |  |  | 213200 | 0 | 16 | 0.01 | 0 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 22060016 | HighPoint Industrial Bldg 4 |  |  | 481000 | 0 | 0 | 0.01 | 387184.59
Denver Operations | 22060039 | Denargo Market - Multifamily |  |  | 527000 | 0 | 0 | 0.01 | 0
Energy Storage & Solutions Operations | 22149001 | AVEP BESS Project |  |  | 0 | 1693 | 0 | 832769 | 559055.46
Energy Storage & Solutions Operations | 22149002 | Revolution Energy Storage |  |  | 0 | 394273.14 | 0 | 22892009.16 | 2513727.83 | 37438.74 | 409 | 94.87% | 0% | 5.134%
Energy Storage & Solutions Operations | 22149003 | EMTOC Microgrid |  |  | 0 | 0 | 0 | 909640.02 | 637593.02
Energy Storage & Solutions Operations | 22149004 | Chap Springs |  |  | 0 | 305949.47 | 0 | 14312536.68 | 1256513.09 | 33663.05 | 32 | 37.5% | 62.5% | 0%
Energy Storage & Solutions Operations | 22149005 | Beaumont Energy Storage |  |  | 0 | 0 | 0 | 5280406.49 | 1908773.82
Energy Storage & Solutions Operations | 22149006 | Canyon Country Energy Storage |  |  | 0 | 0 | 0 | 4909796.15 | 1760786.31
Energy Storage & Solutions Operations | 22149007 | Nova Power |  |  | 0 | 0 | 0 | 16470081.6 | 232037.85
Energy Storage & Solutions Operations | 22149008 | Tumbleweed Energy Storage |  |  | 0 | 0 | 0 | 14978142 | 2346751.84
FCG Operations | 22110001 | AMJV MercilessMing JV-Int |  |  | 0 | 0 | 0 | 110.01 | 763.55
FCG Operations | 22110002 | AMJV BallisticBass JV-Int |  |  | 0 | 0 | 0 | 127537 | 29979.04
FCG Operations | 22110004 | EHW 2 and 3 Unilateral Mod |  |  | 0 | 0 | 0 | 3253679.8116 | 3284636.38 | 0 | 536.5 | 81.17% | 16.96% | 1.864%
FCG Operations | 22110008 | Hill AFB UT GBSD SSC |  |  | 0 | 250404 | 0 | 91448691 | 6554147.21
FCG Operations | 22110011 | USG Perimeter Fence |  |  | 0 | 306 | 0 | 18144559 | 238366.46
FCG Operations | 22110005 | Chantilly VA Loop Road |  |  | 80 | 0 | 0 | 35667 | 32105.79
FCG Operations | 22110003 | DC Office Secure Room |  |  | 325 | 0 | 0 | 259778 | 0
FCG Operations | 22110001-174 | UDC MercilessMing |  |  | 2000 | 0 | 0 | 31875 | 30250.14
FCG Operations | 22110002-174 | UDC BallisticBass |  |  | 4000 | 0 | 0 | 2002971 | 1891057.09
FCG Operations | 22110006 | Bldg 9700B Substation Install |  |  | 5000 | 163 | 0 | 9935126.08 | 119590.25
FCG Operations | 22110010 | ASH3 DC1 Dev Office |  |  | 6100 | 0 | 0 | 1923144 | 155341.61
FCG Operations | 22110007 | ASH3 Data Center |  |  | 55358 | 118 | 0 | 21447210.51 | 13340349.49 | 0 | 362 | 93.92% | 6.077% | 0%
FCG Operations | 22110009 | Offutt AFB NE Security Campus |  |  | 106372 | 139443 | 0 | 63872156.6 | 3308399.1
Milwaukee Operations | 22080006 | MRMC Window Replacement |  |  | 0 | 40 | 0 | 327505.69 | 625 | 400 | 0 | 0% | 0% | 0%
Milwaukee Operations | 22080008 | RockGen Firestopping Repairs |  |  | 0 | 0 | 0 | 25470 | 21165.7 | 60 | 40 | 100% | 0% | 0%
Milwaukee Operations | 22080010 | Froedtert SW Expansion |  |  | 0 | 0 | 0 | 0.01 | 176223.32
Milwaukee Operations | 22080013 | WisDOT I43 Year2 |  |  | 0 | 0 | 0 | 0.01 | 15074.12
Milwaukee Operations | 22080018 | Froedtert - Cold Storage |  |  | 0 | 0 | 0 | 0.01 | 6656
Milwaukee Operations | 22080012 | NML - Sculpture Move |  |  | 256 | 1113.1 | 650 | 281353.77 | 258340.64 | 345.4 | 137 | 97.08% | 2.92% | 0%
Milwaukee Operations | 22080017 | ASLMC OR Lights |  |  | 650 | 0 | 0 | 0.01 | 179
Milwaukee Operations | 22080007 | Froedtert Volunteer Services |  |  | 1700 | 14178 | 0 | 241970.96 | 253960.86 | 628.6 | 911 | 100% | 0% | 0%
Milwaukee Operations | 22080015 | MCW Cryo Suite |  |  | 1890 | 0 | 0 | 0.01 | 3178.9 | 0 | 40 | 100% | 0% | 0%
Milwaukee Operations | 22080011 | ASLMC Hyperbaric Upgrades |  |  | 2500 | 4 | 0 | 131195.22 | 108072.28 | 136 | 29 | 3.448% | 96.55% | 0%
Milwaukee Operations | 22080016 | MRMC - MCW Cancer Tunnel |  |  | 2500 | 0 | 0 | 0.01 | 0
Milwaukee Operations | 22080003 | Froedtert Inpatient Supp |  |  | 4000 | 89800 | 3186 | 2549427.61 | 1924263.74 | 5053.6 | 4730.8 | 95.14% | 4.815% | 0.04228%
Milwaukee Operations | 22080001 | Froedtert - MF CT Reno |  |  | 5000 | 132 | 0 | 19344 | 14785.13
Milwaukee Operations | 22080005 | MRMC Tunnel G-1 |  |  | 5000 | 69320.98 | 24799 | 5296929.77 | 4851414.88 | 5297.1 | 6685.5 | 97.02% | 2.737% | 0.2393%
Milwaukee Operations | 22080009 | Froedtert OR Growth |  |  | 12030 | 0 | 0 | 0.01 | 104789.6
Milwaukee Operations | 22080014 | MRMC - Childrens Lateral |  |  | 26000 | 0 | 0 | 0.01 | 13657
Milwaukee Operations | 22080004 | JCI Glendale Build Out |  |  | 100000 | 0 | 0 | 0.01 | 3375.75
Milwaukee Operations | 22080002 | WEAS -JCI Core & Shell |  |  | 110000 | 0 | 0 | 0.01 | 22439.95 | 0 | 8 | 100% | 0% | 0%
Minneapolis Operations | 22030001 | Fairview - Annual 2022 |  |  | 0 | 0 | 0 | 0.01 | 3555051.24 | 0 | 11282.5 | 96.76% | 2.907% | 0.3368%
Minneapolis Operations | 22030002 | Allina - Annual Contract 2022 |  |  | 0 | 5698.5 | 0 | 2459481.59 | 2336136.78 | 12897 | 11478.75 | 87.57% | 10.14% | 2.291%
Minneapolis Operations | 22030003 | Fairview Small Cap Proj 2022 |  |  | 0 | 22 | 0 | 875396.9332 | 485002.47 | 1383 | 892 | 94.62% | 5.381% | 0%
Minneapolis Operations | 22030004 | Sanford - Master Agreement |  |  | 0 | 1 | 0 | 376463.58 | 443882.57 | 207 | 871.5 | 95.3% | 4.705% | 0%
Minneapolis Operations | 22030005 | Fairview - Southdale Nurse Cal |  |  | 0 | 0 | 0 | 1136093 | 2335.2 | 3590 | 2 | 100% | 0% | 0%
Minneapolis Operations | 22030006 | Fairview - St Paul Comm Health |  |  | 0 | 136444.5 | 2361.5 | 3204818.67 | 3056905.43 | 7994.91 | 7208.48 | 95.72% | 4.279% | 0%
Minneapolis Operations | 22030007 | Northern Stacks - Res Med TI |  |  | 0 | 3 | 0 | 2166235.47 | 2061933.17 | 1217 | 968.62 | 97.15% | 2.026% | 0.8259%
Minneapolis Operations | 22030008 | Fairview - Unit J Elevator Ren |  |  | 0 | 0 | 0 | 1933517 | 896542.03 | 2871 | 1998 | 97.57% | 0.4254% | 2.002%
Minneapolis Operations | 22030009 | Fairview - Roche Lab Analyzer |  |  | 0 | 6198.59 | 0 | 817322.3792 | 598044.02 | 1719 | 895 | 98.94% | 1.061% | 0%
Minneapolis Operations | 22030010 | Target - '22 Remodel - Grafton |  |  | 0 | 29900.94 | 0 | 2158245.44 | 2230812.32 | 2927.6 | 4940 | 96.23% | 3.036% | 0.7287%
Minneapolis Operations | 22030011 | Fairview - UMMC WB EmPATH |  |  | 0 | 0 | 0 | 197582.71 | 174033.59 | 549 | 330.5 | 91.68% | 8.321% | 0%
Minneapolis Operations | 22030012 | Marvin WFN - Breakroom Reno |  |  | 0 | 64096.79 | 0 | 2329867.17 | 2070937.69 | 2822.2 | 3020 | 90.56% | 9.437% | 0%
Minneapolis Operations | 22030013 | UMN - Williamson Hall ASR Relo |  |  | 0 | 1239.09 | 0 | 285966.55 | 273886.6 | 245 | 310.5 | 100% | 0% | 0%
Minneapolis Operations | 22030014 | Fairview-UMMC WB Pharmacy Exp |  |  | 0 | 0 | 0 | 2274582.59 | 1624673.36 | 4686 | 4058.5 | 98.92% | 1.084% | 0%
Minneapolis Operations | 22030015 | Target - '22 Remodel - Oshkosh |  |  | 0 | 112843.66 | 0 | 4535044.617 | 4800527.37 | 6697.68 | 8873.48 | 86.92% | 13% | 0.07889%
Minneapolis Operations | 22030023 | US Bank - USB Edina Redevel |  |  | 0 | 98666.9 | 29751 | 4483585.31 | 4719262.69 | 5477 | 7831 | 99.6% | 0.4022% | 0%
Minneapolis Operations | 22030024 | MDI - USB Edina Demo/Abate |  |  | 0 | 0 | 0 | 831286 | 295402.56 | 125 | 96 | 100% | 0% | 0%
Minneapolis Operations | 22030030 | SilverLakeInv-ODS Pent & Dock |  |  | 0 | 0 | 0 | 464716 | 455921.76 | 0 | 120 | 100% | 0% | 0%
Minneapolis Operations | 22030031 | MN United - Allianz Field -'22 |  |  | 0 | 5143 | 0 | 159638.03 | 122829.31 | 292 | 287 | 98.43% | 1.568% | 0%
Minneapolis Operations | 22030041 | Allina - ANW - Care (Design) |  |  | 0 | 0 | 0 | 726228 | 283389.16
Minneapolis Operations | 22030042 | North Wirth - MAM HQ Sealant |  |  | 0 | 0 | 0 | 162714 | 170081.38 | 957 | 1121.5 | 96.26% | 3.032% | 0.7133%
Minneapolis Operations | 22030044 | BSC - Weaver Lake Lots 2&6 |  |  | 0 | 78033.7 | 0 | 3606940.03 | 3565360.83 | 858.1 | 1460.5 | 99.11% | 0.8901% | 0%
Minneapolis Operations | 22030045 | UMN-3MAM & Ridder Reno |  |  | 0 | 134436.15 | 0 | 12872679.17 | 750872.2 | 3357.8 | 0 | 0% | 0% | 0%
Minneapolis Operations | 22030047 | MDI-USB Redev - JDA Scope |  |  | 0 | 213 | 0 | 665328.23 | 586489.86 | 714 | 388 | 100% | 0% | 0%
Minneapolis Operations | 22030048 | Allina - Care Pavilion(Enable) |  |  | 0 | 0 | 1 | 10000000 | 848283.84 | 0 | 3543.5 | 96.81% | 2.85% | 0.3386%
Minneapolis Operations | 22030051 | UMN-Vet Med Ctr & Lin Acc |  |  | 0 | 5361.99 | 0 | 648804.89 | 316675.72 | 497.5 | 117.5 | 100% | 0% | 0%
Minneapolis Operations | 22030052 | Swervo-Century Plaza Demo |  |  | 0 | 0 | 0 | 0.01 | 23308.68
Minneapolis Operations | 22030055 | Westminster Chapel Plaster |  |  | 0 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 22030099 | MAM-HQ Campus Renovations |  |  | 0 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 22030056 | MN Twins-Target Field Ply Rep |  |  | 1000 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 22030037 | Allina - ANW CK 3&4 Seclusion |  |  | 1500 | 0 | 0 | 344101 | 276957.34 | 988 | 1102 | 96.82% | 3.176% | 0%
Minneapolis Operations | 22030026 | Fairview-UMMC WB Histology |  |  | 1680 | 5 | 0 | 545879.64 | 457076.58 | 1033 | 811 | 96.92% | 3.083% | 0%
Minneapolis Operations | 22030017 | Target Field - Grounds Crew |  |  | 2000 | 0 | 0 | 325825.73 | 415910.86 | 312 | 419.5 | 95.83% | 3.218% | 0.9535%
Minneapolis Operations | 22030043 | IDT - Small Capital Projects |  |  | 2000 | 8378.85 | 0 | 163859.84 | 110593.89 | 595.1 | 419.5 | 97.26% | 2.741% | 0%
Minneapolis Operations | 22030019 | Allina - Mercy CT1, CT2, Spin |  |  | 2500 | 0 | 0 | 718748 | 587491.58 | 2549 | 2664 | 98.91% | 1.089% | 0%
Minneapolis Operations | 22030020 | Jackson I - Naomi 77 9th East |  |  | 2500 | 352 | 6 | 524167.0324 | 479775.53 | 2427 | 2412 | 93.41% | 6.592% | 0%
Minneapolis Operations | 22030028 | IDT - Tank Farm |  |  | 2586 | 22579.34 | 788.3 | 3562821.64 | 2236343.49 | 2165.4 | 1997 | 94.64% | 5.358% | 0%
Minneapolis Operations | 22030032 | Crown College - Welcome Ctr |  |  | 2800 | 30610.6 | 0 | 1345622.88 | 1237357.76 | 3030.5 | 2265 | 94.3% | 5.166% | 0.5298%
Minneapolis Operations | 22030034 | Fairview - Dietary Expansion |  |  | 2985 | 6606 | 0 | 1127168.19 | 579261.4 | 1409.8 | 1096.5 | 96.63% | 1.186% | 2.189%
Minneapolis Operations | 22030054 | Fairview-UMMC Unit J Cath Lab2 |  |  | 3315 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 22030040 | Rochester 2 Assoc - 2DS Lobby |  |  | 12000 | 1 | 0 | 2276702.71 | 495765.35 | 16 | 328 | 100% | 0% | 0%
Minneapolis Operations | 22030039 | BSC - Weaver Lake 4 TI |  |  | 14500 | 21369.42 | 1221 | 1592287.55 | 1590255.41 | 637.8 | 923.5 | 99.24% | 0.758% | 0%
Minneapolis Operations | 22030027 | Target - Stevens Point |  |  | 15000 | 20084.03 | 0 | 2294196.97 | 2247418.5 | 2977.48 | 3342 | 87.21% | 12.79% | 0%
Minneapolis Operations | 22030025 | Target - Fond Du Lac |  |  | 18750 | 45525.72 | 0 | 4886423.884 | 4176292.2 | 5311 | 6366.5 | 92.74% | 6.346% | 0.911%
Minneapolis Operations | 22030018 | Fairview - 10th Street Ramp |  |  | 24284 | 129097.72 | 2 | 3767880.43 | 2842408.56 | 5913.17 | 3320 | 98.01% | 1.747% | 0.241%
Minneapolis Operations | 22030029 | IDT - 2600 Crosspark |  |  | 25992 | 119070.43 | 42306.2 | 7414425.49 | 4855530.02 | 4688.7 | 4060 | 95.52% | 4.483% | 0%
Minneapolis Operations | 22030016 | CentraCare - Paynesville Hosp |  |  | 35000 | 299245.28 | 0 | 11724961.32 | 3953612.88 | 19972.4 | 6065 | 96.7% | 3.298% | 0%
Minneapolis Operations | 22030022 | Warroad Real Estate - Main Ave |  |  | 38500 | 201796.92 | 0 | 7160533.01 | 5565694.89 | 12268.1 | 9486.88 | 73.33% | 26.67% | 0%
Minneapolis Operations | 22030053 | Fairview-St Paul Wellness Ph2A |  |  | 43476 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 22030050 | Dunwoody - 712 Ontario Cond |  |  | 45000 | 1 | 0 | 9320 | 9848.75 | 0 | 16 | 100% | 0% | 0%
Minneapolis Operations | 22030036 | Towner County - Medical Ctr |  |  | 78999 | 158720.71 | 0 | 43536549.92 | 3054250.6 | 12459.8 | 892 | 95.96% | 4.036% | 0%
Minneapolis Operations | 22030046 | City of Coralville-Hyatt Reno |  |  | 100000 | 0 | 0 | 0.01 | 103500.41 | 0 | 520.9196 | 66.02% | 28.03% | 5.951%
Minneapolis Operations | 22030035 | Anne Carlsen - Rplcmnt Facil |  |  | 110000 | 229241.75 | 2874 | 47045229.73 | 13827627.34 | 19203.4 | 1460.5 | 98.97% | 1.027% | 0%
Minneapolis Operations | 22030033 | MDI - Three Discovery Square |  |  | 144000 | 0 | 0 | 0.01 | 368120.47
Minneapolis Operations | 22030021 | MDI - Cornell - New Residence |  |  | 213000 | 0 | 0 | 136000.01 | 489683.56
Mortenson Infrastructure Milw Operations | 22080013-063 | WisDOT I43 Years 2-2 |  |  | 0 | 5 | 0 | 594939.27 | 16784.89
Phoenix Operations | 22040001 | SCAHC - Design Phase |  |  | 0 | 7 | 0 | 3344588.58 | 2640955.3
Phoenix Operations | 22040017 | Alaska USA Signal Butte Rd TI |  |  | 0 | 0 | 0 | 0 | 403.78
Phoenix Operations | 22040012 | CBR Sox Perf Lab Reno |  |  | 200 | 20 | 0 | 38338.81 | 25819.86 | 325 | 283 | 96.11% | 3.887% | 0%
Phoenix Operations | 22040003 | WhiteSox Camelback Fac Reno |  |  | 500 | 12149 | 0 | 208504.11 | 84522.93 | 726 | 46 | 91.3% | 8.696% | 0%
Phoenix Operations | 22040013 | Reds Female Locker Room |  |  | 835 | 12952 | 2053 | 292568 | 140197.86 | 580.4 | 665.5 | 92.64% | 7.363% | 0%
Phoenix Operations | 22040002 | AlaskaUSA Scottsdale |  |  | 2900 | 20162 | 15868 | 392021.3 | 404231.65 | 1124 | 1111.5 | 94.24% | 5.758% | 0%
Phoenix Operations | 22040014 | Exact Science MRD Lab TI |  |  | 3040 | 16551 | 3152 | 396912.34 | 35622.35 | 905 | 215 | 99.53% | 0.4651% | 0%
Phoenix Operations | 22040007 | AlaskaUSA Glendale Op Cntr |  |  | 3200 | 7136 | 79753 | 683041.94 | 387187.47 | 1524.7 | 2644 | 93.84% | 6.165% | 0%
Phoenix Operations | 22040006 | Allstate Chandler One TI |  |  | 6500 | 4647 | 10 | 507165.39 | 401322.12 | 0 | 94 | 100% | 0% | 0%
Phoenix Operations | 22040005 | SCAHC SanCarlos Reg/Check In |  |  | 10050 | 8 | 0 | 69604.28 | 33182.6
Phoenix Operations | 22040004 | Dodgers Reno Camelback |  |  | 14000 | 0 | 0 | 0.02 | 47607.99
Phoenix Operations | 22040011 | SCAHC Warehouse Facility |  |  | 46500 | 16 | 0 | 1313676.54 | 28152.45
Phoenix Operations | 22040015 | MDI - The Edith Hotel - Design |  |  | 200000 | 26 | 0 | 1058843 | 5058.94
Phoenix Operations | 22040009 | CCG CCPAZ Petro Manu Fac |  |  | 537000 | 436.65 | 0 | 11681312.81 | 298380.52 | 866 | 0 | 0% | 0% | 0%
Portland Operations | 22055002 | OHSU CHH1 12th Flr HPL |  |  | 0 | 11829.96 | 0 | 1015726.58 | 476108.76 | 1132.3 | 889.5 | 91.96% | 8.038% | 0%
Portland Operations | 22055003 | OHSU CHH1 6th Flr |  |  | 0 | 10 | 0 | 2559 | 2270.6
Portland Operations | 22055004 | OHSU CDW Roof Repl |  |  | 0 | 9 | 0 | 2170.11 | 2404.42
Portland Operations | 22055005 | Kaiser ORD Fire Alarm Repl |  |  | 0 | 15 | 0 | 18422.35 | 18658.77
Portland Operations | 22055006 | BPA TO4 PMO |  |  | 0 | 10 | 0 | 297397.82 | 160325.98
Portland Operations | 22055007 | Kaiser SST Nurse Call Const |  |  | 0 | 24 | 0 | 128219.47 | 104320.31 | 172 | 97.33 | 100% | 0% | 0%
Portland Operations | 22055008 | Kaiser SST Air Handle Constru |  |  | 0 | 30 | 0 | 1870401.42 | 1649266.08 | 633.9 | 1074.17 | 96.97% | 3.026% | 0%
Portland Operations | 22055009 | OHSU MQ2 MMBR |  |  | 0 | 0 | 0 | 0.02 | 0
Portland Operations | 22055010 | COH Ron Tonkin Stad Impr |  |  | 0 | 25 | 0 | 2113309.38 | 1632423.41
Portland Operations | 22055012 | Pac Seafood Clack. TI |  |  | 0 | 39133.29 | 20756 | 1092547.3792 | 1157884.17 | 1603.03 | 2411.5 | 95.96% | 4.043% | 0%
Portland Operations | 22055014 | Microchip Nitrogen Plant |  |  | 0 | 41865.65 | 28653 | 4061759.05 | 3494178.18 | 3548.9 | 2910.5 | 96.43% | 3.178% | 0.3951%
Portland Operations | 22055015 | Microchip Silane Bulk System |  |  | 0 | 36043.52 | 0 | 5479419.55 | 521959.18 | 1168.7 | 0 | 0% | 0% | 0%
Portland Operations | 22055016 | Microchip Boiler Addition |  |  | 0 | 4004.71 | 1667 | 2457406.72 | 1893446.56 | 1213.4 | 625.35 | 100% | 0% | 0%
Portland Operations | 22055017 | Microchip HF Treatment |  |  | 0 | 42 | 0 | 5175037.46 | 307958.99
Portland Operations | 22055019 | OHSU RPV MCECC Reloc |  |  | 0 | 10 | 0 | 4865 | 10100.57 | 8 | 0 | 0% | 0% | 0%
Portland Operations | 22055020 | BPA TO5 CCL/Survey Garage |  |  | 0 | 17 | 0 | 798953 | 295059.66
Portland Operations | 22055024 | Kaiser SST Lighting Constr |  |  | 0 | 27 | 0 | 797478.34 | 297394.49 | 457 | 18 | 100% | 0% | 0%
Portland Operations | 22055025 | Kaiser SST Emerg lghtg Constr |  |  | 0 | 27 | 0 | 222293.97 | 77574.46 | 376 | 46 | 100% | 0% | 0%
Portland Operations | 22055026 | Kaiser ORC Fire Alarm Constr |  |  | 0 | 31 | 0 | 897386.84 | 193430.78 | 569 | 16 | 100% | 0% | 0%
Portland Operations | 22055028 | Microchip Corrosive Storage |  |  | 0 | 14 | 0 | 18435.98 | 369.14 | 88 | 3.9 | 100% | 0% | 0%
Portland Operations | 22055030 | OHSU OCB LineAc |  |  | 0 | 12 | 0 | 14792.81 | 12791.98
Portland Operations | 22055031 | Prov Reed Retail Corridor |  |  | 0 | 23 | 0 | 199080.79 | 30640.89 | 40 | 0 | 0% | 0% | 0%
Portland Operations | 22055032 | Prov Reeds Addl TIs |  |  | 0 | 12 | 0 | 58855.36 | 669.42
Portland Operations | 22055033 | Microchip PE Scrubber |  |  | 0 | 21 | 0 | 1342215.89 | 21925.71
Portland Operations | 22055035 | BPA TO6 Ampere Demo |  |  | 0 | 0 | 0 | 0.01 | 25751
Portland Operations | 22055036 | Kaiser Reg 2021 Life Safety |  |  | 0 | 15 | 0 | 41621.97 | 29246.07
Portland Operations | 22055037 | Kaiser WMC OR & MPU Light Prec |  |  | 0 | 17 | 0 | 13792.95 | 5670.32 | 4 | 0 | 0% | 0% | 0%
Portland Operations | 22055038 | Kaiser ORC Optometry Precon |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 22055039 | Kaiser NSC Maintenance |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 22055040 | OHSU Prkg Structure C Est Feas |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 22055041 | Microchip Oxygen Tank Replace |  |  | 0 | 0 | 0 | 0.02 | 10800
Portland Operations | 22055042 | Microchip Site Security Improv |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 22055022 | OHSU IPA 8A Skybridge |  |  | 1780 | 0 | 0 | 0 | -3.99
Portland Operations | 22055027 | Microchip Medium Voltage Add |  |  | 2000 | 14153.72 | 192 | 2094566.23 | 197332.31 | 854 | 0 | 0% | 0% | 0%
Portland Operations | 22055021 | OHSU MP Pharm Admin |  |  | 3650 | 13 | 0 | 16085.18 | 6585.71 | 24 | 0 | 0% | 0% | 0%
Portland Operations | 22055029 | OHSU CDRC Eugene |  |  | 10000 | 12 | 0 | 7626 | 9374.75
Portland Operations | 22055034 | OHSU RWC Rehab |  |  | 10000 | 14 | 0 | 7394.4 | 0
Portland Operations | 22055043 | Microchip Chem Storage Ware |  |  | 23000 | 0 | 0 | 0.01 | 0
Portland Operations | 22055018 | Microchip Gresham Off Reno |  |  | 33000 | 114798.23 | 14934 | 7090685.25 | 2152686.67 | 7364.7 | 2528.43 | 97.43% | 2.571% | 0%
Portland Operations | 22055001 | Clark Advanced Manu Cntr |  |  | 61000 | 43 | 0 | 3460152.24 | 1622207.54 | 166.21 | 117.37 | 100% | 0% | 0%
Portland Operations | 22055013 | MDI Seran Comm Manu Fac |  |  | 90000 | 22 | 0 | 5992451.54 | 777247.89
Power Delivery Solutions Operations | 22146001 | White Rock Wind - Power |  |  | 0 | 484331.96 | 0 | 31796250.01 | 2514029.82 | 30362.44 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 22146002 | Abilene NW |  |  | 0 | 0 | 0 | 2539540 | 283709.83
Power Delivery Solutions Operations | 22146003 | AEP Series Cap MOV Replace |  |  | 0 | 0 | 0 | 128745.8 | 98632.6 | 0 | 901 | 78.47% | 21.53% | 0%
Power Delivery Solutions Operations | 22146004 | Corpus Christi |  |  | 0 | 0 | 0 | 2438869.07 | 1820890.78
Power Delivery Solutions Operations | 22146005 | Outpost Solar Interconnect |  |  | 0 | 0 | 0 | 906271 | 5992.46
Power Delivery Solutions Operations | 22146007 | Tierra Bonita Solar - Power |  |  | 0 | 682 | 0 | 8992726 | 2000.38
Power Delivery Solutions Operations | 22146008 | GE SC Maintenance |  |  | 0 | 21 | 0 | 222851.95 | 49588.12 | 0 | 292.5 | 77.61% | 22.39% | 0%
Power Delivery Solutions Operations | 22146009 | 2022 MSA Maintenance Work |  |  | 0 | 0 | 0 | 496926.42 | 193550.12 | 0 | 888.5 | 78.39% | 21.61% | 0%
Salt Lake City Operations | 22065003 | MDI-Saratoga Springs MOB |  |  | 0 | 0 | 0 | 7000 | 6116.01
Salt Lake City Operations | 22065004 | Mortenson SLC Office Space |  |  | 12300 | 0 | 0 | 0.01 | 14617.89 | 0 | 94 | 94.68% | 5.319% | 0%
Salt Lake City Operations | 22065005 | West Temple Hotel |  |  | 150000 | 0 | 0 | 0.01 | 76480.84
Salt Lake City Operations | 22065002 | Pacificorp-RMP HQ |  |  | 186000 | 0 | 0 | 200000 | 389061.36
Salt Lake City Operations | 22065001 | Domain-West Temple |  |  | 380000 | 0 | 0 | 0.01 | 418885.06
Seattle Operations | 22050001 | Virtual Insights 2022 |  |  | 0 | 0 | 0 | 0.09 | 239598.01
Seattle Operations | 22050002 | KP Everett - Sitework |  |  | 0 | 38260.79 | 5324.07 | 14647378.66 | 8810382.16 | 4703.8 | 2514.6 | 92.7% | 7.162% | 0.1392%
Seattle Operations | 22050003 | Davita Fed Way TI |  |  | 0 | 27124.29 | 28532.65 | 649810.87 | 539088.33 | 528.9 | 560.5 | 99.64% | 0.3568% | 0%
Seattle Operations | 22050004 | Sidewalk Labs Facility |  |  | 0 | 2 | 24 | 302489.65 | 310349.93 | 116 | 69 | 69.57% | 30.43% | 0%
Seattle Operations | 22050005 | AMLI 5L Residential Tower |  |  | 0 | 30.29 | 0 | 1079051.19 | 558791.4
Seattle Operations | 22050006 | Key Bank Pavilion |  |  | 0 | 0 | 0 | 78488.18 | 58664.77
Seattle Operations | 22050007 | Seatac Meet Me Room |  |  | 0 | 15625.5 | 0 | 5389879.4 | 141119.03 | 1162.7 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145011 | NSA Crane PV Replace - Duke |  |  | 0 | 1200 | 0 | 81500 | 50135.66 | 1100 | 960 | 83.33% | 16.67% | 0%
Solar and Emerging Renewables Operations | 22145013 | FPL - Monarch (NEE) |  |  | 89 | 6 | 0 | 9108967 | 69203.64
Solar and Emerging Renewables Operations | 22145012 | FPL - Caloosahatchee (NEE) |  |  | 100 | 6 | 0 | 9771265 | 70262.87
Solar and Emerging Renewables Operations | 22145008 | Winquepin Solar - Duke |  |  | 103 | 6 | 0 | 6572253 | 1941504.7
Solar and Emerging Renewables Operations | 22145009 | Falmouth Solar - Duke |  |  | 103 | 6 | 0 | 974812 | 307202.01
Solar and Emerging Renewables Operations | 22145014 | FPL - Orchard (NEE) |  |  | 108 | 6 | 0 | 10249694 | 76436.3
Solar and Emerging Renewables Operations | 22145001 | Vistra - Newton |  |  | 300 | 123 | 0 | 640290.51 | 482871.55 | 104 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145002 | Vistra - Coffeen |  |  | 300 | 123 | 0 | 610222.51 | 362202.47 | 104 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145003 | Vistra - Baldwin |  |  | 300 | 122 | 0 | 651140.01 | 382117.22 | 104 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145004 | Vistra - Duck Creek |  |  | 300 | 111 | 0 | 594498.51 | 401234.31 | 104 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145005 | Vistra - Kincaid |  |  | 300 | 123 | 0 | 588526.01 | 296381.19 | 104 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145006 | Vistra - Hennepin |  |  | 300 | 123 | 0 | 672378.51 | 286846.57 | 104 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 22145007 | Greasewood II - Tierra Bonita |  |  | 398 | 20 | 0 | 12359081 | 6730219.02 | 479 | 555 | 84.95% | 15.05% | 0%
Solar and Emerging Renewables Operations | 22145010 | Tierra Blanco - CIG DS1, LLC |  |  | 507 | 0 | 0 | 71566.01 | 34644.48 | 0 | 0 | 0% | 0% | 0%
Sports + Entertainment Group Operations | 22150001 | CNS - ASU Multipurpose Arena |  |  | 0 | 0 | 0 | 710589.4 | 608821.26
Sports + Entertainment Group Operations | 22150002 | DIG - Vikrell West Manufac |  |  | 0 | 0 | 0 | 2814652 | 862767.68 | 0 | 0 | 0% | 0% | 0%
Sports + Entertainment Group Operations | 22150003 | PSU Lasch 6 Phase 2 |  |  | 0 | 0 | 0 | 143206 | 50950.99
Sports + Entertainment Group Operations | 22150004 | Hotel Mort/McCarthy Gaylord |  |  | 0 | 0 | 0 | 32105600 | 15060799.55
Sports + Entertainment Group Operations | 22150004-143 | Gaylord Pacific HOTEL Resort |  |  | 0 | 121150 | 0 | 511828604.38 | 81102500.87 | 32581 | 10685.5 | 88.03% | 11.13% | 0.8376%
Sports + Entertainment Group Operations | 22150005 | Convention Ctr Mort/McCarthy |  |  | 0 | 0 | 0 | 0.01 | 0
Sports + Entertainment Group Operations | 22150005-143 | Gaylord Pacific CONVENTION CTR |  |  | 0 | 96230 | 0 | 294383075.14 | 46127129.39 | 85557.66 | 0 | 0% | 0% | 0%
Sports + Entertainment Group Operations | 22150006 | 1A Gaylord Pacific Resort |  |  | 0 | 0 | 0 | 0.01 | 4495.7
Sports + Entertainment Group Operations | 22150006-143 | Gaylord Pacific 1A INFRAST |  |  | 0 | 1 | 0 | 27170957 | 8775414.03 | 0 | 3813.5 | 89.08% | 9.86% | 1.062%
Sports + Entertainment Group Operations | 22150007 | Garage Mort/McCarthy Gaylord |  |  | 0 | 0 | 0 | 0.01 | 0
Sports + Entertainment Group Operations | 22150007-143 | Gaylord Pacific GARAGE Resort |  |  | 0 | 495187 | 0 | 24711782 | 1100156.66 | 3937 | 0 | 0% | 0% | 0%
Sports + Entertainment Group Operations | 22150008 | Cleveland Browns NFL Precon |  |  | 0 | 0 | 0 | 0.02 | 150377.88
Sports + Entertainment Group Operations | 22150009 | MLB Cleveland Guardians |  |  | 0 | 0 | 0 | 0.01 | 340835.89
Sports + Entertainment Group Operations | 22150010 | MLB Angels Feasibility Study |  |  | 0 | 0 | 0 | 130000 | 126333.25
Wind Energy I Operations | 22141001 | Hawkeye Repower |  |  | 0 | 0 | 0 | 660250 | 350328.7
Wind Energy I Operations | 22141003 | Comm Wind South (CWS) Repower |  |  | 0 | 0 | 0 | 14569082.28 | 116219.63 | 0 | 30 | 66.67% | 33.33% | 0%
Wind Energy I Operations | 22141004 | Bishop Hill Repower |  |  | 0 | 0 | 0 | 256765 | 143284.96
Wind Energy I Operations | 22141005 | Bishop Hill II Repower |  |  | 0 | 0 | 0 | 194750 | 163194.11
Wind Energy I Operations | 22141006 | Delta Wind |  |  | 0 | 0 | 0 | 800634 | 691492.54
Wind Energy I Operations | 22141007 | Grand Meadow Repower |  |  | 0 | 2714.45 | 488 | 19925561.34 | 12654275.5 | 49401 | 37552.7 | 74.31% | 16.66% | 9.03%
Wind Energy I Operations | 22141009 | California Ridge Repower |  |  | 0 | 0 | 0 | 271700 | 25275
Wind Energy I Operations | 22141010 | Nobles ADLS Repower |  |  | 0 | 0 | 0 | 1156420 | 670998.17
Wind Energy I Operations | 22141011 | Nobles V136 Repower |  |  | 0 | 661.33 | 0 | 1208764.5 | 825723.4 | 1620 | 195 | 70.51% | 29.49% | 0%
Wind Energy I Operations | 22141012 | Fowler Ridge Repower |  |  | 0 | 0 | 0 | 24479678.59 | 84418.37
Wind Energy I Operations | 22141013 | Boswell Springs Wind |  |  | 0 | 0 | 0 | 2053817 | 113572.92
Wind Energy I Operations | 22141015 | Moraine Sands Wind |  |  | 0 | 0 | 0 | 31632361.99 | 233715.45
Wind Energy I Operations | 22141016 | Grand Meadow ADLS Repower |  |  | 0 | 0 | 0 | 151937 | 2542.15
Wind Energy I Operations | 22141017 | Skeleton Creek Grout Install |  |  | 0 | 0 | 0 | 35030.68 | 6224.71 | 152 | 0 | 0% | 0% | 0%
Wind Energy I Operations | 22141018 | Pyron Repower |  |  | 0 | 154 | 73 | 6564697.3 | 1653989.54 | 4410 | 3308.5 | 86.88% | 13.12% | 0%
Wind Energy I Operations | 22141019 | Pioneer Hutt Wind |  |  | 0 | 0 | 0 | 48426665.15 | 25
Wind Energy I Operations | 22141021 | Shamrock Wind |  |  | 0 | 0 | 0 | 72950887 | 1790.08
Wind Energy I Operations | 22141023 | Vestas 25 Mile Creek Wind |  |  | 0 | 9 | 0 | 498586.5 | 439258.18 | 3902.5 | 5981.5 | 81.74% | 18.26% | 0%
Total | [5 empty] | 104615828.7 | 3518431.12 | 2354233942.0046 | 522742377.23 | 1173556.56 | 570331.5796 | 82.42% | 16.7% | 0.8816%
Applied filters: Project Number starts with '22'

## 2021
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Minneapolis Operations | 21024 | 3M BLDG 220 INTERIORREMODEL | 2005-11-05 | 2005-09-02 | 0 | 163479 | 119905 | 8760201 | 9083594 | 0 | 19899 | 100% | 0% | 0%
Minneapolis Operations | 21030 | ALLINA-ABBOTT NORTHWESTERN HE | 2004-12-31 | 2005-01-14 | 419600 | 679171 | 829740 | 43362002 | 44034787 | 0 | 126524 | 100% | 0% | 0%
Minneapolis Operations | 21020 | ALLINA/MERCY HOSPITAL CARDIAC | 2004-05-31 | 2004-07-01 | 95000 | 213931 | 287004 | 12754593 | 12732663 | 0 | 45814 | 100% | 0% | 0%
Minneapolis Operations | 21032 | DICKINSON COMMUNITYCENTER | 2004-04-07 | 2004-05-13 | 0 | 0 | 0 | 713631 | 715572 | 0 | 3580 | 100% | 0% | 0%
Denver Operations | 21203 | HAMMES-ST MARY'S HEALTHCARE C | 2004-03-14 | 2004-03-14 | 50500 | 0 | 0 | 10050580 | 9901859 | 0 | 8730 | 100% | 0% | 0%
Minneapolis Operations | 21003 | U OF MN /ANNUAL CONTRACT 2002 | 2002-12-31 | 2003-12-31 | 0 | 964 | 0 | 6201368 | 6206174 | 0 | 11062 | 100% | 0% | 0%
Minneapolis Operations | 21040 | WESTMINSTER CHURCH -MISC WORK | 2003-12-31 | 2003-12-31 | 0 | 0 | 0 | 10256 | 11630 | 0 | 94 | 100% | 0% | 0%
Minneapolis Operations | 21026 | WALKER ART CENTER -PARKING RA | 2003-11-01 | 2003-10-12 | 267493 | 10002747816 | 2467135 | 0 | 20418080 | 0 | 95271 | 100% | 0% | 0%
Minneapolis Operations | 21038 | ALLINA-ANW MRI ADDITION | 2003-06-30 | 2003-09-22 | 10200 | 41993 | 0 | 406597 | 412605 | 0 | 2429 | 100% | 0% | 0%
Minneapolis Operations | 21021 | 3M DATA CENTER | 2003-07-11 | 2003-08-08 | 0 | 1633293 | 925167 | 10256630 | 10843513 | 0 | 35451 | 100% | 0% | 0%
Minneapolis Operations | 21014 | RADISSON HOTELS -PLAZA VII RE | 2003-11-01 | 2003-07-01 | 0 | 229676 | 218130 | 6006022 | 6008075 | 0 | 17821 | 100% | 0% | 0%
Minneapolis Operations | 21001 | FAIRVIEW UMC ANNUAL-CONTRACT | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 0 | 796772 | 0 | 7753 | 100% | 0% | 0%
Minneapolis Operations | 21002 | FAIRVIEW UMC-MAINTENANCE CONT | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 0 | 42279 | 0 | 630 | 100% | 0% | 0%
Minneapolis Operations | 21023 | SPRC-LANDMARK PLAZA-PARK CONS | 2003-06-01 | 2002-11-27 | 21000 | 25657 | 25611 | 831372 | 1293351 | 0 | 4395 | 100% | 0% | 0%
Minneapolis Operations | 21025 | CARLSON-DEGERMAN FIELD | 2002-09-30 | 2002-09-30 | 500000 | 89 | 0 | 433040 | 432981 | 0 | 0 | 0% | 0% | 0%
Minneapolis Operations | 21022 | MHVP-XCEL CENTER BOARDROOM | 2002-09-20 | 2002-09-25 | 4000 | 1819 | 0 | 167056 | 259910 | 0 | 1799 | 100% | 0% | 0%
Minneapolis Operations | 21011 | WATEROUS -MID-SHIP -PUMP TEST | 2002-07-01 | 2002-08-27 | 4000 | 106629 | 44573 | 4472022 | 5313301 | 0 | 13231 | 100% | 0% | 0%
Minneapolis Operations | 21007 | BETHEL COLLEGE - CLCORGAN | 2002-09-01 | 2002-08-20 | 0 | 2362 | 0 | 416036 | 416346 | 0 | 1243 | 100% | 0% | 0%
Minneapolis Operations | 21010 | MORTENSON 4TH FLOORSLT OFFICE | 2002-03-31 | 2002-03-31 | 192 | 5 | 0 | 5310 | 5672 | 0 | 40 | 100% | 0% | 0%
Minneapolis Operations | 21015 | U OF MN-HUMPHREY MUSEUM | 2002-02-28 | 2002-02-28 | 0 | 0 | 0 | 0 | 1583 | 0 | 0 | 0% | 0% | 0%
Chicago Operations | 21090002 | RUMC - 2021 Small Projects |  |  | 0 | 59391.39 | 0 | 1714223.85 | 2075388.8 | 5 | 4867.5 | 96.5% | 2.969% | 0.5342%
Chicago Operations | 21090003 | LCH - 2021 Small Projects |  |  | 0 | 699 | 0 | 4012824.1362 | 3357422.36 | 4280.17 | 9855.5 | 85.15% | 10.09% | 4.764%
Chicago Operations | 21090005 | NWM - Delnor Cancer Center |  |  | 0 | 0 | 0 | 68763 | 100781.15 | 0 | 21 | 0% | 19.05% | 80.95%
Chicago Operations | 21090991 | Chicago 2021 Prefab Shop |  |  | 0 | 1189 | 738 | 0 | 447911.22 | 106 | 4141.5 | 99.28% | 0.6278% | 0.09658%
Chicago Operations | 21090004 | SAIC-MacLean & Lakeview |  |  | 5900 | 50176 | 1 | 2016518.2 | 1799244.21 | 1500.88 | 1220.5 | 89.55% | 9.34% | 1.106%
Chicago Operations | 21090001 | WR Meadows - Innovation Center |  |  | 30356 | 231222.27 | 59592 | 12499905.5408 | 11369946.5 | 6603.58 | 5190 | 92.94% | 6.811% | 0.2505%
Civil Group Operations | 21148001 | Emerald Grove Solar - Civil |  |  | 0 | 3148525.35 | 173445 | 3286433.86 | 2761468.89 | 8019.8 | 5351.5 | 84.51% | 15.49% | 0%
Civil Group Operations | 21148002 | Glass Sands Wind - Civil |  |  | 0 | 7161369.6 | 501299 | 9706820.48 | 11503246.03 | 29694.71 | 49859.5 | 80.43% | 19.57% | 0%
Civil Group Operations | 21148003 | Pocahontas Repower - Civil |  |  | 0 | 21535.39 | 36676 | 2507303.49 | 2194055.57 | 7116.9 | 10215 | 76.32% | 23.43% | 0.2496%
Civil Group Operations | 21148005 | Chokecherry Sierra Madre 2021 |  |  | 0 | 809966.44 | 816231 | 17288938.52 | 14519868.32 | 60845.78 | 51949.5 | 83.74% | 16.1% | 0.1598%
Civil Group Operations | 21148006 | Richland (Sac) Wind - Civil |  |  | 0 | 5045033 | 340839 | 5777493.1646 | 6204060.39 | 18812.26 | 19413.5 | 77.01% | 22.98% | 0.0103%
Civil Group Operations | 21148007 | Mountain View I & II - Civil |  |  | 0 | 4650563 | 72632 | 4439146.14 | 3611841.8 | 19259.96 | 15241.5 | 79.29% | 20.15% | 0.5577%
Civil Group Operations | 21148008 | Midland Wind - Civil |  |  | 0 | 12642566.16 | 221787 | 14045325.86 | 15510797.43 | 40300.5 | 53340.8 | 68.24% | 30.63% | 1.138%
Civil Group Operations | 21148009 | Pomeroy Repower Civil |  |  | 0 | 2246318.32 | 20882.69 | 2060474.4542 | 1394311.77 | 6166.78 | 4420 | 74.4% | 24.72% | 0.8824%
Civil Group Operations | 21148010 | Laurel Repower Civil |  |  | 0 | 5297409.79 | 1750 | 6572756.2408 | 4825090.39 | 19440.57 | 14905.5 | 78.21% | 20.11% | 1.674%
Civil Group Operations | 21148011 | Rolling Hills Repower Civil |  |  | 0 | 18245742.83 | 166546.25 | 22911594.3217 | 20185545.05 | 43821.49 | 72012.5 | 70.99% | 27.68% | 1.336%
Civil Group Operations | 21148012 | Sheph Flats(NorH) Wind - Civil |  |  | 0 | 2030296.42 | 15338 | 5969002.85 | 5021551.62 | 5663.75 | 11053.75 | 70.35% | 28.13% | 1.52%
Civil Group Operations | 21148013 | Sheph Flats(SthH) Wind - Civil |  |  | 0 | 2396970.85 | 130 | 5180391.68 | 4244971 | 6280.85 | 12326.31 | 74.89% | 24.44% | 0.6652%
Civil Group Operations | 21148014 | Sheph Flats (HoB) Wind - Civil |  |  | 0 | 2281370.85 | 87 | 2645740.29 | 2261825.78 | 6875.13 | 9408 | 69.94% | 29.44% | 0.6271%
Civil Group Operations | 21148015 | 25 Mile Creek Wind - Civil |  |  | 0 | 12308824.17 | 1671260 | 14819898.8468 | 14112373.56 | 53130.65 | 58306.33 | 75.74% | 24.26% | 0%
Civil Group Operations | 21148016 | Nobles Repower - Civil |  |  | 0 | 5835882.2 | 40095 | 7403314.08 | 6544641.57 | 20344.46 | 23259.5 | 76.63% | 23.29% | 0.07954%
Civil Group Operations | 21148017 | Sagebrush Storage - Civil |  |  | 0 | 938461.5 | 0 | 1115023.64 | 936284.15 | 794.36 | 622 | 72.35% | 27.65% | 0%
Civil Group Operations | 21148018 | UNO1A Mass Grading |  |  | 0 | 4931871.08 | 5084686.75 | 38521111.1245 | 29763847.03 | 113517.87 | 112345 | 75.94% | 24.06% | 0%
Data Center Operations | 21120001 | Google - CLB Masterplan |  |  | 0 | 10 | 0 | 172745 | 111836.05
Data Center Operations | 21120002 | Google-UNO1-A Master Planning |  |  | 0 | 0 | 0 | 171389.09 | 80158.63
Data Center Operations | 21120004 | Facebook - Lego Phase 3 DC |  |  | 0 | 2816 | 0 | 1921084.75 | 815375.6
Data Center Operations | 21120005 | Facebook - Community Relations |  |  | 0 | 0 | 0 | 490000 | 443573.08
Data Center Operations | 21120006 | Google - UNO1 Data Center |  |  | 0 | 219152.32 | 0 | 315027854.09 | 116381374.38 | 4870.1 | 6861.5 | 78.44% | 19.83% | 1.727%
Data Center Operations | 21120007 | Meta - 2021 MCM |  |  | 0 | 2 | 0 | 1396863.8 | 1164672.71
Data Center Operations | 21120008 | Meta - DC Type X Product DFMA |  |  | 0 | 0 | 0 | 520960 | 403456.7
Data Center Operations | 21126001 | Facebook - Prg Serv. 2021 |  |  | 0 | 9 | 0 | 2557258 | 2193414.58
Data Center Operations | 21120003 | Facebook - DKL 3¦5¦6 |  |  | 1507646 | 3598017.15 | 667849.26 | 1392024809.63 | 566043337.71 | 431420.68 | 122536.83 | 87.2% | 10.03% | 2.768%
Denver Operations | 21060004 | SCL-LMC Sprinkler |  |  | 0 | 18 | 565.01 | 220151.65 | 241157.4 | 274.2 | 721.5 | 92.24% | 7.762% | 0%
Denver Operations | 21060005 | SCL-LMC Chapel AHU Replacement |  |  | 0 | 159 | 15 | 19883.81 | 19957.38 | 46 | 32 | 96.88% | 3.125% | 0%
Denver Operations | 21060009 | 324 Office Building |  |  | 0 | 0 | 0 | 0.01 | 0
Denver Operations | 21060011 | SCL-Butte Transformer |  |  | 0 | 5889.91 | 0 | 257970.15 | 270409.83 | 241.2 | 0 | 0% | 0% | 0%
Denver Operations | 21060017 | SCL-LMC Steam Blow Down |  |  | 0 | 7.5 | 0 | 16693.46 | 16394.66
Denver Operations | 21060018 | SCL-SJH Restrooms |  |  | 0 | 493 | 183 | 275030.19 | 254322.07 | 131 | 98 | 98.47% | 1.531% | 0%
Denver Operations | 21060020 | SCL-SJB Elevator Refurbishment |  |  | 0 | 1141.21 | 0 | 1249183.1804 | 1131353.15 | 40 | 0 | 0% | 0% | 0%
Denver Operations | 21060023 | MC G150 Utilities Package |  |  | 0 | 0 | 1 | 1383873.19 | 1183830.51 | 0 | 143 | 95.1% | 4.895% | 0%
Denver Operations | 21060025 | Vestas Project X |  |  | 0 | 0 | 0 | 5558.41 | 6326.98
Denver Operations | 21060026 | Modern Aviation-Hangar |  |  | 0 | 462024.31 | 334799.75 | 18648227.365 | 18918663.84 | 19317.3 | 27959.53 | 93.57% | 6.428% | 0%
Denver Operations | 21060029 | Aurora One Develop - Precon |  |  | 0 | 0 | 0 | 0.01 | 3722.98
Denver Operations | 21060033 | WCR2 Borrow Pit |  |  | 0 | 92884.97 | 59460 | 501909 | 0 | 1810.97 | 0 | 0% | 0% | 0%
Denver Operations | 21060041 | WCR 2 Borrow Pit |  |  | 0 | 132193.34 | 79189 | 714533.3117 | 793314.27 | 1810.97 | 1839.5 | 71.92% | 28.08% | 0%
Denver Operations | 21060042 | SCL-SJD Medivator |  |  | 0 | 85 | 95 | 25054.73 | 25902.6 | 108 | 150 | 86.67% | 13.33% | 0%
Denver Operations | 21060044 | SCL-Lutheran CT Equipment |  |  | 0 | 1703 | 91 | 28939.1 | 32126.81 | 440.8 | 253 | 92.49% | 7.51% | 0%
Denver Operations | 21060046 | Park Creek Filing 34 |  |  | 0 | 0 | 3595 | 1298683 | 1246658.31 | 3161 | 3764.5 | 98.62% | 1.381% | 0%
Denver Operations | 21060048 | Park Creek-Civil Phase 3 |  |  | 0 | 0 | 914 | 515830 | 525001.44 | 1505 | 2025 | 100% | 0% | 0%
Denver Operations | 21060050 | MC 2022 Capital Improvements |  |  | 0 | 19129.13 | 6648 | 827677.57 | 810024.3 | 314.5 | 3416.5 | 88% | 12% | 0%
Denver Operations | 21060056 | CoorsTek-CCAM R&D |  |  | 0 | 78 | 16 | 598016.12 | 580921.19 | 347 | 180 | 82.5% | 17.5% | 0%
Denver Operations | 21060062 | Park Creek- Filing 60 |  |  | 0 | 0 | 134 | 306472 | 307316.58 | 873 | 214 | 100% | 0% | 0%
Denver Operations | 21060063 | DHHA Sterile Processing Dept |  |  | 0 | 1366 | 199.26 | 297373.7 | 283122.34 | 1234.7 | 368.5 | 75.31% | 24.69% | 0%
Denver Operations | 21060064 | Box Elder Infrastruct Phas 1 |  |  | 0 | 509432.8 | 302200.5 | 25733405.54 | 18191955.47 | 15181.38 | 7356.2 | 81.43% | 18.57% | 0%
Denver Operations | 21060065 | CoorsTek 9th St Utility |  |  | 0 | 7447.5 | 5071.5 | 1780234.387 | 1698977.45 | 7562.5 | 11419.5 | 97.19% | 2.811% | 0%
Denver Operations | 21060003 | SCL-LMC DA Tank Controls |  |  | 1 | 136 | 15 | 42921.16 | 42576.17 | 55 | 36 | 97.22% | 2.778% | 0%
Denver Operations | 21060053 | SCL-SJH Brachy Therapy |  |  | 1 | 26726 | 1768.83 | 1204750.2285 | 1217582.53 | 4011.29 | 4462.59 | 87.88% | 12.12% | 0%
Denver Operations | 21060030 | SCL-SJH Midtown Roof |  |  | 2 | 27018 | 608.26 | 1382945.59 | 1410244.1 | 115 | 1272 | 91.19% | 8.805% | 0%
Denver Operations | 21060031 | SCL-LMC W Pines Security |  |  | 2 | 330.6 | 0 | 52823.62 | 52405.09 | 325.4 | 69 | 100% | 0% | 0%
Denver Operations | 21060015 | SCL SJD Misc AV Support |  |  | 100 | 18.85 | 24 | 19910.06 | 20076.15 | 129 | 70.5 | 90.78% | 9.22% | 0%
Denver Operations | 21060039 | SCL-SJB Steam Hot Water |  |  | 100 | 1020.21 | 0 | 90422.44 | 90043.14
Denver Operations | 21060032 | DHHA -Payroll Suite Renovation |  |  | 120 | 38 | 49 | 11540.88 | 11433.4 | 83 | 72 | 87.5% | 12.5% | 0%
Denver Operations | 21060057 | DHHA-Pav C Milk Prep |  |  | 150 | 261 | 74.2 | 76525.49 | 74124.8 | 214.45 | 338.5 | 88.04% | 11.96% | 0%
Denver Operations | 21060027 | SCL-SJB Butte Humidity |  |  | 500 | 1022.17 | 0 | 272353.06 | 270277.18
Denver Operations | 21060028 | SCL-SJB Butte Life Safety |  |  | 500 | 1132.27 | 0 | 392598.34 | 410811.72 | 106.6 | 0 | 0% | 0% | 0%
Denver Operations | 21060036 | SCL-SJB Fire Doors |  |  | 500 | 1093.67 | 0 | 132677.95 | 135343.03
Denver Operations | 21060038 | SCL-SJB MRI Roof Replacement |  |  | 500 | 817.6 | 0 | 660661.65 | 676302.2
Denver Operations | 21060055 | Highpoint-Phase 1 Metro Dist |  |  | 500 | 70291 | 44340.1 | 7551226.35 | 6857298.97 | 10403.61 | 15239.45 | 79.42% | 20.58% | 0%
Denver Operations | 21060059 | SCL-SJB Card Reader Precon |  |  | 500 | 0 | 0 | 0.01 | 0
Denver Operations | 21060006 | SCL-SJB RAMP Chiller |  |  | 1000 | 1132.5 | 0 | 411069.03 | 425144.92 | 381.2 | 0 | 0% | 0% | 0%
Denver Operations | 21060007 | SCL-SJB Deareator Tank |  |  | 1000 | 2858.55 | 0 | 688556.32 | 717909.41 | 347.6 | 0 | 0% | 0% | 0%
Denver Operations | 21060052 | CHCO-AMC Kitchen Remodel |  |  | 1500 | 1343.5 | 1798.99 | 1278046 | 953958.15 | 3888.3 | 2769 | 85.61% | 14.39% | 0%
Denver Operations | 21060021 | CoorsTek-STM Gov't Storage |  |  | 2100 | 0 | 41 | 197055.01 | 185830.09 | 412 | 266 | 99.62% | 0.3759% | 0%
Denver Operations | 21060047 | SCL-Candelas Pharmacy TI's |  |  | 2100 | 0 | 0 | 361027.07 | 360454.97
Denver Operations | 21060002 | SCL-SJB Pneumatic Tube System |  |  | 2500 | 21 | 0 | 183983.45 | 190354.87
Denver Operations | 21060049 | CoorsTek Pilot Plant Cell |  |  | 5000 | 4 | 214 | 820705.11 | 1156955.18 | 222 | 3364.71 | 92.51% | 7.49% | 0%
Denver Operations | 21060010 | SCL-NJH Primary Care Clinic |  |  | 9000 | 190 | 0 | 1613950.38 | 1612235.99 | 190 | 66 | 100% | 0% | 0%
Denver Operations | 21060040 | Girls Inc. Courtyard |  |  | 9360 | 6190.39 | 5876 | 404339.31 | 406582.04 | 1394.2 | 2203 | 93.92% | 6.083% | 0%
Denver Operations | 21060016 | SCL Butte Flats Primary Clinic |  |  | 10000 | 2314 | 0 | 2001598.69 | 2062900.54 | 708.1 | 0 | 0% | 0% | 0%
Denver Operations | 21060008 | SCL-LMC Cancer Center |  |  | 12000 | 110188 | 41788.25 | 2811289.9086 | 2884669.35 | 4370.92 | 5429.5 | 95.27% | 4.733% | 0%
Denver Operations | 21060045 | AEI - Ft Collins Refresh |  |  | 20000 | 11471 | 37.5 | 6449194.41 | 6414181.87 | 4900.3 | 3888.91 | 91.63% | 8.373% | 0%
Denver Operations | 21060051 | CHCO-Research Enterprise |  |  | 21000 | 7241.5 | 199.41 | 272330.64 | 285193.29 | 1052.8 | 1454.5 | 91.51% | 8.491% | 0%
Denver Operations | 21060066 | SCL-Midtown Fireproofing |  |  | 25000 | 294 | 707.85 | 2185730.3552 | 2183983.67 | 3206 | 5564.22 | 84.68% | 15.32% | 0%
Denver Operations | 21060022 | TerraCO Comm Plant 1 |  |  | 30000 | 0 | 0 | 20072 | 20071.97
Denver Operations | 21060035 | Willis Towers 20th & 21st TI |  |  | 40000 | 117089 | 75954.97 | 5957945.3267 | 5661634.67 | 5739.99 | 11795 | 96.21% | 3.79% | 0%
Denver Operations | 21060013 | Tritower - Sterling Campus Lab |  |  | 95292 | 0 | 0 | 76402 | 109429.81
Denver Operations | 21060061 | Centura-SAN Tower & Renovation |  |  | 112500 | 788051.3 | 145 | 65750616.09 | 4778134.9 | 38298.9 | 953 | 90.03% | 9.969% | 0%
Denver Operations | 21060034 | BCSP 1740 Broadway |  |  | 113084 | 50128.58 | 49943 | 14629833.234 | 12432192.39 | 9941.1 | 8978 | 87.1% | 12.9% | 0%
Denver Operations | 21060024 | Train Denver CM Phase I Office |  |  | 125000 | 0 | 0 | 0.01 | 8548.03
Denver Operations | 21060037 | MDI-Walnut Park Multifamily |  |  | 269000 | 0 | 0 | 0.01 | 70707.26
Denver Operations | 21060001 | CoorsTek 9th St. Precon |  |  | 400000 | 0 | 0 | 25000 | 107981.35 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 21060043 | MDI-SLC Industrial |  |  | 465000 | 0 | 0 | 0.01 | 62023.73
Denver Operations | 21060060 | Dollar General |  |  | 918000 | 1778946.96 | 745910 | 120918244.0504 | 39880276.65 | 51149.72 | 23353 | 74.02% | 25.98% | 0%
Energy Storage & Solutions Operations | 21149001 | CATS EV Bus |  |  | 0 | 45097.16 | 41144 | 3407815.16 | 3254909.92 | 2015.31 | 2560.5 | 89.14% | 10.86% | 0%
Energy Storage & Solutions Operations | 21149002 | Fighting Jays BESS |  |  | 0 | 0 | 113 | 748117.4 | 497921.29 | 0 | 123 | 100% | 0% | 0%
Energy Storage & Solutions Operations | 21149003 | Sagebrush BESS |  |  | 0 | 342253.64 | 270802.12 | 60448661.8404 | 57040100.64 | 49526.89 | 63227.77 | 82.91% | 16.34% | 0.7544%
FCG Operations | 21110001 | AMJV Tropical Pyramid JV-Int |  |  | 0 | 0 | 0 | 35019 | 32547.94
FCG Operations | 21110002 | AMJV Backsaw JV-Int |  |  | 0 | 0 | 0 | 297 | 462.5
FCG Operations | 21110003-159 | McCarthy/Mortenson JV-NBAF 8 |  |  | 0 | 0 | 0 | 53237697 | 0
FCG Operations | 21110004 | AMJV SCADA Upgrades JV-Int |  |  | 0 | 0 | 0 | 524060 | 485586.27 | 0 | 1100 | 100% | 0% | 0%
FCG Operations | 21110006 | AMJV CHW Upgrade JV-Int |  |  | 0 | 0 | 0 | 21575 | 29706.78
FCG Operations | 21110008 | Bolling AFB Photolab |  |  | 0 | 5822 | 0 | 644249.09 | 490565.63
FCG Operations | 21110009 | AMJV Abundant Shield JV-Int |  |  | 0 | 0 | 0 | 5572 | 1484.45
FCG Operations | 21110009-174 | UDC Abundant Shield |  |  | 0 | 0 | 0 | 128796 | 117205.11
FCG Operations | 21110010 | AMJV DCM 4 Pre-Fit Up JV-Int |  |  | 0 | 0 | 0 | 1060138 | 679918.31 | 0 | 1640 | 100% | 0% | 0%
FCG Operations | 21110010-174 | UDC DCM 4 Pre-Fit Up |  |  | 0 | 0 | 0 | 18842330 | 8795209.09
FCG Operations | 21110002-174 | UDC Backsaw |  |  | 2000 | 0 | 0 | 12939 | 12072.26
FCG Operations | 21110006-174 | UDC Chilled Water Upgrades |  |  | 2000 | 0 | 0 | 276003 | 272960.64
FCG Operations | 21110001-174 | UDC Tropical Pyramid |  |  | 6000 | 0 | 0 | 189062 | 181166.84
FCG Operations | 21060012 | NREL RAIL |  |  | 16500 | 3360 | 1493.4 | 16367611.45 | 17282503.05 | 2221 | 10374.55 | 88.01% | 11.99% | 0%
FCG Operations | 21110003 | McCarthy/Mortenson NBAF 8 |  |  | 18000 | 0 | 0 | 390000.01 | 2210868.12 | 0 | 7420 | 91.39% | 8.612% | 0%
FCG Operations | 21110004-174 | UDC SCADA Upgrades |  |  | 25000 | 0 | 0 | 3046382 | 2997885.3
FCG Operations | 21110007 | Bldg 9840 AHU 6 Cooling Coil |  |  | 34306 | 36 | 0 | 319423 | 301269.37
FCG Operations | 21110005 | NGIC Rivanna |  |  | 88000 | 117643 | 0 | 62961278.015 | 19661576.47 | 0 | 2067.5 | 99.9% | 0.09674% | 0%
Milwaukee Operations | 21080005 | DRS-Dallas Masterplan Study |  |  | 0 | 0 | 0 | 10000 | 9991.72
Milwaukee Operations | 21080010 | Ever Green Misc Project 21-22 |  |  | 0 | 13 | 1 | 112155 | 121549.9 | 700 | 676 | 97.63% | 2.367% | 0%
Milwaukee Operations | 21080015 | RockGen Concrete Pad 3-3 |  |  | 0 | 804.45 | 0 | 41918.96 | 25195.18 | 280.7 | 227 | 100% | 0% | 0%
Milwaukee Operations | 21080018 | WisDOT I43 North |  |  | 0 | 0 | 0 | 0.01 | 13139.71
Milwaukee Operations | 21080004 | MRMC Cooling Tower Basin |  |  | 100 | 9881.16 | 5974 | 556964.92 | 553310.58 | 1405.4 | 1507.5 | 98.54% | 1.459% | 0%
Milwaukee Operations | 21080002 | AAH Misc Projects 2021-2022 |  |  | 200 | 19 | 0 | 1357307.48 | 1016449.78 | 2448 | 3043.98 | 94.12% | 5.782% | 0.09856%
Milwaukee Operations | 21080012 | MRMC City Water Office |  |  | 400 | 4125.3 | 0 | 113021.81 | 113894.92 | 304.6 | 258 | 100% | 0% | 0%
Milwaukee Operations | 21080007 | AMCMP Misc Projects 21-22 |  |  | 1500 | 39037.61 | 11761 | 2431298 | 2097083.69 | 3108.8 | 1977.5 | 96.79% | 3.211% | 0%
Milwaukee Operations | 21080017 | Froedtert - MF Pharm Reno |  |  | 3800 | 90710 | 13019 | 5844470.28 | 1672524.89 | 4879.5 | 2430.5 | 94.65% | 5.225% | 0.1234%
Milwaukee Operations | 21080013 | Froedtert Complex Intervention |  |  | 10856 | 102223 | 5394 | 5653850.7 | 5096856.38 | 7434.3 | 9104 | 91.48% | 7.958% | 0.5602%
Milwaukee Operations | 21080011 | Froedtert GI Diagnostic |  |  | 53500 | 736877 | 56 | 18545006.8 | 8787473.96 | 24690.1 | 10343 | 98.46% | 1.503% | 0.03867%
Milwaukee Operations | 21080014 | Dane Cty Arpt CA Phase STE |  |  | 60000 | 0 | 0 | 64488 | 31862.34
Milwaukee Operations | 21080006 | Mulva Cultural Center |  |  | 80000 | 328608.5 | 5584 | 78591777.2602 | 51279707.92 | 18212.04 | 8644.48 | 88.91% | 10.94% | 0.1446%
Milwaukee Operations | 21080019 | MCW Cancer Research |  |  | 150000 | 40586.63 | 3619.5 | 13891384.42 | 2468612.36 | 7417.1 | 1859 | 96.88% | 3.093% | 0.0269%
Milwaukee Operations | 21080016 | Embassy Suites Madison |  |  | 153800 | 1275910.07 | 226604.5 | 58778015.418 | 20216895.81 | 43483.72 | 21071.25 | 89.24% | 10.72% | 0.03797%
Milwaukee Operations | 21080001 | Milwaukee Public Museum |  |  | 200000 | 844 | 575 | 874379.93 | 451826.51 | 96 | 133 | 98.5% | 1.504% | 0%
Milwaukee Operations | 21080008 | UW Madison - CDIS |  |  | 310000 | 0 | 0 | 19800 | 3667.62
Milwaukee Operations | 21080009 | Milwaukee Tool-ProjRed Beacon |  |  | 370000 | 2883936.47 | 1492184.76 | 88187650.43 | 81043608.81 | 76900.7 | 71137.04 | 95.23% | 4.671% | 0.09629%
Milwaukee Operations | 21080003 | ULINE DISTRIBUTION FAC - FL |  |  | 937000 | 82890 | 0 | 93978580.96 | 88223984.19 | 0 | 2243.5 | 86.56% | 13.44% | 0%
Minneapolis Operations | 21008 | MORTENSON PROPERTIESMORTENSON | 2002-12-31 |  | 0 | 0 | 0 | 0 | 6956 | 0 | 102 | 100% | 0% | 0%
Minneapolis Operations | 21009 | NORTHWIRTH ASSOCIATET.I. 2002 | 2002-12-31 |  | 0 | 0 | 0 | 9087 | 36245 | 0 | 310 | 100% | 0% | 0%
Minneapolis Operations | 21016 | MSFC- MISC CONSULTING | 2002-12-31 |  | 0 | 0 | 0 | 0 | 18163 | 0 | 5 | 100% | 0% | 0%
Minneapolis Operations | 21019 | HGA-WAC TEAM BUILD -OUT | 2002-04-29 |  | 0 | 0 | 1324 | 0 | 11705 | 0 | 196 | 100% | 0% | 0%
Minneapolis Operations | 21027 | HABITAT FOR HUMANITY | 2002-10-31 |  | 0 | 0 | 0 | 0 | 11193 | 0 | 121 | 100% | 0% | 0%
Minneapolis Operations | 21029 | MORTENSON DEVELOPMENT-FAIRVIE | 2003-10-30 |  | 0 | 129527 | 87770 | 1868019 | 1876591 | 0 | 4599 | 100% | 0% | 0%
Minneapolis Operations | 21030001 | Fairview Facility Annual 2021 |  |  | 0 | 778 | 0 | 3093971.36 | 3742040.32 | 0 | 7598 | 94.12% | 4.271% | 1.606%
Minneapolis Operations | 21030002 | Allina Annual Contract 2021 |  |  | 0 | 3519 | 0 | 5105415.26 | 4554673.58 | 23028.5 | 20023.25 | 85.13% | 14.42% | 0.4545%
Minneapolis Operations | 21030003 | Fairview Small Cap Proj 2021 |  |  | 0 | 52 | 0 | 880892.4 | 854171.41 | 0 | 1805.5 | 97.76% | 1.8% | 0.4431%
Minneapolis Operations | 21030008 | Allina Mercy EP 2 Replacement |  |  | 0 | 15 | 0 | 304482.72 | 320305.42 | 1002 | 1065.5 | 97.28% | 2.722% | 0%
Minneapolis Operations | 21030014 | BSC - Access Drive/Parking Exp |  |  | 0 | 24 | 0 | 4375232.19 | 4402212.27 | 24 | 0 | 0% | 0% | 0%
Minneapolis Operations | 21030015 | MMC - Sanford Cooling Tower |  |  | 0 | 0 | 0 | 172153.1 | 175793.51 | 30 | 8 | 100% | 0% | 0%
Minneapolis Operations | 21030018 | TA - Edgewood Demo |  |  | 0 | 0 | 0 | 2513015.587 | 2607033.92 | 8 | 225 | 81.78% | 18.22% | 0%
Minneapolis Operations | 21030025 | Allina ANW Road Curb Walkway |  |  | 0 | 372 | 0 | 316885.58 | 278351.86 | 1601 | 1310.5 | 92.22% | 6.257% | 1.526%
Minneapolis Operations | 21030026 | Skogman Office Bldg Renovation |  |  | 0 | 0 | 0 | 299214 | 240474.13 | 612 | 306 | 77.45% | 22.55% | 0%
Minneapolis Operations | 21030029 | Augustana - East Granskou Park |  |  | 0 | 13 | 0 | 551513.77 | 552491.44
Minneapolis Operations | 21030030 | Basilica 2021 Masonry Restore |  |  | 0 | 4109 | 0 | 505321.23 | 471745.61 | 4489 | 2361.18 | 89.29% | 10.71% | 0%
Minneapolis Operations | 21030032 | Augustana - Electrical Infrast |  |  | 0 | 13 | 0 | 539386.45 | 541130.94
Minneapolis Operations | 21030033 | Augustana - Bergsaker Hall Ren |  |  | 0 | 105832.66 | 47438 | 8670418.1 | 8752313.02 | 5765.72 | 5619.5 | 87% | 13% | 0%
Minneapolis Operations | 21030034 | Augustana - Campus Greens Impr |  |  | 0 | 27 | 0 | 2486112.1 | 2318185.5 | 432 | 1079.5 | 89.53% | 10.47% | 0%
Minneapolis Operations | 21030037 | The Basilica - School Foundati |  |  | 0 | 50 | 0 | 217867.52 | 192859.49 | 424 | 344.59 | 95.5% | 4.498% | 0%
Minneapolis Operations | 21030044 | Cirrus Aircraft - Master Plann |  |  | 0 | 304 | 0 | 139675 | 348987.96
Minneapolis Operations | 21030045 | IDT - ECO Stack Replacement |  |  | 0 | 973.06 | 0 | 129279.33 | 108259.85 | 173.6 | 141.5 | 93.29% | 6.714% | 0%
Minneapolis Operations | 21030049 | ANW-CK LL Cafeteria Plmb Rpr |  |  | 0 | 57 | 0 | 414460.29 | 411200.81 | 1437 | 1259.5 | 88.13% | 11.71% | 0.1588%
Minneapolis Operations | 21030053 | Swervo - Ampitheater |  |  | 0 | 0 | 0 | 249438.46 | 185192.93 | 0 | 11 | 27.27% | 72.73% | 0%
Minneapolis Operations | 21030054 | IDT - 2400 Oakdale |  |  | 0 | 157751.41 | 54812 | 11658216.82 | 9778811.4 | 5733.5 | 8054.5 | 93.17% | 6.704% | 0.1242%
Minneapolis Operations | 21030055 | Allina-Security Upgrd-Clinics |  |  | 0 | 501 | 0 | 3321290.5 | 2476409.64 | 10999 | 5880.45 | 73.36% | 26.32% | 0.3231%
Minneapolis Operations | 21030056 | Allina-Security Upgrd-Hospital |  |  | 0 | 37 | 0 | 1300502 | 985084.5 | 580 | 4436.05 | 72.77% | 27.23% | 0%
Minneapolis Operations | 21036 | EILA KORPI TRUSTEE HUGH-EDINA | 2002-10-31 |  | 0 | 0 | 0 | 0 | 3381 | 0 | 45 | 100% | 0% | 0%
Minneapolis Operations | 21901 | CLOSED JOB - MINNEAPOLIS - MA | 2002-12-31 |  | 0 | 0 | 0 | 0 | 27568 | 0 | 0 | 0% | 0% | 0%
Minneapolis Operations | 21999 | MORTENSON-CLOSED JOBMINNEAPOL | 2002-12-31 |  | 0 | 0 | 0 | 0 | 195510 | 0 | 469 | 100% | 0% | 0%
Minneapolis Operations | 21030013 | UMN - Rebld Tool Shed/PH |  |  | 500 | 180 | 0 | 98644.47 | 85401.91 | 265 | 267 | 100% | 0% | 0%
Minneapolis Operations | 21031 | GLASRUD ASSOCIATES /WIRTH PAR | 2002-09-30 |  | 550 | 0 | 0 | 10393 | 10967 | 0 | 48 | 100% | 0% | 0%
Minneapolis Operations | 21041 | NORTH STAR STEEL-FURNACE/RAIL | 2003-01-10 |  | 775 | 1424 | 1116 | 135234 | 136601 | 0 | 1118 | 100% | 0% | 0%
Minneapolis Operations | 21017 | MINNESOTA VIKINGS-MEDIA ROOM | 2002-04-30 |  | 895 | 0 | 0 | 21460 | 21478 | 0 | 142 | 100% | 0% | 0%
Minneapolis Operations | 21030005 | MNU Mt Airy B&G Club STEM/Gym |  |  | 1000 | 1 | 0 | 447196 | 430408.85 | 898 | 1515.55 | 100% | 0% | 0%
Minneapolis Operations | 21012 | WALKER - GUTHRIETHEATER SELEC | 2002-03-30 |  | 1200 | 2043 | 0 | 25839 | 128585 | 0 | 157 | 100% | 0% | 0%
Minneapolis Operations | 21030046 | CentraCare Monticello - Linear |  |  | 1500 | 5 | 0 | 513483.73 | 504081.07 | 1028 | 999 | 76.58% | 23.22% | 0.2002%
Minneapolis Operations | 21030007 | Twins - Target Field Market |  |  | 1630 | 7381 | 0 | 774283.82 | 1179589.1 | 1123.8 | 2520 | 97.5% | 2.5% | 0%
Minneapolis Operations | 21030042 | 4150 LLC - MNUFC TI |  |  | 1630 | 0 | 0 | 136659 | 127978.39 | 280 | 269.5 | 100% | 0% | 0%
Minneapolis Operations | 21030038 | Dunwoody Classroom 78 & 80 |  |  | 1700 | 256 | 0 | 158745.1 | 127788.36 | 132 | 101 | 96.04% | 3.96% | 0%
Minneapolis Operations | 21030052 | Allina Health - Mercy CV-1 |  |  | 2000 | 6 | 0 | 305010.95 | 305229.35 | 1123 | 973.5 | 93.27% | 6.728% | 0%
Minneapolis Operations | 21030009 | Allina ANW SPS Sinks/Caviwaves |  |  | 2200 | 938 | 0 | 292820.16 | 284531.7 | 905 | 619 | 85.7% | 13.49% | 0.8078%
Minneapolis Operations | 21030051 | Marvin Fargo West - Breakroom |  |  | 5000 | 23800 | 0 | 985434.58 | 992366.21 | 1321.8 | 1001.5 | 97.15% | 2.846% | 0%
Minneapolis Operations | 21030040 | Allina - Mercy PET/CT |  |  | 8500 | 26 | 0 | 1250860.9 | 1212289.48 | 5495 | 4881.2 | 95.44% | 3.948% | 0.6146%
Minneapolis Operations | 21030028 | UMN Lind Hall Temp Space |  |  | 9000 | 1 | 0 | 73669 | 66655.96 | 15 | 0 | 0% | 0% | 0%
Minneapolis Operations | 21030036 | Fairview UMMCH WB AAR 3.0 |  |  | 11200 | 4 | 0 | 401560.28 | 172409.76 | 727 | 865 | 99.71% | 0.289% | 0%
Minneapolis Operations | 21030031 | UIHC - JohnPappaPav 5FL OR Exp |  |  | 11437 | 35191.72 | 12457 | 830924.88 | 977395.63 | 1711.4 | 1706 | 83.91% | 15.18% | 0.9086%
Minneapolis Operations | 21013 | GORDY AAMOTH, JR. MEMORIAL ST | 2002-09-11 |  | 20000 | 113224 | 113315 | 2078379 | 2224771 | 0 | 11470 | 100% | 0% | 0%
Minneapolis Operations | 21030041 | Sanford - 7CD Build-out |  |  | 25677 | 36815 | 14763 | 6842499.85 | 6833947.95 | 7018.1 | 8351.95 | 84.99% | 14.26% | 0.7543%
Minneapolis Operations | 21030011 | Fairview UMMC Corp Bldg Refrsh |  |  | 30000 | 69 | 0 | 1445541.71 | 1432009.85 | 3646 | 3192.5 | 98.1% | 1.895% | 0%
Minneapolis Operations | 21030027 | NS IV - Business Essentials TI |  |  | 31216 | 614 | 24 | 1002360.96 | 988431.85 | 905 | 1424 | 96.88% | 3.125% | 0%
Minneapolis Operations | 21030048 | Blake School - New Early Learn |  |  | 33250 | 615453.41 | 120498 | 15244392.06 | 6441676.85 | 36070.12 | 20553.5 | 96.86% | 3.141% | 0%
Minneapolis Operations | 21030043 | St. Michael Addition & Alterat |  |  | 34980 | 74034.78 | 0 | 6134762.814 | 6038545.81 | 5997.8 | 8474.6 | 97.37% | 2.537% | 0.0944%
Minneapolis Operations | 21030012 | NS IV - Red Bull TI |  |  | 42994 | 12 | 0 | 1327210.11 | 1124630.35 | 1912 | 1510 | 98.87% | 1.126% | 0%
Minneapolis Operations | 21030039 | Wuollet Bakery Commissary Kitc |  |  | 54020 | 406802.96 | 0 | 20059851.27 | 967701.27 | 18665.09 | 0 | 0% | 0% | 0%
Minneapolis Operations | 21030021 | Target Corp - Plymouth T-0664 |  |  | 55000 | 8 | 0 | 934569.71 | 960615.67 | 3028 | 1631.5 | 84.34% | 15.66% | 0%
Minneapolis Operations | 21030022 | Target Corp - Knollwood T-2189 |  |  | 55000 | 5 | 0 | 768602.6525 | 818833.36 | 2347 | 2284.15 | 99.65% | 0.3502% | 0%
Minneapolis Operations | 21030024 | Target Corp - Chaska T-1352 |  |  | 55000 | 246 | 0 | 1069174.4714 | 1096508.55 | 2613.64 | 2076.33 | 95.16% | 4.84% | 0%
Minneapolis Operations | 21030050 | Augustana University - Solberg |  |  | 56938 | 91931.32 | 39579 | 8116026.84 | 4256853.67 | 3783.3 | 4698.5 | 84.88% | 15.12% | 0%
Minneapolis Operations | 21030035 | BSC - Weaver Lake 4 Expansion |  |  | 74000 | 214260 | 56837.97 | 46921894.09 | 48330684.46 | 9969.3 | 19686 | 94.8% | 5.019% | 0.1829%
Minneapolis Operations | 21030023 | Target Corp-Eden PrairieT-0220 |  |  | 100000 | 503.28 | 8 | 3617880.2955 | 3645156.89 | 5507.16 | 5118.5 | 85.85% | 14.15% | 0%
Minneapolis Operations | 21030019 | MDI - AU South Residence Hall |  |  | 120000 | 145139 | 14113 | 16661900.17 | 16510642.66 | 5889 | 4040.22 | 81.08% | 18.84% | 0.07425%
Minneapolis Operations | 21030016 | Tri-County -Replcment Hospital |  |  | 126000 | 186189 | 61920 | 29973964.513 | 27754637.27 | 32659.3 | 31054.5 | 92.13% | 7.87% | 0%
Minneapolis Operations | 21028 | MINNESOTA PUBLIC RADIO EXPANS |  |  | 129858 | 1650494 | 1431854 | 34807648 | 32809650 | 0 | 84166 | 100% | 0% | 0%
Minneapolis Operations | 21030006 | Vermeer Legacy 7 Cooling |  |  | 150000 | 714 | 0 | 3033497.35 | 3014841.02 | 789 | 1090.5 | 55.94% | 35.17% | 8.895%
Minneapolis Operations | 21030047 | Fairview - Unit J Nurse Call |  |  | 207481 | 0 | 0 | 1326110.21 | 396790 | 4488 | 1532 | 96.41% | 3.003% | 0.5875%
Minneapolis Operations | 21030020 | Oberlin - Sustain Infra Prog |  |  | 238660 | 71843.5 | 0 | 89533047.3292 | 59123786.05 | 13223 | 15830.25 | 76.99% | 22.33% | 0.6822%
Minneapolis Operations | 21004 | CITY OF SIOUX CITY -TYSON/IBP | 2003-12-20 |  | 250000 | 0 | 0 | 699038 | 685608 | 0 | 358 | 100% | 0% | 0%
Minneapolis Operations | 21035 | RAMSEY COUNTY PUBLICWORKS | 2004-10-01 |  | 250000 | 3406282 | 2271715 | 43636884 | 43635397 | 0 | 94425 | 100% | 0% | 0%
Minneapolis Operations | 21030017 | TA - 6400 Replace HVAC/RTU |  |  | 270000 | 6 | 0 | 4156040.3269 | 4096181.84 | 1810.18 | 2161 | 78.85% | 21.15% | 0%
Minneapolis Operations | 21030004 | MDI - Augustana Univ Housing |  |  | 280000 | 0 | 0 | 965658.26 | 54536.87
Minneapolis Operations | 21030010 | Allina ANW Care Pavilion |  |  | 500000 | 0 | 0 | 261226 | 214711.48 | 100 | 0 | 0% | 0% | 0%
Mortenson Energy Services-Operations | 21157001 | Prairie Hills Blade Re-Tension |  |  | 0 | 0 | 0 | 0 | 331870.93 | 0 | 6437.46 | 78.35% | 21.65% | 0%
Mortenson Energy Services-Operations | 21157002 | Sungrow- MN Support 2021 |  |  | 0 | 0 | 0 | 0 | 4772.97 | 0 | 90.5 | 91.16% | 8.84% | 0%
Mortenson Energy Services-Operations | 21157003 | Great Plains T63 & T104 GBX Ex |  |  | 0 | 0 | 0 | 0 | 288046.56 | 0 | 1594 | 92.35% | 7.654% | 0%
Mortenson Energy Services-Operations | 21157004 | Roundhouse T52 Rebuild |  |  | 0 | 0 | 0 | 0 | 803782.75 | 0 | 2531 | 79.87% | 20.13% | 0%
Mortenson Energy Services-Operations | 21157005 | GE Gearbox Slip Ring Retrofit |  |  | 0 | 0 | 0 | 0 | 11293.34 | 0 | 133.5 | 97% | 2.996% | 0%
Mortenson Energy Services-Operations | 21157006 | Chisholm Battery Commissioning |  |  | 0 | 0 | 0 | 0 | 68025.9 | 0 | 995 | 93.92% | 6.08% | 0%
Mortenson Energy Services-Operations | 21157007 | Battle Mtn. Battery Commission |  |  | 0 | 0 | 0 | 0 | 13635.83 | 0 | 301 | 61.46% | 38.54% | 0%
Mortenson Energy Services-Operations | 21157008 | Blue Canyon T-283 Removal |  |  | 0 | 0 | 0 | 0 | 70987.89
Mortenson Energy Services-Operations | 21157009 | Diamond Springs T36 Tower Demo |  |  | 0 | 0 | 0 | 0 | 53619.82
Mortenson Infrastructure Milw Operations | 21080018-063 | WISDOT Proj I43 North |  |  | 0 | 2 | 0 | 265979.95 | 201103.95
National Projects Group Operations | 21018 | MAPBA-MEMPHIS GRIZZLIES NBA A | 2004-08-01 |  | 1444385 | 1000715 | 2360430 | 174430351 | 174516331 | 0 | 203716 | 100% | 0% | 0%
Phoenix Operations | 21040001 | ASU Misc Small Works |  |  | 0 | 1 | 0 | 35311.99 | 17199.63 | 0 | 166.5 | 91.89% | 8.108% | 0%
Phoenix Operations | 21040004 | Allstate InfoArmor Mod |  |  | 0 | 7 | 0 | 47890.49 | 45265.74 | 21 | 0 | 0% | 0% | 0%
Phoenix Operations | 21040011 | AlaskaUSA Branch Flr Repl |  |  | 0 | 1545 | 0 | 26693.39 | 15487.89 | 147.4 | 66 | 35.61% | 64.39% | 0%
Phoenix Operations | 21040008 | Allstate Chandler Legal Off TI |  |  | 1100 | 1956 | 0 | 90075.5 | 68132.66 | 347.8 | 303 | 85.48% | 14.52% | 0%
Phoenix Operations | 21040006 | PCH Mercy Ophthalmology |  |  | 2000 | 220 | 784 | 545634.27 | 519784.87 | 285.3 | 232.75 | 98.71% | 1.289% | 0%
Phoenix Operations | 21040009 | PCH Mercy Cardiology |  |  | 2147 | 206 | 1241 | 567943.42 | 542285.18 | 299.9 | 226.5 | 93.16% | 6.843% | 0%
Phoenix Operations | 21040002 | PCH Mercy Gilbert Audiology TI |  |  | 2700 | 220 | 7 | 540688.15 | 528122.3 | 247.6 | 209.75 | 94.28% | 5.721% | 0%
Phoenix Operations | 21040005 | SanCarlos Hosp JOC |  |  | 5000 | 349.5 | 0 | 79819.17 | 78285.97 | 307.3 | 322.5 | 75.66% | 24.34% | 0%
Phoenix Operations | 21040010 | The Beam Mortenson Office TI |  |  | 15527 | 21433.4 | 0 | 4353344.68 | 287106.13 | 829.3 | 2051 | 85.2% | 14.8% | 0%
Phoenix Operations | 21040012 | COT Diablo Stadium Reno |  |  | 40000 | 18 | 0 | 834577.23 | 263570.58
Phoenix Operations | 21040003 | Kohler Vikrell West Manu Fac |  |  | 455000 | 191410 | 52756 | 257668584.48 | 121853471.54 | 37731 | 16920.5 | 85.85% | 14.15% | 0%
Phoenix Operations | 21040013 | MDI Signal Butte |  |  | 896281 | 652195.44 | 83 | 51806855.05 | 11299437.25 | 4849.6 | 112 | 100% | 0% | 0%
Portland Operations | 21055002 | Kaiser WMC SPD Ultra |  |  | 0 | 27 | 0 | 143747.53 | 133649.18 | 284 | 375.02 | 92.53% | 5.866% | 1.6%
Portland Operations | 21055003 | Kaiser WMS Kiosks |  |  | 0 | 237 | 8 | 143943 | 146872.27 | 416 | 464 | 100% | 0% | 0%
Portland Operations | 21055005 | BPA T03 HMB Adaptive |  |  | 0 | 42 | 0 | 1824809.53 | 1511108.64
Portland Operations | 21055009 | OHSU CDRC Feasibility Study |  |  | 0 | 7 | 0 | 2014.18 | 1289.92 | 0 | 5 | 100% | 0% | 0%
Portland Operations | 21055010 | OHSU HRC to CDW Relocation |  |  | 0 | 8056.01 | 0 | 870579.8253 | 702481.64 | 438.3 | 734.3 | 98.64% | 1.362% | 0%
Portland Operations | 21055011 | OHSU Sample Prep Microscope |  |  | 0 | 2872.98 | 0 | 677327.05 | 627319.96 | 324.8 | 295 | 97.63% | 2.373% | 0%
Portland Operations | 21055012 | OHSU CCSR Seismic Resil |  |  | 0 | 9 | 0 | 6986.26 | 8132.07 | 12 | 21 | 100% | 0% | 0%
Portland Operations | 21055013 | Kaiser SAL Arc Flash Upgrade |  |  | 0 | -1039.52 | 0 | 329955.14 | 324700.93 | 446 | 79 | 73.42% | 24.05% | 2.532%
Portland Operations | 21055014 | Kaiser TUA Nurse Call Precon |  |  | 0 | 24 | 0 | 17810.86 | 18899.21 | 36 | 48 | 100% | 0% | 0%
Portland Operations | 21055015 | OHSU Urology Adv POB2 |  |  | 0 | 14 | 0 | 5305.09 | 5519.49 | 6 | 32 | 100% | 0% | 0%
Portland Operations | 21055016 | OHSU Vollum Inst PH3 |  |  | 0 | 33424.39 | 0 | 3898541.25 | 3689631.24 | 867 | 1075.85 | 97.86% | 1.766% | 0.3718%
Portland Operations | 21055017 | Kaiser TNB HW 3rd Floor Loop |  |  | 0 | 23 | 0 | 75820.76 | 76374.69 | 136 | 155.98 | 91.02% | 1.923% | 7.052%
Portland Operations | 21055018 | Kaiser WMC Patient Rm Light |  |  | 0 | 9 | 0 | 839399.49 | 840670.83 | 814 | 514 | 97.28% | 2.335% | 0.3891%
Portland Operations | 21055019 | OHSU HMC OBYN |  |  | 0 | 13 | 0 | 11791.26 | 10626.65 | 16 | 0 | 0% | 0% | 0%
Portland Operations | 21055020 | Kaiser SST Air Hndlg Precon |  |  | 0 | 13 | 0 | 62609.45 | 65925.17 | 100 | 48 | 100% | 0% | 0%
Portland Operations | 21055021 | OHSU Urology Adven POB1 |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 21055022 | Kaiser WMC Ultrasound Const |  |  | 0 | 29 | 0 | 332311.06 | 334737.93 | 596 | 422 | 100% | 0% | 0%
Portland Operations | 21055023 | Kaiser BVT Qmatics |  |  | 0 | 38.25 | 0 | 7438.55 | 7565.71 | 44 | 24 | 100% | 0% | 0%
Portland Operations | 21055024 | Kaiser SST Arc Flash Const |  |  | 0 | 30 | 0 | 119688.87 | 111601.4 | 52 | 97 | 86.6% | 10.31% | 3.093%
Portland Operations | 21055026 | OHSU MNP DOM Reloc |  |  | 0 | 9200.5 | 0 | 387480.3 | 336730.91 | 378.1 | 219 | 100% | 0% | 0%
Portland Operations | 21055027 | OHSU HMC Cath Lab |  |  | 0 | 12 | 0 | 5541.2 | 5623.07 | 6 | 0 | 0% | 0% | 0%
Portland Operations | 21055028 | OHSU CEDAR Lab Buildout |  |  | 0 | 10 | 0 | 2283.71 | 2789.84 | 2 | 0 | 0% | 0% | 0%
Portland Operations | 21055029 | OHSU CHH1 Family Med Exp |  |  | 0 | 1 | 0 | 6476.86 | 6757.98 | 16 | 0 | 0% | 0% | 0%
Portland Operations | 21055030 | OHSU RJH Pathology Lab |  |  | 0 | 6472.59 | 0 | 1375843.21 | 303080.92 | 1294.74 | 739.1 | 99.86% | 0.1353% | 0%
Portland Operations | 21055031 | OHSU EJH Bldg Feas Study |  |  | 0 | 11 | 0 | 9206.69 | 9089.84 | 16 | 0 | 0% | 0% | 0%
Portland Operations | 21055032 | Kaiser MHO Decommissioning |  |  | 0 | 155 | 0 | 43873.35 | 40276.89 | 136 | 204 | 100% | 0% | 0%
Portland Operations | 21055034 | Kaiser WMC Scope Wash Const |  |  | 0 | 361 | 0 | 196474.47 | 30764.61 | 440 | 36 | 100% | 0% | 0%
Portland Operations | 21055035 | Kaiser TNB Exam Lane |  |  | 0 | 37 | 0 | 14833.85 | 16369.54 | 97 | 110 | 100% | 0% | 0%
Portland Operations | 21055036 | Kaiser ORC Exam Lane Precon |  |  | 0 | 0 | 0 | 3862.26 | 3601.09
Portland Operations | 21055037 | Kaiser ORC Boiler Repl Precon |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 21055038 | Kaiser SST Nurse Call Precon |  |  | 0 | 15 | 0 | 10382.7 | 12044.95
Portland Operations | 21055039 | OHSU HMC IM GME Remodel |  |  | 0 | 5031.18 | 0 | 1342685.48 | 1169011.52 | 526.8 | 1071.5 | 92.81% | 5.693% | 1.493%
Portland Operations | 21055040 | OHSU FG XRAY |  |  | 0 | 12 | 0 | 3527.61 | 4279.64 | 12 | 0 | 0% | 0% | 0%
Portland Operations | 21055044 | Microchip Fab 4.3 Study |  |  | 0 | 0 | 0 | 636100.01 | 578587.79
Portland Operations | 21055045 | Kaiser TUA NCPA Repl Const |  |  | 0 | 19 | 0 | 217710.11 | 230077.87 | 196 | 304 | 100% | 0% | 0%
Portland Operations | 21055046 | OHSU DCH Exp Feas. |  |  | 0 | 6 | 0 | 59910.78 | 61557.83
Portland Operations | 21055047 | Microchip Fab 4 D-B Scoping |  |  | 0 | 14 | 0 | 309780.78 | 344336.4
Portland Operations | 21055048 | Microchip New Office Study |  |  | 0 | 4 | 0 | 156606.07 | 153956.67
Portland Operations | 21055049 | Microchip Fab 4 Support Svcs |  |  | 0 | 11 | 0 | 48738.09 | 814.68
Portland Operations | 21055050 | Kaiser SST Lghtg Repl Prec |  |  | 0 | 17 | 0 | 13069.63 | 13605.69
Portland Operations | 21055051 | OHSU Dotter Seismic Impro |  |  | 0 | 6484.04 | 0 | 455541.46 | 402860.35 | 928.2 | 1076.6 | 99.44% | 0.5573% | 0%
Portland Operations | 21055052 | OHSU KVCI Cardiology |  |  | 0 | 12 | 0 | 4217.29 | 4874.94 | 4 | 0 | 0% | 0% | 0%
Portland Operations | 21055043 | Microchip Thin Film Exp |  |  | 4500 | -308 | 0 | 156771.316 | 149426.7 | 962 | 805.96 | 100% | 0% | 0%
Portland Operations | 21055033 | Microchip Implant Annex |  |  | 9000 | 75631.13 | 7785 | 11852266.4 | 11637698.62 | 5300.2 | 4280.65 | 96.1% | 3.574% | 0.3271%
Portland Operations | 21055025 | Micro Systems Flagship Bld |  |  | 40000 | 19 | 0 | 34032.72 | 48473.15 | 0 | 0 | 0% | 0% | 0%
Portland Operations | 21055001 | BPA T01 TSB |  |  | 60000 | 294429.64 | 185616.5 | 59415006.7956 | 41333333.69 | 15998 | 10279.25 | 93.16% | 6.725% | 0.1167%
Portland Operations | 21055004 | BPA T02.1 VCC |  |  | 150000 | 294 | 0 | 71631164.89 | 11871938.13
Portland Operations | 21055008 | Nordstrom Dist Cntr |  |  | 200000 | 3 | 0 | 62939.36 | 62501.68 | 23 | 260.62 | 91.94% | 8.058% | 0%
Power Delivery Solutions Operations | 21146002 | Glass Sands Wind - Power |  |  | 0 | 242762.4 | 193052 | 12841360.04 | 13790645.27 | 8787.74 | 27933 | 77.59% | 22.41% | 0%
Power Delivery Solutions Operations | 21146003 | Orsted Series Cap |  |  | 0 | 47 | 0 | 17486.68 | 10597.34 | 76 | 40 | 100% | 0% | 0%
Power Delivery Solutions Operations | 21146004 | Kirchhoff Series Cap |  |  | 0 | 49 | 0 | 31739.97 | 18614.32 | 60 | 80 | 87.5% | 12.5% | 0%
Power Delivery Solutions Operations | 21146005 | 25 Mile Creek Wind - Power |  |  | 0 | 482351.1 | 281886.44 | 23654245.29 | 21379265.37 | 17920.03 | 23133 | 87.09% | 12.91% | 0%
Power Delivery Solutions Operations | 21146006 | Abilene Data Center |  |  | 0 | 133697.45 | 108517 | 14927046.77 | 12605004.16 | 5643.23 | 5465 | 86.94% | 12.99% | 0.07319%
Power Delivery Solutions Operations | 21146007 | Brass Fork Interconnect |  |  | 0 | 893 | 0 | 6812447.56 | 930490.27
Power Delivery Solutions Operations | 21146008 | Forest Grove Solar - Power |  |  | 0 | 0 | 0 | 213750 | 150387.26
Power Delivery Solutions Operations | 21146009 | Oak Hill Solar - Power |  |  | 0 | 0 | 0 | 180805 | 125327
Power Delivery Solutions Operations | 21146010 | AEP Rio Hondo |  |  | 0 | 0 | 0 | 148598.04 | 121435.63 | 48 | 374 | 95.59% | 4.412% | 0%
Power Delivery Solutions Operations | 21146011 | Greenfield Substation #498 |  |  | 0 | 148 | 0 | 12767998.57 | 8233352.24 | 0 | 308.5 | 90.76% | 9.238% | 0%
Power Delivery Solutions Operations | 21146012 | Hildreth Solar - Power |  |  | 0 | 69437.23 | 0 | 3678908.76 | 3513138.8 | 3192.24 | 4083.5 | 96.74% | 3.257% | 0%
Power Delivery Solutions Operations | 21146013 | Ft Stockton |  |  | 0 | 202521.91 | 180328 | 14998579.64 | 14083754.44 | 7774.76 | 6856.5 | 75.38% | 24.62% | 0%
Power Delivery Solutions Operations | 21146014 | Greenville |  |  | 0 | 0 | 0 | 113210 | 93432.78 | 0 | 16 | 100% | 0% | 0%
Power Delivery Solutions Operations | 21146015 | Northern Wind Repower-Power |  |  | 0 | 4986.46 | 0 | 3885513.93 | 3418734.82
Power Delivery Solutions Operations | 21146016 | Stampede Project |  |  | 0 | 439018.72 | 84100 | 16866588.6175 | 15497017.57 | 27379.76 | 36011 | 78.28% | 21.72% | 0%
Power Delivery Solutions Operations | 21146017 | Wolf Hollow Phase 0 |  |  | 0 | 55761.6 | 0 | 2475236.18 | 2559581.66 | 4022.08 | 7756.09 | 84.16% | 15.84% | 0%
Power Delivery Solutions Operations | 21146018 | Colorado Bend Phase 0 |  |  | 0 | 0 | 0 | 934804 | 847115.21
Power Delivery Solutions Operations | 21146019 | Wolf Hollow Phase 1 |  |  | 0 | 612933.38 | 174705 | 30232878.89 | 27469416.25 | 79722.12 | 81763.77 | 80.96% | 19.04% | 0%
Power Delivery Solutions Operations | 21146020 | Rob Park |  |  | 0 | 88164.03 | 0 | 14788148.34 | 627886.52 | 26106.48 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 21146021 | Chevelon Butte Wind - Power |  |  | 0 | 569177.61 | 538803 | 32565763.87 | 29748069.83 | 16642.09 | 25726.5 | 78.38% | 21.62% | 0%
Power Delivery Solutions Operations | 21146022 | Texas Solar Nova 1 - Power |  |  | 0 | 198064.17 | 97362 | 6666937.33 | 4602138.87 | 6187.92 | 3960 | 93.51% | 6.49% | 0%
Power Delivery Solutions Operations | 21146023 | Texas Solar Nova 2 - Power |  |  | 0 | 103429.26 | 41591 | 5135474.89 | 2050589.97 | 3916.33 | 1092 | 84.02% | 15.98% | 0%
Power Delivery Solutions Operations | 21146024 | King Mountain |  |  | 0 | 490358.86 | 4 | 26369996 | 23387280.97 | 78890.84 | 78380.8 | 75.68% | 24.32% | 0%
Power Delivery Solutions Operations | 21146025 | Angus Solar - Power |  |  | 0 | 0 | 0 | 180805 | 140432.86
Power Delivery Solutions Operations | 21146026 | Abilene - Phase 2 |  |  | 0 | 0 | 0 | 58995 | 46716.13
Salt Lake City Operations | 21060014 | 324 Office Bldg |  |  | 0 | 1 | 7 | 1676423.85 | 693573.01 | 230 | 295 | 81.36% | 18.64% | 0%
Salt Lake City Operations | 21060067 | SLC Industrial Inland Logisti |  |  | 0 | 480868 | 0 | 36502649.62 | 33221964.33 | 737 | 1508.25 | 93.49% | 6.514% | 0%
Seattle Operations | 21050001 | 2021 Virtual Insights |  |  | 0 | 0 | 0 | 0.06 | 16519.01
Seattle Operations | 21050002 | Arnold Water Intrusion - Swed |  |  | 0 | 0 | 1364 | 3190657.83 | 1592637.29 | 0 | 2744.29 | 96.45% | 2.988% | 0.5648%
Seattle Operations | 21050003 | CBRE - Arnold Water Intrusion |  |  | 0 | 0 | 208 | 440492.76 | 440441.59 | 0 | 397.89 | 83.16% | 14.07% | 2.765%
Seattle Operations | 21050004 | PRMCE Instr. Washer Replace |  |  | 0 | 469.9 | 221 | 439146.5675 | 426083.11 | 924.5 | 1102 | 96.82% | 2.813% | 0.363%
Seattle Operations | 21050005 | Cutline - Swedish |  |  | 0 | 4178.8 | 2994.5 | 10312545.27 | 9459826.88 | 4168.3 | 9278.77 | 95.87% | 3.411% | 0.7167%
Seattle Operations | 21050006 | American Air 3428B TI |  |  | 0 | 833 | 6737 | 188278.3 | 190011.81 | 400.83 | 487 | 98.87% | 1.129% | 0%
Seattle Operations | 21050007 | WWU EE/CSE Building |  |  | 0 | 973 | 44 | 5028016.49 | 1968980.16 | 2.1 | 51.5 | 82.52% | 16.5% | 0.9709%
Seattle Operations | 21050008 | PRMCE CM Services |  |  | 0 | 0 | 0 | 1352.12 | 1500.07
Seattle Operations | 21050009 | Delta A12A Boarding Bridge |  |  | 0 | 5326.3 | 0 | 5866842.84 | 2095822.1 | 299.9 | 185 | 97.3% | 2.703% | 0%
Seattle Operations | 21050010 | UW Basketball H2P Center |  |  | 0 | 0 | 0 | 2385533.32 | 2186010.89 | 40 | 40 | 100% | 0% | 0%
Seattle Operations | 21050011 | Swedish NT - Constr |  |  | 0 | 98 | 0 | 13964630.58 | 4698820.62
Seattle Operations | 21050012 | Four106 |  |  | 0 | 5428785.75 | 1578 | 211971447.01 | 16428527.12 | 132886.63 | 3283 | 95.51% | 3.914% | 0.5787%
Seattle Operations | 21050013 | Swedish Cancer Institute |  |  | 0 | 0 | 0 | 4378661.24 | 2615068.11
Seattle Operations | 21050050 | KP Everett IDIQ 2021 |  |  | 0 | 12.5 | 0 | 60220.15 | 70591.84 | 13 | 158 | 90.82% | 9.177% | 0%
Seattle Operations | 21050051 | KP Cap Hill IDIQ 2022 |  |  | 0 | 311 | 16 | 2626368.4917 | 1752850.14 | 341 | 400 | 89.88% | 10.12% | 0%
Solar and Emerging Renewables Operations | 21145003 | Monticello Solar - Vistra |  |  | 0 | 46 | 0 | 137694 | 137603.75 | 40 | 390 | 82.82% | 17.18% | 0%
Solar and Emerging Renewables Operations | 21145005 | Misae Solar 1 - Defective Mod |  |  | 0 | 5596 | 0 | 227722.5 | 235446.51 | 2632 | 3613 | 65.25% | 34.75% | 0%
Solar and Emerging Renewables Operations | 21145006 | TSN 1 - Clearway |  |  | 0 | 6545913.72 | 708656.5 | 160412656.74 | 104588729.51 | 436141.84 | 132974 | 90.02% | 9.976% | 0%
Solar and Emerging Renewables Operations | 21145007 | TSN 2 - Clearway |  |  | 0 | 8191324.11 | 0 | 123728184.94 | 15132961.65 | 368094.35 | 302.5 | 80.99% | 19.01% | 0%
Solar and Emerging Renewables Operations | 21145008 | Angus Solar - Vistra |  |  | 154 | 93 | 0 | 819067.02 | 825418.62 | 520 | 1327.5 | 70.85% | 29.15% | 0%
Solar and Emerging Renewables Operations | 21145001 | Forest Grove Solar - Vistra |  |  | 260 | 172 | 0 | 1551545 | 918416.34 | 500 | 836.5 | 82.68% | 17.32% | 0%
Solar and Emerging Renewables Operations | 21145002 | Oak Hill Solar - Vistra |  |  | 260 | 88 | 0 | 1464672 | 851672.85 | 500 | 937 | 87.08% | 12.92% | 0%
Solar and Emerging Renewables Operations | 21145004 | Hildreth Solar |  |  | 106606800 | 3178185.63 | 1960390 | 59979283.03 | 57272031.31 | 184310.59 | 137300.02 | 83.7% | 16.3% | 0.0007283%
Sports + Entertainment Group Operations | 21150001 | Pitt New Football Stadium |  |  | 0 | 0 | 0 | 15000 | 2001.47
Sports + Entertainment Group Operations | 21150002 | Hudson Valley Renegades |  |  | 0 | 0 | 0 | 9380.01 | 9166.72
Sports + Entertainment Group Operations | 21150004 | DAS MLS - St. Louis |  |  | 0 | 0 | 0 | 342145 | 311937.08
Sports + Entertainment Group Operations | 21150004-164 | MLS - St. Louis DAS |  |  | 0 | 0 | 0 | 803780 | 519825.2
Sports + Entertainment Group Operations | 21150006 | Gaylord Pacific Resort |  |  | 0 | 0 | 0 | 0.01 | 0
Sports + Entertainment Group Operations | 21150007 | MDI - Titan Industrial Storage |  |  | 0 | 0 | 0 | 52285134.53 | 30009661.28 | 0 | 607.5 | 65.84% | 34.16% | 0%
Sports + Entertainment Group Operations | 21150005 | DAS - ASU Multi Purpose Arena |  |  | 1000 | 0 | 0 | 1504402 | 1253909.74
Sports + Entertainment Group Operations | 21150003 | MLB - Tampa Bay Rays Precon |  |  | 690000 | 0 | 0 | 103378.54 | 66448.55
Wind Energy I Operations | 21141001 | Pocahontas Prairie Repower |  |  | 0 | 10438.02 | 745 | 16687154.83 | 15725114.6 | 51509 | 48709.5 | 72.97% | 26.21% | 0.8161%
Wind Energy I Operations | 21141002 | Golden Hills Wind |  |  | 0 | 7139.2 | 2518 | 94772963.3005 | 90024634.33 | 125801 | 98243.36 | 73.48% | 23.91% | 2.614%
Wind Energy I Operations | 21141003 | Shep Flats (NorH) Repower |  |  | 0 | 13177.59 | 1000 | 32408252.64 | 34044809.75 | 82767 | 135903.7 | 66.33% | 24.97% | 8.698%
Wind Energy I Operations | 21141004 | Sac County Wind |  |  | 0 | 9993.65 | 1247 | 27559923.623 | 27843531.39 | 37526 | 38317.4 | 66.52% | 30.99% | 2.494%
Wind Energy I Operations | 21141005 | Cedro Hill Repower |  |  | 0 | 0 | 0 | 110235.66 | 65378.78
Wind Energy I Operations | 21141006 | Midland Wind |  |  | 0 | 4551.82 | 2440 | 56511014.5996 | 55422028.51 | 75386 | 79370.72 | 67.32% | 31.59% | 1.09%
Wind Energy I Operations | 21141007 | Shep Flats (SouH) Repower |  |  | 0 | 1906 | 1124 | 30554240.8314 | 31855389.71 | 76459 | 129251.65 | 64.43% | 29.69% | 5.872%
Wind Energy I Operations | 21141008 | Shep Flats (HorB) Repower |  |  | 0 | 1455 | 1129 | 29310464.8895 | 30212099.21 | 79185 | 124274 | 67.12% | 30.29% | 2.588%
Wind Energy I Operations | 21141009 | Mountain View I & II Full RP |  |  | 0 | 4373.73 | 1460 | 39950179.91 | 35314338.69 | 46555 | 39241.6 | 77.98% | 20.4% | 1.618%
Wind Energy I Operations | 21141010 | 25 Mile Creek Wind |  |  | 0 | 21153.09 | 5178 | 89634628.31 | 80195025.73 | 119062 | 113317.5 | 82.74% | 17.26% | 0%
Wind Energy I Operations | 21141011 | Nobles Repower |  |  | 0 | 17528.86 | 923 | 41101725.5214 | 31882276.57 | 88655.5 | 75951.5 | 76.35% | 23.65% | 0%
Wind Energy I Operations | 21141012 | Northern Full Repower |  |  | 0 | 3583.4 | 2538 | 53152898.06 | 47808476.96 | 56703 | 49428.5 | 73.8% | 26.11% | 0.09711%
Wind Energy I Operations | 21141013 | Steelhead - 25 Mile Creek Wind |  |  | 0 | 0 | 0 | 659490 | 529372.09
Wind Energy I Operations | 21141014 | Chevelon Butte Wind |  |  | 0 | 18550.9 | 2420.5 | 99886068.5624 | 87379423.33 | 138084 | 74026.25 | 88.94% | 11.06% | 0%
Wind Energy I Operations | 21141015 | Laurel Mtn AES Repower |  |  | 0 | 0 | 0 | 5242221 | 4379108.27
Wind Energy I Operations | 21141016 | Laurel Mtn GE Repower |  |  | 0 | 2628.32 | 1318 | 28468629 | 18600726.48 | 63006 | 115200.34 | 82.72% | 13.75% | 3.526%
Wind Energy I Operations | 21141017 | Appaloosa Run Wind |  |  | 0 | 18317.15 | 3210 | 41512364.25 | 40574956.18 | 68272 | 62092.92 | 75.06% | 24.93% | 0.003221%
Wind Energy I Operations | 21141018 | Inertia Wind |  |  | 0 | 22460.1 | 4927.5 | 76615614.294 | 75483978.23 | 115720 | 110115.93 | 75.34% | 24.66% | 0%
Wind Energy I Operations | 21141019 | Eclipse/Morning Light Repower |  |  | 0 | 4805.73 | 1790 | 43128440.08 | 40660102.37 | 109745 | 139882.8 | 63.13% | 31.97% | 4.892%
Wind Energy I Operations | 21141020 | Cimarron Grout Install Wind |  |  | 0 | 4 | 4 | 42490.68 | 22706.32 | 152 | 168 | 61.9% | 38.1% | 0%
Wind Energy I Operations | 21141021 | White Rock Wind |  |  | 0 | 4001.21 | 0 | 114748898.68 | 20810726.9 | 171070 | 2715.5 | 86.3% | 13.7% | 0%
Wind Energy I Operations | 21141022 | Marshal Yd - Laurel Mt GE RP |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -65565.84 | 92.86% | 5.277% | 1.862%
Total | [5 empty] | 10147859439.68 | 30004918.52 | 5789409738.4756 | 3459987539.62 | 4582627.2 | 4090963.47 | 82.81% | 16.07% | 1.117%

## 2020
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Chicago Operations | 20090005 | QTS - Misc Projects |  |  | 0 | 48 | 146.5 | 2763551 | 2578027.49 | 329.5 | 602.5 | 89.29% | 10.71% | 0%
Chicago Operations | 20090009 | QTS - DH3 E1 E2 |  |  | 0 | 3028 | 156 | 22769795.33 | 22485966.48 | 1384.1 | 4360.5 | 94.61% | 5.263% | 0.1261%
Chicago Operations | 20090991 | Chicago 2020 Prefab Shop |  |  | 0 | 121 | 52 | 0 | 129499.29 | 212 | 1421.86 | 99.33% | 0.3517% | 0.3165%
Chicago Operations | 20090992 | Chicago Laser Scanning 2020 |  |  | 0 | 0 | 0 | 0 | 68859.64 | 0 | 237 | 86.08% | 13.92% | 0%
Chicago Operations | 20090006 | Northwestern-Welsh Ryan Floor |  |  | 20000 | 479.5 | 0 | 421068.05 | 422158.47 | 294 | 167 | 91.02% | 5.389% | 3.593%
Chicago Operations | 20090004 | QTS - DH2W 3MW D1 D2 |  |  | 39899 | 5682.8 | 209 | 17247458.93 | 17081202.25 | 4224 | 4615.5 | 83.3% | 14.64% | 2.069%
Chicago Operations | 20090008 | UIC - CDRLC Construction |  |  | 65000 | 570.5 | 0 | 7307028 | 2240576.06 | 10460 | 3 | 100% | 0% | 0%
Chicago Operations | 20090003 | Wheaton - Traber Hall Reno |  |  | 70000 | 155637.57 | 8.5 | 9050509.75 | 8907815.57 | 2767.8 | 3289 | 82.53% | 15.37% | 2.098%
Chicago Operations | 20090007 | FDB&R - Chicago Office |  |  | 105000 | 16670 | 209 | 17787126.07 | 16246289.59 | 8204 | 7058 | 80.88% | 11.63% | 7.495%
Chicago Operations | 20090002 | UIC - CDRLC Precon |  |  | 160000 | 304 | 0 | 201236 | 204431.18 | 0 | 20 | 100% | 0% | 0%
Chicago Operations | 20090001 | DeKalb Data Center |  |  | 980000 | 0 | 20 | 0 | 55.49 | 0 | 0 | 0% | 0% | 0%
Civil Group Operations | 20148001 | TG East Civil (Wind) |  |  | 0 | 14396148 | 840261 | 18289500 | 14749088.15 | 54323.17 | 54183.7 | 81.06% | 18.94% | 0%
Civil Group Operations | 20148002 | Snipesville Civil (Solar) |  |  | 0 | 2820797.62 | 168415 | 2714599.4 | 2545533.42 | 5346.24 | 3740 | 82.13% | 17.87% | 0%
Civil Group Operations | 20148003 | Chokecherry Sierra Madre 2020 |  |  | 0 | 20407680.84 | 820131 | 17455480.41 | 15635223.41 | 62797.97 | 61934 | 82.13% | 17.51% | 0.3593%
Civil Group Operations | 20148004 | Smoky Hills 2 Civil (Wind) |  |  | 0 | 3218196.04 | 110 | 3626246.63 | 2859388.13 | 10617.97 | 4493 | 78.51% | 21.49% | 0%
Civil Group Operations | 20148005 | Hawkeye Civil (Wind) |  |  | 0 | 2214265.72 | 82461 | 3418141.2902 | 2718910.17 | 11379.82 | 8766.5 | 84.45% | 15.07% | 0.4848%
Civil Group Operations | 20148006 | Santa Fe Civil (Solar) |  |  | 0 | 3722575.02 | 160667 | 2865587.3232 | 2145765.53 | 11509.26 | 6288.42 | 79.84% | 20.16% | 0%
Civil Group Operations | 20148007 | Phoenix Civil (Solar) |  |  | 0 | 4011675.47 | 229034 | 3974819.45 | 3995743.12 | 13149.09 | 18469.5 | 85.45% | 14.55% | 0%
Civil Group Operations | 20148008 | Langford Civil (Wind) |  |  | 0 | 3160519.77 | 55484 | 3733933.2905 | 2443741.13 | 16314.26 | 10327 | 79.59% | 20.41% | 0%
Civil Group Operations | 20148009 | Maiden Creek Civil (Solar) |  |  | 0 | 2019442 | 59765 | 1755947.71 | 1816313 | 5516.92 | 6171 | 86.7% | 13.3% | 0%
Civil Group Operations | 20148010 | Trent Mesa Civil (Wind) |  |  | 0 | 0 | 0 | 510659.81 | 308318.12 | 0 | 1442.5 | 80.1% | 19.9% | 0%
Civil Group Operations | 20148011 | Fighting Jays Civil (Solar) |  |  | 0 | 12169845.69 | 285334 | 10141490.15 | 9559503.62 | 19988.65 | 21607 | 85.22% | 14.78% | 0%
Civil Group Operations | 20148012 | Desert Sky Civil (Wind) |  |  | 0 | 2 | 0 | 416689.61 | 334037.05 | 0 | 891 | 86.53% | 13.47% | 0%
Civil Group Operations | 20148013 | Blue Canyon II RePower Civil |  |  | 0 | 2725795.59 | 140509 | 4449524.56 | 3018492.52 | 17135.17 | 12312.27 | 80.01% | 19.99% | 0%
Civil Group Operations | 20148014 | Rockhaven Civil (Wind) |  |  | 0 | 740130.62 | 437134 | 16252070.38 | 15037743.2 | 46829.15 | 49803.75 | 77.11% | 22.89% | 0%
Data Center Operations | 20120001 | Facebook-Program Services 2020 |  |  | 0 | 11 | 0 | 1351814 | 1349206.05
Data Center Operations | 20120002 | Google - Mesa Data Center-MP |  |  | 0 | 1122 | 0 | 267542 | 198978.45
Data Center Operations | 20120003 | Lego - Facebook Data Centers |  |  | 0 | 0 | 0 | 421834 | 315955.88
Data Center Operations | 20126002 | Facebook - EAG 5/6 |  |  | 0 | 3002553.2 | 458745.62 | 642714803.6686 | 555767799.29 | 253676.23 | 261130.37 | 82.34% | 17.66% | 0%
Data Center Operations | 20126001 | EAG IBOS Building |  |  | 30000 | 557 | 160 | 9902581.82 | 10070523.77 | 144 | 1320.5 | 84.85% | 15.15% | 0%
Data Center Operations | 20030079 | Google - SLN4A Data Center |  |  | 350000 | 0 | 0 | 545094 | 582649.18
Data Center Operations | 20126004 | Facebook - DKL 1/2 |  |  | 998280 | 1192210.03 | 827920 | 722631143.1765 | 705265919.49 | 216228 | 212599.05 | 83.12% | 12.41% | 4.465%
Data Center Operations | 20060035 | Facebook EAG 5/6 |  |  | 1000000 | 0 | 0 | 0.01 | 0
Denver Operations | 20060008 | Northridge Behavioral Health |  |  | 0 | 0 | 0 | 0.01 | 1106.51
Denver Operations | 20060017 | SCL Lutheran COVID 19 |  |  | 0 | 797 | 0 | 65187.397 | 59164.4 | 6 | 0 | 0% | 0% | 0%
Denver Operations | 20060018 | SCL SJH COVID |  |  | 0 | 0 | 0 | 124525.68 | 125892.03
Denver Operations | 20060019 | SCL Lutheran West Hospice |  |  | 0 | 12 | 90 | 183753.99 | 187170.9 | 258 | 106 | 100% | 0% | 0%
Denver Operations | 20060020 | St Anthony North Rehab |  |  | 0 | 14496.5 | 61 | 1656074.13 | 1674504.87 | 2462.7 | 710.5 | 90.15% | 9.852% | 0%
Denver Operations | 20060022 | Highpoint Logistics Park |  |  | 0 | 937373.48 | 733186.35 | 39356686.5865 | 38749934.57 | 59365.6 | 31197.25 | 83.75% | 16.25% | 0%
Denver Operations | 20060023 | Molson Coors G150 |  |  | 0 | 3 | 0 | 228785.56 | 299510.95
Denver Operations | 20060027 | MC-Golden Valley |  |  | 0 | 5811.02 | 3492 | 1132548.45 | 1047772.14 | 3095.85 | 2414.25 | 80.94% | 19.06% | 0%
Denver Operations | 20060031 | FRA-FIC3 UCH Parking Lot |  |  | 0 | 0 | 0 | 39361.2 | 39404.47
Denver Operations | 20060033 | MC Bridge Demo |  |  | 0 | 1298.7 | 858 | 543962.72 | 557841.04 | 790.6 | 901 | 91.68% | 8.324% | 0%
Denver Operations | 20060034 | FRA Infrastructure-23rd Ave |  |  | 0 | 0 | 0 | 34000 | 38384.72
Denver Operations | 20060037 | NJH-UPS800 PHarmacy Remodel |  |  | 0 | 3291.56 | 365 | 187035.04 | 193610.83 | 348.96 | 745 | 95.57% | 4.43% | 0%
Denver Operations | 20060038 | MC Capital Improve |  |  | 0 | 695.64 | 351 | 366372.1675 | 448937.93 | 589.2 | 512 | 84.67% | 15.33% | 0%
Denver Operations | 20060048 | SCL-LMC COVID19 Exhaust Fans |  |  | 0 | 126 | 30 | 234913.87 | 231947.8 | 120 | 30 | 100% | 0% | 0%
Denver Operations | 20060049 | MC-Kennys Run Enab |  |  | 0 | 61477.23 | 36693 | 1883646.87 | 1868713.81 | 7641.4 | 7655 | 87.16% | 12.84% | 0%
Denver Operations | 20060003 | SCL SJD Cancer Cntr |  |  | 1 | 6 | 44 | 6443.27 | 6930.43 | 0 | 38 | 55.26% | 44.74% | 0%
Denver Operations | 20060005 | SCL SJD CCC Roof Replacement |  |  | 1 | 35984.5 | 1457 | 1035284.1 | 1077176.39 | 1145 | 1635.5 | 91.56% | 8.438% | 0%
Denver Operations | 20060026 | SCL - Lutheran CT (8) Machine |  |  | 1 | 3179.23 | 455 | 141118.24 | 143739.89 | 294.7 | 472 | 94.92% | 5.085% | 0%
Denver Operations | 20060030 | DHHA - CT Replacement |  |  | 1 | 5752.96 | 1604 | 396591.0268 | 352310.65 | 1498.28 | 703.5 | 87.21% | 12.79% | 0%
Denver Operations | 20060045 | SCL-LMC 2020 Sewer Line |  |  | 1 | 28 | 28.01 | 75396.14 | 56415.35 | 42 | 168 | 82.14% | 17.86% | 0%
Denver Operations | 20060046 | SCL-LMC West Pines Exhaust Fan |  |  | 1 | 56 | 74 | 221970.04 | 220389.62 | 200 | 66 | 100% | 0% | 0%
Denver Operations | 20060053 | CHCO Dental Clinic Remodel |  |  | 1 | 1190.25 | 515 | 156261.79 | 208528.47 | 612.9 | 627.5 | 82.39% | 17.61% | 0%
Denver Operations | 20060054 | SCL-SJH SPD Medivator |  |  | 1 | 128.75 | 62 | 161713.74 | 160959.05 | 108 | 108 | 100% | 0% | 0%
Denver Operations | 20060055 | SCL-West Campus Signage |  |  | 1 | 58 | 0 | 17683.52 | 10528.01 | 0 | 27 | 100% | 0% | 0%
Denver Operations | 20060057 | NJH Test Pod |  |  | 300 | 305 | 0 | 175506 | 190472.01 | 305 | 1236 | 92.44% | 7.565% | 0%
Denver Operations | 20060043 | NJH - Radiology Remodels |  |  | 400 | 317 | 0 | 36453.83 | 48042.7 | 308 | 356.5 | 89.06% | 10.94% | 0%
Denver Operations | 20060047 | SCL-LMC Front Range Command |  |  | 400 | 108 | 26 | 73088.29 | 72567.8 | 88 | 26 | 96.15% | 3.846% | 0%
Denver Operations | 20060001 | SCL - SJH SPD Medivator |  |  | 500 | 82 | 26 | 13344.54 | 14634.47 | 153.4 | 259.5 | 87.09% | 12.91% | 0%
Denver Operations | 20060040 | SCL-SJB Mezzaine Repairs |  |  | 1000 | 975.17 | 0 | 127680.9 | 151744.86 | 90 | 0 | 0% | 0% | 0%
Denver Operations | 20060041 | SCL-SJB Oncology AHU |  |  | 1000 | 33 | 0 | 117358.42 | 123176.3
Denver Operations | 20060059 | CoorsTek Small Projects |  |  | 1000 | 133 | 8 | 384617.665 | 403442.42 | 2247.1 | 2497 | 97.32% | 2.683% | 0%
Denver Operations | 20060010 | Stoltz Cable Building |  |  | 2000 | 13438.7 | 4502 | 1051254.87 | 376922.45 | 1221.77 | 1274 | 92.27% | 7.732% | 0%
Denver Operations | 20060024 | Stadium Mgmt Broncos 2020 |  |  | 2000 | 14 | 116 | 291357.59 | 277406.44 | 1286 | 596 | 90.02% | 9.983% | 0%
Denver Operations | 20060060 | SCL-SJB MRI Corridor |  |  | 2000 | 16 | 0 | 70935.2 | 78106.29
Denver Operations | 20060036 | DHHA-Pav K (Office Reno) |  |  | 2212 | 849.5 | 0 | 99491.51 | 106414.22 | 217.8 | 136 | 82.72% | 17.28% | 0%
Denver Operations | 20060025 | Tiny Homes Project |  |  | 5000 | 378 | 164 | 641149 | -1.6303e-10 | 1584 | 4416 | 98.4% | 1.596% | 0%
Denver Operations | 20060050 | CO Rockies-Coors Field Gate E |  |  | 5000 | 60074.89 | 19237 | 593609.743 | 628873.04 | 1931.39 | 2660.5 | 86.26% | 13.74% | 0%
Denver Operations | 20060056 | SCL St James Foundation Roof |  |  | 5000 | 11 | 0 | 43344.07 | 45954.47 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 20060062 | DHHA 4C |  |  | 6000 | 15 | 397 | 151032.43 | 158010.17 | 602 | 495 | 95.15% | 4.848% | 0%
Denver Operations | 20060014 | Stoltz Wazee Exchange |  |  | 7000 | 65346.95 | 28642 | 1883033.06 | 1894931.08 | 2128.43 | 4602.5 | 95.61% | 4.389% | 0%
Denver Operations | 20060012 | Aramark Concessions 2020 |  |  | 8500 | 0 | 0 | 0.01 | 41919.44
Denver Operations | 20060004 | Stadium Mgmt - Bronco 2020 |  |  | 8520 | 1454.5 | 556 | 2026435.57 | 2015753.86 | 2821.7 | 2449 | 99.04% | 0.9596% | 0%
Denver Operations | 20060058 | SCL Candelas Primary Care |  |  | 9000 | 274 | 38 | 2010240.76 | 2011888.29 | 272 | 396.5 | 96.47% | 3.531% | 0%
Denver Operations | 20060007 | RMPM - 3rd Floor TI |  |  | 10000 | 12954 | 23 | 900219.3865 | 917619.23 | 261.3 | 369.5 | 99.59% | 0.406% | 0%
Denver Operations | 20060013 | Stoltz - Blake Street |  |  | 11500 | 109413.85 | 56191 | 3398990.4079 | 3320578.47 | 6790 | 7279.5 | 96.75% | 3.249% | 0%
Denver Operations | 20060044 | NJH-Bridge |  |  | 15000 | 12898 | 1516 | 5941440.484 | 6043227.45 | 2969.7 | 6336.5 | 80.53% | 19.47% | 0%
Denver Operations | 20060006 | MIC-Buckley SBIRS Operations |  |  | 20000 | 0 | 23414 | 0 | -1296 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 20060028 | MIC-Buckley SBIRS Operation |  |  | 20000 | 153331.11 | 203565 | 1290035.7904 | 1561183.12 | 13670.9 | 15082 | 93.16% | 6.843% | 0%
Denver Operations | 20060052 | Woodward-Windsor Campus |  |  | 20000 | 68131 | 49175.5 | 22826206.6724 | 20110024.21 | 5620 | 17395.04 | 89.73% | 10.27% | 0%
Denver Operations | 20060029 | UofU-Public Safety Building |  |  | 26000 | 0 | 0 | 32153 | 31102.51
Denver Operations | 20060011 | Facebook-EAG IBOS Building |  |  | 30000 | 0 | 0 | 0.01 | 0
Denver Operations | 20060016 | FRA Bioscience 3 Bldg Mgt |  |  | 50000 | 600 | 2113 | 91600 | 98795.53 | 600 | 1301 | 93.31% | 6.687% | 0%
Denver Operations | 20060042 | SCL Candelas 12" Water Line |  |  | 50000 | 1029 | 965 | 125179.12 | 137165.24 | 616 | 632.5 | 91.46% | 8.538% | 0%
Denver Operations | 20060021 | St Mary-Corwin Med Cntr Rehab |  |  | 80000 | 91319.71 | 0 | 6652916.18 | 6720007.99 | 3850.6 | 1444 | 76.7% | 23.3% | 0%
Denver Operations | 20060015 | FRA Bioscience 5 |  |  | 98000 | 0 | 0 | 227128 | 223011.59
Denver Operations | 20060002 | 2424 Larimer |  |  | 98254 | 15 | 0 | 45768 | 45333.83
Denver Operations | 20060039 | Stoltz-Checkr Atrium Reno |  |  | 180000 | 111010.4 | 21 | 3825876.99 | 3786891.65 | 3376.5 | 4658.5 | 91.95% | 8.05% | 0%
Denver Operations | 20060061 | MDI-2506 W Colfax Multifamily |  |  | 234156 | 0 | 16 | 60419545 | 2389825.52 | 0 | 24 | 100% | 0% | 0%
Denver Operations | 20060009 | Township Resident Apartment |  |  | 400000 | 4 | 0 | 599664.84 | 575833.5 | 3 | 165.5 | 89.12% | 10.88% | 0%
Denver Operations | 20060032 | 76 Comm Bldg 1 |  |  | 546000 | 1703956.79 | 834323.62 | 38239452.15 | 36528971.87 | 28691.97 | 32855.78 | 82.69% | 17.31% | 0%
Energy Storage & Solutions Operations | 20149001 | Upton 1 BESS |  |  | 0 | 242 | 0 | 228183 | 166861.37
Energy Storage & Solutions Operations | 20149004 | Valley Center Energy Storage |  |  | 0 | 235542 | 260391 | 54914777.3554 | 63745201.61 | 31673.31 | 103437.71 | 71.05% | 19.52% | 9.429%
Energy Storage & Solutions Operations | 20149005 | Crossett Battery Storage |  |  | 0 | 399427.17 | 301645 | 15365690.86 | 15664912.05 | 33992.56 | 43381.5 | 78.42% | 21.58% | 0%
Energy Storage & Solutions Operations | 20149006 | Decordova Battery Storage |  |  | 0 | 622662.68 | 354518 | 27398591.31 | 26371911.31 | 46380.14 | 43824.25 | 86% | 14% | 0%
Energy Storage & Solutions Operations | 20149007 | Brookville Bus Depot MicroGrid |  |  | 0 | 182272.28 | 25449 | 10778930.9568 | 10230105 | 14131.96 | 24237 | 76.08% | 23.92% | 0%
FCG Operations | 20110001 | Site R ITIU |  |  | 0 | 3925 | 0 | 6985160.368 | 6985490.17
FCG Operations | 20110002 | ECB-MC Elevators JV-Internal |  |  | 0 | 0 | 0 | 82102 | 131721.01 | 0 | 362 | 99.45% | 0.5525% | 0%
FCG Operations | 20110002-151 | ECB-MC Elevators |  |  | 0 | 0 | 0 | 181720.65 | 199597
FCG Operations | 20110004-144 | Kings Bay Dry Dock |  |  | 0 | 0 | 0 | 536777413 | 0
FCG Operations | 20110012 | Storm Window Prototypes |  |  | 0 | 12 | 0 | 1887827.9999 | 687052.62
FCG Operations | 20110014 | Aberdeen Proving Ground |  |  | 500 | 579 | 0 | 544692.29 | 471401.53
FCG Operations | 20110003 | Tech Library 3B34 Renovation |  |  | 1000 | 502 | 0 | 290930.02 | 225394.45
FCG Operations | 20110013 | General Briefing Room |  |  | 1000 | 2069 | 0 | 788425.82 | 775770.82 | 0 | 525 | 99.05% | 0.9524% | 0%
FCG Operations | 20110005 | UDC Gremlin Prank |  |  | 2000 | 0 | 0 | 35706 | 30670.13
FCG Operations | 20110011 | 9800 Toilet Room Reno |  |  | 15413 | 37 | 0 | 18650974.58 | 12624874.14 | 0 | 3380.89 | 96.07% | 3.934% | 0%
FCG Operations | 20110009 | Building 9838 Renovation |  |  | 16611 | 17130 | 0 | 15423545.3758 | 14474864.82 | 0 | 36 | 100% | 0% | 0%
FCG Operations | 20110004 | A-M JV Kings Bay Dry Dock Int |  |  | 21373 | 0 | 8 | 27612978.77 | 25992933.45 | 0 | 23839.88 | 75.75% | 23.17% | 1.078%
FCG Operations | 20110015 | Fort McNair Building 60 |  |  | 22657 | 129 | 0 | 16338382.18 | 16054421 | 0 | 1050 | 98.29% | 1.714% | 0%
FCG Operations | 20110010 | Bldg 9840 AHU Replacement |  |  | 34306 | 46283 | 0 | 13363460.5 | 11974851.54 | 0 | 16.7 | 100% | 0% | 0%
FCG Operations | 20110007 | 9800 Core Renovation |  |  | 65000 | 8182 | 0 | 26910039.738 | 26680736.07 | 63 | 7924.05 | 87.11% | 12.89% | 0%
FCG Operations | 20110016 | BAO North Parking Lot |  |  | 97621 | 88 | 0 | 3410441.56 | 3409448.5
FCG Operations | 20110006 | USDA - ARTC |  |  | 108000 | 154501 | 0 | 88530366.35 | 70690450.76 | 12040 | 4854 | 100% | 0% | 0%
FCG Operations | 20110008 | Big 4 Fence Removal |  |  | 2100000 | 263 | 0 | 25654008.45 | 13784139.99 | 0 | 62 | 64.52% | 35.48% | 0%
Milwaukee Operations | 20080001 | Froedtert - Park Temp Lighting |  |  | 0 | 13827.06 | 5039 | 895972.5 | 993356.8 | 2742 | 3154.5 | 80.38% | 9.574% | 10.05%
Milwaukee Operations | 20080009 | AMC Sheboygan Union Ave |  |  | 0 | 229.5 | 0 | 4695286.03 | 4563492.43 | 277.5 | 32.5 | 92.31% | 7.692% | 0%
Milwaukee Operations | 20080011 | Foxconn - Utility Upgrades |  |  | 0 | 3 | 0 | 126272 | 115778.05
Milwaukee Operations | 20080014 | RockGen Concrete Repairs |  |  | 0 | 456.27 | 0 | 12176.28 | 11933.89 | 63.6 | 120 | 96.25% | 3.75% | 0%
Milwaukee Operations | 20080010 | Harley Davidson Kitch Remodel |  |  | 100 | 65 | 0 | 19993.3 | 23284.9 | 40 | 89 | 93.26% | 6.742% | 0%
Milwaukee Operations | 20080004 | MRMC E. Tunnel N. Junc |  |  | 500 | 8686.83 | 93 | 699634.4 | 687176.23 | 1538.1 | 1516.08 | 94.46% | 5.508% | 0.03298%
Milwaukee Operations | 20080007 | Delta DNC Refresh |  |  | 500 | 0 | 0 | 3396 | 3416.48
Milwaukee Operations | 20080006 | AHC - At Home Pharm Remodel |  |  | 944 | 13343.32 | 7373 | 1673054.53 | 1729626.43 | 1722.1 | 3445.2 | 93.83% | 5.852% | 0.3193%
Milwaukee Operations | 20080013 | DRS - CT Equip Demo |  |  | 2000 | 3 | 0 | 11145.44 | 10372.76
Milwaukee Operations | 20080003 | Froedtert IPP 9,8,1 Equip Swap |  |  | 2381 | 25313 | 1464 | 1077024.43 | 1113684.42 | 2437.9 | 4104 | 91.35% | 5.592% | 3.058%
Milwaukee Operations | 20080008 | Leonardo DRS Cafe Reno |  |  | 3550 | 5990.33 | 2539 | 217201.64 | 187145.08 | 304.6 | 374 | 99.6% | 0.4011% | 0%
Milwaukee Operations | 20080012 | Lodge Kohler Spa Exp |  |  | 14000 | 204 | 0 | 601873.26 | 633288.16 | 0 | 30.67 | 100% | 0% | 0%
Milwaukee Operations | 20080002 | Froedtert - North Tower Elev |  |  | 27380 | 201823.76 | 5355 | 16762355.23 | 697993.08 | 15596.61 | 863 | 99.77% | 0.2317% | 0%
Milwaukee Operations | 20080005 | Fii 5052020 |  |  | 98000 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 20030001 | Fairview Facility Annual 2020 |  |  | 0 | 0 | 0 | 1826490.57 | 1945158.19 | 0 | 5453 | 95.19% | 4.814% | 0%
Minneapolis Operations | 20030002 | Allina Annual Contract 2020 |  |  | 0 | 141355 | 2 | 3648025.8434 | 3964892.18 | 24581.2 | 23682.71 | 91.11% | 8.694% | 0.1942%
Minneapolis Operations | 20030004 | Marvin Master Agreement |  |  | 0 | 139.03 | 0 | 807288.62 | 726746.28 | 1570 | 1362 | 79% | 21% | 0%
Minneapolis Operations | 20030005 | Fairview - Unit J CW Infra |  |  | 0 | 0 | 0 | 433434.2 | 431469.26
Minneapolis Operations | 20030010 | Fairview -Northland Nurse Call |  |  | 0 | 0 | 0 | 45502.07 | 41310.98 | 1595 | 75 | 85.33% | 14.67% | 0%
Minneapolis Operations | 20030013 | MSFA - USB Exterior Envelope |  |  | 0 | 120 | 1000 | 21716975.89 | 19662555.26 | 7497 | 8304.5 | 98.59% | 1.319% | 0.09633%
Minneapolis Operations | 20030015 | Allianz Field 2020 Sponsor Act |  |  | 0 | 0 | 0 | 212675.58 | 206956.79 | 48 | 40 | 100% | 0% | 0%
Minneapolis Operations | 20030017 | Sunny Hollow Life Safety |  |  | 0 | 0 | 0 | 157037 | 157768.71 | 280 | 352 | 100% | 0% | 0%
Minneapolis Operations | 20030025 | Lansing Tenant Improvements |  |  | 0 | 0 | 0 | 1622923 | 1559331.07 | 2002 | 1594 | 99.44% | 0.5646% | 0%
Minneapolis Operations | 20030028 | City of Mpls - NPSB Site Imprv |  |  | 0 | 40822.18 | 8557 | 766945.8 | 638451.21 | 2935.5 | 1440 | 96.77% | 3.229% | 0%
Minneapolis Operations | 20030030 | Fairview - Princeton ED Rm #2 |  |  | 0 | 0 | 0 | 23229 | 23411.03 | 45 | 77 | 89.61% | 10.39% | 0%
Minneapolis Operations | 20030031 | Fairview FRH ED BH Ligature |  |  | 0 | 0 | 0 | 97965 | 96248.14 | 146 | 146.5 | 98.63% | 1.365% | 0%
Minneapolis Operations | 20030039 | Fairview - Unit J Cath Lab #5 |  |  | 0 | 70 | 0 | 561948.36 | 564418.8 | 1142.5 | 1048.5 | 87.17% | 12.83% | 0%
Minneapolis Operations | 20030040 | Twin Cities Community Re-Build |  |  | 0 | 0 | 0 | 0.01 | 149442.63 | 0 | 3338.48 | 96.54% | 3.34% | 0.1198%
Minneapolis Operations | 20030041 | JR Ferche - Miss Heights |  |  | 0 | 1424 | 17259 | 96586 | 121694.26 | 538 | 834 | 91.07% | 8.933% | 0%
Minneapolis Operations | 20030043 | MAM Mortenson-M |  |  | 0 | 0 | 0 | 0.01 | 65814.78 | 0 | 502.5 | 99.5% | 0.4975% | 0%
Minneapolis Operations | 20030046 | UMN PAN Water Infiltration |  |  | 0 | 40 | 0 | 153226.57 | 153431.95 | 68 | 31 | 100% | 0% | 0%
Minneapolis Operations | 20030047 | Fairview UMMC EB CSSD Washers |  |  | 0 | 119 | 0 | 1041931.105 | 1010097.89 | 2878 | 2310.5 | 95.78% | 0.6276% | 3.592%
Minneapolis Operations | 20030048 | EGE Oberlin Sustainable Infra |  |  | 0 | 0 | 0 | 374425 | 555783.74 | 0 | 90 | 100% | 0% | 0%
Minneapolis Operations | 20030051 | Fairview MH Unit J Chiller Rep |  |  | 0 | 0 | 0 | 756265.5 | 752484.25 | 62 | 59.5 | 100% | 0% | 0%
Minneapolis Operations | 20030063 | Baker - Vermeer Sewer Main |  |  | 0 | 0 | 0 | 154030.25 | 131247.18 | 754 | 907 | 81.15% | 18.41% | 0.441%
Minneapolis Operations | 20030067 | Tri-County - Front Entry Mod |  |  | 0 | 64 | 0 | 120381.76 | 125027.63 | 248 | 357 | 100% | 0% | 0%
Minneapolis Operations | 20030068 | Fairview UMMC WB PCW Upgrade |  |  | 0 | 2 | 0 | 602866.82 | 613399.02 | 532 | 442.5 | 99.77% | 0.226% | 0%
Minneapolis Operations | 20030069 | Harris - River Towers HVAC |  |  | 0 | 20 | 0 | 347181.79 | 296501.96 | 2675 | 2212.5 | 99.73% | 0.2712% | 0%
Minneapolis Operations | 20030071 | FRB MN Security Enhancements |  |  | 0 | 91842.29 | 48760 | 4462359.87 | 4617320.64 | 10877.3 | 10906.5 | 87.78% | 11.85% | 0.3668%
Minneapolis Operations | 20030076 | Faegre - Capital Improv WO#1 |  |  | 0 | 0 | 0 | 15419.26 | 15216.46 | 72 | 62.5 | 100% | 0% | 0%
Minneapolis Operations | 20030077 | Innovation Assoc Program Mgmt |  |  | 0 | 3 | 0 | 471943.34 | 376904.37
Minneapolis Operations | 20030009 | Welltower - Roseville Canopy |  |  | 50 | 0 | 0 | 12193.02 | 12910.59 | 52 | 52 | 100% | 0% | 0%
Minneapolis Operations | 20030033 | State of Minnesota - ACF |  |  | 50 | 0 | 0 | 185156.77 | 189415.8 | 0 | 80 | 100% | 0% | 0%
Minneapolis Operations | 20030019 | Cuningham Office Elevator Rpl |  |  | 500 | 0 | 0 | 317514.49 | 323136.58 | 263 | 516 | 99.42% | 0.5814% | 0%
Minneapolis Operations | 20030022 | BluVera Plant TI |  |  | 500 | 3377 | 0 | 265096.32 | 273630.28 | 792 | 987.5 | 99.49% | 0.5063% | 0%
Minneapolis Operations | 20030053 | Allina Buffalo Hospital PT/OT |  |  | 700 | 691 | 10 | 243823.29 | 242010.15 | 1229 | 1548 | 99.35% | 0.646% | 0%
Minneapolis Operations | 20030024 | FV - UMMC EB Rplc TomoTherapy |  |  | 800 | 4 | 0 | 376475.87 | 374402.38 | 460 | 449.5 | 84.87% | 13.79% | 1.335%
Minneapolis Operations | 20030044 | Blake Northrop Campus 2020 |  |  | 1000 | 12395.07 | 0 | 513192.7612 | 509512.5 | 681.93 | 872.04 | 98.62% | 1.376% | 0%
Minneapolis Operations | 20030055 | Basilica 2020 Masonry Restore |  |  | 1000 | 4 | 0 | 93557.46 | 75714.06 | 1527 | 563.67 | 85.63% | 14.37% | 0%
Minneapolis Operations | 20030054 | Fairview UMMC MFM Clinic US |  |  | 1271 | 7 | 0 | 148558.09 | 135202.88 | 625 | 403.5 | 98.39% | 1.611% | 0%
Minneapolis Operations | 20030074 | Fairview UMMC WB EB 5B 6B |  |  | 1404 | 339109.71 | 25689 | 13798261.5 | 14331653.6 | 28409.1 | 33657.6 | 97.15% | 2.477% | 0.3744%
Minneapolis Operations | 20030027 | UMN Larson FB Perf Ctr Rec Ste |  |  | 1500 | 4767 | 2359 | 650995.87 | 646250.74 | 793.2 | -1267.38 | 100.6% | -0.5918% | 0%
Minneapolis Operations | 20030008 | SLI - ODS100,280 RTU240,350 |  |  | 1587 | 0 | 0 | 585308 | 525300.45 | 412 | 334 | 98.8% | 1.198% | 0%
Minneapolis Operations | 20030018 | FV -UMMC EB CathLab (OR 18/19) |  |  | 1803 | 0 | 0 | 153549.16 | 164344.81 | 316 | 231 | 91.34% | 8.658% | 0%
Minneapolis Operations | 20030056 | Fairview UMMC WB EB IR Suite |  |  | 2261 | 0 | 0 | 573653.8 | 550953.1 | 1199 | 989 | 96.41% | 3.589% | 0%
Minneapolis Operations | 20030034 | Allina ANW Omnicell Carousels |  |  | 3800 | 131.61 | 0 | 208062.96 | 199308.23 | 600.5 | 652.33 | 90.11% | 6.209% | 3.679%
Minneapolis Operations | 20030042 | Cemstone Project Refresh |  |  | 4000 | 9 | 0 | 20293 | 30332.41 | 164 | 220.5 | 97.05% | 2.948% | 0%
Minneapolis Operations | 20030007 | Target Field - Clubhse/Bullpen |  |  | 4300 | 0 | 0 | 339528.56 | 361760.36 | 652 | -35119.46 | 100.1% | -0.07546% | 0%
Minneapolis Operations | 20030036 | Allina Mercy MPP Relocation |  |  | 4500 | 61 | 0 | 695828.77 | 688871.26 | 998 | 1571.58 | 94.91% | 2.545% | 2.545%
Minneapolis Operations | 20030012 | Allina - Mercy Oncology AHG |  |  | 6300 | 36 | 0 | 1287956.9984 | 1243021.86 | 5951.38 | 5192.91 | 95.22% | 4.622% | 0.1541%
Minneapolis Operations | 20030016 | Vermeer Central Utility Plant |  |  | 7100 | 51509.58 | 13995 | 10377590.33 | 10371853.5 | 3293.2 | 2886 | 80.2% | 19.46% | 0.3465%
Minneapolis Operations | 20030026 | Allina ANW 2020 Roof Replace |  |  | 7800 | 32 | 0 | 551089.93 | 549491.64 | 150 | 150.27 | 76.71% | 23.29% | 0%
Minneapolis Operations | 20030057 | Allina Courage Kenny Kids |  |  | 8550 | 29 | 0 | 1239828.78 | 1339532.93 | 4322 | 4385 | 98.19% | 1.562% | 0.2509%
Minneapolis Operations | 20030052 | Sanford 8th Flr B wing Bld-out |  |  | 9400 | 11436 | 7510 | 2461155.19 | 2476569 | 3379 | 2999.5 | 83.31% | 16.59% | 0.1%
Minneapolis Operations | 20030072 | Blake Hopkins Campus 2021 |  |  | 10000 | 3617 | 8 | 1234624.032 | 1242268.57 | 3498 | 2495.64 | 99.14% | 0.8615% | 0%
Minneapolis Operations | 20030029 | Fairview 10A ICU UMMC EB |  |  | 10661 | 0 | 0 | 4086996.92 | 4066264.1 | 8054 | 6624 | 93.75% | 6.25% | 0%
Minneapolis Operations | 20030014 | The Bakken Museum Renovation |  |  | 11600 | 46294.78 | 4 | 3782590.66 | 3771709.91 | 7278 | 8190 | 97.61% | 2.393% | 0%
Minneapolis Operations | 20030058 | St Cloud Surgical Ctr Exp P1 |  |  | 12935 | 101693 | 73698 | 7035682.23 | 6865132.37 | 7832 | 9475 | 94.23% | 5.641% | 0.1266%
Minneapolis Operations | 20030049 | Fairfax-Parsons Building |  |  | 13000 | -7500.21 | 0 | 846533.55 | 1227409.23 | 4914 | 6624 | 99.49% | 0.5133% | 0%
Minneapolis Operations | 20030021 | HHS Redleaf Ctr Family Healing |  |  | 14980 | 83592.58 | 23040 | 4904930.65 | 4903638.14 | 6482.5 | 6586 | 97.84% | 2.156% | 0%
Minneapolis Operations | 20030073 | HHS CSC Front Entrance Repairs |  |  | 14980 | 2 | 0 | 130941 | 97206.09 | 148 | 24.5 | 87.76% | 12.24% | 0%
Minneapolis Operations | 20030066 | Cornell College Storm Remed |  |  | 16000 | 2056 | 0 | 2926031.46 | 2094389.19 | 5066.61 | 4376 | 85.83% | 13.48% | 0.6856%
Minneapolis Operations | 20030032 | Allina Mercy Onc Womens Health |  |  | 22500 | 15076 | 0 | 3278429.5361 | 3275617.26 | 5961.83 | 6118.56 | 96.81% | 3.187% | 0%
Minneapolis Operations | 20030037 | Cornell - College Hall Renov |  |  | 30000 | 115175.33 | 39502 | 3092281.74 | 3147948.98 | 4337.6 | 6473.5 | 73.31% | 23.97% | 2.719%
Minneapolis Operations | 20030061 | Legacy Mpls Data Center Renov |  |  | 34734 | 80 | 0 | 6276071.7706 | 6157160.36 | 3014 | 3752 | 98.59% | 1.413% | 0%
Minneapolis Operations | 20030006 | TFP - The Family Partnership |  |  | 42450 | 359549.07 | 206305 | 10538171.24 | 9620081.54 | 23987.18 | 20923.87 | 98.02% | 1.933% | 0.04301%
Minneapolis Operations | 20030038 | Cornell - Small Sport Center |  |  | 45000 | 418611.35 | 114495 | 17130164.12 | 17378621.85 | 21314.4 | 27934.2105 | 83.01% | 16.35% | 0.6372%
Minneapolis Operations | 20030070 | UMN Lind Hall Renovations |  |  | 58687 | 467608.89 | 101134 | 14081854.8475 | 13672413.41 | 29713.21 | 31657.83 | 96.68% | 3.215% | 0.1011%
Minneapolis Operations | 20030075 | UMN - Mech Eng Phase III |  |  | 59286 | 288222.18 | 89868 | 10986950.0166 | 11103097.86 | 17345.9 | 17727.05 | 98.37% | 1.227% | 0.4062%
Minneapolis Operations | 20030035 | State MN - ACF Presb Langton S |  |  | 80000 | 310299 | 0 | 1283995.68 | 1308361.39 | 3574.7 | 3077.5 | 88.66% | 11.34% | 0%
Minneapolis Operations | 20030045 | UMN Fraser Hall Chemistry |  |  | 101600 | 77 | 0 | 278372.2 | 270320.97 | 76 | 72 | 100% | 0% | 0%
Minneapolis Operations | 20030062 | HERC Hmong College Prep PhV |  |  | 107000 | 517792.48 | 386925 | 15523002.945 | 14759618.83 | 26448 | 26394.04 | 98.19% | 1.811% | 0%
Minneapolis Operations | 20030011 | Target Corp - Sun PrairieT2491 |  |  | 110000 | 1779.4 | 0 | 1519304.48 | 1480976.83 | 2598 | -5949 | 108.7% | -7.943% | -0.8069%
Minneapolis Operations | 20030023 | Target Corp - Aberdeen T-0848 |  |  | 110000 | -2025 | 0 | 77411.41 | 55291.34 | 2145 | 94 | 95.74% | 4.255% | 0%
Minneapolis Operations | 20030050 | Midway Shopping Cntr-Dmg Asmt |  |  | 120000 | 204 | 0 | 1420852.97 | 1347896.39 | 396 | 20 | 100% | 0% | 0%
Minneapolis Operations | 20030064 | Transamerica Storm Response |  |  | 150000 | 2440 | 0 | 1017267.47 | 1076443.44 | 1441 | 1312 | 54.34% | 34.45% | 11.2%
Minneapolis Operations | 20030065 | US Bank Storm Response |  |  | 150000 | 583 | 0 | 128229.31 | 146487.32 | 346 | 405.56 | 57.71% | 33.66% | 8.63%
Minneapolis Operations | 20030059 | MDI Platia Place (i4) |  |  | 248000 | 0 | 0 | 72150 | 194441.41
Minneapolis Operations | 20030078 | NWA - Bldg Automation Upgrades |  |  | 284000 | 0 | 0 | 612270.75 | 591316.92
Minneapolis Operations | 20030020 | Allina ANW Hospital Trans Hub |  |  | 683962 | 3803714.24 | 1960647.2 | 44064770.6545 | 40156905.54 | 114541.87 | 111192.31 | 91.55% | 8.329% | 0.1234%
Minneapolis Operations | 20030060 | MDI US Bank Edina Dev (i4) |  |  | 1000000 | 0 | 0 | 1348654 | 1160878.79 | 0 | 9 | 100% | 0% | 0%
Mortenson Energy Services-Operations | 20157001 | GE Hub Stiffener Plates TM |  |  | 0 | 0 | 0 | 0.02 | 1265815.32 | 0 | 26618 | 73.94% | 26.06% | 0%
Mortenson Energy Services-Operations | 20157002 | Chisolm View M08 BT Scrap |  |  | 0 | 0 | 0 | 0 | 33799.72 | 0 | 246.5 | 87.42% | 12.58% | 0%
Mortenson Energy Services-Operations | 20157003 | Canadian Hill T-44 Dismantle |  |  | 0 | 0 | 0 | 0 | 425109.95 | 0 | 681 | 74.08% | 25.92% | 0%
Mortenson Energy Services-Operations | 20157004 | Alamo 6 O&M 2020 Extension |  |  | 0 | 0 | 0 | 1394858 | 1015024.51 | 0 | 11514 | 88.84% | 11.16% | 0%
Mortenson Energy Services-Operations | 20157005 | Pearl O&M 2020 Extension |  |  | 0 | 0 | 0 | 557310 | 247296.17 | 0 | 2520 | 90% | 10% | 0%
Mortenson Energy Services-Operations | 20157006 | GE Commissioning Support |  |  | 0 | 0 | 0 | 0.03 | 716002.2 | 0 | 13937.5 | 70.95% | 29.05% | 0%
Mortenson Energy Services-Operations | 20157007 | Torrecillas WTG T-115 Demo |  |  | 0 | 0 | 0 | 0.01 | 269908.16 | 0 | 1699.5 | 70.81% | 29.19% | 0%
Mortenson Energy Services-Operations | 20157008 | Rim Rock WTG 198 Re-Assembly |  |  | 0 | 0 | 0 | 0 | 116674.15 | 0 | 1966.5 | 67.3% | 32.7% | 0%
Mortenson Energy Services-Operations | 20157009 | Colorado Green MET Tower Demo |  |  | 0 | 0 | 0 | 0.01 | 24245.61 | 0 | 189 | 86.24% | 13.76% | 0%
Mortenson Energy Services-Operations | 20157010 | Mortenson New Wind Assistance |  |  | 0 | 0 | 0 | 0 | 636563.75 | 0 | 17453 | 73.24% | 26.76% | 0%
Mortenson Energy Services-Operations | 20157011 | Rocksprings Tower Disposal |  |  | 0 | 0 | 0 | 0 | 27244.67 | 0 | 239.5 | 77.24% | 22.76% | 0%
Mortenson Energy Services-Operations | 20157012 | Torrecillas T-115 Rebuild |  |  | 0 | 0 | 0 | 0 | 579306.08 | 0 | 1135.5 | 76.27% | 23.73% | 0%
Phoenix Operations | 20040001 | Allstate Facilities Requests |  |  | 0 | 2 | 0 | 14439.46 | 14645.25 | 160 | 169.5 | 94.1% | 5.9% | 0%
Phoenix Operations | 20040003 | San Carlos T&M |  |  | 0 | 0 | 0 | 25087.18 | 24637.01 | 0 | 107.5 | 100% | 0% | 0%
Phoenix Operations | 20040005 | Allstate Tempe Facilities |  |  | 0 | 0 | 0 | 0.01 | 0
Phoenix Operations | 20040006 | Allstate-Tempe Facilities |  |  | 0 | 16 | 0 | 11119.08 | 10400.38 | 16 | 44.5 | 100% | 0% | 0%
Phoenix Operations | 20040007 | Lucid Tempe Renovation |  |  | 0 | 27447.62 | 3502 | 3451381.9072 | 3248499.99 | 1172.1 | 994.5 | 96.88% | 3.117% | 0%
Phoenix Operations | 20040008 | AlaskaUSA Safeway Peoria |  |  | 0 | 2647 | 2616 | 53339.34 | 56670.82 | 273.1 | 302.5 | 80% | 20% | 0%
Phoenix Operations | 20040009 | AlaskaUSA Safeway Arcadia |  |  | 0 | 2048 | 0 | 52281.48 | 49663.62 | 215.7 | 305 | 88.2% | 11.8% | 0%
Phoenix Operations | 20040010 | AlaskaUSA Frys Tempe |  |  | 0 | 2572 | 2540 | 64168.85 | 56968.38 | 319.9 | 279 | 98.57% | 1.434% | 0%
Phoenix Operations | 20040004 | AlaskaUSA 2nd Floor TI |  |  | 25000 | 27910 | 10910 | 3433225.11 | 3235182.93 | 1579.7 | 2170 | 93.27% | 6.728% | 0%
Phoenix Operations | 20040002 | MDI-ASU Arena |  |  | 166500 | 4793524.58 | 123075 | 117336071.78 | 111117966.11 | 47289.4 | 49949.35 | 87.49% | 12.51% | 0%
Portland Operations | 20055004 | OHSU Baird Hall Lab |  |  | 0 | 8 | 0 | 883.05 | 542.31
Portland Operations | 20055005 | Kaiser WMC Emerg Triage |  |  | 0 | 1 | 0 | 73604.47 | 73910.9 | 0 | 140.5 | 86.48% | 13.52% | 0%
Portland Operations | 20055007 | Kaiser Sunset Boiler Constr |  |  | 0 | 677 | 0 | 426686.0445 | 434363.04 | 885 | 843.58 | 99.76% | 0.2371% | 0%
Portland Operations | 20055008 | Adventist Med Air Compressor |  |  | 0 | 25 | 0 | 229967.22 | 223157.63 | 31 | 0 | 0% | 0% | 0%
Portland Operations | 20055011 | Kaiser WMU Vaporizer Replace |  |  | 0 | 19 | 0 | 28927.74 | 28738.26 | 80 | 44 | 100% | 0% | 0%
Portland Operations | 20055012 | Kaiser WMC SPD Ultrasonics |  |  | 0 | 15 | 0 | 12147.14 | 12754.59 | 24 | 8 | 100% | 0% | 0%
Portland Operations | 20055013 | Kaiser WMC Radio Rd |  |  | 0 | 61 | 56 | 98038.19 | 93604.77 | 208 | 176.85 | 100% | 0% | 0%
Portland Operations | 20055014 | Kaiser SST Infusion Clinic |  |  | 0 | 1925 | 0 | 162491.21 | 170070.84 | 345 | 438 | 98.86% | 1.142% | 0%
Portland Operations | 20055015 | Kaiser Fac Direct Sml Wrks |  |  | 0 | 65 | 10 | 392165.63 | 357355.93 | 753 | 1167 | 94.17% | 5.827% | 0%
Portland Operations | 20055016 | Kaiser Red Message Mgmt Precon |  |  | 0 | 15 | 0 | 10776.55 | 10352.24 | 24 | 0 | 0% | 0% | 0%
Portland Operations | 20055017 | Kaiser WMC TJC Door Mod Constr |  |  | 0 | 87 | 0 | 48199.75 | 48914.59 | 152 | 133 | 36.09% | 63.91% | 0%
Portland Operations | 20055019 | OHSU/Adven WHV Fam Med Clinic |  |  | 0 | 145.8 | 0 | 115836.33 | 112835.3 | 505 | 427 | 99.06% | 0.9368% | 0%
Portland Operations | 20055020 | UO Huestis Hall Surge |  |  | 0 | 26523.65 | 1605 | 2969457.23 | 3086484.95 | 3848.5 | 4048.07 | 89.17% | 10.19% | 0.6423%
Portland Operations | 20055021 | Kaiser Red Message Mgmt |  |  | 0 | 63 | 0 | 28877.99 | 30010.64 | 138 | 149 | 96.64% | 3.356% | 0%
Portland Operations | 20055022 | Kaiser WMC Ultrasound Precon |  |  | 0 | 9 | 0 | 11250.38 | 9171.45 | 16 | 0 | 0% | 0% | 0%
Portland Operations | 20055025 | Kaiser WMC Replace SPB |  |  | 0 | 10 | 0 | 6506.98 | 7187.9 | 16 | 8 | 100% | 0% | 0%
Portland Operations | 20055003 | OHSU Emerg Med Off Reloc |  |  | 1400 | 8 | 0 | 983.33 | 565.78
Portland Operations | 20055002 | OHSU 9A Remodel |  |  | 6000 | 13 | 0 | 5518.62 | 8096.33
Portland Operations | 20055001 | Nike Cool Pads |  |  | 16000 | 13 | 0 | 23929.54 | 10616.51
Portland Operations | 20055006 | Studio PPS Terwilliger Study |  |  | 21000 | 0 | 0 | 9000 | 1167.96
Portland Operations | 20055024 | UO Huestis Hall Renovation |  |  | 60000 | 22314.89 | 0 | 29395131.52 | 5452996 | 3796.5 | 2024.43 | 93.41% | 6.57% | 0.0247%
Portland Operations | 20055010 | CitizenM Hotel - FB Menlo |  |  | 90868 | 493629.22 | 5084.59 | 87844527.26 | 42565862.54 | 6039.2 | 929 | 94.89% | 5.113% | 0%
Portland Operations | 20055009 | PPS Emerg COVID Support |  |  | 2500000 | 25 | 0 | 119242.57 | 102041.39 | 256 | 411.5 | 98.18% | 1.823% | 0%
Power Delivery Solutions Operations | 20146001 | Corazon Solar Interconnection |  |  | 0 | 280328.92 | 254705 | 12552025.93 | 12608755.32 | 14280.67 | 16347 | 76.29% | 23.71% | 0%
Power Delivery Solutions Operations | 20146002 | West Raymond Interconnect |  |  | 0 | 144337.16 | 161307 | 4381781.6 | 4018678.95 | 4863.47 | 7406.5 | 78.11% | 21.89% | 0%
Power Delivery Solutions Operations | 20146003 | Blackjack Creek Interconnect |  |  | 0 | 391370 | 377076 | 8799109.08 | 8357171.43 | 11845.34 | 9745.5 | 90.71% | 9.291% | 0%
Power Delivery Solutions Operations | 20146004 | Dakota Range Wind - Power |  |  | 0 | 618915.97 | 613472 | 21073600 | 20035902.71 | 23565.84 | 21477 | 82.17% | 17.83% | 0%
Power Delivery Solutions Operations | 20146005 | Toms Fork |  |  | 0 | 957 | 0 | 7237514.25 | 29182.66
Power Delivery Solutions Operations | 20146006 | Fighting Jays Solar - Power |  |  | 0 | 191200.8 | 191448.8 | 7563984 | 7364813.64 | 7972.25 | 12907 | 89.01% | 10.99% | 0%
Power Delivery Solutions Operations | 20146007 | Andrews 4 Solar - Power |  |  | 0 | 0 | 0 | 1399065 | 945979.39
Power Delivery Solutions Operations | 20146008 | Emerald Grove Solar - Power |  |  | 0 | 94420.46 | 86813 | 6208916.76 | 6163106.29 | 4928.69 | 4746 | 87.85% | 12.15% | 0%
Power Delivery Solutions Operations | 20146009 | Dawn Solar - Power |  |  | 0 | 240 | 0 | 1444815 | 1039331.91
Power Delivery Solutions Operations | 20146010 | Blue Canyon II Repower-Power |  |  | 0 | 33537.56 | 1652 | 3792652.05 | 3815632.05 | 5737 | 7309.5 | 80.41% | 19.59% | 0%
Power Delivery Solutions Operations | 20146011 | Rockhaven Wind - Power |  |  | 0 | 170082.69 | 161860 | 12593137.54 | 14039633.03 | 6529.54 | 15203.5 | 79.14% | 20.86% | 0%
Seattle Operations | 20050001 | PRMCE Colby 4A Behavioral |  |  | 0 | 34931.3 | 2440 | 7014752.8576 | 7145040.4 | 2530.1 | 4431 | 91.57% | 8.023% | 0.4062%
Seattle Operations | 20050002 | PRMCE Colby D Wing CT Install |  |  | 0 | 4302 | 509 | 451496.772 | 440220.7 | 452.2 | 604.74 | 85.82% | 10.38% | 3.803%
Seattle Operations | 20050003 | Hyla Crossing Pump Station |  |  | 0 | 0 | 0 | 12141.06 | 8745.85
Seattle Operations | 20050004 | KP ESC Demolition |  |  | 0 | 284 | 0 | 553260.17 | 523244.61 | 282.4 | 307.81 | 100% | 0% | 0%
Seattle Operations | 20050005 | Make Ready - Swedish |  |  | 0 | 31 | 495 | 1306111.45 | 1301925.73 | 960 | 715 | 97.48% | 2.517% | 0%
Seattle Operations | 20050006 | Swedish NT - Demo/Abatement |  |  | 0 | 5746 | 0 | 26601901.97 | 19126341.11 | 7531.5 | 5485.1 | 94.61% | 5.35% | 0.03646%
Seattle Operations | 20050007 | Block 95 - Swedish |  |  | 0 | 32969.5 | 32 | 42016452.39 | 12883303.76 | 7939.4 | 1717 | 96.59% | 2.941% | 0.4659%
Seattle Operations | 20050008 | KP ESC Site Prep |  |  | 0 | 21 | 0 | 303001.52 | 284289.65 | 8 | 4 | 0% | 100% | 0%
Seattle Operations | 20050009 | Swedish COVID19 Response |  |  | 0 | 0 | 2 | 416668.62 | 378954.69 | 0 | 5 | 100% | 0% | 0%
Seattle Operations | 20050010 | Bend Interceptor Phase 2 |  |  | 0 | 1392 | 1 | 19647142.83 | 20134910.92 | 254 | 24 | 100% | 0% | 0%
Seattle Operations | 20050011 | Fifth and Union Hotel (Mstrwrk |  |  | 0 | 0 | 0 | 43228.32 | 49891.52
Seattle Operations | 20050012 | Kaiser ASC Parking Garage |  |  | 0 | 1103397.77 | 21724.96 | 23388914.9 | 4813468.56 | 19664 | 7840.5 | 94.87% | 4.681% | 0.4528%
Seattle Operations | 20050013 | Fana Four106 |  |  | 0 | 0 | 0 | 507127.75 | 546825.97
Seattle Operations | 20050014 | Prov NWSA EP Lab Reno |  |  | 0 | 3165.1 | 430 | 1048236.1 | 1039431.21 | 568.2 | 746.76 | 61.07% | 36.46% | 2.477%
Seattle Operations | 20050015 | Cedar Mills No 6882 |  |  | 0 | 55 | 0 | 11553677.6471 | 11177565.44
Seattle Operations | 20050050 | Kaiser Everett IDIQ 2020 |  |  | 0 | 1008.13 | 483 | 626237.3545 | 641456.84 | 708.13 | 728 | 95.54% | 2.266% | 2.198%
Seattle Operations | 20050051 | Kaiser Lynwood IDIQ 2020 |  |  | 0 | 2319 | 0 | 4368.72 | 5874.33 | 0 | 0 | 0% | 0% | 0%
Seattle Operations | 20050052 | KP Port Orchard IDIQ 2020 |  |  | 0 | 1232 | 0 | 384987.95 | 394749.53 | 701.8 | 725.95 | 98.9% | 1.102% | 0%
Seattle Operations | 20050053 | KP EVM Roof Replacement |  |  | 0 | 39.5 | 0 | 518237.35 | 480019.79 | 34.3 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 20145002 | Texas Solar Nova 2 Geotech |  |  | 0 | 260 | 0 | 194265 | 187905.75 | 160 | 276 | 86.96% | 13.04% | 0%
Solar and Emerging Renewables Operations | 20145006 | Emerald Grove Solar - Vistra |  |  | 140 | 3023127.7112 | 2724497.39 | 65503365.33 | 66327681.08 | 261326.74 | 317287.34 | 86.19% | 13.81% | 0%
Solar and Emerging Renewables Operations | 20145005 | Andrews 4 Solar - Vistra |  |  | 261 | 585 | 0 | 4302346.04 | 2639820.77 | 386 | 384.5 | 72.43% | 27.57% | 0%
Solar and Emerging Renewables Operations | 20145001 | Fighting Jays Solar-CIP |  |  | 476 | 12961792.56 | 8790948.73 | 236866438.17 | 232598848.77 | 1054810.02 | 1131922.42 | 86.36% | 13.64% | 0.0004859%
Solar and Emerging Renewables Operations | 20145008 | Dawn Solar-Blue Planet |  |  | 683 | 1387 | 0 | 7796037 | 2896120.54 | 600 | 238 | 79.83% | 20.17% | 0%
Solar and Emerging Renewables Operations | 20145007 | Edwards & Sanborn 1A&1B |  |  | 1113 | 16817754.46 | 14360299.08 | 836870271.29 | 732549556.05 | 2155844.61 | 2180545.52 | 84.46% | 14.55% | 0.9959%
Sports + Entertainment Group Operations | 20150003 | MPLS Enterprise DAS Projects |  |  | 0 | 0 | 0 | 115208 | 130924.12
Sports + Entertainment Group Operations | 20150004 | MCC - CANA - Calgary Flames |  |  | 0 | 0 | 0 | 0.02 | 578583.72
Sports + Entertainment Group Operations | 20150004-110 | CANA - Calgary Flames Arena |  |  | 0 | 0 | 0 | 1069573.98 | 756106.4
Sports + Entertainment Group Operations | 20150006 | Climate Pledge Arena DAS |  |  | 0 | 1 | 0 | 12957558.8358 | 12093720.93 | 16435 | 0 | 0% | 0% | 0%
Sports + Entertainment Group Operations | 20150007 | MLS - Nashville - DAS |  |  | 100 | 0 | 0 | 606593.712 | 666102.89
Sports + Entertainment Group Operations | 20150005 | PSU - Lasch Phase 4 - QB Lab |  |  | 1200 | 1227 | 0 | 1975172.73 | 1930091.65
Sports + Entertainment Group Operations | 20150001 | MLS - Sacramento Republic FC |  |  | 404875 | 0 | 0 | 1 | 1078098.42
Wind Energy I Operations | 20141001 | Smoky Hills II Repower |  |  | 0 | 1601.68 | 734 | 16294067.102 | 10931550.62 | 38410 | 31350 | 81.32% | 18.68% | 0%
Wind Energy I Operations | 20141002 | Hawkeye Wind |  |  | 0 | 13562.18 | 643 | 25703700.52 | 16812095.93 | 31640 | 21618.5 | 78.57% | 18.16% | 3.263%
Wind Energy I Operations | 20141003 | Langford Repower |  |  | 0 | 2984 | 1285 | 23227823.88 | 18687352.52 | 78840 | 81256.58 | 79.77% | 20.23% | 0%
Wind Energy I Operations | 20141004 | Dakota Range Wind |  |  | 0 | 11456.68 | 4726 | 101827957.5718 | 91177666.12 | 159155.5 | 115278.5 | 78.23% | 21.03% | 0.7378%
Wind Energy I Operations | 20141005 | Trent Mesa Repower |  |  | 0 | 6 | 0 | 599210.14 | 595006.6
Wind Energy I Operations | 20141006 | Mesa Alta & Mesa Wind |  |  | 0 | 0 | 0 | 758962.5 | 671012.09
Wind Energy I Operations | 20141007 | Mulqueeney Ranch Wind |  |  | 0 | 0 | 0 | 340349 | 259112.45
Wind Energy I Operations | 20141008 | Desert Sky Repower |  |  | 0 | 4 | 0 | 860359 | 477135.83 | 0 | 145 | 100% | 0% | 0%
Wind Energy I Operations | 20141009 | Big Sky Repower |  |  | 0 | 0 | 0 | 154035.67 | 147415.4
Wind Energy I Operations | 20141010 | Blue Canyon Repower |  |  | 0 | 3944 | 2555 | 39353923.7198 | 34076940.33 | 81081 | 82518 | 74.2% | 25.8% | 0%
Wind Energy I Operations | 20141011 | Oasis Wind |  |  | 0 | 1772 | 1295 | 38618613.98 | 36561723.04 | 47420 | 43481.5 | 75.68% | 20% | 4.324%
Wind Energy I Operations | 20141012 | Rockhaven Wind |  |  | 0 | 27206.77 | 5950 | 65035217.1587 | 62157948.23 | 106504 | 89888.33 | 79.45% | 20.55% | 0%
Wind Energy I Operations | 20141013 | Glass Sands Wind |  |  | 0 | 6128 | 6172 | 52718623.0132 | 52828054.31 | 69002.09 | 86343.35 | 79.34% | 20.66% | 0%
Total | [5 empty] | 130031579.7912 | 38578927.85 | 4905488352.1264 | 3833530094.07 | 5804564.93 | 6013048.6705 | 84.29% | 14.91% | 0.7904%

## 2019
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Chicago Operations | 19090001 | FermiLab Engineering Research | 2019-07-01 | 2023-08-01 | 102000 | 404891 | 8487 | 62164929.9174 | 59937279.78 | 13485.14 | 15106.5 | 82.98% | 15.56% | 1.463%
Minneapolis Operations | 19030027 | HCMC - MCP Phase 2A | 2020-02-01 | 2022-02-28 | 100000 | 0 | 0 | 45162 | 29437.12
Milwaukee Operations | 19080004 | AMC Mount Pleasant | 2019-09-01 | 2022-02-01 | 299000 | 3552220.89 | 2252566 | 155409326.9107 | 155865635.3 | 137235.84 | 159813.37 | 90.78% | 9.166% | 0.05475%
Denver Operations | 19060011 | MDI-NJH COH | 2019-10-01 | 2021-07-30 | 104820 | 1425129.76 | 901412 | 62888862.2096 | 60432420.69 | 82353.96 | 85860.5 | 88.85% | 11.15% | 0%
Minneapolis Operations | 19030008 | UMN-CMRR MDT Optical Imaging | 2019-06-07 | 2021-03-26 | 30170 | 285346.52 | 158967 | 12809997.99 | 13215131.1 | 21088.7 | 24339.47 | 98.2% | 1.795% | 0%
FCG Operations | 19110001 | SBIRS Operations Facility | 2019-06-01 | 2021-03-11 | 58760 | 1308 | 0 | 33895292.38 | 35924451.92 | 0 | 0 | 0% | 0% | 0%
Chicago Operations | 19090991 | Chicago 2019 Prefab Shop | 2019-01-01 | 2020-12-31 | 0 | 1921 | 2990 | 226487 | 617038.24 | 1044 | 3479.45 | 99.4% | 0.6035% | 0%
Denver Operations | 19060019 | EX Vail-Vail Four Seasons | 2019-04-22 | 2020-12-07 | 0 | 161115 | 10769 | 5696911.17 | 5833592.67 | 14595.1 | 14192 | 93.46% | 6.542% | 0%
Wind Energy I Operations | 19141018 | Gonzaga Ridge Wind | 2020-04-06 | 2020-12-01 | 0 | 0 | 0 | 91100 | 72401.66
Wind Energy I Operations | 19141015 | Diamond Trail Wind | 2019-08-01 | 2020-11-09 | 0 | 6811 | 4016 | 122586746.1894 | 109282444.93 | 240797.2 | 146442.75 | 66.48% | 33.03% | 0.4923%
Phoenix Operations | 19040004 | MDI - The Beam on Farmer | 2019-04-19 | 2020-10-31 | 0 | 866886.6 | 0 | 52557329.8 | 54088575.7 | 7855.6 | 9981.78 | 83.71% | 16.29% | 0%
Solar and Emerging Renewables Operations | 19145001 | Crane Solar - CED Crane Solar | 2019-01-14 | 2020-10-31 | 212592800 | 1814148.54 | 9321186 | 84328075.02 | 87807940.38 | 378456.13 | 407869.83 | 85.02% | 14.98% | 0.0009807%
Denver Operations | 19060029 | LoneTree-Ridgegate Pkwy Exp P2 | 2019-06-01 | 2020-10-28 | 0 | 390843.08 | 508776 | 11411748.85 | 16364311.16 | 29700 | 56951 | 78.04% | 21.96% | 0%
Power Delivery Solutions Operations | 19146004 | Palo Alto Wind - HVT | 2019-04-01 | 2020-10-17 | 0 | 804789 | 38375 | 30701338.89 | 30458883.91 | 21257 | 34863.5 | 78.88% | 21.12% | 0%
Wind Energy I Operations | 19141003 | El Campo | 2019-06-17 | 2020-10-01 | 0 | 4841 | 3710 | 69310825.0776 | 70827585.39 | 154313 | 169954.75 | 82.04% | 17.96% | 0%
Chicago Operations | 19090002 | MDI-Hilton Garden Inn Madison | 2019-06-03 | 2020-09-30 | 220000 | 97515.65 | 5860 | 38200931.96 | 38169437.03 | 4990.2 | 2824.4 | 85.18% | 13.86% | 0.956%
Power Delivery Solutions Operations | 19146015 | Cheyenne Ridge Wind - HVT | 2019-05-01 | 2020-09-01 | 0 | 641887 | 610941 | 48921315.33 | 47594183.34 | 141513 | 87180.76 | 72.29% | 27.71% | 0%
Power Delivery Solutions Operations | 19146013 | Misae II Interconnect | 2020-03-01 | 2020-08-31 | 0 | 360838.11 | 255306 | 12485275.45 | 6221918.39 | 12680.7 | 3195 | 80.23% | 19.77% | 0%
Minneapolis Operations | 19030017 | RiverView Health - AC&IP | 2019-04-29 | 2020-08-28 | 80657 | 244252.26 | 71670 | 24308389.436 | 24540639.65 | 27721.1 | 25587.5 | 94.82% | 5.081% | 0.1016%
Minneapolis Operations | 19030015 | Blake Lobby Addition | 2019-06-03 | 2020-08-11 | 19617 | 329537.79 | 151810 | 7878956.5 | 8008407.3 | 20134.8 | 23567.67 | 96.54% | 3.445% | 0.01697%
Minneapolis Operations | 19030016 | Vermeer Building 5 & 6 | 2019-06-01 | 2020-08-01 | 500000 | 618522.4 | 49852 | 73830787.48 | 73280737.43 | 17569.6 | 18158.25 | 74.58% | 24.67% | 0.7545%
Power Delivery Solutions Operations | 19146008 | Kings Point Wind Design-HVT | 2020-02-01 | 2020-08-01 | 0 | 8 | 0 | 231306 | 211742
Denver Operations | 19060023 | Park Creek-Filing MF Dstrct IV |  | 2020-07-30 | 0 | 0 | 0 | 989999.7 | 982037.74 | 3750 | 4389 | 96.39% | 3.611% | 0%
Energy Storage & Solutions Operations | 19146016 | Chisholm Energy Storage | 2019-07-08 | 2020-07-24 | 0 | 292464.06 | 229691 | 20736968.63 | 18007760.03 | 38673.11 | 39370.5 | 80.5% | 19.5% | 0%
Phoenix Operations | 19040002 | MDI-ASU HH/HP FFE | 2019-02-11 | 2020-07-21 | 156611 | 7 | 0 | 4262041.39 | 4235659.99
Seattle Operations | 19050003 | PRMCE Colby 9D Patient Rms | 2019-04-01 | 2020-06-30 | 0 | 136839.13 | 4524 | 17740173.8161 | 17597139.51 | 9500.18 | 8387.74 | 93.03% | 4.697% | 2.271%
Power Delivery Solutions Operations | 19146012 | King Plains Wind - HVT | 2019-08-15 | 2020-06-29 | 0 | 567317 | 640552 | 20785778.7425 | 20534244.82 | 59027.3 | 35908.5 | 84.12% | 15.88% | 0%
Power Delivery Solutions Operations | 19146010 | Nobles 2 Wind - HVT | 2019-09-10 | 2020-06-09 | 0 | 3092 | 0 | 6600792.43 | 6063273.25
Solar and Emerging Renewables Operations | 19145005 | Phoenix Solar - Pattern Energy | 2019-07-29 | 2020-06-05 | 0 | 2320878.09 | 2581904 | 58248046.22 | 63617220.62 | 218675.17 | 281291.25 | 88.4% | 11.6% | 0%
Power Delivery Solutions Operations | 19146006 | El Campo Wind - HVT | 2019-08-01 | 2020-06-01 | 0 | 0 | 0 | 108697.7 | 148702.61
Power Delivery Solutions Operations | 19146009 | North Fork Rdg Wind Design-HVT | 2019-10-01 | 2020-06-01 | 0 | 195367 | 0 | 270750 | 184118.13
Denver Operations | 19060020 | MDI-Bioscience 5 | 2019-08-01 | 2020-05-01 | 90000 | 0 | 0 | 373718 | 391969.66
Power Delivery Solutions Operations | 19146003 | Crane I Solar - HVT | 2019-10-17 | 2020-04-29 | 0 | 103822.75 | 66329 | 5291076.72 | 5050260.47 | 3614.68 | 3973 | 85.04% | 14.96% | 0%
Milwaukee Operations | 19080003 | Project Walleye | 2019-04-08 | 2020-04-01 | 350098 | 11 | 0 | 1026419.09 | 873427.94
Minneapolis Operations | 19030012 | Thrivent Financial TI | 2019-10-01 | 2020-04-01 | 110000 | 304175 | 81018 | 14667001.55 | 14705950.41 | 11380.6 | 15200 | 92.96% | 6.99% | 0.05263%
Chicago Operations | 19090003 | Allstate Jacksonville 2019 | 2019-04-01 | 2020-03-31 | 27750 | 1003 | 0 | 3699934.8662 | 3581834.83
Denver Operations | 19060022 | Broadmoor Exhibit Hall |  | 2020-03-20 | 172988 | 951312.66 | 619504 | 37503685.44 | 37496766.89 | 40684.6 | 43022.75 | 79.53% | 20.47% | 0%
Denver Operations | 19060001 | BMD-Baseline W Sheridan | 2019-01-04 | 2020-01-31 | 0 | 0 | 0 | 14581 | 8189.67
Denver Operations | 19060010 | CDOT-Hwy 72 Coal Creek Canyon | 2019-04-01 | 2020-01-13 | 0 | 640445.45 | 136268 | 13066982.97 | 16418354.06 | 49488 | 78835.25 | 76.09% | 23.91% | 0%
Denver Operations | 19060007 | Park Creek - Filing PC Park | 2019-04-01 | 2019-12-31 | 0 | 1 | 0 | 577344.9974 | 605189.41 | 482 | 215 | 99.3% | 0.6977% | 0%
Denver Operations | 19060009 | Woodward-2019 Misc Projects | 2019-01-28 | 2019-12-31 | 0 | 623 | 164 | 296952.6886 | 304539.71 | 376 | 1486.5 | 89.84% | 10.16% | 0%
Denver Operations | 19060012 | SCL-LMC Foothills Renovation | 2019-02-18 | 2019-12-31 | 0 | 20890.82 | 381 | 2581422.57 | 2784058.73 | 1615.6 | 5406 | 85.15% | 14.85% | 0%
Minneapolis Operations | 19030001 | FUMC-Annual Contract 2019 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0 | 1183843.94 | 1195962.18 | 0 | 3955.5 | 92.34% | 5.916% | 1.744%
Minneapolis Operations | 19030002 | Allina Annual Contract - 2019 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0 | 5931787.07 | 5931786.98 | 0 | 28840.13 | 91.43% | 7.982% | 0.586%
Minneapolis Operations | 19030013 | Basilica Annual 2019 | 2019-05-01 | 2019-12-31 | 0 | 672 | 176 | 293976.8603 | 338402.5 | 1412 | -1976.67 | 103.8% | -3.491% | -0.3541%
Solar and Emerging Renewables Operations | 19145002 | Grazing Yak - NextEra Energy | 2019-06-07 | 2019-12-31 | 47251000 | 7687464 | 1130118 | 21019294.33 | 19789713.98 | 90270 | 74350 | 81.41% | 18.59% | 0%
Power Delivery Solutions Operations | 19146014 | Asheville Rock Hill BESS | 2019-04-01 | 2019-12-20 | 0 | 176562 | 22265 | 2575676.29 | 2574732.41 | 3004 | 5860 | 78.24% | 21.76% | 0%
Minneapolis Operations | 19030023 | Philips Elec Realty - TI DS | 2019-09-20 | 2019-12-09 | 5973 | 6500 | 0 | 1642487.08 | 1494179.26 | 477.7 | 575.5 | 98.09% | 1.911% | 0%
Denver Operations | 19060015 | SCL-SJB P Tube Expansion | 2019-01-01 | 2019-12-01 | 0 | 0 | 0 | 852026.33 | 853632.22
Denver Operations | 19060016 | SCL-SJB Boiler Phase II | 2019-01-01 | 2019-12-01 | 0 | 0 | 0 | 550796.11 | 550833.01
Civil Group Operations | 19148001 | Chokecherry Sierra Madre 2019 | 2019-03-18 | 2019-11-30 | 0 | 1174897 | 725358 | 17298436.15 | 18145102.16 | 73310 | 71736.5 | 76.23% | 23.45% | 0.322%
Seattle Operations | 19050004 | PRMCE Colby 2D OR Pre OP | 2019-06-01 | 2019-11-30 | 0 | 28881 | 2539 | 2754581.2704 | 2704985.13 | 2127.9 | 1334.5 | 82.58% | 15.96% | 1.461%
Power Delivery Solutions Operations | 19146007 | Ida Grove II Wind - HVT | 2019-04-01 | 2019-11-23 | 0 | 497926 | 5588 | 21258838.88 | 19430680.13 | 25932 | 22566.5 | 79.41% | 20.59% | 0%
Denver Operations | 19060030 | SCL-LMC Foothills PrimCare |  | 2019-11-22 | 11500 | 28482.12 | 3000 | 1965241.06 | 2063237.22 | 2238.8 | 5802.5 | 89.8% | 10.2% | 0%
Minneapolis Operations | 19030024 | Boston Scientific - TI DS | 2019-08-28 | 2019-11-22 | 5973 | 3769 | 0 | 487657.41 | 480722.05 | 370.9 | 376 | 98.94% | 1.064% | 0%
Power Delivery Solutions Operations | 19146011 | Arbor Hill 2019 Wind - HVT | 2019-07-08 | 2019-11-18 | 0 | 382143 | 150669 | 8661883.84 | 7984380 | 7596 | 2965 | 80.03% | 19.97% | 0%
Denver Operations | 19060002 | SCL-SJB 4th Floor-AHU | 2019-01-01 | 2019-11-01 | 0 | 0 | 0 | 399622.08 | 400245.84
Denver Operations | 19060003 | SCL-SJB Admin/Cath/Enab | 2019-01-01 | 2019-11-01 | 0 | 2 | 0 | 3597140.52 | 3707737.58 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 19060013 | SCL-SJB Facilities Agreement | 2019-01-01 | 2019-11-01 | 0 | 0 | 0 | 1047603.87 | 1362052.02
Denver Operations | 19060026 | SCL-SJB Fluoroscopy Ph2 | 2019-01-01 | 2019-11-01 | 0 | 0 | 0 | 113845 | 113683.93 | 0 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 19146001 | Clear Creek Wind - HVT | 2019-06-01 | 2019-11-01 | 0 | 8409 | 9240 | 7370991 | 6308965.02 | 8381 | 9211.5 | 78.41% | 21.59% | 0%
Wind Energy I Operations | 19141016 | Glenrock-Rolling Hills Repower | 2019-04-01 | 2019-10-31 | 0 | 2007 | 1868 | 22677279.86 | 22181079.18 | 64928 | 88060.79 | 79.22% | 20.51% | 0.2771%
Denver Operations | 19060031 | SCL-LMC Foothills Scheduling | 2019-06-01 | 2019-10-23 | 7000 | 22211.76 | 1098 | 921833.42 | 952097.42 | 1556 | 2835 | 83.23% | 16.77% | 0%
Power Delivery Solutions Operations | 19146005 | Rondo SVC | 2019-07-15 | 2019-10-15 | 0 | 94750 | 4579 | 1370711 | 1070694.75 | 10496 | 3434 | 82.27% | 17.73% | 0%
Power Delivery Solutions Operations | 19146002 | Stadium Rebuild | 2019-01-21 | 2019-09-30 | 0 | 27312 | 14831 | 2132339.94 | 1952621.8 | 6459 | 6334.75 | 74.45% | 25.55% | 0%
Solar and Emerging Renewables Operations | 19145003 | Alamo 7 Expansion | 2019-04-29 | 2019-09-06 | 993630 | 23889 | 45190 | 1133919 | 1155307.69 | 8490 | 5605.5 | 81.28% | 18.72% | 0%
Minneapolis Operations | 19030028 | NS II - Certified Power TI | 2019-05-13 | 2019-09-03 | 55237 | 144 | 0 | 1966531.44 | 1994000.38 | 1622 | 1073 | 94.41% | 5.592% | 0%
Denver Operations | 19060025 | Westfield-Parcel B/C Demo | 2019-04-15 | 2019-09-01 | 0 | 0 | 0 | 1716388.6 | 1719292.77
Denver Operations | 19060027 | Westfield-Pecos Logistics Park | 2019-04-15 | 2019-09-01 | 0 | 0 | 0 | 0 | -4019.17
Denver Operations | 19060018 | Murphy-AB Clarifier | 2019-04-09 | 2019-08-30 | 0 | 0 | 0 | 0.01 | 0
Denver Operations | 19060024 | Stadium Mgmt-Aramark Conc |  | 2019-08-30 | 13684 | 0 | 1080 | 2634323.61 | 2756130.24 | 366.4 | 4101.5 | 81.36% | 18.64% | 0%
Minneapolis Operations | 19030007 | UMN Volleyball Remodel | 2019-04-01 | 2019-08-23 | 9000 | 56190.15 | 44002 | 3080257.51 | 3115299.79 | 4892.7 | 4294.5 | 99.17% | 0.6404% | 0.1863%
Minneapolis Operations | 19030026 | MPI-Upper Miss Academy TI | 2019-05-06 | 2019-08-16 | 35160 | 23 | 55 | 1628183.68 | 1587808.57 | 1642 | 2212.5 | 98.37% | 1.627% | 0%
FCG Operations | 19110003 | DC Office Remodel-To Be Cap. | 2019-01-01 | 2019-08-09 | 12000 | 0 | 0 | 1397721 | 2.3283e-10
Solar and Emerging Renewables Operations | 19145004 | Alamo 4 ACT Labor - OCI | 2019-04-15 | 2019-08-02 | 0 | 142668 | 124605 | 2079297.81 | 1356520.36 | 33561 | 27333 | 88.93% | 11.07% | 0%
Minneapolis Operations | 19030010 | ANW-Punched Windows | 2018-12-26 | 2019-07-31 | 0 | 9988.6 | 0 | 2850440 | 2774861.37 | 7605.6 | 5283 | 95.69% | 4.155% | 0.1514%
Minneapolis Operations | 19030021 | Target Corp - StillwaterT0931 | 2019-04-15 | 2019-07-31 | 110000 | 0 | 0 | 1194268.39 | 1202164.76 | 1680 | 1876 | 94.35% | 5.65% | 0%
Minneapolis Operations | 19030022 | Target Corp - Crystal T0003 | 2019-04-15 | 2019-07-31 | 110000 | 5 | 0 | 2063757.82 | 1927390.14 | 1680 | 1866.83 | 91.72% | 8.276% | 0%
Minneapolis Operations | 19030029 | Fairview - SBldg AV 5122-5123 | 2019-06-20 | 2019-07-20 | 2000 | 0 | 0 | 87035.11 | 84375.88 | 56 | 56.5 | 99.12% | 0.885% | 0%
Solar and Emerging Renewables Operations | 19145008 | Greasewood Solar - Concho | 2019-04-15 | 2019-06-28 | 0 | 8461855.75 | 8718497 | 136700537.036 | 126952753.44 | 575202.73 | 513053.3 | 87.42% | 12.58% | 0%
Phoenix Operations | 19040006 | Allstate Tempe | 2019-04-22 | 2019-06-13 | 2000 | 28483 | 0 | 860313.15 | 646017.31 | 406 | 1797.5 | 92.71% | 7.288% | 0%
Wind Energy I Operations | 19141001 | WY Reload Repower Wind | 2019-01-16 | 2019-06-01 | 0 | 201 | 0 | 6142681.54 | 4745100.21 | 11000 | 16249.41 | 80.13% | 19.87% | 0%
Denver Operations | 19060014 | Ardent Mills-Commerce City Br | 2019-03-01 | 2019-05-31 | 0 | 0 | 0 | 3623 | 4740.61 | 0 | 48 | 87.5% | 12.5% | 0%
Denver Operations | 19060004 | SCL-LMC Security Camera Prep | 2019-02-01 | 2019-05-31 | 480 | 806 | 131 | 114074.67 | 115357.82 | 659 | 263 | 89.54% | 10.46% | 0%
Denver Operations | 19060017 | Mile High United Way Tenant | 2019-04-01 | 2019-05-31 | 2600 | 4774 | 0 | 188595.302 | 189569.48 | 1939.9 | 493 | 94.73% | 5.274% | 0%
Mortenson Energy Services-Operations | 19157016 | Horse Hollow Main Bearing Rep | 2019-05-21 | 2019-05-25 | 0 | 0 | 0 | 46562 | 41408.2 | 320 | 698 | 67.62% | 32.38% | 0%
Denver Operations | 19060006 | MillerCoors-Condenser Pads | 2019-01-18 | 2019-05-13 | 282 | 3 | 0 | 72800.3 | 54854.86 | 255 | 468 | 95.94% | 4.06% | 0%
Denver Operations | 19060008 | SCL-SJH Cancer Center Pharmacy | 2019-01-21 | 2019-05-01 | 0 | 23 | 60 | 11602.45 | 17612.03 | 59 | 67 | 94.03% | 5.97% | 0%
Milwaukee Operations | 19080002 | Fiserv Forum New Signage Work | 2019-01-21 | 2019-05-01 | 0 | 399 | 0 | 2844848.48 | 2925976.3 | 255 | 244 | 85.04% | 14.96% | 0%
Minneapolis Operations | 19030005 | Target Corp - BlmngtonT-0005 | 2019-01-01 | 2019-05-01 | 0 | 3756 | 0 | 2066049.02 | 2040417.6 | 2008 | 2377 | 96.68% | 3.324% | 0%
Minneapolis Operations | 19030006 | Target Corp - CottGroveT-0062 | 2019-02-01 | 2019-05-01 | 0 | 1607 | 0 | 1299715.91 | 1323654.94 | 906 | 2176.5 | 96.67% | 3.331% | 0%
Minneapolis Operations | 19030014 | Fairview-MB236 & MB241 | 2019-02-04 | 2019-04-30 | 0 | 1 | 0 | 22446.11 | 23268.41 | 93.5 | 88.5 | 100% | 0% | 0%
Phoenix Operations | 19040001 | Allstate Chandler Bldg 5 | 2019-02-01 | 2019-04-30 | 118953 | 0 | 0 | 2052182.52 | 2109691.89 | 16 | 2070 | 92.71% | 7.295% | 0%
Minneapolis Operations | 19030011 | Allina-Cambridge USP-800 Ph | 2018-11-19 | 2019-04-12 | 950 | 0 | 0 | 465273.48 | 438167.06 | 1919 | 2242.5 | 93.71% | 6.288% | 0%
Minneapolis Operations | 19030004 | NS VI-ThyssenKrupp TI | 2019-01-14 | 2019-04-01 | 23938 | 0 | 0 | 1153212.51 | 1091074.17 | 1169 | 1360.5 | 99.08% | 0.9188% | 0%
Minneapolis Operations | 19030009 | ANW-Curtainwall | 2018-12-26 | 2019-03-15 | 0 | 162 | 0 | 153627 | 124661.48 | 90 | 60 | 96.67% | 3.333% | 0%
Minneapolis Operations | 19030018 | MPR-Fitzgerald Satellite | 2019-02-01 | 2019-02-08 | 0 | 0 | 0 | 248246.7 | 248183.54 | 1491.12 | 1509.12 | 99.17% | 0.8283% | 0%
Denver Operations | 19060005 | Molson Coors-Keenesburg Energy | 2019-01-01 | 2019-02-01 | 0 | 0 | 0 | 15000 | 723.88
Minneapolis Operations | 19030003 | Cresa Minneapolis Inc-CresaTI | 2018-12-18 | 2019-01-30 | 1500 | 0 | 0 | 57490.57 | 58670.45 | 120 | 122.67 | 100% | 0% | 0%
Chicago Operations | 19090008 | AHC-AMC Sheboygan Wall Panels |  |  | 0 | 211476 | 27223 | 2849752.81 | 3198251.8 | 5076.8 | 3165.93 | 92.48% | 7.028% | 0.4896%
Chicago Operations | 19090009 | Sheboygan Wall Panels Install |  |  | 0 | 36357 | 68749 | -1.1096e-10 | -2.0009e-11 | 10940.2 | 16207.5 | 96.03% | 3.97% | 0%
Chicago Operations | 19090010 | RRU 134-Robbins Biorefinery |  |  | 0 | 2 | 0 | 99206 | 92121.42
Chicago Operations | 19090013 | QTS - South DH Munters Install |  |  | 0 | 939 | 4 | 852998.52 | 800318.26 | 716.4 | 618 | 98.38% | 1.618% | 0%
Chicago Operations | 19090016 | Ascent - Project Consulting |  |  | 0 | 0 | 0 | 171600 | 170759.62
Chicago Operations | 19090018 | SAIC - 25 E Washington |  |  | 0 | 0 | 0 | 133111 | 116203.75
Chicago Operations | 19090017 | Allstate - Drift |  |  | 1500 | 0 | 0 | 10644 | 8364.5 | 0 | 97 | 56.7% | 43.3% | 0%
Chicago Operations | 19090019 | Lurie - Pharmacy 7-18 |  |  | 2500 | 14989.54 | 2 | 3529523 | 3326029.69 | 12548.01 | 4826.5 | 85.79% | 9.531% | 4.682%
Chicago Operations | 19090006 | COD Gallery Addition |  |  | 3000 | 9253.09 | 8 | 2426682.7 | 2368572.29 | 1991.5 | 2052.18 | 96.13% | 3.484% | 0.3898%
Chicago Operations | 19090005 | Mercy Riverside Misc. |  |  | 5000 | 131 | 72 | 406575.337 | 383782.71 | 586.2 | 367 | 73.57% | 17.71% | 8.719%
Chicago Operations | 19090004 | Mercy Riverside MPUS |  |  | 5500 | 48241.31 | 26084 | 2037118.27 | 1982613.9 | 1256.8 | 2064.82 | 94.62% | 4.94% | 0.4359%
Chicago Operations | 19090021 | Mercy Rockton - GI Suite Reno |  |  | 12381 | 35410 | 3530 | 2497110.18 | 2505412.74 | 1717.1 | 2046.81 | 85.25% | 13.14% | 1.612%
Chicago Operations | 19090020 | QTS - DH2W B1 C3 |  |  | 42500 | 1717 | 2302 | 9548207.72 | 9409335.95 | 1600 | 2740.5 | 93.6% | 6.076% | 0.3284%
Chicago Operations | 19090014 | MDI-Ann Arbor Campus Hotel |  |  | 85000 | 0 | 0 | 0 | 187322.42
Chicago Operations | 19090011 | Madison HGI Light Gauge Panels |  |  | 104936 | 214844.94 | 131435 | 2306347.36 | 2932267.06 | 5690.9 | 6988.48 | 93.81% | 6.146% | 0.04293%
Chicago Operations | 19090012 | HGI Light Gauge Panels Install |  |  | 104936 | 171678 | 32341 | -3.8654e-11 | 6.0027e-11 | 3679.6 | 5322.5 | 90.22% | 9.46% | 0.3194%
Chicago Operations | 19090007 | Ferrero - Master Plan |  |  | 150000 | 15746.66 | 0 | 7654407.12 | 7392185.3 | 937.6 | 1144.5 | 76.71% | 18.17% | 5.111%
Chicago Operations | 19090015 | PGA-Four Winds Casino & Hotel |  |  | 417771 | 240 | 0 | 5212945.88 | 5075152.99 | 477 | 2452.21 | 96.55% | 2.936% | 0.5097%
Civil Group Operations | 19148002 | Clear Creek Civil (Wind) | 2019-02-06 |  | 0 | 4391454 | 2622299 | 33188179.1627 | 42113777.16 | 111697 | 182761.21 | 73% | 27% | 0%
Civil Group Operations | 19148003 | Crane I Civil (Solar) | 2019-01-17 |  | 0 | 3571657.5 | 175626 | 4252755.05 | 4465275.6 | 8433.46 | 13635 | 79.07% | 20.93% | 0%
Civil Group Operations | 19148004 | Wilkinson Civil (Solar) | 2019-04-29 |  | 0 | 38432 | 14895 | 3482590.0852 | 3424152.57 | 20410 | 10501.5 | 83.16% | 16.84% | 0%
Civil Group Operations | 19148005 | Bonilla Station Civil |  |  | 0 | 221 | 233235 | 2791834.76 | 2360231.11 | 5301 | 4462.5 | 73.4% | 26.6% | 0%
Civil Group Operations | 19148006 | Ida Grove II Civil (Wind) | 2019-04-01 |  | 0 | 972269.07 | 446908 | 18927419.2938 | 15542005.28 | 54907.9 | 55336.55 | 65.93% | 33.74% | 0.328%
Civil Group Operations | 19148007 | Trenton Solar - Civil | 2019-05-13 |  | 0 | 343038 | 228949 | 2962056.36 | 3849081.44 | 8700 | 15684.5 | 74.01% | 25.99% | 0%
Civil Group Operations | 19148008 | Columbia Civil (Solar) |  |  | 0 | 4637340.1 | 243642 | 2662128.23 | 2841052.85 | 7521.54 | 9857.5 | 70.65% | 29.35% | 0%
Civil Group Operations | 19148009 | Arbor Hill 2019 Civil (Wind) | 2019-08-01 |  | 0 | 3368353.08 | 111885 | 4986903.265 | 4630267.23 | 10299.52 | 16313.25 | 64.24% | 35.07% | 0.6927%
Civil Group Operations | 19148010 | Grazing Yak Civil (Solar) |  |  | 0 | 204 | 0 | 1955558 | 2305865.8
Civil Group Operations | 19148011 | Diamond Trail Civil (Wind) | 2019-08-05 |  | 0 | 1383924.84 | 1264255 | 18281953.5865 | 15978016.44 | 62591.93 | 56563.25 | 71.54% | 28.35% | 0.1149%
Civil Group Operations | 19148012 | Cheyenne Ridge Civil (Wind) | 2019-05-15 |  | 0 | 21109936 | 2277818 | 23474911.49 | 22207298.18 | 75085.97 | 85991.3 | 77.99% | 22.01% | 0%
Civil Group Operations | 19148013 | El Campo Civil (Wind) |  |  | 0 | 4249894.62 | 588432 | 9444392.03 | 9720547.16 | 25019.89 | 34301 | 83.72% | 16.28% | 0%
Civil Group Operations | 19148014 | Walnut Repower Civil (Wind) |  |  | 0 | 18 | 332 | 2892275.6762 | 2620479.13 | 8781.5 | 10596.5 | 71.56% | 27.84% | 0.604%
Civil Group Operations | 19148015 | Nobles 2 Civil (Wind) |  |  | 0 | 8637346.4 | 427473 | 17304386.3863 | 16660011.6 | 51795.66 | 52665.5 | 73.29% | 26.22% | 0.4937%
Civil Group Operations | 19148016 | Bitter Ridge Civil (Wind) |  |  | 0 | 11162343.5 | 384947 | 8400240.08 | 9279446.39 | 24062.36 | 32396 | 71.69% | 27.66% | 0.6482%
Civil Group Operations | 19148017 | King Plains Civil (Wind) |  |  | 0 | 10888027.5 | 848653 | 14437586.78 | 15316114.49 | 49066.96 | 63163.5 | 78.27% | 21.7% | 0.03008%
Civil Group Operations | 19148018 | Grissom Substation (HVT) |  |  | 0 | 1802226.29 | 80903 | 2592359.9 | 1894648.1 | 4597.38 | 3629.5 | 76.61% | 23.39% | 0%
Civil Group Operations | 19148019 | North Fork Ridge Civil (Wind) |  |  | 0 | 8210413.73 | 762585 | 15784736.3823 | 15801231.22 | 309803.17 | 59101 | 75.3% | 24.7% | 0%
Civil Group Operations | 19148020 | Kings Point Civil (Wind) |  |  | 0 | 8532717.01 | 823078 | 21588398.95 | 23413752.64 | 38771.59 | 75690.5 | 76.36% | 23.64% | 0%
Civil Group Operations | 19148021 | White Hills Civil (Wind) |  |  | 0 | 21890510.48 | 2247818 | 27405427.8275 | 24318731.28 | 96819.04 | 87808.5 | 75.62% | 24.38% | 0%
Civil Group Operations | 19148022 | Pryor Mountain Civil (Wind) |  |  | 0 | 13458843 | 778195 | 13599567.9588 | 10654932.28 | 41765.19 | 35023 | 82.58% | 17.42% | 0%
Civil Group Operations | 19148023 | Prairie Hill Civil (Wind) |  |  | 0 | 16746899.12 | 671061 | 21318623.6099 | 19444651.66 | 74529.58 | 80578.56 | 80.44% | 19.56% | 0%
Civil Group Operations | 19148024 | Greasewood Civil (Solar) |  |  | 0 | 5489583.55 | 288275 | 6009647.83 | 5960952.76 | 22185.37 | 17485.5 | 78.91% | 21.09% | 0%
Civil Group Operations | 19148025 | Blazing Star II Civil (Wind) |  |  | 0 | 9426201 | 990054 | 16668060.55 | 17159729.9 | 50183.39 | 61737.1 | 75.46% | 24.42% | 0.1182%
Data Center Operations | 19126001 | Facebook EAG 3 |  |  | 450000 | 1558763 | 465739.4 | 371701186.5858 | 343485684.59 | 226102.38 | 202813.27 | 83.51% | 16.49% | 0.002465%
Denver Operations | 19060033 | City of CO Spg-Garden of Gods | 2019-06-01 |  | 0 | 680666 | 538230 | 7678608.05 | 9922862.33 | 30212 | 33318.25 | 73.36% | 26.64% | 0%
Denver Operations | 19060036 | MillerCoors-CBU Floor Penetrat | 2019-05-28 |  | 0 | 680 | 1698 | 379634.9519 | 363623.85 | 2431 | 2033 | 88.34% | 11.66% | 0%
Denver Operations | 19060039 | Charles Schwab P3 Parking |  |  | 0 | 0 | 0 | 993427.08 | 1006897.9
Denver Operations | 19060040 | SCL-SJB Exhaust Fans |  |  | 0 | 0 | 0 | 288787.56 | 292278.41
Denver Operations | 19060041 | SCL-SJB Laundry HVAC Upgrades |  |  | 0 | 0 | 0 | 1250487.21 | 1203634.48
Denver Operations | 19060042 | SCL-SJB Window Repl/Bldg Envel |  |  | 0 | 0 | 0 | 258288.13 | 218163.75
Denver Operations | 19060043 | SCL-SJB MPOP/CPOP Upgrades |  |  | 0 | 0 | 0 | 1056671.35 | 1052695.36
Denver Operations | 19060044 | SCL-SJB Life Safety Deficiency |  |  | 0 | 0 | 0 | 449931 | 434233.29 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 19060050 | NJH-Non MDI COH |  |  | 0 | 0 | 212 | 682334 | 553999.53 | 0 | 926.5 | 66.32% | 33.68% | 0%
Denver Operations | 19060052 | SCL-SJH MPOP UPS |  |  | 0 | 7634.3 | 48 | 194753.43 | 195313.34 | 547.3 | 837 | 91.76% | 8.244% | 0%
Denver Operations | 19060057 | Park Creek-Filing 59 |  |  | 0 | 150 | 0 | 196358 | 224627.26 | 190 | 1005.5 | 96.92% | 3.083% | 0%
Denver Operations | 19060058 | Stadium Mgmt-Light Pole Work |  |  | 0 | 0 | 0 | 155451 | 136983.91 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 19060059 | MillerCoors RMCC Bldg 33 Concr |  |  | 0 | 16 | 897 | 117912 | 104174.05 | 1068 | 991.5 | 86.74% | 13.26% | 0%
Denver Operations | 19060034 | SCL-LMC Sewer Line Repl |  |  | 100 | 726 | 38 | 47971.89 | 55450.63 | 386 | 915 | 93.83% | 6.175% | 0%
Denver Operations | 19060051 | SCL-LMC CT Equipment |  |  | 336 | 571 | 0 | 87336.73 | 87174.88 | 284 | 11.5 | 100% | 0% | 0%
Denver Operations | 19060070 | SCL SJH SPD Sonic Irrigator |  |  | 500 | 20 | 29 | 44534.96 | 45402.4 | 14 | 446.5 | 94.4% | 5.599% | 0%
Denver Operations | 19060071 | SCL-SJH Pharmacy Workstations |  |  | 500 | 415.4 | 3 | 7377.48 | 8906.69 | 108 | 135.5 | 80.81% | 19.19% | 0%
Denver Operations | 19060028 | NJH-NucMed Spect/CT Repl |  |  | 504 | 645 | 485 | 139267 | 137480.09 | 496 | 580 | 83.19% | 16.81% | 0%
Denver Operations | 19060062 | Lockheed Martin-ADM Restrm |  |  | 550 | 1186.2 | 0 | 188217.95 | 195479.25 | 577.2 | 681.5 | 92.44% | 7.557% | 0%
Denver Operations | 19060060 | SCL-SJH Mammography Reno |  |  | 600 | 40 | 0 | 10084.04 | 11550 | 24 | 11 | 81.82% | 18.18% | 0%
Denver Operations | 19060021 | NJH-Boiler Replacement |  |  | 676 | 208 | 966 | 545405.22 | 534210.78 | 1093 | 1144 | 89.25% | 10.75% | 0%
Denver Operations | 19060064 | NJH Tunnel Washer |  |  | 1000 | 518 | 316 | 107239 | 107688.91 | 469 | 377 | 70.03% | 29.97% | 0%
Denver Operations | 19060037 | SCL-SJH LinAcc Remodel | 2019-06-11 |  | 1240 | 10344.5 | 733 | 1119652.13 | 1143292.4 | 3602.9 | 4558 | 82.62% | 17.38% | 0%
Denver Operations | 19060045 | SCL SJH Spec CT Replacement |  |  | 1240 | 6374.75 | 197 | 645233.33 | 647319.16 | 1962.25 | 2495 | 80.26% | 19.74% | 0%
Denver Operations | 19060049 | SCL-MG Wellmore Decommiss |  |  | 1240 | 0 | 17 | 31708.98 | 29552.42 | 90 | 62.5 | 84.8% | 15.2% | 0%
Denver Operations | 19060066 | NJH - USP800 |  |  | 1500 | 102 | 8 | 163741.01 | 158065.27 | 250 | 223.5 | 74.94% | 25.06% | 0%
Denver Operations | 19060047 | Lockheed-FAC Chem Lab |  |  | 2964 | 14104 | 0 | 7378488.554 | 7798534.7 | 2692.7 | 6669.5 | 87.52% | 12.48% | 0%
Denver Operations | 19060067 | SCL-LMC Temp Conference Space |  |  | 4500 | 1643 | 0 | 263938.35 | 271346.75 | 294 | 297 | 96.63% | 3.367% | 0%
Denver Operations | 19060054 | Childrens Hospital-Tejon UC |  |  | 10000 | 18 | 0 | 630303.94 | 722041.46 | 0 | 382.5 | 96.86% | 3.137% | 0%
Denver Operations | 19060053 | Childrens Hosp-Briargate MOB |  |  | 12000 | 19270.9 | 813.01 | 2872294.45 | 3035264.14 | 3434.4 | 5341 | 86.79% | 13.21% | 0%
Denver Operations | 19060046 | Dominican Friars-St Dominic |  |  | 24761 | 83036.51 | 33978 | 6724028.6001 | 7057229.1 | 7715 | 13973.75 | 93.33% | 6.668% | 0%
Denver Operations | 19060068 | FireFly-Hoyt School Renova |  |  | 30000 | 87525.86 | 68225 | 2344338.0664 | 2235089.69 | 2546.23 | 5471 | 92.33% | 7.668% | 0%
Denver Operations | 19060055 | Children's Hosp-Telstar MOB |  |  | 30001 | 7 | 0 | 35811.53 | 87131.89
Denver Operations | 19060065 | Clayton ELC Bldg 3506 Office |  |  | 35000 | 20486.98 | 8745 | 447251.4 | 453264.77 | 681.76 | 785 | 98.22% | 1.783% | 0%
Denver Operations | 19060063 | Stoltz-Denver Renovations |  |  | 37945 | 42205.76 | 32930 | 1359904.93 | 1371069.51 | 1347.37 | 3804.5 | 96.89% | 3.115% | 0%
Denver Operations | 19060035 | MIC-Buckley AFB Doc Dest Fac | 2019-06-03 |  | 50000 | 45194.23 | 6095 | 408984.1836 | 592613.79 | 1992.6 | 6347.25 | 90.46% | 9.536% | 0%
Denver Operations | 19060061 | WelArm-EG Glenarm Retail |  |  | 50000 | 274 | 20 | 3746503.24 | 3779296.61 | 141 | 506 | 91.8% | 8.202% | 0%
Denver Operations | 19060032 | MDI-Bio3 Parking Garage | 2019-05-13 |  | 153000 | 805066.67 | 504514 | 9328049.1802 | 9525803.24 | 31067.3 | 39861.5 | 90.6% | 9.399% | 0%
Denver Operations | 19060072 | Wiens-8383 Arista Place |  |  | 194000 | 0 | 0 | 117753 | 107949.02
Denver Operations | 19060048 | 76 Commerce Bldg 4 |  |  | 352240 | 413792.08 | 274634 | 23041045.9973 | 21329306.63 | 10977.74 | 15396 | 92.17% | 7.833% | 0%
Denver Operations | 19060069 | Wewatta-Dwntwn Denver Marriott |  |  | 433858 | 3008 | 0 | 505079.7 | 543292.25 | 0 | 129.5 | 100% | 0% | 0%
Denver Operations | 19060056 | 76 Commerce Bldg 3 |  |  | 526400 | 407978.68 | 385712 | 27867060.6733 | 25199542.43 | 18696.82 | 21154.5 | 84.04% | 15.96% | 0%
FCG Operations | 19110010 | ECB Elevator Inspection |  |  | 0 | 31 | 0 | 559684.13 | 539831.79 | 720 | 499 | 96.19% | 3.808% | 0%
FCG Operations | 19110012 | 21ST BDE HEMP - VA |  |  | 0 | 0 | 0 | 534882.45 | 533882.49
FCG Operations | 19110013 | 21ST BDE HEMP - PA |  |  | 0 | 0 | 0 | 476396 | 474224.18
FCG Operations | 19110014 | 21ST BDE HEMP - MD |  |  | 0 | 0 | 0 | 175944 | 175192.86
FCG Operations | 19110006 | UDC Turtle Power |  |  | 1000 | 0 | 0 | 29756 | 25057.29
FCG Operations | 19110008 | UDC HVAC Replacements |  |  | 1000 | 0 | 0 | 1695708.01 | 1713953.87
FCG Operations | 19110002 | UDC Mystic Potions 3 | 2019-01-22 |  | 2000 | 0 | 0 | 480502.98 | 476462.67
FCG Operations | 19110015 | UDC Typhoon Vortex |  |  | 2000 | 0 | 0 | 30740 | 30685.87
FCG Operations | 19110007 | Sugar Grove Research Station |  |  | 3200 | 0 | 0 | 9533937.67 | 8969127.07 | 0 | 6562.8 | 96.52% | 3.482% | 0%
FCG Operations | 19110016 | UDC Silvermind |  |  | 4000 | 0 | 0 | 2088584.92 | 2090174.68
FCG Operations | 19110009 | Bldg 3245 Cages |  |  | 8000 | 1069 | 0 | 1712771.19 | 1715331.6
FCG Operations | 19110011 | BAO Bldg 13 Renovation |  |  | 8820 | 0 | 0 | 1519681.85 | 1552119.32
FCG Operations | 19110005 | Chiller Plant Building 9706 |  |  | 13800 | 0 | 0 | 11647008.7092 | 11323043.26 | 0 | 204.38 | 100% | 0% | 0%
FCG Operations | 19110004 | SAB4 Renovation | 2019-07-23 |  | 19667 | 0 | 0 | 6368367.24 | 6163361.79
MAK-DAS | 19150002-LOW | St Louis MLS - SPW Low Voltage |  |  | 0 | 0 | 0 | 19543600 | 0
MAK-Earthwork | 19150002-ETH | St Louis MLS - SPW Earthwork |  |  | 0 | 0 | 0 | 72185058 | 0
MAK-Steel | 19150002-STE | St Louis MLS - SPW Steel |  |  | 0 | 0 | 0 | 58633641 | 0
Milwaukee Operations | 19080005 | 2019 Master Agmt Fiserv Forum | 2019-04-24 |  | 0 | -629 | 0 | 134814 | 133707.23 | 222 | 284 | 99.65% | 0.3521% | 0%
Milwaukee Operations | 19080013 | AAH Misc Jobs 2019-2020 |  |  | 500 | 139 | 0 | 543664 | 474232.58 | 889 | 1050.5 | 87.39% | 12.61% | 0%
Milwaukee Operations | 19080007 | Intel 360 Cameras |  |  | 3000 | 0 | 0 | 780332.76 | 752558.71 | 336 | 320.5 | 97.82% | 2.184% | 0%
Milwaukee Operations | 19080014 | AHC Grafton Medical Obs |  |  | 6060 | 14731.43 | 5459 | 665251.35 | 655560.2 | 1364.4 | 1616.96 | 87.88% | 11.26% | 0.8658%
Milwaukee Operations | 19080001 | Froedtert - Loading Dock Reno | 2019-08-19 |  | 11500 | 59108.29 | 29143 | 2411723.6 | 2442581.47 | 4503.7 | 5281 | 91.92% | 7.697% | 0.3787%
Milwaukee Operations | 19080012 | Fii HPC DC |  |  | 28000 | 379095.06 | 201052 | 30104819.1441 | 28841788.63 | 25501.13 | 22997.89 | 92.44% | 7.226% | 0.3305%
Milwaukee Operations | 19080006 | WEC - Master Planning |  |  | 30000 | 798 | 0 | 389652.51 | 432638.98
Milwaukee Operations | 19080011 | NM Data Center Mod |  |  | 31600 | 116775.18 | 4461 | 25850702.64 | 24448211.59 | 7086.7 | 5946.44 | 94.24% | 5.608% | 0.1514%
Milwaukee Operations | 19080008 | UHS/West Allis - Psych Hosp. |  |  | 78000 | 932338.65 | 480130 | 33721466.0641 | 33553251.03 | 31572.55 | 37454.76 | 94.71% | 5.221% | 0.07342%
Milwaukee Operations | 19080009 | Fii SMC |  |  | 290023 | 272800.48 | 84647 | 54236408.285 | 50134415.87 | 22824.2 | 18407.32 | 93.01% | 6.962% | 0.0326%
Milwaukee Operations | 19080010 | UW Health ECD |  |  | 440000 | 1754202.8 | 0 | 22381147.4609 | 7482637.39 | 51528.25 | 6140.75 | 92.86% | 7.137% | 0%
Milwaukee Operations | 19080010-142 | UW Health ECD-JV |  |  | 440000 | 3257817.75 | 0 | 247499802.01 | 54945585.08 | 179963.65 | 34311.75 | 93.14% | 6.86% | 0%
Minneapolis Operations | 19030020 | Fairview-M246 2FL Pharm Mech |  |  | 0 | 1 | 0 | 580589.39 | 570438.74 | 1008 | 972.25 | 97.81% | 2.186% | 0%
Minneapolis Operations | 19030032 | Colwell Partners -Glenwd Site |  |  | 0 | 1685.44 | 7744 | 154428.93 | 198867.86 | 1057 | 1480 | 98.89% | 1.115% | 0%
Minneapolis Operations | 19030033 | 30 Group - YMCA Demolition |  |  | 0 | 5936.3 | 46463 | 2375901.465 | 2599923.32 | 8021.85 | 20326.5 | 97.24% | 2.755% | 0%
Minneapolis Operations | 19030044 | City of Mpls - NPSB Carpentry |  |  | 0 | 162516.5 | 71645 | 6114883.93 | 6212186.02 | 27906.8 | 19935 | 96.95% | 3.055% | 0%
Minneapolis Operations | 19030054 | FUMC -UMMC WB EB M2722 Rad RM3 |  |  | 0 | 0 | 0 | 79746.31 | 80222.53 | 0 | 197 | 99.75% | 0.2538% | 0%
Minneapolis Operations | 19030055 | MAM - Kimball Misc 2019 |  |  | 0 | 0 | 0 | 0.01 | 1727.08
Minneapolis Operations | 19030056 | WFPS - Heritage MS Consultant |  |  | 0 | 0 | 0 | 9858 | 7910.64
Minneapolis Operations | 19030062 | Transamerica 6910 Bollard Proj |  |  | 0 | 0 | 0 | 142152.87 | 112400.96 | 348 | 126 | 100% | 0% | 0%
Minneapolis Operations | 19030063 | Target Field Scoreboard 2.0 DP |  |  | 0 | 13194 | 0 | 25268403.42 | 15722369.4 | 3796 | 3315 | 99.88% | 0.1207% | 0%
Minneapolis Operations | 19030064 | FUMC -UMMC Unit-J Nurse Call |  |  | 0 | 3 | 0 | 163426.34 | 137844.43 | 6662 | 516 | 94.96% | 5.039% | 0%
Minneapolis Operations | 19030066 | Fairview-WB InPatient PhrmM246 |  |  | 0 | 199 | 0 | 51803.62 | 49823.46 | 199 | 175.5 | 82.91% | 10.26% | 6.838%
Minneapolis Operations | 19030067 | Fairview -1 FL Bridging Clinic |  |  | 0 | 0 | 0 | 174525.475 | 187272.2 | 473.5 | 469 | 99.68% | 0.3198% | 0%
Minneapolis Operations | 19030068 | Fairview -WB Lact MB106 & F190 |  |  | 0 | 0 | 0 | 15421.11 | 14807.12 | 0 | 58 | 100% | 0% | 0%
Minneapolis Operations | 1999 | MORTENSON-CLOSED JOBMINNEAPOL | 2000-12-31 |  | 0 | 0 | 0 | 0 | 327608 | 0 | 1118 | 100% | 0% | 0%
Minneapolis Operations | 19030051 | ANW - ETO Sterilizer Replcmnt |  |  | 150 | -171 | 0 | 263845.4 | 227920.29 | 760 | 529.1 | 71.65% | 28.35% | 0%
Minneapolis Operations | 19030065 | St. Davids -Wall Removal et al |  |  | 400 | 81.3 | 0 | 16010.97 | 23402.08 | 3.5 | 205.5 | 99.76% | 0.2433% | 0%
Minneapolis Operations | 19030043 | SCCR - Site Concrete Repair |  |  | 450 | 100 | 0 | 12264 | 10163.94 | 96 | 87 | 65.52% | 34.48% | 0%
Minneapolis Operations | 19030045 | CentraCare - Master Ag 2019 |  |  | 896 | 0 | 0 | 228629.01 | 189786.27 | 712 | 633.51 | 96.05% | 3.946% | 0%
Minneapolis Operations | 19030030 | Fairview - SBldg PICULight3123 |  |  | 1000 | 0 | 0 | 5144.07 | 2555.54 | 0 | 2 | 100% | 0% | 0%
Minneapolis Operations | 19030060 | Westminster - WPC Bells Tower |  |  | 1000 | 13917.75 | 0 | 338244.75 | 363611.97 | 279 | 444.5 | 88.75% | 5.849% | 5.399%
Minneapolis Operations | 19030025 | ANW Imaging Prep and Recovery | 2019-04-08 |  | 1489 | 12866.73 | 0 | 626547.91 | 594479.42 | 1792 | 2011.91 | 94.68% | 4.97% | 0.3479%
Minneapolis Operations | 19030036 | Blake Black Box Restoration |  |  | 2682 | 2331.5 | 0 | 787037.48 | 806418.83 | 1606 | 2580.12 | 98.26% | 1.744% | 0%
Minneapolis Operations | 19030042 | ES - Suite240 TI - Disc Sq |  |  | 2885 | 2700 | 0 | 773327.59 | 642898.62 | 228 | -2258.56 | 100% | 0% | 0%
Minneapolis Operations | 19030049 | Fairview - M-Health MG LINAC |  |  | 3000 | 447 | 0 | 860803.8 | 851608.72 | 1555 | 1805.5 | 78.7% | 21.3% | 0%
Minneapolis Operations | 19030057 | Graco Koch PO Work |  |  | 3600 | 0 | 143 | 270725.01 | 215908.15 | 752 | 277.5 | 92.79% | 7.207% | 0%
Minneapolis Operations | 19030059 | Target Field 2020 Improvements |  |  | 4300 | 95 | 0 | 656000.81 | 669274.32 | 1939 | 2418 | 99.71% | 0.2895% | 0%
Minneapolis Operations | 19030052 | Fairview-MHealthWB EB 1.5T MRI |  |  | 4371 | 19535.81 | 0 | 1328799.34 | 1313217.8 | 1918.4 | 2076 | 86.73% | 11.68% | 1.59%
Minneapolis Operations | 19030069 | Fairview - UMH FV E 11FL NICU |  |  | 4531 | 24789 | 0 | 1200437.96 | 1179091.57 | 2101 | 2467.5 | 96.09% | 3.911% | 0%
Minneapolis Operations | 19030034 | Fairview - L4&5 B2512 Nurse |  |  | 5000 | 0 | 0 | 310282.82 | 284135.24 | 1178 | 1072 | 99.58% | 0.4198% | 0%
Minneapolis Operations | 19030048 | Nura PA - Edina 7400 Remodel |  |  | 7600 | 26 | 1367 | 2577737.29 | 2522789.04 | 3431 | 2923.5 | 97.9% | 2.104% | 0%
Minneapolis Operations | 19030041 | UGC - McNamara Alumni TO |  |  | 8000 | 57442 | 24500 | 1436814.4 | 1203465.54 | 5739 | 3875.5 | 96.84% | 3.161% | 0%
Minneapolis Operations | 19030058 | ANW - TAF 3FL HIM Renovation |  |  | 9000 | 49 | 0 | 475310.57 | 433110.94 | 714 | 792.3 | 97.79% | 2.209% | 0%
Minneapolis Operations | 19030035 | UMN Moos 2FL CancerCtr Lab Exp |  |  | 12000 | 37271.98 | 538 | 2563800.62 | 2676798.78 | 1745.8 | 1807.5 | 99.06% | 0.9405% | 0%
Minneapolis Operations | 19030037 | Axalta Coatings Expansion |  |  | 15000 | 0 | 0 | 1835650.57 | 1689610.63 | 1299 | 946 | 95.93% | 4.07% | 0%
Minneapolis Operations | 19030050 | Fabcon - Roof Repair & Modif |  |  | 15500 | 11610 | 2 | 1940696.9956 | 1816438.99 | 2730 | 6404.25 | 84.76% | 11.24% | 3.997%
Minneapolis Operations | 19030061 | NS VII - Laird Plastics TI |  |  | 25475 | 0 | 0 | 824534.07 | 710092.68 | 769 | 629.5 | 94.6% | 5.401% | 0%
Minneapolis Operations | 19030019 | Marvin Windows Corp Office Ren | 2019-03-25 |  | 30000 | 465679.69 | 255850 | 29126742.19 | 23708234.37 | 46461.6 | 37041.5 | 76.22% | 23.7% | 0.08369%
Minneapolis Operations | 19030046 | NS V - Heraeus Medical TI |  |  | 62257 | 0 | 0 | 3865381.46 | 3901247.53 | 4393 | 3205 | 94.4% | 5.351% | 0.2496%
Minneapolis Operations | 19030053 | Ramsey - Vadnais Sports Turf |  |  | 80000 | 140914.33 | 18252 | 7816003.71 | 7816377.5 | 3763.5 | -4472.5 | 101.1% | -1.118% | 0%
Minneapolis Operations | 19030031 | Sanford - Ortho Clinic Relo |  |  | 81685 | 166138.73 | 162096 | 18068311.0773 | 18541618.88 | 13610.46 | 18975.03 | 93.84% | 5.731% | 0.4242%
Minneapolis Operations | 19030038 | Target Corp - VadnaisHtsT0751 |  |  | 110000 | 6 | 0 | 1634116.3 | 1624918.81 | 1120 | 1277.5 | 92.72% | 7.28% | 0%
Minneapolis Operations | 19030039 | Target Corp - HutchinsonT1210 |  |  | 110000 | 6 | 0 | 1283459.59 | 1260574.12 | 1120 | 1280 | 90.94% | 9.062% | 0%
Minneapolis Operations | 19030040 | Target Corp - Carson CityT1239 |  |  | 110000 | 178 | 0 | 1421806 | 1492455.54 | 800 | 1375 | 96% | 4% | 0%
Minneapolis Operations | 19030047 | BSC - Bldg 2 East Expansion |  |  | 110000 | 840474.7 | 486589 | 41771089.0525 | 42837255.71 | 36681.16 | 39465.5 | 85.62% | 13.42% | 0.9641%
Mortenson Energy Services-Operations | 19157001 | GE 2019 MSA MCE |  |  | 0 | 0 | 0 | 2.08 | 7991830.8 | 0 | 201574.6 | 73.35% | 26.62% | 0.02952%
Mortenson Energy Services-Operations | 19157002 | GE 2019 MCE MSA LS |  |  | 0 | 0 | 0 | 0.01 | 2660552.33 | 0 | 53580.5 | 69.22% | 30.78% | 0%
Mortenson Energy Services-Operations | 19157003 | GE Gen Alignment LS |  |  | 0 | 0 | 0 | 0 | 168095.29 | 0 | 1681 | 88.99% | 11.01% | 0%
Mortenson Energy Services-Operations | 19157004 | GE Mech/Electrical CP |  |  | 0 | 0 | 0 | 0.03 | 5099160.71 | 0 | 115202.5 | 74.81% | 25.19% | 0%
Mortenson Energy Services-Operations | 19157005 | GE Blades 2019 CP |  |  | 0 | 0 | 0 | 0.04 | 2962229.83 | 0 | 68787.52 | 84.99% | 15.01% | 0%
Mortenson Energy Services-Operations | 19157006 | GE Blades 2019 LS |  |  | 0 | 0 | 0 | 57637.01 | 24483.74 | 272 | 273 | 87.91% | 12.09% | 0%
Mortenson Energy Services-Operations | 19157007 | Mortenson Repower |  |  | 0 | 0 | 0 | 0.02 | 614524.73 | 0 | 13468 | 75.74% | 23.93% | 0.3267%
Mortenson Energy Services-Operations | 19157008 | FPL No Co Pitch Cylinder RE |  |  | 0 | 0 | 0 | 0 | 20953.12 | 0 | 262.5 | 62.1% | 37.9% | 0%
Mortenson Energy Services-Operations | 19157009 | BLUEarth A&D Wind Farm 2019 |  |  | 0 | 0 | 0 | 0 | 18226.43 | 0 | 530.5 | 72.67% | 27.33% | 0%
Mortenson Energy Services-Operations | 19157010 | Ewington Due Diligence Walk D |  |  | 0 | 0 | 0 | 0 | 9369.28 | 0 | 182 | 92.31% | 7.692% | 0%
Mortenson Energy Services-Operations | 19157011 | Nextera-No Co Main Shaft Rep |  |  | 0 | 0 | 0 | 0 | 74537.97 | 0 | 704.5 | 63.59% | 36.41% | 0%
Mortenson Energy Services-Operations | 19157012 | GE Casa Mesa Wind Demolition | 2019-04-15 |  | 0 | 0 | 0 | 433132.0001 | 246774.49 | 2043 | 1377 | 69.86% | 30.14% | 0%
Mortenson Energy Services-Operations | 19157013 | Rim Rock Wind Farm Decomm |  |  | 0 | 0 | 0 | 0 | 75334.56 | 0 | 835 | 61.8% | 38.2% | 0%
Mortenson Energy Services-Operations | 19157014 | OG&E MISC SERVICES |  |  | 0 | 0 | 0 | 0.02 | 545867.54 | 0 | 9657 | 72.9% | 27.1% | 0%
Mortenson Energy Services-Operations | 19157015 | Geronimo Nordic 1 SWPPP Mon |  |  | 0 | 0 | 0 | 0.01 | 42347.7 | 0 | 317.5 | 88.35% | 11.65% | 0%
Mortenson Energy Services-Operations | 19157017 | Chisolm View II Wind Farm Demo |  |  | 0 | 0 | 0 | 377875 | 233003.86 | 1320 | 1461.5 | 69.14% | 30.86% | 0%
Mortenson Energy Services-Operations | 19157018 | GE Garden City Hub Stiffeners |  |  | 0 | 267 | 0 | 688095.02 | 705412.53 | 4145 | 7516.5 | 64.08% | 34.2% | 1.716%
Mortenson Energy Services-Operations | 19157019 | Sungrow Commissioning Support |  |  | 0 | 0 | 0 | 0.02 | 308799.81 | 0 | 6458 | 86.24% | 13.76% | 0%
Mortenson Energy Services-Operations | 19157020 | GE Upstream T-57 Tower Demo |  |  | 0 | 0 | 0 | 374529 | 211178.28 | 1320 | 1806.5 | 64.82% | 35.18% | 0%
Mortenson Energy Services-Operations | 19157021 | Stockyard Due Diligence Inspec |  |  | 0 | 0 | 0 | 0.01 | 34183.95 | 0 | 501 | 79.54% | 20.46% | 0%
Mortenson Energy Services-Operations | 19157022 | GE Bolt Tensioning LS |  |  | 0 | 180 | 0 | 243336 | 280097.87 | 1920 | 5313 | 80.68% | 19.32% | 0%
Mortenson Energy Services-Operations | 19157997 | Direct Overhead SC |  |  | 0 | 0 | 0 | 0.05 | 21723481.54 | 0 | 109617.92 | 93.93% | 6.072% | 0%
Mortenson Engineering Services Operations | 19156001 | Engineering Svs Direct Costs |  |  | 0 | 0 | 0 | 42.78 | 15465646.54
Phoenix Operations | 19040003 | Chandler Office Remodel | 2019-01-14 |  | 0 | 0 | 0 | 0 | 0
Phoenix Operations | 19040011 | MDI - Hyatt DT - FFE |  |  | 0 | 0 | 0 | 4140860.49 | 4118145.06
Phoenix Operations | 19040015 | SRF Patio Bars |  |  | 0 | 9376.35 | 9204 | 169215.44 | 191138.5 | 495.34 | 804.5 | 75.08% | 24.92% | 0%
Phoenix Operations | 19040010 | White Sox Expansion |  |  | 9132 | 51744 | 28065 | 3012194.3 | 2951514.39 | 378 | 469.5 | 94.68% | 5.325% | 0%
Phoenix Operations | 19040013 | Clarence Wesley Health Center |  |  | 19325 | 0 | 0 | 19337.28 | 23241.98 | 0 | 35 | 0% | 100% | 0%
Phoenix Operations | 19040014 | Allstate InfoArmor 2 |  |  | 24000 | 132338 | 132323 | 290311.7 | 290311.7 | 1649.9 | 1031 | 84.48% | 15.52% | 0%
Phoenix Operations | 19040009 | Allstate - InfoArmor TI |  |  | 36805 | 39277 | 0 | 4780233.33 | 4483800.27 | 252.7 | 2734.5 | 76.91% | 23.09% | 0%
Phoenix Operations | 19040005 | Alaska USA GDC TI | 2019-05-13 |  | 60000 | 15134 | 0 | 675373.22 | 676989.95 | 325 | 198 | 56.57% | 43.43% | 0%
Phoenix Operations | 19040008 | MDI Hyatt Place - Downtn PHX |  |  | 111885 | 411681 | 0 | 38511301.04 | 37409173.78 | 7402.7 | 9248.5 | 92.18% | 7.817% | 0%
Phoenix Operations | 19040012 | SRP ISB Modernization Precon |  |  | 303902 | 0 | 0 | 101391.28 | 51871.39
Phoenix Operations | 19040007 | Nike - Project 40 |  |  | 900000 | 317062.18 | 140956 | 47303012.5277 | 46727128.65 | 32102.32 | 33376 | 96.94% | 3.056% | 0%
Portland Operations | 19055003 | Mortenson Portland 2nd Flr Exp |  |  | 0 | 0 | 1 | 0.01 | -1.819e-11 | 0 | 1258.5 | 92.65% | 6.397% | 0.9535%
Portland Operations | 19055004 | OHSU Tram Laser Scanning |  |  | 0 | 0 | 0 | 15550.28 | 27085.81
Portland Operations | 19055005 | OHSU Building ReAddressing |  |  | 0 | 0 | 0 | 8478.2 | 26433.69
Portland Operations | 19055006 | OHSU Tuality Block 67 TI |  |  | 0 | 0 | 0 | 9677.63 | 37206.59
Portland Operations | 19055007 | OHSU Modular Bldg/Assoc Moves |  |  | 0 | 0 | 0 | 14025.08 | 19965.18
Portland Operations | 19055008 | Kaiser SST Boiler Replacement |  |  | 0 | 7 | 0 | 38862.7068 | 30814.83
Portland Operations | 19055012 | Adventist Mill Plain Sign |  |  | 0 | 0 | 0 | 8101.13 | 7733.51
Portland Operations | 19055014 | Everett Hotel 14th & Everett |  |  | 0 | 0 | 0 | 0.01 | 99724.76
Portland Operations | 19055015 | PAM Ceiling Emergency |  |  | 0 | 10 | 1917 | 989464.84 | 1000865.51 | 1312 | 1726.07 | 98.96% | 1.043% | 0%
Portland Operations | 19055016 | Metro Schnitzer Concert Hall |  |  | 0 | 66119.54 | 20740 | 7126171.0652 | 7125196.57 | 3135.7 | 4444.22 | 99.71% | 0.2925% | 0%
Portland Operations | 19055021 | Prosper - OCC Off Exp |  |  | 0 | 25 | 0 | 1434196.01 | 1282385.57
Portland Operations | 19055022 | OHSU KPV-6 Controls |  |  | 0 | 0 | 0 | 0.01 | 0
Portland Operations | 19055023 | OHSU Tuality Forest Grove TI |  |  | 0 | 10 | 0 | 2482.32 | 179.99
Portland Operations | 19055025 | LOSD Hallinan Elementary |  |  | 0 | 0 | 0 | 65000 | 75001.66 | 0 | 64 | 100% | 0% | 0%
Portland Operations | 19055027 | JLL Fac Direct Small Works |  |  | 0 | 1 | 3 | 12391 | 9730.81 | 86 | 79.5 | 85.53% | 14.47% | 0%
Portland Operations | 19055028 | OHSU CCSR Study |  |  | 0 | 0 | 0 | 5683.64 | 8390.76
Portland Operations | 19055011 | Kaiser WMC TJC OR |  |  | 500 | 13 | 0 | 18630.335 | 17407.17 | 83.5 | 80 | 75% | 25% | 0%
Portland Operations | 19055024 | Oregon Sport Office TI |  |  | 2200 | 86 | 0 | 217233.4 | 217295.4 | 718 | 671.5 | 94.64% | 3.574% | 1.787%
Portland Operations | 19055018 | OHSU MRB Survivial |  |  | 4000 | 10 | 0 | 2126.33 | 7171.97
Portland Operations | 19055019 | OHSU CDRC Feasibility |  |  | 4000 | 10 | 0 | 14126.88 | 14811.24
Portland Operations | 19055020 | Crane Bldg TI |  |  | 5000 | 16645.57 | 0 | 371528.25 | 396692.18 | 397.5 | 962 | 92.1% | 7.9% | 0%
Portland Operations | 19055009 | Adventist West HV Clinic TI |  |  | 20250 | 7905.27 | 62 | 4349423.72 | 4243450.79 | 3349.08 | 3035 | 91.35% | 6.458% | 2.191%
Portland Operations | 19055017 | Multnomah Behavioral Health |  |  | 27000 | 91099 | 60838 | 18163149.8269 | 19493310.15 | 17511.43 | 25566.5 | 91.83% | 8.109% | 0.05671%
Portland Operations | 19055002 | KYDO Dalles Data Center |  |  | 51000 | 0 | 0 | 25179 | 27381.66
Portland Operations | 19055013 | OHSU CHH-2 I-2 |  |  | 60000 | 0 | 0 | 52803.62 | 98542.34
Portland Operations | 19055026 | MDI - Prov Reeds Crossing |  |  | 118000 | 593794.97 | 324119.72 | 53872853 | 54754503.18 | 30200.08 | 27665.07 | 91.52% | 8.415% | 0.06868%
Portland Operations | 19055001 | Nike Project 40 |  |  | 160000 | 0 | 0 | 91055 | 81532.51
Portland Operations | 19055010 | Nike Dunk |  |  | 210000 | 1023.5 | 0 | 600386 | 510388.04 | 12 | 936 | 100% | 0% | 0%
Power Delivery Solutions Operations | 19146017 | Phoenix Solar - HVT |  |  | 0 | 89785.26 | 93709 | 3522167.78 | 3454142.98 | 3038.54 | 5217 | 94.52% | 5.485% | 0%
Power Delivery Solutions Operations | 19146018 | Solemio Solar - HVT |  |  | 0 | 0 | 0 | 52999 | 11178.86
Power Delivery Solutions Operations | 19146019 | Prairie Hill Wind - HVT |  |  | 0 | 653487 | 668531 | 24893846 | 23496316.8 | 32555 | 38571 | 80.42% | 19.58% | 0%
Power Delivery Solutions Operations | 19146020 | Old Jackson Solar - HVT |  |  | 0 | 0 | 0 | 59383 | 38675.71
Power Delivery Solutions Operations | 19146021 | Greasewood Solar - HVT |  |  | 0 | 163570.06 | 73588 | 8835274.26 | 8637634.57 | 6676.18 | 6264 | 84.9% | 15.1% | 0%
Power Delivery Solutions Operations | 19146022 | North Fork Ridge Wind - HVT |  |  | 0 | 311826 | 33266 | 20111992.78 | 19262952.87 | 13453.23 | 20152.5 | 80.34% | 19.66% | 0%
Power Delivery Solutions Operations | 19146023 | Kings Point Wind - HVT |  |  | 0 | 331030.26 | 100115 | 28358161.48 | 27622693.57 | 14364.59 | 23665 | 84.64% | 15.36% | 0%
Power Delivery Solutions Operations | 19146024 | TG East Wind - Power |  |  | 0 | 198529.33 | 549121 | 18912147.37 | 17766932.1 | 16878.81 | 22964.05 | 88.09% | 11.91% | 0%
Power Delivery Solutions Operations | 19146025 | Liberty 91-0 Line Rebuild |  |  | 0 | 1002 | 2070 | 33138305.36 | 31564205.53 | 14842.42 | 25140.5 | 82.45% | 17.55% | 0%
Seattle Operations | 19050001 | WWU Academic Facility | 2019-07-03 |  | 0 | 1087.02 | 0 | 437069.7 | 425648.34 | 188.14 | 14.5 | 96.55% | 3.448% | 0%
Seattle Operations | 19050002 | 2019/2020 Virtual Insights |  |  | 0 | 0 | 0 | 137465 | 335958.62
Seattle Operations | 19050005 | UW Softball Performance Center |  |  | 0 | 37439 | 27647 | 4247299.99 | 5055867.73 | 2415.5 | 4868.5 | 91.17% | 8.832% | 0%
Seattle Operations | 19050006 | Swedish Edmonds Behavioral |  |  | 0 | 28091.83 | 512 | 2164348.51 | 2182750.8 | 1865.7 | 1430.5 | 92.42% | 7.585% | 0%
Seattle Operations | 19050008 | POS MTLV (MC-0320490/U00159) |  |  | 0 | 63389.44 | 0 | 72755363.94 | 3168457.52 | 15160.9 | 204.5 | 98.29% | 1.711% | 0%
Seattle Operations | 19050009 | KP Everett Specialty Center |  |  | 0 | 1072945.67 | 140650.24 | 96311699.8813 | 28941755.3 | 38701.07 | 26975.6 | 89.17% | 10.62% | 0.2141%
Seattle Operations | 19050010 | Everett CC LRC |  |  | 0 | 251285.87 | 251420.5 | 32289406.89 | 29723115.06 | 14129.1 | 14750.93 | 90.75% | 8.83% | 0.4169%
Seattle Operations | 19050011 | 5th & John Hotel |  |  | 0 | 0 | 0 | 86168.42 | 77314.79
Seattle Operations | 19050012 | Kaiser Yesler Terrace |  |  | 0 | 27 | 0 | 435303.2 | 113067.32
Seattle Operations | 19050050 | KPWA PBO Brand |  |  | 0 | 2516.25 | 0 | 276180.1139 | 263242.9 | 343.83 | 310.14 | 87.91% | 12.09% | 0%
Seattle Operations | 19050051 | KP Master Plan Cost Model |  |  | 0 | 0 | 0 | 17519.65 | 17323.64
Solar and Emerging Renewables Operations | 19145007 | Solemio Solar - Pattern Energy | 2019-10-07 |  | 0 | 764 | 0 | 464146 | 329118.1 | 0 | 136.5 | 87.91% | 12.09% | 0%
Solar and Emerging Renewables Operations | 19145009 | Old Jackson - Pattern Energy |  |  | 0 | 201 | 0 | 175448.3 | 93834.28
Solar and Emerging Renewables Operations | 19145010 | Renegade - Blue Planet |  |  | 0 | 0 | 0 | 120897 | 61128.04
Solar and Emerging Renewables Operations | 19145011 | Texas Solar Nova 1 - Clearway |  |  | 0 | 295 | 0 | 223137 | 216096.36 | 600 | 475.5 | 73.76% | 26.24% | 0%
Solar and Emerging Renewables Operations | 19145012 | Maiden Creek Solar - Duke |  |  | 0 | 3013835.45 | 3396721 | 41010356.88 | 46191290 | 210537.85 | 276050 | 85.55% | 14.45% | 0%
Solar and Emerging Renewables Operations | 19145013 | Alamo 5 - DC Addition |  |  | 0 | 0 | 0 | 82114.98 | 46874.07
Solar and Emerging Renewables Operations | 19145014 | Snipesville I - Silicon Ranch |  |  | 0 | 3279971.59 | 3665057 | 58085762.41 | 63973749.54 | 237783.19 | 307536.68 | 84.84% | 15.16% | 0%
Solar and Emerging Renewables Operations | 19145015 | Santa Fe Solar - Duke Energy |  |  | 0 | 3384092.54 | 2905406 | 52112309.7871 | 47831327.94 | 216933.47 | 165008.5 | 88.9% | 11.1% | 0%
Sports + Entertainment Group Operations | 19150001 | Mortenson/Consigli - NER SS |  |  | 0 | 0 | 0 | 1015000 | 521203.05
Sports + Entertainment Group Operations | 19150002 | MAK - St Louis MLS |  |  | 0 | 0 | 266 | 59960055.21 | 48328399.81 | 0 | 0 | 0% | 0% | 0%
Sports + Entertainment Group Operations | 19150005 | PSU - Holuba Hall Renovations |  |  | 0 | 0 | 0 | 109089 | 14993.57
Sports + Entertainment Group Operations | 19150006 | PSU - Nittany Outdoor Football |  |  | 0 | 0 | 0 | 856815.634 | 792904.98
Sports + Entertainment Group Operations | 19150004 | PSU - Lasch Phase 6 |  |  | 53100 | 675 | 0 | 37200138.7906 | 35488928.49 | 436 | 1052 | 86.69% | 13.31% | 0%
Sports + Entertainment Group Operations | 19150001-172 | New England Revolution Soccer. |  |  | 450000 | 0 | 0 | 818284.98 | 1076955.99
Sports + Entertainment Group Operations | 19150002-164 | TKFC - St Louis MLS |  |  | 520000 | 5229427.56 | 0 | 484540873.8602 | 486561788 | 632534.38 | 698570.75 | 100% | 0% | 0%
Wind Energy I Operations | 19141002 | Ida Grove II Wind | 2019-04-15 |  | 0 | 9217 | 5892 | 82715590.35 | 80259602.74 | 95747 | 108556.2 | 65.2% | 33.99% | 0.8185%
Wind Energy I Operations | 19141004 | North Fork Ridge Wind - Design | 2019-09-15 |  | 0 | 0 | 0 | 302669.52 | 318412.6
Wind Energy I Operations | 19141005 | Kings Point Wind - Design | 2019-09-15 |  | 0 | 0 | 0 | 249810.1 | 289442.19
Wind Energy I Operations | 19141006 | Bright Stalk - Wind - EDPR | 2019-04-01 |  | 0 | 985 | 653 | 41536655.3954 | 42469063.22 | 15115 | 23045.83 | 74.07% | 25.55% | 0.3775%
Wind Energy I Operations | 19141007 | Wildorado Repower Wind | 2019-04-08 |  | 0 | 1892 | 1319 | 21862755.19 | 20546946.85 | 64943 | 85423.35 | 83.08% | 16.92% | 0%
Wind Energy I Operations | 19141008 | Elbow Creek Repower Wind | 2019-05-06 |  | 0 | 7865.03 | 1418 | 10847149.8772 | 12120383.82 | 25890 | 68228.75 | 80.84% | 19.16% | 0%
Wind Energy I Operations | 19141009 | Bitter Ridge Wind | 2019-06-24 |  | 0 | 25096.85 | 2990 | 48772150.72 | 49169553.52 | 79274 | 82558.25 | 70.21% | 23.87% | 5.919%
Wind Energy I Operations | 19141010 | Nobles 2 Wind Project | 2019-08-15 |  | 0 | 4415 | 3883 | 77773246.5633 | 81149311.24 | 112838 | 117228 | 71.78% | 27.92% | 0.299%
Wind Energy I Operations | 19141011 | Cheyenne Ridge Wind | 2019-05-01 |  | 0 | 27237.63 | 17419 | 144705439.95 | 144160558.44 | 248911 | 222345.6 | 81.3% | 18.7% | 0%
Wind Energy I Operations | 19141012 | Arbor Hill 2019 | 2019-07-01 |  | 0 | 3155 | 1531 | 38784214.64 | 38914783.95 | 49260 | 66734.54 | 63.39% | 31.66% | 4.952%
Wind Energy I Operations | 19141013 | King Plains Wind | 2019-07-24 |  | 0 | 458317.85 | 437230 | 75649851.5455 | 81160982.82 | 119321 | 102699.28 | 81.71% | 18.29% | 0%
Wind Energy I Operations | 19141014 | GE MISC. REPOWER |  |  | 0 | 0 | 0 | 142339.56 | 158060.5 | 0 | 3910.5 | 73.75% | 26.25% | 0%
Wind Energy I Operations | 19141017 | Prairie Hill Wind | 2019-07-01 |  | 0 | 26974.2 | 9938 | 112966183.95 | 109800158.52 | 211760 | 175054.9 | 77.2% | 22.8% | 0%
Wind Energy I Operations | 19141019 | High Plains/McFadden Repower |  |  | 0 | 0 | 0 | 85133.31 | 97415.36
Wind Energy I Operations | 19141020 | Walnut Repower Wind |  |  | 0 | 1239 | 1057 | 21240119.377 | 18119714.63 | 66402 | 69963 | 66.07% | 29.84% | 4.094%
Wind Energy I Operations | 19141021 | Colorado Green Repower |  |  | 0 | 3348 | 3320 | 27615741.0926 | 21741182.91 | 102553.7 | 87519.5 | 83.97% | 16.03% | 0%
Wind Energy I Operations | 19141022 | North Fork Ridge Wind |  |  | 0 | 17739.44 | 4176 | 92592497.0523 | 89308087.19 | 120511 | 142609.63 | 81.37% | 18.63% | 0%
Wind Energy I Operations | 19141023 | Pryor Mountain Wind |  |  | 0 | 36965.04 | 6673 | 116934959.89 | 93924194.3 | 109148 | 114600.48 | 72.96% | 25.86% | 1.18%
Wind Energy I Operations | 19141024 | Kings Point Wind |  |  | 0 | 8053.41 | 4643 | 114586334.7416 | 108437161.1 | 151510 | 152932.27 | 87.7% | 12.3% | 0%
Wind Energy I Operations | 19141025 | Dunlap Repower |  |  | 0 | 100 | 74 | 2860752.72 | 2072798.84 | 7890 | 8506 | 88.75% | 11.25% | 0%
Wind Energy I Operations | 19141026 | Trimont Repower |  |  | 0 | 924 | 561 | 16892294.89 | 15241772.22 | 55711.5 | 54307.4 | 65.64% | 28% | 6.368%
Wind Energy I Operations | 19141027 | White Hills Wind |  |  | 0 | 32977.18 | 6913 | 108289439.6614 | 99723721.82 | 152829 | 100924.88 | 75.27% | 24.73% | 0%
Wind Energy I Operations | 19141028 | Adair Repower Wind |  |  | 0 | 0 | 0 | 2901231.78 | 1599588.68 | 0 | 10475.5 | 62.54% | 25.46% | 12%
Wind Energy I Operations | 19141029 | High Plains Repower |  |  | 0 | 11 | 4 | 102305.66 | 81696.08 | 6936 | 970 | 98.71% | 1.289% | 0%
Wind Energy I Operations | 19141030 | Truscott Gilliland East Wind |  |  | 0 | 3351 | 2138 | 71933089.19 | 70134193.6 | 22088 | 23756.03 | 85.15% | 14.85% | 0%
Total | [5 empty] | 231020838.63 | 63868548.87 | 5501274713.6678 | 4921811630.27 | 8200952.52 | 8718112.37 | 83% | 16.73% | 0.2696%

## 2018
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Sports + Entertainment Group Operations | 18150006 | Mortenson/Consigli - NER | 2018-05-14 | 2022-12-31 | 0 | 0 | 0 | 0.01 | -4.5475e-13
Seattle Operations | 18050030 | AMLI 1101 Western Res Tower | 2020-12-01 | 2022-12-01 | 0 | 3988 | 0 | 2259348.47 | 2414651.17 | 0 | 260 | 100% | 0% | 0%
Denver Operations | 18060001 | MAM/McCarthy-Gaylord Pacific | 2020-01-01 | 2022-08-01 | 1784035 | 0 | 0 | 0 | -2624
Milwaukee Operations | 18080010 | WI DOT - Foxconn Dev | 2018-06-07 | 2022-03-31 | 0 | 0 | 4 | 0.01 | -3.74 | 0 | 0 | 0% | 0% | 0%
Mortenson Infrastructure Milw Operations | 18080010-063 | WI DOT-Foxconn Roads Develpmnt | 2018-06-07 | 2022-03-31 | 0 | 0 | 0 | 736829 | 772106.19
FCG Operations | 18110012 | DON-EHW Repairs Phases 2 and 3 | 2019-01-02 | 2022-03-19 | 133795 | 217 | 0 | 104162229.41 | 77861693.85 | 4880 | 2270 | 99.6% | 0.3965% | 0%
Milwaukee Operations | 18080011 | WI DOT-Const Project Ctrls | 2018-07-01 | 2021-12-31 | 0 | 0 | 0 | 0.01 | 115.1
Mortenson Infrastructure Milw Operations | 18080011-063 | WI DOT-IH 94 N-S Corridor | 2018-08-01 | 2021-12-31 | 0 | 0 | 0 | 2025737 | 1518308.76
Sports + Entertainment Group Operations | 18150001 | Rapid City - Rushmore Plaza | 2018-03-08 | 2021-07-31 | 250000 | 1330950.62 | 1277642 | 110010384.6157 | 109128213.66 | 81372.1 | 70865 | 85.25% | 14.75% | 0.005645%
Milwaukee Operations | 18080008 | AHC - Mount Pleasant | 2019-06-01 | 2021-07-21 | 0 | 816 | 0 | 1638116.97 | 1732390.92 | 0 | 25 | 96% | 4% | 0%
Minneapolis Operations | 18030007 | PureCycle Technologies | 2018-02-15 | 2021-07-15 | 200000 | 0 | 0 | 2711670.4461 | 2638732.63
Power Delivery Solutions Operations | 18146017 | Ekola Flats Wind - HVT | 2019-05-20 | 2021-06-30 | 0 | 715372 | 719211 | 26658660.2258 | 25745651.66 | 21766 | 28344 | 82.25% | 17.72% | 0.03528%
Denver Operations | 18060005 | CCD-DIA On-Call | 2018-06-01 | 2021-06-01 | 0 | 0 | 0 | 286928.27 | 331268.26 | 0 | 130 | 100% | 0% | 0%
Denver Operations | 18126001 | Facebook-EAG 1/2 | 2018-07-03 | 2021-04-21 | 986000 | 1054958.3 | 935052 | 651059982.3058 | 640336992.31 | 87314.78 | 153710.2 | 66.83% | 33.17% | 0%
Seattle Operations | 18050042 | Climate Pledge Arena | 2018-12-10 | 2021-04-01 | 0 | 4750703.81 | 3446885 | 841948897.9186 | 843073902.61 | 446258.59 | 533641.02 | 79.95% | 17.77% | 2.28%
Seattle Operations | 18050027 | Port Angeles Waterfront Center | 2019-09-03 | 2021-03-01 | 0 | 356646.69 | 249227 | 38914390.2316 | 28262206.37 | 24901.7 | 19584.25 | 94.41% | 5.53% | 0.06127%
Sports + Entertainment Group Operations | 18150008 | Mortenson/Messer - Nashville |  | 2021-03-01 | 0 | 0 | 0 | 23458451.23 | 21616087.68
Denver Operations | 18060048 | LPMD-I-70/32nd Avenue | 2019-01-28 | 2021-01-28 | 0 | 3981537 | 59887 | 7912251.185 | 9212986.49 | 10391 | 20851.5 | 85.02% | 14.97% | 0.01439%
Chicago Operations | 18090991 | Chicago Prefabrication Shop | 2018-01-01 | 2020-12-31 | 0 | 127567.61 | 63243 | 813261.7478 | 994717.84 | 6414.77 | 11719.32 | 91.65% | 7.082% | 1.271%
Denver Operations | 18060008 | CoorsTek-Capital Improvements | 2018-02-07 | 2020-12-31 | 0 | 0 | 0 | 0.01 | 26.73
Denver Operations | 18060028 | Forest City-FC Directed Work | 2018-05-01 | 2020-12-31 | 0 | 1 | 0 | 730648 | 593363.1 | 0 | 323.5 | 94.74% | 5.255% | 0%
Power Delivery Solutions Operations | 18146020 | Blazing Star 2 Wind - HVT | 2019-07-15 | 2020-12-01 | 0 | 1042 | 0 | 34375016.66 | 33294396.82
Power Delivery Solutions Operations | 18146016 | TB Flats I & II Wind HVT | 2019-05-20 | 2020-11-01 | 0 | 1371645 | 1231223 | 52317676.343 | 50736472.57 | 40957 | 79960.5 | 84.52% | 15.47% | 0.01251%
Wind Energy I Operations | 18141013 | TB Flats Wind | 2019-04-01 | 2020-11-01 | 0 | 11051 | 12494 | 136193192.3912 | 146007131.41 | 260284.5 | 321035.25 | 78.38% | 21.6% | 0.02025%
Wind Energy I Operations | 18141017 | Ekola Flats Wind | 2019-04-01 | 2020-11-01 | 0 | 19132 | 22470 | 73439435.0062 | 78588654.17 | 84250 | 140719.3 | 80.78% | 19.22% | 0%
Phoenix Operations | 18040006 | Steeplechase | 2018-07-03 | 2020-10-30 | 986000 | 0 | 0 | 0.01 | 0
Seattle Operations | 18050007 | citizenM Downtown LA | 2019-06-04 | 2020-10-20 | 0 | 150138.36 | 1982 | 68037369.1607 | 71177072.99 | 2768 | 3667.79 | 82.48% | 16.96% | 0.5589%
FCG Operations | 18110007 | JBLM Shopping Center | 2018-07-20 | 2020-10-05 | 291000 | 0 | 0 | 57687784.84 | 59112914.91 | 0 | 2004 | 100% | 0% | 0%
Denver Operations | 18060051 | MDI-2099 Chestnut Courtyard | 2019-08-01 | 2020-09-30 | 110000 | 0 | 0 | 0.01 | 826320.31
Denver Operations | 18126002 | Facebook-Program Services |  | 2020-09-17 | 0 | 2520 | 0 | 1460502 | 1495886.24
FCG Operations | 18110019 | S1S Roof Reinforcement Renov. | 2019-08-05 | 2020-09-03 | 14000 | 0 | 0 | 946316.2493 | 902971.31
Minneapolis Operations | 18030003 | City of Mpls-NPSB | 2018-06-18 | 2020-08-31 | 330000 | 305733 | 11 | 15698572.8259 | 16053437.34 | 61837.17 | 68374.5 | 87.7% | 11.85% | 0.4527%
Chicago Operations | 18090014 | Wheels Inc HQ Addition & Ren | 2019-08-01 | 2020-07-31 | 49245 | 0 | 0 | 24750 | 24816.42
Phoenix Operations | 18040012 | SRP PAB Phase 4 Center Core | 2018-10-15 | 2020-07-31 | 143680 | 18419 | 8211 | 49089220.87 | 48315277.2 | 13316.3311 | 18327.05 | 85.83% | 14.17% | 0%
Seattle Operations | 18050038 | DaVita CBO Expansion | 2019-03-01 | 2020-07-31 | 0 | 704650.65 | 675443 | 44511072.2449 | 44455907.89 | 16991.6 | 23573.73 | 92.49% | 7.108% | 0.403%
Denver Operations | 18060002 | MDI-St. John's XXII Student | 2019-01-01 | 2020-06-30 | 0 | 0 | 0 | 0.01 | 3608.61
Wind Energy I Operations | 18141021 | Tenaska Clear Creek Wind | 2019-01-01 | 2020-06-26 | 0 | 8216 | 7236 | 114378918.3589 | 119271696.67 | 147992 | 153343.1 | 79.18% | 20.82% | 0%
Phoenix Operations | 18040002 | MDI - HP/HH Tempe Downtown | 2019-01-01 | 2020-06-01 | 149000 | 572352.67 | 3982 | 40983283.53 | 42175036.69 | 12758.2 | 16430 | 82.66% | 17.34% | 0%
Chicago Operations | 18090015 | Glen Ellyn Parking Garage | 2019-08-01 | 2020-05-31 | 116234 | 209922.01 | 39254 | 15217524.77 | 15169887.83 | 10201.4 | 10718.5 | 88.61% | 10.99% | 0.3965%
Power Delivery Solutions Operations | 18146015 | Tesla Phase 1 | 2018-08-02 | 2020-05-30 | 0 | 333931.08 | 335487 | 6183833.003 | 6086143.31 | 15000.56 | 7940.5 | 77.49% | 22.51% | 0%
FCG Operations | 18110004 | DON P-930 Combat Veh Rpr Fac | 2018-12-01 | 2020-05-02 | 61193 | 0 | 0 | 21650499.83 | 20621570.97 | 0 | 3352 | 100% | 0% | 0%
Civil Group Operations | 18148013 | Blazing Star I - Civil | 2018-07-31 | 2020-05-01 | 0 | 646021 | 453439 | 12617660.72 | 15169675.5 | 31268 | 56549.94 | 72.7% | 26.77% | 0.5296%
Portland Operations | 18050034 | PCC OMIC | 2019-05-01 | 2020-05-01 | 0 | 51629.82 | 0 | 20721311.79 | 20650667.56 | 2180.4 | 4531.96 | 98.83% | 1.169% | 0%
Phoenix Operations | 18040007 | SRP PAB Expense and Repair PO | 2018-05-01 | 2020-04-30 | 80000 | 0 | 0 | 0.01 | 1694.86
Power Delivery Solutions Operations | 18146021 | East Fork Wind - HVT | 2019-01-18 | 2020-04-21 | 0 | 264689 | 257800 | 16542177.57 | 15655462.59 | 29333 | 32259.05 | 80.71% | 19.29% | 0%
Denver Operations | 18060058 | WBVP-Northridge Behaviorial | 2019-02-07 | 2020-04-16 | 82627 | 468118.52 | 0 | 29693544.55 | 116547.33 | 20520.3 | 0 | 0% | 0% | 0%
Seattle Operations | 18050008 | citizenM Sea Pioneer Square | 2019-01-15 | 2020-04-11 | 66640 | 277100.73 | 82838.5 | 54378167.4462 | 58188100.27 | 25842.9 | 46538.22 | 85.06% | 13.65% | 1.287%
Wind Energy I Operations | 18141020 | Seneca Wind | 2019-04-01 | 2020-04-01 | 0 | 0 | 0 | 1048700 | 876029.31
Milwaukee Operations | 18080016 | Kohler Co - North Crane Yard | 2018-09-17 | 2020-03-31 | 13120 | 14627.91 | 58024 | 5527447.2352 | 4998905.42 | 7360.4 | 4139.23 | 93.5% | 6.318% | 0.1812%
Denver Operations | 18060047 | MDI-Candelas MOB | 2019-06-01 | 2020-03-30 | 40000 | 453127.81 | 209398 | 8670348.4206 | 8934704.66 | 17338.64 | 16435.5 | 88% | 12% | 0%
Denver Operations | 18060050 | MDI-Arista MOB | 2019-06-01 | 2020-03-30 | 60000 | 0 | 0 | 115531.25 | 242258.74
Denver Operations | 18060057 | FRA-BioScience 3-TI | 2019-01-01 | 2020-02-28 | 90000 | 261768.07 | 25416 | 15379814.15 | 15261935.52 | 5477.5 | 11232.5 | 92.63% | 7.371% | 0%
Denver Operations | 18060025 | BCSP Rino-Hub Phase 2 | 2018-11-01 | 2020-02-21 | 110606 | 493569.66 | 252058 | 23888440.27 | 23904463.6 | 23581.7 | 28631 | 91.53% | 8.472% | 0%
FCG Operations | 18110009 | Buckley AFB Document Dest | 2019-05-09 | 2020-02-10 | 4377 | 0 | 0 | 4882603.24 | 5405997.72 | 0 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 18145013 | Terrell - Silicon Ranch | 2018-04-22 | 2020-02-04 | 103289550 | 5869277 | 8276895 | 57784700.14 | 69591027.98 | 233845 | 514634.39 | 86.89% | 13.11% | 0%
Phoenix Operations | 18040003 | Downtown Phx Hyatt Place | 2018-12-15 | 2020-02-01 | 126214 | 0 | 0 | 0.01 | 34117.45
Power Delivery Solutions Operations | 18146023 | Grissom Interconnect | 2019-06-03 | 2020-01-31 | 0 | 863584 | 773677 | 22267822.87 | 20820748.39 | 17251 | 21028 | 79.19% | 20.81% | 0%
Sports + Entertainment Group Operations | 18150004 | Mortenson/GE Johnson - K-State | 2019-01-03 | 2020-01-30 | 0 | 0 | 0 | 2187309.77 | 1371637.23 | 0 | 11 | 0% | 100% | 0%
Sports + Entertainment Group Operations | 18150004-168 | K-State Baseball/Soccer | 2019-01-03 | 2020-01-30 | 58818 | 24458 | 0 | 19038022.11 | 19634468.97 | 2302.1 | 1968.75 | 86.08% | 13.92% | 0%
Energy Storage & Solutions Operations | 18146019 | CTA EV Bus Charging Stn | 2018-05-17 | 2020-01-14 | 0 | 4728 | 5114 | 9790711.2 | 10689204.65 | 10 | 5479.92 | 90.61% | 7.902% | 1.487%
Power Delivery Solutions Operations | 18146014 | Misae I Solar - HVT | 2018-06-25 | 2020-01-10 | 0 | 179631 | 166790 | 8137904.53 | 8219947.82 | 8203 | 8670.6 | 83.37% | 16.63% | 0%
Denver Operations | 18060014 | SCL-St Joe's Facilities Agree | 2018-03-01 | 2019-12-31 | 0 | 117 | 498 | 333836.04 | 362754.31 | 234 | 2214.23 | 84.85% | 15.15% | 0%
Denver Operations | 18060035 | Children's Hosp.-Potomac MOB | 2018-10-01 | 2019-12-31 | 114000 | 179545 | 33793 | 24468365.4698 | 24456902.26 | 11000.1 | 15419.5 | 89.39% | 10.61% | 0%
Milwaukee Operations | 18080025 | Kohler - Misc Projects 18-19 | 2019-01-01 | 2019-12-31 | 0 | 0 | 0 | 0.01 | 26062.61
Minneapolis Operations | 18030025 | Sanford Fargo-Master Agrmt | 2018-05-07 | 2019-12-31 | 1020 | -3684.5 | 40 | 2812012.372 | 2889613.51 | 3737.07 | 5222.97 | 91.35% | 8.242% | 0.4116%
Portland Operations | 18050037 | OHSU Chem Bio Relocation | 2019-05-01 | 2019-12-31 | 0 | 13275 | 6 | 1104552.49 | 1105936.2 | 652.6 | 1363.25 | 91.25% | 8.161% | 0.5868%
Power Delivery Solutions Operations | 18146006 | Blazing Star 1 Wind - HVT | 2018-08-06 | 2019-12-31 | 0 | 1499 | 0 | 19486890.22 | 18798198.89
Power Delivery Solutions Operations | 18146024 | Bonilla Interconnect | 2019-05-01 | 2019-12-31 | 0 | 779595 | 762175 | 23089643.91 | 22627623.55 | 19564 | 32009.5 | 71.13% | 28.87% | 0%
Seattle Operations | 18050025 | Kaiser WA IDIQ Everett Misc | 2018-07-18 | 2019-12-31 | 0 | 477.91 | 364 | 418812.88 | 388926.37 | 232 | 561.02 | 77.01% | 11.23% | 11.76%
Solar and Emerging Renewables Operations | 18145008 | Misae I Solar | 2018-06-25 | 2019-12-31 | 326810540 | 8044264 | 9094356 | 122299437 | 124076779.11 | 531290 | 594505.31 | 86.95% | 13.05% | 0%
Denver Operations | 18060007 | Park Creek-Filing ME | 2018-01-02 | 2019-12-30 | 0 | 287 | 33 | 696632 | 677189.32 | 1280 | 4515 | 96.95% | 3.045% | 0%
Denver Operations | 18060039 | SCL-SJH NICU Expansion | 2019-01-14 | 2019-12-20 | 14100 | 132397.5 | 4614 | 4338493.97 | 4396260.12 | 5398.8 | 14049.27 | 89.56% | 10.44% | 0%
Power Delivery Solutions Operations | 18146004 | Solomon Forks Wind - HVT | 2018-04-10 | 2019-12-17 | 0 | 431698 | 432292 | 30930056.315 | 30115995.93 | 35893 | 40827 | 81.58% | 18.42% | 0%
Seattle Operations | 18050006 | Bend WRF Cap Improvement Proj | 2018-02-22 | 2019-11-30 | 0 | 198029.07 | 57760 | 7390721.867 | 16470271.18 | 24814.8 | 70523.76 | 92.54% | 6.653% | 0.8104%
FCG Operations | 18110015 | DCNG Armory Ventilation Rehab | 2019-05-20 | 2019-11-27 | 29937 | 0 | 0 | 1987453.94 | 1965710.47 | 0 | 138 | 100% | 0% | 0%
Denver Operations | 18060060 | SCL-LMC Main Pharmacy USP 800 | 2019-02-11 | 2019-11-26 | 0 | 1812.14 | 1968 | 993877.28 | 1006465.9 | 2517.39 | 3185.5 | 91.45% | 8.554% | 0%
Minneapolis Operations | 18030048 | Graco Koch Center Expansion | 2018-10-29 | 2019-11-21 | 795970 | 2324475.86 | 2332581 | 78522078.7635 | 78797731.23 | 103685.3 | 93047 | 89.95% | 9.868% | 0.1768%
FCG Operations | 18110025 | UDC LSI Upgrades | 2018-10-15 | 2019-11-15 | 10000 | 0 | 0 | 3227659.44 | 3179110.23
FCG Operations | 18110026 | UDC Roll-Up Fire Door Mech. | 2018-10-15 | 2019-11-15 | 13800 | 0 | 0 | 878979 | 889435.64
Denver Operations | 18060006 | MDI-Pine Creek MOB | 2019-03-04 | 2019-11-04 | 0 | 0 | 0 | 0.01 | 31110.21
FCG Operations | 18110008 | Fort Shafter Data Center 2 | 2018-09-06 | 2019-11-04 | 4320 | 0 | 0 | 117477.98 | 1952610.87
Denver Operations | 18060056 | SCL-SJB Mom/Baby/Women's | 2019-01-01 | 2019-11-01 | 11000 | 0 | 0 | 1765218.04 | 1813460.73
Power Delivery Solutions Operations | 18146025 | Highlander Solar - HVT | 2019-03-01 | 2019-11-01 | 0 | 417106 | 457003 | 21490733.21 | 22212014.5 | 14169 | 26184.92 | 79.5% | 20.5% | 0%
Seattle Operations | 18050035 | Swedish Ballard South Wing AHU | 2019-03-01 | 2019-11-01 | 0 | 6734.86 | 26 | 1263936.1854 | 1189492.95 | 433.82 | 442.12 | 94.01% | 5.315% | 0.6785%
Power Delivery Solutions Operations | 18146018 | Gillrina Cut-In | 2019-03-01 | 2019-10-31 | 0 | 1046 | 398 | 498475.51 | 508794.59 | 2234 | 1292 | 85.9% | 14.1% | 0%
Seattle Operations | 18050039 | AAFES 03X Concrete Package | 2018-11-01 | 2019-10-31 | 0 | 833891.85 | 500512 | 3207352.6295 | 3307023.54 | 17887.9 | 16126.37 | 92.61% | 6.641% | 0.7503%
Minneapolis Operations | 18030033 | Allina-Schulze Neuroscience C | 2018-08-01 | 2019-10-21 | 42000 | 63891.5 | 66400 | 11020199.925 | 11212337.36 | 25198 | 29883.1 | 89.26% | 9.95% | 0.7897%
FCG Operations | 18110020 | 21st Shielding Cert.-MD | 2019-01-14 | 2019-10-12 | 1 | 0 | 0 | 209940 | 203847.46
FCG Operations | 18110021 | 21st Shielding Cert. -VA | 2019-02-04 | 2019-10-12 | 1 | 0 | 0 | 450222.15 | 444374.96
FCG Operations | 18110022 | 21st Shielding Cert. -PA | 2019-01-14 | 2019-10-12 | 1 | 0 | 0 | 438589 | 440487.52
Denver Operations | 18060049 | LPMD-CC Ph 2 Utilities | 2019-03-01 | 2019-10-01 | 0 | 20118 | 28246 | 1954644.6296 | 2069199.22 | 4727.1 | 3967 | 84.32% | 15.68% | 0%
Chicago Operations | 18090013 | SAIC Wellness Center | 2019-05-15 | 2019-09-30 | 5000 | 47431.15 | 13504 | 1305726.61 | 1218672.56 | 1612.84 | 1580.61 | 88.17% | 9.49% | 2.341%
Chicago Operations | 18090004 | Lurie Inpatient Exp2 -17th FL | 2018-07-01 | 2019-09-30 | 35000 | 21748 | 17015 | 19229564.88 | 15695157.35 | 22658 | 23835.76 | 89.67% | 8.892% | 1.435%
Chicago Operations | 18090002 | Performing Arts Center | 2019-02-04 | 2019-09-30 | 35506 | 224752.5 | 121374 | 25940397.6072 | 26777833.84 | 22828 | 23953.78 | 90.76% | 8.718% | 0.5239%
Phoenix Operations | 18040009 | Arroyo Seco Well Site | 2018-03-19 | 2019-09-30 | 187900 | 67319 | 15964 | 7815000.64 | 9645390.93 | 9317 | 19464.5 | 87.74% | 12.26% | 0%
Civil Group Operations | 18148020 | East Fork - Civil (Wind) | 2018-11-01 | 2019-09-14 | 0 | 650842 | 270434 | 7741710.3774 | 10773355.27 | 27056.5 | 30923.5 | 72.55% | 27.45% | 0%
Seattle Operations | 18050051 | Kaiser WA LYM Rebranding | 2019-03-22 | 2019-09-04 | 0 | 32683.5 | 2347 | 1619806.8982 | 1696869.95 | 2354.71 | 3523.78 | 91.6% | 6.385% | 2.015%
Minneapolis Operations | 18030012 | Blake Classroom Refresh | 2018-06-11 | 2019-09-02 | 57000 | 177890 | 101184 | 2436648.75 | 2471663.29 | 7904.1 | 6204.68 | 77.3% | 22.02% | 0.6769%
Minneapolis Operations | 18030013 | MCTC-Hennepin Ave Skyway | 2019-05-01 | 2019-09-01 | 3232 | 31760.1 | 19396 | 2767329.93 | 2750641.66 | 4019.7 | 4273 | 90.43% | 8.168% | 1.404%
Wind Energy I Operations | 18141014 | Glenrock Repower Wind | 2018-09-10 | 2019-09-01 | 0 | 503 | 243 | 2993794.13 | 2536592.95 | 9140 | 9972.09 | 77.19% | 22.81% | 0%
Wind Energy I Operations | 18141015 | Seven Mile Repower Wind | 2018-09-10 | 2019-09-01 | 0 | 1059 | 972 | 13807519.54 | 12307350.73 | 42711 | 48198.3 | 77.4% | 22.6% | 0%
Chicago Operations | 18090017 | Faegre Baker Daniels-45th Exp. | 2018-10-23 | 2019-08-31 | 1830 | 6682.52 | 0 | 232411.11 | 234204.57 | 417.68 | 361.95 | 85.63% | 5.526% | 8.841%
Chicago Operations | 18090001 | CHI Bears Halas Hall | 2017-12-04 | 2019-08-31 | 198000 | 657708.51 | 449945 | 77242395.8359 | 79033178.02 | 41884.5 | 52911.04 | 82.18% | 11.86% | 5.965%
Denver Operations | 18060031 | Woodward-Drake Equip Fit Up | 2018-06-25 | 2019-08-30 | 0 | 10631 | 0 | 4730168.82 | 4526862.77 | 1112.3 | 5138 | 96.34% | 3.659% | 0%
Minneapolis Operations | 18030057 | WuXi Diagnostic TI - Dis Sq | 2019-06-03 | 2019-08-30 | 2367 | 341 | 0 | 744228.09 | 659655.81 | 419.6 | 321 | 99.07% | 0.9346% | 0%
FCG Operations | 18110014 | DCNG Armory HVAC | 2019-03-01 | 2019-08-25 | 15450 | 0 | 0 | 703760.3 | 653348.07
Milwaukee Operations | 18080001 | MSOE-ComputationalScienceHall | 2018-05-04 | 2019-08-22 | 64000 | 822132.37 | 543836 | 29622287.7602 | 29659942.13 | 37603.91 | 46101.61 | 90.29% | 9.477% | 0.2299%
FCG Operations | 18110017 | DCNG Armory Museum North | 2019-03-01 | 2019-08-14 | 1967 | 0 | 0 | 1184449.65 | 1180666.93
FCG Operations | 18110016 | DCNG Armory Restroom Renov | 2019-04-01 | 2019-08-06 | 2156 | 0 | 0 | 1151707.27 | 1175832.25 | 0 | 2 | 100% | 0% | 0%
Denver Operations | 18060041 | WelArm-Glenarm Bldgs Remodel | 2018-09-01 | 2019-08-01 | 72000 | 0 | 0 | 0.01 | 0
Denver Operations | 18060062 | AIMCO 21-Faculty Club Hotel | 2018-11-15 | 2019-08-01 | 108000 | 0 | 0 | 0.01 | 147239.97
Portland Operations | 18050031 | OHSU Vollum Phase II | 2018-08-01 | 2019-08-01 | 0 | 5896.3 | 1986 | 4342409.85 | 4350045.05 | 3192.18 | 1629.89 | 91.89% | 7.316% | 0.7976%
Sports + Entertainment Group Operations | 18150009 | Mortenson/Clark - Chase Cen | 2018-12-01 | 2019-08-01 | 0 | 0 | 0 | 1334535.94 | 843049.28
Milwaukee Operations | 18080015 | Dane Cnty Terminal Mod | 2020-01-01 | 2019-07-31 | 0 | 0 | 0 | 344835 | 277767.8
Seattle Operations | 18050018 | Harborview 2MB Cart Washers | 2018-10-01 | 2019-07-31 | 2375 | 39095.35 | 8227 | 2929653.35 | 2431358.46 | 6032.4 | 3993.16 | 99.55% | 0.3756% | 0.07513%
Wind Energy I Operations | 18141019 | Carroll Repower Wind | 2018-10-15 | 2019-07-31 | 0 | 1268 | 926 | 20333500.67 | 16840478.69 | 65295 | 67255.51 | 66% | 30.28% | 3.728%
Milwaukee Operations | 18080027 | Milwaukee Office Buildout | 2019-02-18 | 2019-07-30 | 19200 | 68177 | 86566 | 4354164.75 | 1.5334e-09 | 3975.1 | 5166.15 | 87.66% | 11.24% | 1.103%
Denver Operations | 18060040 | Faegre Baker Daniels-TI. | 2018-10-04 | 2019-07-25 | 0 | 97577 | 4 | 7727203.1872 | 7698295.68 | 1359.5 | 224 | 77.68% | 22.32% | 0%
FCG Operations | 18110003 | UDC Silver Universe 3&4 | 2018-06-01 | 2019-07-22 | 12500 | 88 | 0 | 5509273.65 | 5360445.1
Milwaukee Operations | 18080012 | Kohler-Water Spa Lincoln Comm | 2018-12-17 | 2019-07-20 | 17830 | 69456 | 0 | 6856768.25 | 7253753.08 | 2188.2 | 3057.71 | 95.36% | 3.418% | 1.226%
Denver Operations | 18060030 | Considine-Compositive Primary | 2018-09-01 | 2019-07-19 | 0 | 393900.16 | 176923 | 12918200.3647 | 13357559.11 | 22092.47 | 34957.5 | 89.46% | 10.54% | 0%
Civil Group Operations | 18148018 | Panther Creek Repower - Civil | 2018-10-01 | 2019-07-15 | 0 | 62106.92 | 27 | 3595246.068 | 3243067.17 | 16310 | 19176 | 76.22% | 23.78% | 0%
Denver Operations | 18060052 | SCL-Superior Primary & OBGYN | 2019-01-14 | 2019-07-12 | 0 | 51299 | 24826 | 2720447.6 | 2774866.66 | 1900.8 | 3050 | 88.07% | 11.93% | 0%
Denver Operations | 18060010 | Westfield-Parcel E Office Bldg | 2018-08-01 | 2019-07-01 | 0 | 261146 | 94688 | 14350285.75 | 14190758.94 | 10722 | 14399 | 87.79% | 12.21% | 0%
Minneapolis Operations | 18030047 | Sanford 8th Floor Build Out | 2018-10-15 | 2019-07-01 | 11759 | 12389 | 10333 | 3345113.89 | 3326833.9 | 3141 | 3418.5 | 90.42% | 9.405% | 0.1755%
Chicago Operations | 18090016 | Rush MC Transplant Ren. | 2019-01-03 | 2019-06-30 | 3980 | 457.46 | 0 | 240605.35 | 207410.9 | 434 | 396 | 61.62% | 15.4% | 22.98%
Civil Group Operations | 18148004 | Meadow Lake VI - Civil | 2018-04-04 | 2019-06-30 | 0 | 747140 | 1287947 | 14094955.14 | 14188923.99 | 33376 | 34025.5 | 67.92% | 30.83% | 1.251%
Denver Operations | 18060046 | Park Creek-Filing 56 | 2018-11-01 | 2019-06-30 | 0 | 150 | 0 | 348558 | 352555.2 | 1600 | 3119.5 | 97.74% | 2.26% | 0%
FCG Operations | 18110018 | DCNG Davison Airfield ACLS | 2019-02-04 | 2019-06-30 | 1600 | 0 | 0 | 700836.97 | 663756.41
Minneapolis Operations | 18030054 | NS VIII Renovation | 2018-12-05 | 2019-06-30 | 180188 | 385 | 0 | 5736028.3672 | 5751710.62 | 5460 | 6696 | 96.39% | 3.614% | 0%
Portland Operations | 18050057 | Adventist Electrophysiology | 2019-01-02 | 2019-06-30 | 4700 | 47813.3 | 551 | 3862698.3432 | 3753949.24 | 9356.21 | 7580.6 | 95.89% | 2.579% | 1.53%
Wind Energy I Operations | 18141002 | Mendota Hills Wind | 2018-06-01 | 2019-06-30 | 0 | 2754 | 2363 | 29877257.26 | 31165810.19 | 40927 | 65765.25 | 67.11% | 27.36% | 5.533%
Wind Energy I Operations | 18141010 | Heartland Divide Wind | 2018-08-06 | 2019-06-29 | 0 | 3236 | 2194 | 31054234.88 | 34418406.86 | 46291 | 71517.25 | 60.12% | 33.45% | 6.429%
Denver Operations | 18060034 | Woodward-Drake Campus Site Imp | 2018-08-01 | 2019-06-28 | 0 | 141 | 0 | 419452.45 | 394983.05 | 32 | 220 | 97.27% | 2.727% | 0%
Milwaukee Operations | 18080024 | Johnson Controls - B1F3 Reno | 2018-12-10 | 2019-06-28 | 15340 | 63731 | 43733 | 1208009.08 | 1164594.48 | 2161.7 | 2243.91 | 88.44% | 11.3% | 0.2674%
Minneapolis Operations | 18030042 | MDI-Blaine BTS-Site Prep | 2018-09-27 | 2019-06-24 | 0 | 0 | 0 | 1687141.59 | 1739829.95
Denver Operations | 18060053 | SCL-Denver West Foothills | 2019-01-14 | 2019-06-21 | 0 | 54563 | 97665 | 1775303.45 | 1808145.37 | 2664.4 | 7137.5 | 93.17% | 6.83% | 0%
Milwaukee Operations | 18080020 | Froedtert - Cath Lab FitOut | 2019-02-21 | 2019-06-21 | 1250 | 11615.6 | 7819 | 801278.6 | 805206.72 | 1098.3 | 1072.5 | 90.49% | 7.879% | 1.632%
Milwaukee Operations | 18080023 | MRMC - East Tunnel Repair | 2019-04-03 | 2019-06-17 | 2500 | 34007.37 | 24010 | 1599644.64 | 1589808.1 | 2548.3 | 3089.12 | 93.59% | 6.41% | 0%
Milwaukee Operations | 18080019 | S.C. Johnson - Lighthouse Exp | 2018-10-22 | 2019-06-17 | 10378 | 1374 | 0 | 2345046.55 | 2339924.11
Denver Operations | 18060054 | SCL-Cherry Creek Primary | 2019-01-14 | 2019-06-14 | 8200 | 45803 | 13572 | 1430842.95 | 1474626.95 | 2325 | 3301.5 | 84.49% | 15.51% | 0%
FCG Operations | 18110013 | DIA Parking Garage Repairs | 2018-11-12 | 2019-06-14 | 0 | 0 | 0 | 702640.27 | 952891.45
Wind Energy I Operations | 18141012 | East Fork Wind | 2018-10-15 | 2019-06-13 | 0 | 16665 | 101113 | 58033160.7 | 59610132.61 | 69364 | 85416.59 | 76.16% | 23.83% | 0.01346%
Civil Group Operations | 18148011 | Solomon Forks | 2018-07-23 | 2019-06-10 | 0 | 1096317 | 217084 | 8832101.6 | 9629715.05 | 28047.24 | 34255.5 | 75.24% | 24.76% | 0%
Minneapolis Operations | 18030011 | UMN Biological Sciences | 2018-08-01 | 2019-06-07 | 16300 | 45329.3 | 13859 | 6566227.7 | 6588035.73 | 4351.3 | 5082.02 | 99.36% | 0.6395% | 0%
Milwaukee Operations | 18080021 | Froedtert - Food Service Reno | 2019-03-27 | 2019-06-06 | 1000 | 17989 | 8114 | 1466343.23 | 1505285.45 | 2009.35 | 2081 | 89.16% | 10.6% | 0.2403%
Minneapolis Operations | 18030039 | Epic Systems Corp - Epic TI DS | 2019-02-19 | 2019-06-04 | 4306 | 6681.76 | 1942 | 980786.05 | 871967.32 | 338.8 | 152 | 89.47% | 10.53% | 0%
Minneapolis Operations | 18030049 | Silver Lake - UMR TI Disc Sq | 2018-12-17 | 2019-06-03 | 8382 | 14441.5 | 2925 | 2879798.7 | 2634554 | 1255.9 | 627.5 | 93.39% | 6.614% | 0%
Denver Operations | 18060033 | FRA-FIC Phase 1 Infrastructure | 2018-10-01 | 2019-06-01 | 0 | 487109.51 | 252327 | 8949960.6409 | 12481922.3 | 20611 | 41889.5 | 80.75% | 19.25% | 0%
Minneapolis Operations | 18030045 | Mayo TI - Discovery Square | 2018-10-08 | 2019-06-01 | 22400 | 50944.77 | 5779 | 9237090.44 | 9165883.92 | 3501.8 | 4363 | 96.81% | 3.14% | 0.04584%
Minneapolis Operations | 18030058 | Xcel-Becker Sands-UMN Lease | 2019-02-01 | 2019-06-01 | 24088 | 0 | 0 | 166078.1 | 182272.34 | 60 | 72 | 100% | 0% | 0%
Denver Operations | 18060059 | FRA-FIC Pond 374 | 2018-12-17 | 2019-05-31 | 0 | 235798.04 | 98701 | 1472360.49 | 1810960.01 | 9711 | 14324.33 | 82.64% | 17.36% | 0%
FCG Operations | 18110011 | Pearl Harbor Bldg 221 Reno | 2019-04-29 | 2019-05-24 | 6600 | 0 | 0 | 161658 | 163672.75
Minneapolis Operations | 18030055 | Allina-ANW Pharmacy USP | 2019-01-07 | 2019-05-24 | 1055 | 12 | 0 | 557175.35 | 556487.73 | 1943 | 2410.25 | 96.1% | 2.074% | 1.826%
Civil Group Operations | 18148016 | Bobcat Bluff RePower | 2018-09-11 | 2019-05-15 | 0 | 6358 | 226 | 3136701.38 | 3369645.87 | 9497.76 | 12165.5 | 82.27% | 17.73% | 0%
Denver Operations | 18060021 | Stadium Mgmt-Denver Bronc | 2018-05-01 | 2019-05-01 | 5000 | 924 | 830 | 289429 | 353672 | 1166 | 2605 | 93.86% | 6.142% | 0%
Power Delivery Solutions Operations | 18146026 | Horseshoe Draw SVC | 2019-07-01 | 2019-05-01 | 0 | 97549 | 93890 | 2620134.07 | 2910335.17 | 10968 | 16151.5 | 71.5% | 28.5% | 0%
Chicago Operations | 18090008 | Mercyhealth-Water Event | 2018-06-20 | 2019-04-30 | 0 | 328 | 674 | 5222332 | 4988979.29 | 9900 | 9817.91 | 90.71% | 6.87% | 2.419%
Chicago Operations | 18090011 | Allstate-Rochelle PLC Replace | 2018-11-19 | 2019-04-30 | 0 | 10415 | 0 | 160910 | 126481.12 | 550.6 | 539.25 | 89.99% | 7.603% | 2.411%
Denver Operations | 18060061 | SCL-LMC Rad Room 3 | 2019-02-18 | 2019-04-30 | 270 | 868 | 222 | 136149.7 | 136680.28 | 639 | 221 | 74.89% | 25.11% | 0%
Milwaukee Operations | 18080004 | AHC - Summit Main Pharm Reno | 2018-07-20 | 2019-04-30 | 670 | 14673 | 11471 | 899790.38 | 835743.15 | 873.5 | 1047 | 84.91% | 14.04% | 1.051%
Phoenix Operations | 18040017 | San Carlos Rural Health | 2018-12-10 | 2019-04-30 | 6684 | 0 | 0 | 1743982.71 | 1613357.77 | 536 | 685 | 74.74% | 25.26% | 0%
Milwaukee Operations | 18080022 | Kohler - ABP Cooling Tower | 2018-10-29 | 2019-04-29 | 4800 | 18113.74 | 5637 | 1056524.5382 | 1011792.45 | 1130.1 | 1578.5 | 90.75% | 6.208% | 3.041%
FCG Operations | 18110024 | UDC Chemical Treat. Upgrades | 2018-10-29 | 2019-04-27 | 40000 | 0 | 0 | 1823767.93 | 1798061.76
Denver Operations | 18060032 | FRA-AIMCO Phase 3A | 2018-08-13 | 2019-04-26 | 0 | 21414.7 | 19011 | 1624730.8192 | 1736918.25 | 12729.07 | 5454 | 86.48% | 13.52% | 0%
Phoenix Operations | 18040011 | Ellsworth Adhesives | 2017-09-18 | 2019-04-26 | 158726 | 0 | 0 | 16053735.77 | 16171498.6 | 0 | 4 | 100% | 0% | 0%
Wind Energy I Operations | 18141007 | Pomeroy I/II Repower Wind | 2018-06-11 | 2019-04-26 | 0 | 1918 | 1629 | 35406593.61 | 28914248.91 | 123355.5 | 117402.3 | 65.4% | 28.96% | 5.635%
Chicago Operations | 18090010 | QTS-Hogan 3/2 | 2018-10-29 | 2019-04-12 | 0 | 416 | 126 | 5102903.12 | 5108737.91 | 2873 | 3554.08 | 94.19% | 5.219% | 0.5909%
Seattle Operations | 18050053 | Kaiser WA PRT Rebranding | 2018-12-01 | 2019-04-12 | 0 | 30404 | 0 | 789623.1643 | 767195.84 | 1518 | 1377.09 | 96.55% | 3.449% | 0%
Milwaukee Operations | 18080007 | AHC-IR/Hybrid OR Suite | 2018-07-09 | 2019-04-11 | 6060 | 68633 | 48790 | 2967723.77 | 2978729.15 | 2914.9 | 3937 | 77.89% | 19.75% | 2.362%
FCG Operations | 18110010 | Westway CRAC Replace UPS | 2018-10-29 | 2019-04-05 | 1000 | 0 | 0 | 717610.11 | 694622.45
Denver Operations | 18060063 | Co Rockies-Coors Field Grease | 2018-12-26 | 2019-04-01 | 8000 | 5 | 0 | 457845.27 | 390079.9 | 689 | 954 | 89.41% | 10.59% | 0%
Denver Operations | 18060055 | Co Rockies-Coors Field 18-19 | 2018-10-29 | 2019-04-01 | 33600 | 0 | 0 | 3109508 | 3018951.41 | 6530 | 10141.55 | 80.7% | 19.3% | 0%
Denver Operations | 18060026 | CO Rockies-Coors Field 2018 | 2018-10-01 | 2019-04-01 | 45500 | 3385.75 | 2432 | 6508029.89 | 6784857.75 | 4730 | 18484 | 85.26% | 14.74% | 0%
Chicago Operations | 18090003 | QTS ComEd Substation | 2017-11-01 | 2019-03-31 | 0 | 198 | 45 | 9814244 | 9755485.83 | 2044 | 2656.5 | 96.2% | 3.614% | 0.1882%
Chicago Operations | 18090006 | Allstate Jcksnville 2018 Misc. | 2018-03-01 | 2019-03-31 | 0 | 7 | 0 | 308511 | 296495.53 | 0 | 40 | 100% | 0% | 0%
Chicago Operations | 18090012 | Mercyhealth - Rockton Misc | 2018-06-20 | 2019-03-31 | 0 | 1865 | 46 | 588892.85 | 594846.48 | 733.1 | 651.5 | 93.71% | 6.293% | 0%
Milwaukee Operations | 18080002 | Kohler Co - Foundry Bldg | 2018-01-27 | 2019-03-31 | 0 | 72.5 | 2 | 6381827.18 | 6451875.6 | 5085.28 | 5387.28 | 88.72% | 10.41% | 0.8631%
Milwaukee Operations | 18080026 | MDI - Hilton Garden Inn |  | 2019-03-31 | 170000 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 18030043 | Target Field 2019 Improvements | 2018-10-08 | 2019-03-31 | 13000 | 142966.24 | 31330 | 5256898 | 5256907.43 | 8095.4 | 10850.11 | 82.59% | 13.03% | 4.378%
Seattle Operations | 18050023 | PRMCE Colby Lab Automation | 2018-10-01 | 2019-03-31 | 0 | 0 | 0 | 4620 | 4994.75
Minneapolis Operations | 18030056 | Coralville Marriott & Conf Ctr | 2018-12-09 | 2019-03-28 | 108000 | 313893 | 0 | 1711471.0125 | 1732973.02 | 5603.41 | 4787 | 68.16% | 27.3% | 4.533%
Chicago Operations | 18090009 | QTS-DH1 B11-DH2 B2 | 2018-09-24 | 2019-03-23 | 0 | 203 | 43 | 2726951.9 | 2627601.06 | 1436 | 1236.5 | 94.66% | 5.135% | 0.2022%
Minneapolis Operations | 18030031 | Land O'Lakes - WT2 and Pilot | 2018-07-20 | 2019-03-15 | 6555 | 16874.3 | 0 | 4661570.4856 | 4639271.35 | 933.87 | 1092.5 | 99.45% | 0.5492% | 0%
Power Delivery Solutions Operations | 18146013 | Falfurrias SVC | 2018-07-02 | 2019-03-15 | 0 | 59800 | 51992 | 2487767.72 | 2954632.97 | 4565 | 13391 | 89.53% | 10.47% | 0%
Milwaukee Operations | 18080028 | Miller Park - SRF Master Plan |  | 2019-03-12 | 0 | 0 | 0 | 27621.6 | 23427.08
Solar and Emerging Renewables Operations | 18145005 | Target Solar Remediation | 2018-04-01 | 2019-03-08 | 0 | 65639 | 136182 | 5439340.81 | 5388419.42 | 0 | 26506.32 | 93.04% | 6.932% | 0.03018%
Minneapolis Operations | 18030052 | UMN-CCRB Mass Spec | 2018-11-12 | 2019-03-01 | 2635 | 0 | 0 | 743096.88 | 720488.73 | 744.5 | 721 | 100% | 0% | 0%
Portland Operations | 18050024 | Kaiser WMC IR Project | 2018-06-01 | 2019-03-01 | 0 | 4409 | 36286 | 2779134.285 | 2796891.58 | 4152.4 | 3561.86 | 89.92% | 8.858% | 1.221%
Denver Operations | 18060022 | SCL-LMC Poz Lok Fire Prot | 2018-04-03 | 2019-02-28 | 0 | 39 | 58 | 88370.07 | 88423.36 | 60 | 57.5 | 58.26% | 41.74% | 0%
Denver Operations | 18060024 | SCL-LMC Transformer and Fire | 2018-06-01 | 2019-02-28 | 0 | 631.35 | 358 | 233366.45 | 232497.69 | 347 | 392 | 87.24% | 12.76% | 0%
Denver Operations | 18060042 | SCL-LMC ED X Ray | 2018-11-09 | 2019-02-28 | 480 | 865 | 931 | 276059.45 | 276114.86 | 1174 | 949 | 90.67% | 9.326% | 0%
FCG Operations | 18110023 | Moss Landing Demo & Upgrade | 2018-11-29 | 2019-02-28 | 0 | 0 | 0 | 270000 | 273445.73
Milwaukee Operations | 18080014 | Johnson Controls - Misc. Jobs | 2018-07-31 | 2019-02-28 | 0 | 0 | 54 | 59025 | 62205.05 | 306 | 267 | 94.94% | 5.056% | 0%
Seattle Operations | 18050005 | 5th & Stewart Hotel | 2018-01-09 | 2019-02-28 | 0 | 0 | 0 | 342743.99 | 645189.49
Seattle Operations | 18050050 | KP Everett Rebranding | 2018-11-09 | 2019-02-28 | 0 | 20275.7 | 2049 | 1709091.8709 | 1642469.38 | 1954.6 | 2314 | 89.91% | 5.38% | 4.71%
Minneapolis Operations | 18030044 | Renaissance Sq-The Andrus | 2018-10-12 | 2019-02-18 | 14469 | 51581.75 | 10 | 2526602.24 | 2533841.37 | 4342 | 6089.25 | 81.04% | 18.87% | 0.09853%
FCG Operations | 18110006 | ECB1 Market Square | 2018-10-01 | 2019-02-15 | 2000 | 57 | 0 | 1193712.18 | 1149059.95
Phoenix Operations | 18040008 | Salt River Fields Restroom | 2018-10-01 | 2019-02-11 | 2236 | 0 | 0 | 639981.1 | 592414.76 | 0 | 8 | 100% | 0% | 0%
Denver Operations | 18060036 | CCC-Phase 1 Utilities | 2018-07-18 | 2019-02-05 | 0 | 8233 | 15332 | 1201513.799 | 1709704.48 | 3366 | 8180 | 86.52% | 13.48% | 0%
Denver Operations | 18060037 | Longs Peak Metro - Clear Creek | 2018-07-20 | 2019-02-05 | 0 | 4977 | 1710 | 6735772.2598 | 6749039.24 | 4370 | 8773 | 84.09% | 15.91% | 0%
Phoenix Operations | 18040004 | Ellsworth Adhesives-Reno | 2018-05-01 | 2019-02-01 | 120000 | 0 | 0 | 0 | 1312.46
Wind Energy I Operations | 18141016 | Leaning Juniper Repower Wind | 2018-10-12 | 2019-02-01 | 0 | 977 | 785 | 8926195.95 | 6121734.27 | 21844 | 21681.5 | 72.81% | 26.42% | 0.7737%
Phoenix Operations | 18040015 | USS Arizona Memorial | 2018-10-18 | 2019-01-31 | 0 | 0 | 0 | 60000 | 4924.07
Phoenix Operations | 18040016 | CoG-Cost Estimating Support | 2018-10-25 | 2019-01-31 | 0 | 0 | 0 | 45662 | 1376.3
Seattle Operations | 18050052 | Kaiser WA RVM Rebranding | 2018-12-01 | 2019-01-31 | 0 | 11219.5 | 0 | 560368.22 | 496222.48 | 1031.4 | 540.74 | 96.3% | 3.699% | 0%
Minneapolis Operations | 18030053 | Allina-Mercy CV-4 | 2018-09-03 | 2019-01-29 | 1400 | 0 | 0 | 383670.68 | 382950.59 | 2120 | 1551.5 | 92.56% | 7.444% | 0%
Phoenix Operations | 18040014 | Allstate One Chandler | 2018-10-22 | 2019-01-23 | 118953 | 0 | 0 | 7379128.892 | 7285997.44 | 396.5 | 1528.5 | 89.7% | 10.3% | 0%
Minneapolis Operations | 18030008 | FBD Wells Fargo TI | 2018-01-02 | 2019-01-21 | 0 | 17 | 133235 | 12439742.103 | 12026944.18 | 16600.5 | 15900 | 92.58% | 7.374% | 0.05031%
Denver Operations | 18060038 | SCL-LMC Nuclear Medicine | 2018-08-24 | 2019-01-16 | 0 | -3 | 1187 | 415050 | 421812.18 | 1314 | 1187 | 87.83% | 12.17% | 0%
Minneapolis Operations | 18030010 | UMN-Golf Practice Facility | 2018-06-01 | 2019-01-15 | 5500 | 45809.13 | 28518 | 2985413.1787 | 3009583.87 | 2969.55 | 3379.82 | 98.39% | 1.613% | 0%
FCG Operations | 18110005 | USSS SCIF Conference Room | 2018-08-06 | 2019-01-09 | 606 | 0 | 0 | 668201.15 | 658009.44
Denver Operations | 18060043 | SCL-LMC W Pines Boiler Replace | 2018-11-01 | 2018-12-31 | 0 | -2 | 465 | 356612.39 | 357499.75 | 555 | 485 | 79.48% | 20.52% | 0%
Denver Operations | 18060044 | Park Creek-Filing 57 | 2018-10-05 | 2018-12-31 | 0 | 1 | 10 | 4417905.92 | 4696593.61 | 4600 | 11242.5 | 97.79% | 2.21% | 0%
Denver Operations | 18060017 | SCL-LMC Linear Accelerator | 2018-03-23 | 2018-12-31 | 1934 | 1460 | 1944 | 673899.76 | 685153.12 | 1884 | 1943.5 | 84.18% | 15.82% | 0%
Minneapolis Operations | 18030001 | FUMC-Annual Contract 2018 | 2018-01-01 | 2018-12-31 | 0 | 0 | 0 | 1517640.42 | 1534850.34 | 0 | 4629.5 | 93.35% | 6.243% | 0.4104%
Minneapolis Operations | 18030002 | Allina Annual Contract - 2018 | 2018-01-01 | 2018-12-31 | 0 | 0 | 25 | 11292062.15 | 11282412.55 | 0 | 57655.57 | 89.15% | 10.34% | 0.5117%
Minneapolis Operations | 18030015 | Basilica Annual 2018 | 2018-05-13 | 2018-12-31 | 0 | 15952 | 16151 | 364155 | 378365.18 | 3129 | 1691.5 | 90.22% | 9.784% | 0%
Minneapolis Operations | 18030034 | Fairview - Zucker Media Lounge | 2018-08-08 | 2018-12-31 | 709 | 87.4 | 0 | 359536.53 | 361523.91 | 699 | 584 | 98.03% | 1.969% | 0%
Minneapolis Operations | 18030038 | Fairview-PEDs ED Remodel | 2018-09-05 | 2018-12-31 | 709 | 2 | 0 | 244830.87 | 232632.39 | 557 | 661 | 96.6% | 3.404% | 0%
Minneapolis Operations | 18030014 | UMN Field House Ext & Flrg | 2018-09-01 | 2018-12-31 | 80000 | 206314.99 | 51940 | 7223842.9701 | 7236012.65 | 7810.3 | 9096.5 | 98.92% | 1.083% | 0%
Portland Operations | 18050011 | OHSU Micro Lab Rennovation | 2018-01-01 | 2018-12-31 | 0 | 20 | 0 | 3114.8 | 802.09
Portland Operations | 18050022 | KSMC FSD Testing & Replace | 2018-04-15 | 2018-12-31 | 0 | 12505.5 | 6136 | 276938.14 | 289814.24 | 470 | 1016.5 | 71.37% | 21.84% | 6.788%
Portland Operations | 18050026 | Kaiser SMC SPC Bridge for CSP2 | 2018-06-07 | 2018-12-31 | 0 | 236255 | 40909 | 2903983.425 | 2901845.45 | 8591 | 6285.5 | 95.62% | 4.113% | 0.2705%
Power Delivery Solutions Operations | 18146002 | Beaver Creek II Wind - HVT | 2018-03-26 | 2018-12-31 | 0 | 1004861 | 371597 | 16578749.23 | 16173405.67 | 13254 | 16996.75 | 79.3% | 20.7% | 0%
Power Delivery Solutions Operations | 18146010 | Ivester Wind - HVT | 2018-07-30 | 2018-12-31 | 0 | 445126 | 351610 | 7820035.8755 | 7835021.46 | 9428 | 12668.25 | 78.15% | 21.85% | 0%
Power Delivery Solutions Operations | 18146022 | GE Rio Hondo 2 | 2018-11-05 | 2018-12-31 | 0 | 17 | 1 | 503433.17 | 382353.95 | 370 | 2427.5 | 78.06% | 21.94% | 0%
Wind Energy I Operations | 18141001 | Mezquite Wind | 2018-02-01 | 2018-12-31 | 0 | 0 | 0 | 19141.67 | 14091.26
Wind Energy I Operations | 18141009 | GE Foundation Analysis Wind | 2018-05-01 | 2018-12-31 | 0 | 0 | 0 | 21087.15 | 10912.37
Wind Energy I Operations | 18141011 | Bobcat Bluff Repower Wind | 2018-06-05 | 2018-12-31 | 0 | 1791 | 1569 | 19797571.86 | 18950361.83 | 70906 | 85292.18 | 81.97% | 18.03% | 0%
Power Delivery Solutions Operations | 18146009 | Arbor Hills Wind - HVT | 2018-05-21 | 2018-12-29 | 0 | 592995 | 453435 | 17748473.41 | 17657166.79 | 16616 | 18543.5 | 76.26% | 23.61% | 0.1294%
Minneapolis Operations | 18030036 | NS VI-Intertek TI | 2018-08-13 | 2018-12-28 | 70509 | 1713 | 0 | 3078984.73 | 2987570.45 | 2059 | 3448.03 | 99.54% | 0.464% | 0%
Seattle Operations | 18050040 | Swedish Edmonds Op Rm 5 | 2018-11-26 | 2018-12-21 | 0 | 2887.62 | 0 | 73954.69 | 70242.07 | 301.57 | 248 | 100% | 0% | 0%
Wind Energy I Operations | 18141004 | Arbor Hill Wind | 2018-06-01 | 2018-12-21 | 0 | 6674 | 3709 | 82254762.049 | 85272434.04 | 109139 | 140744.1 | 59.68% | 34.26% | 6.059%
Power Delivery Solutions Operations | 18146008 | Hamilton Solar - HVT | 2018-08-18 | 2018-12-15 | 0 | 37953 | 34392 | 2434876.27 | 2884562.4 | 1461 | 4655.5 | 72.47% | 27.53% | 0%
Seattle Operations | 18050009 | PRMCE Pacific Lab Equipment | 2018-09-15 | 2018-12-15 | 0 | 0 | 0 | 4620 | 7892.1
Power Delivery Solutions Operations | 18146011 | Upton County 2 BESS | 2018-08-01 | 2018-12-14 | 0 | 22372 | 25751 | 3050937.68 | 3327438.42 | 3624 | 5774.75 | 74.97% | 25.03% | 0%
Wind Energy I Operations | 18141005 | Meadow Lake VI Wind | 2018-04-02 | 2018-12-14 | 0 | 8052 | 7516 | 62367638.06 | 78148932.98 | 98993 | 195613.45 | 60.61% | 20.34% | 19.05%
Wind Energy I Operations | 18141008 | Ivester Wind | 2018-07-16 | 2018-12-07 | 0 | 3492 | 1601 | 29565394.08 | 31682082.21 | 31516 | 53435.3 | 60.82% | 33.7% | 5.479%
Civil Group Operations | 18148002 | Chokecherry Civil | 2018-04-02 | 2018-12-01 | 0 | 1237059 | 940274 | 14407678.616 | 14788980.14 | 84516 | 72171.5 | 76.04% | 23.54% | 0.4219%
Denver Operations | 18060045 | Mile High United Way-BTG | 2018-10-05 | 2018-12-01 | 0 | 716.37 | 16 | 25506.47 | 18993.02 | 68 | 32 | 75% | 25% | 0%
Civil Group Operations | 18148021 | Palo Alto Maintenance Subst | 2018-07-01 | 2018-11-30 | 0 | 0 | 0 | 56954.05 | 57389.61
Denver Operations | 18060029 | SCL-LMC First Responder | 2018-06-01 | 2018-11-30 | 0 | 1026 | 1398 | 1289562.94 | 1284063.69 | 1354 | 1556 | 90.17% | 9.833% | 0%
Milwaukee Operations | 18080018 | IUOE - Shed Door Replacement | 2018-11-27 | 2018-11-30 | 0 | 0 | 0 | 4475 | 3997.53 | 30 | 23 | 100% | 0% | 0%
Phoenix Operations | 18040013 | APS Hub West - RID Relocation | 2018-11-05 | 2018-11-17 | 100000 | 666 | 0 | 73900.9 | 93525.72 | 389 | 584 | 71.23% | 28.77% | 0%
Minneapolis Operations | 18030037 | Allina-Mercy CT #3 Renovation | 2018-07-23 | 2018-11-12 | 3500 | 0 | 11 | 698024.34 | 616846.88 | 2567 | 2226.5 | 90.52% | 9.297% | 0.1797%
Chicago Operations | 18090005 | UAL Pad of the Future (POTF) | 2018-03-01 | 2018-11-06 | 0 | 0 | 0 | 6344983.34 | 6015179.46
Minneapolis Operations | 18030023 | Fairview-BH Ligature Phase 3 | 2018-05-28 | 2018-11-01 | 0 | 2091 | 2 | 683697.83 | 649139.24 | 3828 | 2848 | 93.35% | 6.654% | 0%
Minneapolis Operations | 18030019 | UMN-Bierman Wrestling Prac | 2018-05-01 | 2018-11-01 | 13174 | 29854.59 | 0 | 1876237.9998 | 1908261.51 | 2158.05 | 2162.75 | 99.86% | 0.1387% | 0%
Chicago Operations | 18090007 | Rush Univ Med Center HR Dept | 2018-06-01 | 2018-10-31 | 10661 | 6428.78 | 17 | 742871.6399 | 747445.73 | 503 | 715 | 72.73% | 22.17% | 5.105%
Denver Operations | 18060020 | Woodward-WLC Heat Treat | 2018-04-16 | 2018-10-31 | 0 | 2 | 0 | 898332 | 864808.36 | 0 | 959.5 | 93.85% | 6.149% | 0%
Minneapolis Operations | 18030029 | Sanford Bio Skills Lab Fit Up | 2018-06-11 | 2018-10-31 | 4500 | 4 | 0 | 524870 | 496585.13 | 607 | 452 | 94.91% | 5.088% | 0%
Wind Energy I Operations | 18141003 | Charles City Repower Wind | 2018-05-01 | 2018-10-31 | 0 | 4964.5 | 1764 | 10212716.3182 | 9765221.37 | 32140 | 33932.5 | 63.27% | 35.04% | 1.692%
Milwaukee Operations | 18080006 | AHC - Suite 480 Remodel | 2018-07-03 | 2018-10-24 | 2350 | 22858 | 11014 | 675370.57 | 598345.48 | 1322.3 | 1029 | 95.34% | 4.665% | 0%
Minneapolis Operations | 18030030 | Timberwolves - TIR & Bollards | 2018-08-31 | 2018-10-19 | 7362 | 94539.39 | 46340 | 2447248.93 | 2421365.32 | 4415.4 | 4227 | 90.89% | 9.061% | 0.04731%
Seattle Operations | 18050036 | Alaska Fed Renton Branch | 2018-10-09 | 2018-10-15 | 0 | 11314.5 | 141 | 112399.83 | 109126.27 | 190.3 | 150.5 | 96.01% | 3.987% | 0%
Portland Operations | 18050019 | Kaiser SYB GenRad Replacement | 2018-08-20 | 2018-10-12 | 0 | 8286 | 1975 | 362452.73 | 359627.42 | 974 | 843 | 95.26% | 4.745% | 0%
FCG Operations | 18110001 | UDC Silver Universe LSI | 2018-01-02 | 2018-10-03 | 12500 | 15934 | 0 | 3855776.87 | 3575414.27
Milwaukee Operations | 18080017 | Downstream - Fiserv Forum | 2018-09-25 | 2018-10-03 | 50 | 0 | 0 | 0.01 | 0
Denver Operations | 18060019 | FRA-Master Plan | 2018-04-01 | 2018-10-01 | 0 | 110 | 0 | 55000 | 80569.42
Denver Operations | 18060011 | SCL-LMC Cath Lab #3 | 2018-04-23 | 2018-10-01 | 936 | 1443 | 1742 | 737579.77 | 735664.72 | 1301 | 1727 | 89.87% | 10.13% | 0%
Denver Operations | 18060013 | SCL-LMC-Pharmacy Automation | 2018-05-01 | 2018-09-30 | 960 | 871 | 641 | 276092.06 | 276137.42 | 776 | 678 | 92.55% | 7.448% | 0%
Denver Operations | 18060004 | Woodward-Hydraulics Lab | 2018-01-29 | 2018-09-28 | 0 | 70627.64 | 6919 | 11643214.5 | 11150812.01 | 5924.02 | 6556.5 | 93.99% | 6.009% | 0%
Portland Operations | 18050002 | OHSU Pharmacy & Call Center | 2018-06-17 | 2018-09-28 | 0 | 11727.99 | 839 | 2888104.97 | 2901972.42 | 1579 | 2487.5 | 94.99% | 4.945% | 0.0603%
Milwaukee Operations | 18080009 | S.C.Johnson-Rondelle | 2018-06-11 | 2018-09-24 | 5027 | 788 | 460 | 537824.35 | 739957.11 | 36 | 235.91 | 96.22% | 3.777% | 0%
Minneapolis Operations | 18030024 | Fairview-ECT Bthrm Refurb | 2018-07-03 | 2018-09-15 | 0 | 177 | 0 | 69621.14 | 68485.71 | 199 | 119 | 99.16% | 0.8403% | 0%
Minneapolis Operations | 18030032 | UMN-Anderson Hall Column | 2018-07-31 | 2018-09-01 | 0 | 6444 | 0 | 353500.414 | 321655.31 | 1145.87 | 1959.23 | 89.74% | 9.855% | 0.4083%
Minneapolis Operations | 18030035 | UMN-TCF Bank Eng Review | 2018-07-31 | 2018-09-01 | 0 | 0 | 0 | 24963 | 16040.12 | 106 | 37 | 72.97% | 27.03% | 0%
Minneapolis Operations | 18030016 | Transamerica-6300 Bldg Reno | 2018-04-02 | 2018-08-31 | 160000 | 293629.5 | 17973 | 11535413.0265 | 11622900.04 | 10966 | 10648.74 | 77.74% | 21.45% | 0.8076%
Portland Operations | 18050017 | PPS Tubman Middle School | 2018-04-05 | 2018-08-26 | 0 | 40889.31 | 11756 | 17007949.0555 | 15574863.32 | 5677.4 | 5262 | 91.25% | 7.839% | 0.9122%
Minneapolis Operations | 18030026 | UMN Frontier Hall Int Upgrades | 2018-05-21 | 2018-08-24 | 8151 | 18360 | 12110 | 1071741.3 | 1128207.11 | 2835 | 2933.89 | 98.72% | 1.278% | 0%
Denver Operations | 18060023 | SCL-LMC ED Metal Detect | 2018-05-01 | 2018-08-17 | 0 | 60 | 80 | 40125 | 40593.8 | 76 | 89 | 82.58% | 17.42% | 0%
Minneapolis Operations | 18030018 | Boiler Room Remodel | 2018-05-14 | 2018-08-17 | 0 | 4 | 0 | 1729923.1 | 1449518.04 | 2848 | 3613.74 | 97.87% | 2.131% | 0%
Seattle Operations | 18050032 | Alaska Fed Kirkland Branch | 2018-07-18 | 2018-08-14 | 0 | 9758.37 | 128 | 339639.88 | 297201.34 | 693.2 | 497 | 94.77% | 5.231% | 0%
Minneapolis Operations | 18030022 | UMN Yudof Hall Plaza Repair | 2018-05-21 | 2018-08-10 | 3500 | 17531 | 0 | 210458 | 198599.75 | 892 | 569.19 | 98.07% | 1.933% | 0%
Portland Operations | 18050021 | Kaiser MTS GenRad Replacement | 2018-05-15 | 2018-08-01 | 0 | 3270 | 339 | 300634.47 | 301096.65 | 531 | 610.5 | 85.34% | 11.88% | 2.785%
Power Delivery Solutions Operations | 18146012 | SC Johnson West MILW - HVT | 2018-01-17 | 2018-08-01 | 0 | 0 | 0 | 505283.38 | 490032.3
Denver Operations | 18060012 | SCL-LMC-USP 800 Infusion | 2018-05-01 | 2018-07-31 | 550 | 1197 | 355 | 137555.26 | 137490.26 | 550 | 364 | 89.42% | 10.58% | 0%
Seattle Operations | 18050028 | 427 9th Ave - Design Phase T | 2018-05-01 | 2018-07-31 | 0 | 0 | 0 | 226800 | 291808.84
Phoenix Operations | 18040001 | EPCOR Sun City Well 2 Equip | 2018-03-19 | 2018-07-16 | 25000 | 53973 | 0 | 1177972.13 | 1453823.58 | 1616 | 4613.5 | 92.29% | 7.706% | 0%
Minneapolis Operations | 18030027 | St Cloud Surg. Ctr-Master Ag | 2018-06-29 | 2018-07-14 | 2500 | 103 | 0 | 197224.1 | 189500.07 | 311 | 198.5 | 72.54% | 13.1% | 14.36%
Denver Operations | 18060016 | SCL-LMC RF Imaging Renovate | 2018-04-23 | 2018-07-09 | 800 | 1221.5 | 1178 | 474646.27 | 480860.37 | 1021.5 | 1206 | 88.1% | 11.9% | 0%
Denver Operations | 18060018 | SCL-St Joe's Heritage Russell | 2018-03-26 | 2018-07-01 | 0 | 87 | 0 | 13396 | 15223.62 | 82 | 65 | 63.85% | 36.15% | 0%
Wind Energy I Operations | 18141006 | Fenner RP Civil Works Wind | 2018-03-19 | 2018-07-01 | 0 | 0 | 0 | 70240 | 69561.59
Minneapolis Operations | 18030020 | Swervo-Armory Sidewalk Impr | 2018-05-07 | 2018-06-30 | 0 | 9251 | 0 | 65013 | 63310.87 | 447 | 425.5 | 91.19% | 8.813% | 0%
Portland Operations | 18050015 | OHSU - MAC Auditorium Upgrades | 2018-03-01 | 2018-06-29 | 0 | 2079.1 | 223 | 588034.02 | 620797.43 | 1323.5 | 1922 | 90.63% | 8.949% | 0.4162%
Power Delivery Solutions Operations | 18146005 | Kittie West Substation | 2018-03-22 | 2018-06-22 | 0 | 109600.8 | 120072 | 591723.7389 | 759423.94 | 2989 | 5934.5 | 84.36% | 15.64% | 0%
Denver Operations | 18060003 | SCL-LMC Data Ctr Renovations | 2018-01-03 | 2018-06-18 | 0 | 1798 | 2649 | 1163411.9525 | 1184103.83 | 2850 | 2724 | 89.61% | 10.39% | 0%
Portland Operations | 18050020 | Kaiser SMC GenRad Replacement | 2018-05-01 | 2018-06-15 | 0 | 1562 | 769 | 177075.19 | 177196.48 | 470 | 448 | 93.75% | 5.357% | 0.8929%
Milwaukee Operations | 18080003 | AHC - Manitowoc MRI Swap | 2018-03-23 | 2018-06-11 | 0 | 5468.85 | 729 | 299250.84 | 321441.14 | 473 | 422 | 94.91% | 5.095% | 0%
Denver Operations | 18060027 | SCL-St. Joe's Salad Bar | 2018-05-08 | 2018-06-08 | 0 | 0 | 0 | 8985 | 8844.29 | 0 | 28 | 89.29% | 10.71% | 0%
Denver Operations | 18060015 | SCL-Mt St Vincent Ph1 | 2018-03-19 | 2018-06-01 | 0 | 472 | 1297 | 507788.56 | 513409.72 | 432 | 2185.5 | 92.88% | 7.115% | 0%
Solar and Emerging Renewables Operations | 18145006 | Alamo 7 - MET Towers | 2018-04-23 | 2018-06-01 | 0 | 114 | 0 | 15249.19 | 13478.32 | 96 | 52 | 100% | 0% | 0%
Portland Operations | 18050001 | OHSU Voll. Inst. Bac. Remodel | 2018-03-09 | 2018-05-31 | 0 | 2165.6 | 2068 | 588733.98 | 616484.79 | 576.4 | 873 | 97.71% | 2.291% | 0%
Minneapolis Operations | 18030041 | Silver Lake Investors-428 Demo | 2018-09-17 | 2018-05-25 | 42000 | 0 | 0 | 342186 | 334411.4 | 40 | 62.5 | 100% | 0% | 0%
Power Delivery Solutions Operations | 18146001 | Bishop-Stratton HVT | 2018-02-20 | 2018-05-25 | 0 | 127446 | 126778 | 1560607.1 | 1601358.22 | 5932 | 6155 | 70.33% | 29.67% | 0%
Power Delivery Solutions Operations | 18146003 | Hidalgo Fiber Rpr Wind - HVT | 2018-02-26 | 2018-05-25 | 0 | 5 | 173 | 48589.05 | 62973.54 | 0 | 173.5 | 69.16% | 30.84% | 0%
Phoenix Operations | 18040005 | Allstate-Chandler Desert MCO | 2018-02-19 | 2018-05-18 | 96859 | 30 | 0 | 2699634.2798 | 2665492.44 | 0 | 333 | 98.65% | 1.351% | 0%
Minneapolis Operations | 18030021 | Mortenson Misc 2018 |  | 2018-05-11 | 0 | 0 | 0 | 0.01 | 286501.85 | 0 | 2277 | 98.46% | 1.537% | 0%
Minneapolis Operations | 18030009 | Axalta Coatings-Mfg | 2018-02-19 | 2018-05-04 | 54990 | 0 | 0 | 4969357.6965 | 4273622.61 | 2935 | 2235.85 | 95.89% | 3.757% | 0.3578%
Portland Operations | 18050004 | PPS Tubman Middle Sch. Precon | 2018-01-01 | 2018-04-30 | 0 | 856.4 | 0 | 385492.51 | 437496.14 | 0 | 96 | 100% | 0% | 0%
Minneapolis Operations | 18030005 | NS-Resolution Medical TI | 2018-01-11 | 2018-04-15 | 35880 | 3575 | 5381 | 1603231.97 | 1339716.53 | 1817 | 1456 | 97.73% | 2.266% | 0%
Power Delivery Solutions Operations | 18146007 | GE Rio Hondo HVT | 2018-04-09 | 2018-04-15 | 0 | 0 | 0 | 34506.34 | 19147.41 | 0 | 124 | 64.52% | 35.48% | 0%
Denver Operations | 18060009 | Park Creek-STP SML PRJ | 2018-03-12 | 2018-04-06 | 0 | 22 | 0 | 520926 | 518635.46 | 278 | 80.5 | 100% | 0% | 0%
Sports + Entertainment Group Operations | 18150007 | PSU - Lasch Player's Lounge | 2018-08-06 | 2018-04-01 | 4900 | 0 | 0 | 4158775.0441 | 4149691.11
Portland Operations | 18050016 | OHSU Compounding Pharmacy Duct | 2018-03-03 | 2018-03-03 | 0 | 398 | 0 | 18695.46 | 26206.9 | 25 | 9 | 0% | 100% | 0%
Minneapolis Operations | 18030004 | Transamerica 6350 Bldg Rmdl | 2018-01-08 | 2018-03-02 | 23620 | 5940 | 90859 | 286103.58 | 277941.42 | 243 | 287.5 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 18145001 | Misae I Solar-Childress | 2018-01-22 | 2018-02-28 | 0 | 5 | 0 | 65044 | 60671.37
Minneapolis Operations | 18030028 | MUSC-Allianz Field Exp Ctr | 2017-12-26 | 2018-02-02 | 1835 | 0 | 0 | 174754.65 | 173503.22 | 180 | 56 | 100% | 0% | 0%
FCG Operations | 18110002 | USACE Warehouse Floor Sealer | 2018-01-09 | 2018-01-31 | 8000 | 0 | 0 | 15156 | 15161.64 | 37 | 35.99 | 66.66% | 33.34% | 0%
Wind Energy I Operations | 18819 | ENXCO-CHANARAMBIE WIND FARM | 2003-12-15 | 2003-10-31 | 0 | 3422358 | 60949 | 18012075 | 18012744 | 0 | 65664 | 100% | 0% | 0%
Wind Energy I Operations | 18805 | CHI ENERGY INC.-FENNER WIND P |  | 2001-11-15 | 0 | 110060 | 107796 | 6791769 | 6803509 | 0 | 5073 | 100% | 0% | 0%
Wind Energy I Operations | 18806 | NORTHERN IOWA WINDPOWER-TOP O | 2001-12-01 | 2001-10-12 | 0 | 112312 | 51910 | 11413621 | 11407031 | 0 | 11555 | 100% | 0% | 0%
Wind Energy I Operations | 18807 | MILL RUN WINDPOWER-MILL RUN W | 2001-11-16 | 2001-09-28 | 0 | 773243 | 2806 | 2759073 | 2762007 | 0 | 3608 | 100% | 0% | 0%
Wind Energy I Operations | 18810 | ENRON WIND-MILL RUN/SOMERSET | 2001-09-20 | 2001-09-20 | 0 | 301 | 177 | 670195 | 792433 | 0 | 5241 | 100% | 0% | 0%
Wind Energy I Operations | 18811 | ENXCO-CHANDLER WINDFARM | 2001-09-01 | 2001-09-01 | 0 | 5406 | 3337 | 381592 | 384111 | 0 | 748 | 100% | 0% | 0%
Wind Energy I Operations | 18809 | GREAT RIVER ENERGY-PLEASANT V | 2002-06-01 | 2001-05-24 | 0 | 204 | 0 | 5778285 | 5786677 | 0 | 5067 | 100% | 0% | 0%
Civil Group Operations | 18148001 | Century III Repowering Civil | 2018-01-09 |  | 0 | 0 | 0 | 182170.95 | 173090.75 | 165 | 0 | 0% | 0% | 0%
Civil Group Operations | 18148003 | Beaver Creek II Civil | 2018-01-25 |  | 0 | 328991 | 493154 | 9253759.999 | 8742226.77 | 31194 | 32720.78 | 66.12% | 33.39% | 0.4905%
Civil Group Operations | 18148005 | Fenner RePowering Civil | 2018-03-20 |  | 0 | 0 | 0 | 37636 | 27955.7
Civil Group Operations | 18148006 | Arbor Hill Wind - Civil | 2018-05-21 |  | 0 | 498529 | 635000 | 20700348.0141 | 19524419.78 | 55380.12 | 70691.5 | 64.23% | 34.44% | 1.328%
Civil Group Operations | 18148007 | Charles City RePowering | 2018-04-26 |  | 0 | 466 | 51724 | 1814526.307 | 1673445.25 | 7469 | 6606 | 68.57% | 29.96% | 1.468%
Civil Group Operations | 18148008 | Hamilton Solar - Civil | 2018-06-18 |  | 0 | 151726 | 237482 | 2151914.86 | 1983225.88 | 8406 | 7186 | 76.34% | 23.66% | 0%
Civil Group Operations | 18148009 | Ivester - Civil | 2018-07-16 |  | 0 | 167193 | 143305 | 5708693.6107 | 5771061.52 | 17973.5 | 21843.2 | 69.77% | 28.05% | 2.184%
Civil Group Operations | 18148010 | Heartland Divide Wind - Civil | 2018-07-30 |  | 0 | 557190 | 318357 | 6597638.0115 | 7367568.71 | 27198 | 30294.5 | 68.38% | 31.17% | 0.4506%
Civil Group Operations | 18148012 | Buffalo Ridge Decommissioning | 2018-06-11 |  | 0 | 34803 | 0 | 617685 | 645407.63 | 1561 | 3098 | 84.04% | 15.96% | 0%
Civil Group Operations | 18148014 | Montross Solar - Civil | 2018-07-20 |  | 0 | 76961 | 20612 | 1637282.18 | 1547566.2 | 23822 | 4597.66 | 81.06% | 18.94% | 0%
Civil Group Operations | 18148015 | Pomeroy Repower Civil | 2018-08-13 |  | 0 | 6068 | 724 | 3966364.2387 | 3639394.25 | 17520 | 15046 | 72.89% | 27.11% | 0%
Civil Group Operations | 18148017 | Misae I - Civil (Solar) | 2018-11-07 |  | 0 | 380633 | 268059 | 3971026.9633 | 3974717.98 | 30963 | 17638.5 | 79.78% | 20.22% | 0%
Civil Group Operations | 18148019 | Carroll Repower Wind - CIVIL | 2018-10-10 |  | 0 | 25796.1 | 66 | 2885517.1479 | 2499907.38 | 11969 | 9748 | 81.76% | 18.24% | 0%
Civil Group Operations | 18148022 | Terrell Civil (Solar) | 2019-02-07 |  | 0 | 392575 | 369971 | 11293157.212 | 11120143.88 | 27925 | 50651.08 | 81.66% | 18.33% | 0.01086%
Civil Group Operations | 18148023 | Arlington Civil (Solar) | 2019-01-17 |  | 0 | 326510 | 157965 | 3346521.02 | 3488770.83 | 9950 | 14615 | 81.68% | 18.32% | 0%
Civil Group Operations | 18148024 | Palo Alto Wind - CIVIL | 2019-05-06 |  | 0 | 941175 | 578925 | 19880460.2707 | 18497038.05 | 67307.5 | 63657 | 66.83% | 32.37% | 0.8067%
Milwaukee Operations | 18080013 | Kohler - Riverbend Renovation | 2019-01-02 |  | 11896 | 73728 | 44224 | 2145265.98 | 1999286.68 | 1979.7 | 2096 | 90.62% | 9.065% | 0.3101%
Minneapolis Operations | 18030006 | MDI-Blaine Industrial | 2018-09-01 |  | 0 | 320729.6 | 545 | 4570823.74 | 4480780.66 | 7296.9 | 6560.47 | 96.52% | 3.475% | 0%
Minneapolis Operations | 18030040 | Snelling-Midway-Bank Demo | 2017-12-15 |  | 0 | 0 | 0 | 407036.84 | 405571.85 | 95.92 | 0 | 0% | 0% | 0%
Minneapolis Operations | 18030050 | UMN-Mariucci Arena Weight Rm | 2019-04-01 |  | 8800 | 58311 | 2168 | 1583893.92 | 1631481.55 | 2076.9 | 2539 | 99.82% | 0.1772% | 0%
Minneapolis Operations | 18030046 | Fed Re Bank - Heritage |  |  | 220000 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 18030051 | Fed Reserve Bank - Heritage |  |  | 220000 | 0 | 0 | 88158.7 | 102782.16
Phoenix Operations | 18040010 | ASU Multi-Purpose Arena |  |  | 405000 | 0 | 0 | 648016.02 | 749517.12
Phoenix Operations | 18040010-173 | Mortenson-McCarthy ASU Arenas |  |  | 405000 | 0 | 0 | 924329 | 803747.06
Portland Operations | 18050012 | OHSU NICU Flooring Replacement | 2017-10-18 |  | 0 | 20 | 0 | 3234.04 | 450.69
Portland Operations | 18050013 | OCC Office & Garage Expansion | 2020-01-01 |  | 0 | 0 | 0 | 1429378.75 | 1097834.27
Portland Operations | 18050033 | Portland Art Museum Rothko |  |  | 0 | 421575.71 | 0 | 73950228.39 | 2497116.67 | 23357.8 | 440.5 | 99.32% | 0.681% | 0%
Portland Operations | 18050054 | Nike Air Hangar 2019 | 2019-01-01 |  | 38392 | 68745.62 | 0 | 3566310.96 | 2983613.15 | 48 | 0 | 0% | 0% | 0%
Portland Operations | 18050056 | LOSD Westridge Elementary Reno | 2019-05-31 |  | 40000 | 239077.3 | 124582 | 11040334.05 | 10395518.17 | 16666.25 | 13784 | 84.8% | 13.25% | 1.948%
Seattle Operations | 18050003 | 2018 VI Project |  |  | 0 | 0 | 0 | 87750 | 208877.56
Seattle Operations | 18050010 | SEF New Yard TI |  |  | 0 | 0 | 0 | 1921633 | -2801.09 | 48 | 66.5 | 100% | 0% | 0%
Seattle Operations | 18050014 | Seattle Sports Arena Precon | 2018-11-01 |  | 0 | 2105 | 0 | 275000 | 522930.18 | 0 | 56 | 100% | 0% | 0%
Seattle Operations | 18050029 | Bend N Interceptor No 1SNIP |  |  | 0 | 76616.49 | 61858 | 27608625.695 | 25709230.19 | 12585.8 | 10482.39 | 94.08% | 5.772% | 0.1526%
Seattle Operations | 18050041 | City of Ashland Pro Service |  |  | 0 | 0 | 0 | 112572.95 | 101407.79
Solar and Emerging Renewables Operations | 18145009 | Alamo 4 - Expansion - OCI | 2018-09-20 |  | 0 | 0 | 0 | 0.01 | 328.03
Solar and Emerging Renewables Operations | 18145010 | Misae II Geotech/PLT | 2018-09-20 |  | 0 | 1058 | 0 | 245312 | 247029.14 | 656 | 505 | 84.36% | 15.64% | 0%
Solar and Emerging Renewables Operations | 18145011 | Spotsylvania Solar - SPower | 2019-03-19 |  | 0 | 38853631.78 | 18237641 | 301858678.0797 | 359631497.99 | 1300228.21 | 1941169.9 | 85.36% | 14.64% | 0.00103%
Solar and Emerging Renewables Operations | 18145014 | Wilkinson Solar-Invenergy | 2019-04-01 |  | 95975000 | 10626768.8 | 3940059 | 41031573.182 | 50125076.69 | 205072.4 | 395166.85 | 82.17% | 17.82% | 0.003796%
Solar and Emerging Renewables Operations | 18145015 | Trenton Solar - Duke Energy | 2019-04-22 |  | 101847000 | 3214376 | 3446851 | 47892694.39 | 56161787.75 | 216711.25 | 329750.7 | 82.49% | 17.51% | 0%
Solar and Emerging Renewables Operations | 18145016 | Columbia Solar - Duke Energy | 2019-08-15 |  | 105319200 | 3027036 | 2648892 | 49639199 | 49328471.19 | 186171.66 | 216322 | 88.25% | 11.75% | 0%
Solar and Emerging Renewables Operations | 18145004 | Duke-Hamilton Solar Facility | 2018-06-20 |  | 109589000 | 5033208 | 5314182 | 45758486.6 | 47629682.04 | 165306.36 | 244952.86 | 83.86% | 16.13% | 0.007552%
Solar and Emerging Renewables Operations | 18145012 | Arlington II - Silicon Ranch | 2018-02-27 |  | 138498360 | 3564635 | 5309873 | 57796986.017 | 67950769.21 | 241554.05 | 548641.28 | 85.09% | 14.9% | 0.003099%
Sports + Entertainment Group Operations | 18150001-152 | Chase Center - Concrete | 2017-01-01 |  | 0 | 0 | 0 | 120727281 | 0
Sports + Entertainment Group Operations | 18150006-172 | New England Revolution Soccer |  |  | 0 | 0 | 0 | 0.01 | 0
Sports + Entertainment Group Operations | 18150009-152 | Verizon - Chase Center DAS | 2018-12-01 |  | 0 | 0 | 0 | 20560716 | 0
Sports + Entertainment Group Operations | 18150002 | PSU - Beaver Stadium 3rd Lvl |  |  | 9450 | 0 | 0 | 190621 | 168018.96
Sports + Entertainment Group Operations | 18150008-169 | Sports Auth Nashville - MLS St |  |  | 531467 | 92295 | 0 | 271238809.6167 | 261730943.82 | 153676.65 | 67301.75 | 94.85% | 5.148% | 0%
Wind Energy I Operations | 18141018 | Panther Creek Repower | 2018-10-08 |  | 0 | 1578 | 1462 | 27282501.06 | 31509397.45 | 109340 | 179088.13 | 78.81% | 21.19% | 0%
Wind Energy I Operations | 18801 | POTLATCH-LEWISTON2001 SPRING | 2001-05-31 |  | 0 | 0 | 0 | 167966 | 190931 | 0 | 884 | 100% | 0% | 0%
Wind Energy I Operations | 18802 | BOISE CASCADE-2001WORK | 2001-12-31 |  | 0 | 0 | 0 | 14862 | 14862 | 0 | 88 | 100% | 0% | 0%
Wind Energy I Operations | 18803 | TRUS JOIST-2000 WORK | 2001-12-31 |  | 0 | 0 | 0 | 55492 | 58416 | 0 | 33 | 100% | 0% | 0%
Wind Energy I Operations | 18804 | LAND O LAKES-MISC WORK 2001 | 2001-12-31 |  | 0 | 0 | 0 | 0 | 3222 | 0 | 4 | 100% | 0% | 0%
Wind Energy I Operations | 18808 | KVAERNER-2001 SPRINGOUTAGE | 2001-05-25 |  | 0 | 0 | 0 | 250335 | 262046 | 0 | 1048 | 100% | 0% | 0%
Wind Energy I Operations | 18813 | ENRON WIND-FENNER WIND ERECTI | 2001-11-19 |  | 0 | 371 | 280 | 1454462 | 1455998 | 0 | 8408 | 100% | 0% | 0%
Wind Energy I Operations | 18814 | TEXAS WIND POWER-LLANO ESTACA | 2001-12-31 |  | 0 | 41475 | 37244 | 7025326 | 7029855 | 0 | 30037 | 100% | 0% | 0%
Wind Energy I Operations | 18816 | POTLATCH-BRAINERD2002 WORK | 2002-11-30 |  | 0 | 0 | 0 | 63529 | 63528 | 0 | 166 | 100% | 0% | 0%
Wind Energy I Operations | 18817 | TRUS JOIST-2002 WORK | 2002-11-30 |  | 0 | 0 | 0 | 0 | 648 | 0 | 0 | 0% | 0% | 0%
Wind Energy I Operations | 18818 | CALPINE-METCALF ENERGY CENTER | 2002-06-01 |  | 0 | 0 | 0 | 3114471 | 3111317 | 0 | 54 | 100% | 0% | 0%
Wind Energy I Operations | 18899 | MORTENSON-CLOSED JOBINDUSTRIA | 2001-12-31 |  | 0 | 0 | 0 | 0 | 157013 | 0 | 212 | 100% | 0% | 0%
Wind Energy I Operations | 18815 | SHERBURNE ENVIROCK-2KF WEIGHT | 2001-10-10 |  | 1175 | 271 | 0 | 19676 | 19785 | 0 | 246 | 100% | 0% | 0%
Total | [5 empty] | 126046217.26 | 83640378.5 | 5555972079.4932 | 5401771947.74 | 7085033.0311 | 9855858.01 | 82.09% | 16.98% | 0.9304%

## 2017
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
FCG Operations | 17110009 | USDA SE Poultry Research Lab | 2017-10-15 | 2023-04-12 | 243000 | 95951.5 | 0 | 141118520.89 | 115443924.9 | 0 | 7368 | 80.45% | 19.29% | 0.2647%
Minneapolis Operations | 17030050 | Genesis Silvis MCP Precon | 2018-12-01 | 2022-03-31 | 60000 | 0 | 0 | 33242.73 | 28417.61
Milwaukee Operations | 17080026 | Kohler Kitchen & Bath HQ | 2019-05-01 | 2021-06-01 | 396000 | 2086 | 0 | 300000 | 421118.13
Power Delivery Solutions Operations | 17146022 | Alice to Falfurrias | 2017-06-18 | 2021-04-30 | 0 | 2881634 | 571604 | 49114524.541 | 53858765.99 | 150638.05 | 180730.8 | 76.23% | 23.77% | 0%
FCG Operations | 17110002 | Ft Knox Medical Clinic Rplc | 2017-09-08 | 2021-04-26 | 101606 | 0 | 0 | 58698852.92 | 58428861.07 | 0 | 794.5 | 91.13% | 8.874% | 0%
Milwaukee Operations | 17080024 | Froedtert - Ambulatory | 2018-03-19 | 2021-03-22 | 193000 | 1754786.06 | 539804 | 46283943.32 | 46061599.78 | 67628.12 | 81031.11 | 84.74% | 13.65% | 1.607%
Denver Operations | 17060024 | Evergreen Dev-Clear Creek Cro | 2017-09-01 | 2020-12-31 | 0 | 224 | 0 | 362995.7 | 261181.33 | 0 | 0 | 0% | 0% | 0%
Milwaukee Operations | 17080007 | AHC-AMC Sheboygan County | 2018-09-01 | 2020-12-31 | 462185 | 6549485.06 | 2867375 | 241401451.2122 | 241661661.04 | 149269.78 | 189431.34 | 92.9% | 6.961% | 0.1346%
FCG Operations | 17110010 | UPH-BEQ Bldg 3606 Renovation | 2018-03-12 | 2020-12-22 | 94778 | 0 | 0 | 26558987.1168 | 25716489.37 | 0 | 505 | 80.1% | 19.9% | 0%
Seattle Operations | 17050019 | AC Marriott - Cascade Station | 2017-11-01 | 2020-12-01 | 0 | 0 | 0 | 0 | 35771.88
Minneapolis Operations | 17030040 | Blake-Hopkins Infrastructure | 2018-03-01 | 2020-10-01 | 0 | 12899 | 11742 | 3166193.52 | 3150811.33 | 3266 | 4903 | 95.39% | 4.609% | 0%
Wind Energy I Operations | 17141026 | Blazing Star 2 Wind | 2019-06-03 | 2020-09-08 | 0 | 11066.54 | 9299 | 103916276.1272 | 95589229.23 | 152753.1 | 108977 | 79.49% | 19.58% | 0.9208%
Minneapolis Operations | 17030005 | Coralville-IRL Hockey Arena | 2018-08-13 | 2020-08-25 | 261000 | 1557459.88 | 808432 | 54867481.3374 | 56197100.97 | 78303.15 | 68507.63 | 88.25% | 11.62% | 0.1328%
Sports + Entertainment Group Operations | 17150004 | Las Vegas Raiders | 2017-03-01 | 2020-07-31 | 0 | 0 | 239800 | 65046496.35 | 64507956.33 | 0 | 256237.99 | 81.94% | 14.1% | 3.962%
Sports + Entertainment Group Operations | 17150004-163 | LV Stadium Company-LV Stadium | 2017-11-01 | 2020-07-20 | 0 | 18438 | 0 | 1474028005.2644 | 1480541033.34 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 17060013 | WelArm-EGOS Hotel Remodel | 2018-06-01 | 2020-06-19 | 135000 | 394046.4 | 34320.5 | 37437703.0225 | 42339900.54 | 5844.5 | 38515.8 | 91.66% | 8.337% | 0%
Portland Operations | 17050007 | Nike World Headquarters Bldg 6 | 2017-08-15 | 2020-06-05 | 692087 | 163806.52 | 29567 | 272790290.9213 | 286795512.57 | 39365.5 | 92320.49 | 91.03% | 8.684% | 0.286%
Seattle Operations | 17050008 | South Lake Union Hotel | 2018-02-14 | 2020-05-29 | 0 | 674335.89 | 535843 | 83475021.6041 | 106648790.45 | 72508.24 | 104488.45 | 87.81% | 11.38% | 0.8135%
FCG Operations | 17110013 | P966 Special Ops Forces Fac | 2018-04-16 | 2020-04-19 | 81540 | 619 | 0 | 42828727.28 | 42816711.58
Sports + Entertainment Group Operations | 17150011 | LCFC Preconstruction | 2017-10-01 | 2020-03-31 | 0 | 0 | 0 | 48550 | 8615.56
Mortenson Energy Services-Operations | 17145002 | Alamo 6 O&M Solar | 2017-02-17 | 2020-01-17 | 140313600 | 36729 | 10254 | 4261806.004 | 4243034.52 | 41007 | 34780.75 | 91.97% | 8.029% | 0%
Mortenson Energy Services-Operations | 17145016 | Pearl O&M - MES | 2017-08-21 | 2020-01-01 | 0 | 5594 | 608 | 1347265 | 860825.9 | 8518 | 7125 | 91.67% | 8.33% | 0%
Seattle Operations | 17050017 | Tualatin Interceptor No 6493 | 2018-04-15 | 2019-12-31 | 0 | 47 | 0 | 30383569.916 | 30324183.95 | 46 | 480 | 100% | 0% | 0%
FCG Operations | 17110019 | USACE Site R Substat 3N1 Rplc | 2018-07-25 | 2019-12-26 | 0 | 9001 | 0 | 7032852.9051 | 6891871
Power Delivery Solutions Operations | 17146021 | Ross-Highland 69kV | 2017-07-17 | 2019-12-13 | 0 | 2903 | 0 | 21803082.61 | 22585965.82
Denver Operations | 17060034 | Rocky Mtn Public - Buell Media | 2016-08-01 | 2019-11-22 | 85000 | 935081.5 | 576071 | 28016986.3533 | 29331224.12 | 39691.7 | 49833.5 | 90.9% | 9.096% | 0%
Wind Energy I Operations | 17141025 | Blazing Star 1 Wind | 2018-08-06 | 2019-11-18 | 0 | 6498 | 6181 | 65929837.473 | 69859197.64 | 95662 | 118013.3 | 67.46% | 30.23% | 2.308%
Denver Operations | 17060022 | Charles Schwab-Phase 3 | 2018-04-16 | 2019-11-04 | 430036 | 1862475.26 | 1430007 | 45224270.6383 | 45653872.6 | 72521.98 | 85419.97 | 87.08% | 12.92% | 0%
Minneapolis Operations | 17030051 | MA-Upper Campus Re-Build | 2018-06-01 | 2019-10-31 | 0 | 1183431.42 | 947717 | 25615420.6819 | 25699242.21 | 57716.14 | 51552.98 | 92.26% | 7.713% | 0.02328%
Wind Energy I Operations | 17141012 | Fenner Repower Wind | 2017-08-01 | 2019-10-31 | 0 | 45 | 0 | 1113916.12 | 851297.48 | 466 | 691 | 84.37% | 15.63% | 0%
Milwaukee Operations | 17080023 | MarquetteUniv-12th&Wells Demo | 2017-11-20 | 2019-09-02 | 4120 | 853 | 0 | 912885.05 | 854662.5 | 694 | 201.5 | 90.07% | 3.97% | 5.955%
FCG Operations | 17110007 | DON-Repair Explosive Hndlg Wha | 2017-06-29 | 2019-08-31 | 104942 | 0 | 0 | 22648672.73 | 21725521.74 | 4600 | 7034.85 | 99.88% | 0.1208% | 0%
Milwaukee Operations | 17080017 | AHC-Pharmacy Upgrades | 2018-01-18 | 2019-08-31 | 1500 | 27651.91 | 0 | 4302381.99 | 4223022.26 | 5248.9 | 4644.5 | 90.39% | 9.28% | 0.3337%
Minneapolis Operations | 17030028 | Surmodics-Contract Coating | 2017-10-02 | 2019-08-31 | 6500 | 11677 | 0 | 1453130.4 | 1322736.16 | 746 | 730 | 96.99% | 3.014% | 0%
Denver Operations | 17060036 | Chatfield Reservoir - Modifica | 2017-12-01 | 2019-08-30 | 0 | 391798.02 | 312439 | 43023104.4323 | 46346253.91 | 48099.8 | 61946 | 82.38% | 17.62% | 0.004843%
Phoenix Operations | 17040010 | Great Wolf Lodge Scottsdale | 2018-01-15 | 2019-08-30 | 394500 | 0 | 0 | 83335656.12 | 92532681.45 | 8775 | 13640 | 83.01% | 16.99% | 0%
Milwaukee Operations | 17080009 | JMKAC - Art Preserve | 2018-04-10 | 2019-08-02 | 60000 | 570456.02 | 468835 | 23927573.102 | 24314034.65 | 26819.38 | 30756.12 | 94.58% | 5.384% | 0.03089%
FCG Operations | 17110016 | USACE 902nd OSC Ft Riley | 2019-05-06 | 2019-07-31 | 1500 | 0 | 0 | 101787.85 | 89483.74
Minneapolis Operations | 17030048 | Skogman Companies | 2017-08-01 | 2019-07-31 | 40000 | 25881.75 | 5997 | 9325170.1805 | 9491293.93 | 3298.1 | 9597.5 | 80.14% | 18.66% | 1.203%
FCG Operations | 17110011 | USACE Portal A Security Upgr | 2018-08-01 | 2019-07-09 | 2000 | 1799 | 0 | 1807963 | 1693342.11
Wind Energy I Operations | 17141016 | Rio Bravo Wind-Longroad Energy | 2018-05-15 | 2019-06-30 | 0 | 4703 | 4619 | 57503194.1889 | 66070214.57 | 102415 | 143465.98 | 80.61% | 19.39% | 0%
Minneapolis Operations | 17030023 | Blake Dining Hall Addition | 2018-04-16 | 2019-06-28 | 32200 | 254254.04 | 22893 | 6934502.4 | 6994483.88 | 15750.4 | 21796.12 | 95.32% | 4.368% | 0.312%
Seattle Operations | 17050006 | Clover Park Technical College | 2018-04-23 | 2019-06-27 | 63000 | 657223.51 | 256496 | 30764763.4727 | 29575694.05 | 20562.5 | 15450.26 | 97.01% | 2.964% | 0.02589%
Denver Operations | 17060006 | Westfield-AEG Venue | 2017-11-01 | 2019-06-21 | 0 | 1145833.8 | 612493 | 35768818.0459 | 33837030.44 | 71821.5 | 82327 | 88.39% | 11.61% | 0%
Civil Group Operations | 17148014 | Rio Bravo Civil | 2017-08-21 | 2019-05-31 | 0 | 1402736 | 1328140 | 7072957 | 9471318.67 | 27678.5 | 47620 | 78.22% | 21.78% | 0%
FCG Operations | 17110008 | CyberComm Pershing Hall | 2017-11-27 | 2019-05-31 | 5000 | 0 | 0 | 2583972.57 | 2452676.45 | 0 | 933.1 | 98.93% | 1.072% | 0%
Power Delivery Solutions Operations | 17146018 | Rio Bravo Wind - HVT | 2018-03-16 | 2019-05-18 | 0 | 706664 | 425865 | 15465617.89 | 15415980.17 | 34607.5 | 31716.25 | 83.79% | 16.18% | 0.03153%
Milwaukee Operations | 17080015 | AHC-Misc. Projects 2017-2018 | 2017-08-14 | 2019-05-17 | 0 | 626 | 66 | 1099720.0008 | 838790.86 | 4759 | 3495 | 88.43% | 9.928% | 1.645%
FCG Operations | 17110012 | USACE INSCOM Scalable Mod Data | 2018-08-20 | 2019-05-10 | 8000 | 0 | 0 | 466058.67 | 515349.16
FCG Operations | 17110020 | USACE Site C HEMP UPS Rplmt | 2018-03-08 | 2019-05-09 | 2000 | 3870 | 0 | 1821106.93 | 1690794.99
Milwaukee Operations | 17080028 | Marquette University - AHPRC | 2018-02-26 | 2019-05-01 | 46950 | 519363.48 | 306082 | 16315798.448 | 17295196.68 | 17085.7 | 24091.81 | 91.73% | 7.587% | 0.6787%
FCG Operations | 17110014 | USACE Herndon II Office Reno | 2018-05-29 | 2019-04-30 | 2117 | 0 | 0 | 366211.58 | 353856.87
Phoenix Operations | 17040009 | Polk & Central Apartment Tower | 2017-11-06 | 2019-04-30 | 250999 | 0 | 0 | 0.01 | 33832.98
Sports + Entertainment Group Operations | 17150003 | Mizzou Memorial Stadium Expan | 2018-03-01 | 2019-04-23 | 207000 | 334920.86 | 0 | 81630437.0862 | 88649756.3 | 54729.7 | 76952.5 | 98.09% | 1.791% | 0.1202%
Minneapolis Operations | 17030038 | CentraCare-LP Wellness | 2018-08-06 | 2019-04-05 | 13500 | 28450 | 0 | 2978153.24 | 2915690.29 | 5089 | 6121.49 | 93.2% | 6.6% | 0.196%
Chicago Operations | 17090010 | QTS Chicago - Hogan | 2017-08-01 | 2019-03-31 | 0 | 0 | 1008 | 5537108 | 5452614.02 | 0 | 2154.36 | 96.33% | 3.667% | 0%
Milwaukee Operations | 17080029 | AHC - Summit VLCC Pharmacy | 2018-07-09 | 2019-03-31 | 475 | 14468.5 | 8314 | 1429425.97 | 1349994.59 | 1306.8 | 1728 | 80.38% | 18.17% | 1.447%
Denver Operations | 17060014 | MDI-BioSciences 3 | 2017-12-01 | 2019-03-29 | 90000 | 1154392.59 | 600720 | 24030314.2057 | 24759643.17 | 35895.4 | 56072.97 | 89.44% | 10.56% | 0%
Milwaukee Operations | 17080021 | AHC - Kenosha 22nd Ave Clinic | 2018-03-23 | 2019-03-28 | 6000 | 43572 | 32317 | 1522340.17 | 1464477.56 | 2434.4 | 2020.5 | 89.63% | 10.02% | 0.3464%
FCG Operations | 17110015 | USACE 21st BDE Shielding - MD | 2017-11-01 | 2019-03-15 | 0 | 0 | 0 | 183502 | 175022.48
FCG Operations | 17110023 | USACE 21st DBE Shielding VA | 2017-11-01 | 2019-03-15 | 0 | 0 | 0 | 800918 | 783567.66
FCG Operations | 17110024 | USACE 21st BDE Shielding PA | 2017-11-01 | 2019-03-15 | 0 | 0 | 0 | 212752 | 198766.43
Seattle Operations | 17050021 | SLU Hotal Mockup Rooms & Cor | 2018-01-02 | 2019-03-04 | 0 | 406 | 2 | 293973.72 | 258745.6 | 445 | 295 | 94.41% | 5.593% | 0%
Solar and Emerging Renewables Operations | 17145018 | Montross Solar | 2018-06-25 | 2019-03-01 | 27973000 | 1848190 | 1791627 | 16073374.99 | 18949456.36 | 61802 | 108984.33 | 81.49% | 18.48% | 0.0367%
Milwaukee Operations | 17080020 | AHC - Grafton VLCC Pharmacy | 2018-05-15 | 2019-02-28 | 455 | 13509.5 | 9227 | 947724.37 | 937306.13 | 1179.6 | 1035 | 77.1% | 20.19% | 2.705%
Minneapolis Operations | 17030011 | MAM-HQ Campus-W Bldg Tenant | 2017-01-09 | 2019-02-28 | 15000 | 60 | 17030091 | 4087637 | 26751162.63 | 4987 | 33347.67 | 91.95% | 7.617% | 0.4348%
Phoenix Operations | 17040018 | UofA-ICA Indoor Sports Center | 2018-04-13 | 2019-02-20 | 67000 | 174 | 0 | 13800934.81 | 14265999.35 | 0 | 1682.5 | 57.06% | 35.93% | 7.013%
Minneapolis Operations | 17030043 | Swervo-N Loop Office Bldg | 2017-10-16 | 2019-02-15 | 461299 | 2649148 | 2162379 | 23671121.047 | 23571685.92 | 90428.28 | 92794.93 | 89.22% | 10.71% | 0.0625%
Minneapolis Operations | 17030031 | Faegre Baker Daniels-TI | 2017-08-21 | 2019-02-05 | 220000 | 217 | 0 | 7748785.69 | 7320761.19 | 3177 | 5525 | 78.93% | 18.39% | 2.679%
Minneapolis Operations | 17030020 | MHS-Fort Snelling Visitor Ctr | 2018-10-01 | 2019-02-01 | 50000 | 214898.69 | 174957 | 19051693.75 | 19133459.78 | 30302 | 31030.5 | 98.57% | 1.413% | 0.01289%
Milwaukee Operations | 17080019 | AHC - Grafton MainPharmReno | 2018-07-20 | 2019-01-31 | 465 | 8810 | 5101 | 507584.64 | 495820.1 | 531 | 488 | 89.86% | 10.14% | 0%
Milwaukee Operations | 17080014 | AHC - Mukwonago | 2018-07-11 | 2019-01-24 | 15000 | 130289.41 | 67909 | 5597012.67 | 5513608.14 | 7618.6 | 7416.84 | 95.74% | 4.247% | 0.01348%
Phoenix Operations | 17040020 | Brewers-Maryvale Renovation | 2018-03-26 | 2019-01-15 | 106800 | 2 | 21 | 43605607.35 | 45195701.11 | 6964 | 6945.5 | 71.47% | 28.53% | 0%
Seattle Operations | 17050005 | citizenM Hotel - San Francisco | 2017-09-01 | 2019-01-11 | 92240 | 56 | 0 | 380965.43 | 386027.12 | 56 | 48 | 100% | 0% | 0%
Minneapolis Operations | 17030029 | UMP-DB Master Agreement | 2017-06-05 | 2019-01-01 | 0 | 1 | 0 | 468723.9474 | 479363.59 | 1378.66 | 826 | 89.29% | 7.446% | 3.269%
Civil Group Operations | 17148005 | Upton II Solar - Civil | 2017-04-10 | 2018-12-31 | 0 | 337362 | 339443 | 5534210.6 | 5479461.06 | 18001 | 24963 | 80.82% | 19.18% | 0%
Denver Operations | 17060007 | Westfield-4120 Parcel B&C | 2017-09-01 | 2018-12-31 | 0 | 0 | 0 | 92087.86 | 99904.42
Denver Operations | 17060029 | 76 Commerce Bldg 5 | 2017-11-15 | 2018-12-31 | 265000 | 357943 | 1549204 | 29316324.93 | 27199304.53 | 27406.5 | 39561.5 | 83.21% | 16.79% | 0%
Minneapolis Operations | 17030001 | FUMC-Annual Contract 2017 | 2017-01-01 | 2018-12-31 | 0 | 0 | 0 | 6063010.79 | 6063010.78 | 0 | 14662.72 | 95.08% | 3.881% | 1.043%
Minneapolis Operations | 17030042 | CentraCare Health-Master Ag | 2017-10-09 | 2018-12-31 | 25000 | 707 | 3469 | 1123006.03 | 1096332.67 | 2954 | 2509.71 | 90.46% | 9.304% | 0.2391%
Minneapolis Operations | 17030030 | BSE-Branch Support Center | 2017-08-24 | 2018-12-31 | 119618 | 129574.5 | 96843 | 30057198.2108 | 30079162.36 | 22444.5 | 15859.38 | 91.99% | 8.011% | 0%
Portland Operations | 17050012 | Nike M73 | 2017-06-12 | 2018-12-31 | 0 | 2933 | 0 | 17813236.295 | 17598440.14 | 0 | 161.5 | 97.52% | 2.477% | 0%
Power Delivery Solutions Operations | 17146028 | Rattlesnake Creek Wind - HVT | 2018-04-04 | 2018-12-31 | 0 | 1872351 | 523223 | 17500658.2 | 17177126.48 | 56340 | 29543 | 76.31% | 23.55% | 0.1354%
Solar and Emerging Renewables Operations | 17145003 | Mt Signal 3 - 93LF 8ME,LLC | 2017-07-24 | 2018-12-31 | 328080450 | 22506190 | 22312567 | 318586500.35 | 306242313.05 | 646353 | 731176.86 | 91.45% | 8.177% | 0.378%
Wind Energy I Operations | 17141023 | Rattlesnake Creek Wind | 2017-11-06 | 2018-12-31 | 0 | 14424 | 13827 | 96229956.4413 | 99998588.22 | 146201 | 198476.7 | 74.24% | 24.81% | 0.9561%
FCG Operations | 17110017 | USACE FILS Phase II | 2017-11-01 | 2018-12-21 | 0 | 564 | 0 | 11902679.69 | 11110589.59 | 0 | 982.5 | 74.91% | 25.09% | 0%
Portland Operations | 17050009 | Kaiser Small Works Facilities | 2017-12-04 | 2018-12-18 | 0 | 174 | 0 | 31958 | 19298.35 | 102 | 40 | 100% | 0% | 0%
Wind Energy I Operations | 17141024 | Solomon Fork 345kV Wind | 2018-04-10 | 2018-12-17 | 0 | 20035 | 179964 | 85008674.135 | 88120482.34 | 109294 | 160791.25 | 78.22% | 21.78% | 0%
Phoenix Operations | 17040008 | Scottsdale Booster 56 & 116 | 2017-04-03 | 2018-12-10 | 0 | 153 | 88 | 1435592.992 | 1698806.37 | 3754 | 5149 | 96.11% | 3.894% | 0%
Wind Energy I Operations | 17141013 | Palo Alto Wind | 2017-09-05 | 2018-12-09 | 0 | 9191 | 7214 | 125124809.31 | 118830478.12 | 204505 | 186473.5 | 65.66% | 31.45% | 2.891%
Power Delivery Solutions Operations | 17146019 | Pearl MPT MES - HVT | 2017-12-01 | 2018-12-01 | 0 | 12876 | 350 | 178650 | 171418.78 | 406 | 130 | 79.62% | 20.38% | 0%
Wind Energy I Operations | 17141022 | Green River Wind | 2017-11-11 | 2018-12-01 | 0 | 49410 | 5503 | 85493225.35 | 89731638.19 | 118415 | 152201.13 | 69.76% | 29.16% | 1.083%
Minneapolis Operations | 17030010 | NWA-HQ Campus-W Bldg Link | 2018-05-21 | 2018-11-30 | 15000 | 65757.03 | 8 | 1932396.62 | 1980370.65 | 3986.7 | 4080 | 85.5% | 14.5% | 0%
Denver Operations | 17060041 | SCL-OBGYN Stapleton | 2018-01-22 | 2018-11-26 | 0 | 808 | 35 | 846011.4 | 844825.06 | 1714 | 1926.5 | 90.11% | 9.888% | 0%
Minneapolis Operations | 17030027 | JAUM-University Park Center | 2017-10-01 | 2018-11-09 | 47155 | 194407.16 | 118019 | 6353637.43 | 6313936.3 | 16013.9 | 14623.26 | 98.65% | 1.354% | 0%
Chicago Operations | 17090008 | United North Airfield | 2017-05-01 | 2018-11-06 | 250000 | 310383 | 5550359 | 104949161.44 | 106542645.1 | 17538 | 28524.61 | 82.19% | 14.27% | 3.548%
Sports + Entertainment Group Operations | 17150012 | PSU Lasch Position Room | 2017-12-06 | 2018-11-03 | 9300 | 209 | 0 | 2173848.71 | 2168599.59
Chicago Operations | 17090001 | NU Welsh Ryan Arena Ren. | 2017-02-03 | 2018-11-01 | 210647 | 160406.6 | 115018 | 94689601.2146 | 97633214.79 | 25928 | 21925.89 | 87.74% | 10.83% | 1.428%
Denver Operations | 17060011 | Park Creek-Filing 53 | 2017-04-06 | 2018-10-31 | 0 | 0 | 0 | 340814 | 339949.79 | 80 | 895.5 | 92.35% | 7.649% | 0%
Denver Operations | 17060020 | SCL-LMC Infrastructure 2017 | 2017-09-01 | 2018-10-31 | 0 | 11648 | 8106 | 4919691.4432 | 4915113.49 | 3656.18 | 4018.5 | 88.52% | 11.48% | 0%
Denver Operations | 17060033 | Park Creek-Aurora 3 | 2017-09-12 | 2018-10-31 | 0 | 0 | 0 | 599735 | 661639.15 | 450 | 2217 | 98.24% | 1.759% | 0%
Power Delivery Solutions Operations | 17146010 | Mount Signal 3 Solar - HVT | 2017-09-21 | 2018-10-31 | 0 | 181 | 0 | 9512455.01 | 9490404.92
Denver Operations | 17060008 | BCSP RINO-HUB RiNo Station | 2017-04-10 | 2018-10-19 | 437879 | 2766319.19 | 1144389 | 57020133.4078 | 59525490.03 | 82733.7 | 121654.65 | 87.04% | 12.96% | 0%
Minneapolis Operations | 17030041 | SCCR-Sign Reloc & Sidewalk | 2017-10-02 | 2018-10-12 | 750 | 69 | 0 | 232323.76 | 215315.06 | 484 | 711.5 | 52.28% | 39.28% | 8.433%
Milwaukee Operations | 17080022 | Froedtert - Inpatient Imaging | 2017-11-10 | 2018-10-01 | 14000 | 79773.53 | 53992 | 5049230.26 | 5044588.59 | 7048.6 | 7162.5 | 87.89% | 10.51% | 1.599%
Minneapolis Operations | 17030052 | NS VII-Office Whse | 2018-04-01 | 2018-10-01 | 200000 | 602386.26 | 18496 | 14732632.3405 | 12130890.29 | 24615.59 | 13373.13 | 93.74% | 6.263% | 0%
Sports + Entertainment Group Operations | 17150009 | PSU - Lasch Auditorium Reno | 2017-07-20 | 2018-09-30 | 0 | 0 | 0 | 851400.04 | 845422.35 | 16 | 0 | 0% | 0% | 0%
Phoenix Operations | 17040011 | SRP PAB Phase 3 West Wing | 2017-12-18 | 2018-09-28 | 100000 | 6 | 0 | 21292082.7548 | 21390597.89 | 6244 | 7551 | 94.6% | 5.395% | 0%
Phoenix Operations | 17040003 | Airport WRF Grit Removal | 2017-03-06 | 2018-09-24 | 0 | 92263 | 31313 | 5669268.7612 | 6752075.79 | 13826 | 20034.5 | 95.86% | 4.143% | 0%
Wind Energy I Operations | 17141032 | Beaver Creek Wind Phase 2 | 2018-04-23 | 2018-09-15 | 0 | 7457 | 5068 | 56860227.4705 | 55416142.29 | 83945 | 89715.5 | 59% | 36.62% | 4.381%
Milwaukee Operations | 17080013 | WEC - PSB/PSA Renovations | 2018-01-08 | 2018-09-14 | 38915 | 100643.5 | 66461 | 6376561.645 | 6188127.07 | 5637.9 | 6887.67 | 88.6% | 10.59% | 0.813%
Solar and Emerging Renewables Operations | 17145014 | Legislative Office Building | 2017-12-04 | 2018-09-14 | 132480 | 86 | 0 | 210326 | 177251.6
Minneapolis Operations | 17030036 | Dunwoody College Reno | 2017-11-15 | 2018-08-31 | 10000 | 172451.74 | 47794 | 6094922.4815 | 5353880.02 | 12293.5 | 10179.09 | 96.74% | 3.262% | 0%
Minneapolis Operations | 17030009 | NWA-HQ Campus-Parking | 2017-01-09 | 2018-08-31 | 80000 | 0 | 0 | 743095.48 | 735554.86 | 1032 | 686.76 | 87.4% | 12.6% | 0%
Portland Operations | 17050011 | Newberg ASC | 2017-12-06 | 2018-08-31 | 0 | 84774.69 | 54699 | 9051667.335 | 9184177.34 | 6261.13 | 4753.41 | 91.69% | 8.142% | 0.1683%
Sports + Entertainment Group Operations | 17150002 | Gaylord Rockies DAS | 2017-04-01 | 2018-08-31 | 0 | 0 | 0 | 3443624.02 | 2679276.15
Sports + Entertainment Group Operations | 17150005 | Milwaukee Bucks DAS | 2017-05-15 | 2018-08-31 | 0 | 0 | 0 | 5742710.52 | 5065832.36 | 0 | 312.83 | 100% | 0% | 0%
Milwaukee Operations | 17080025 | HGA-Great Lakes Office Reno | 2017-11-15 | 2018-08-10 | 41020 | 217833.65 | 201024 | 3564198.26 | 3514323.95 | 7886 | 7568.5 | 89.39% | 10.52% | 0.09249%
FCG Operations | 17110018 | USACE Fort Sill Building 2703 | 2018-01-02 | 2018-07-31 | 2000 | 734 | 0 | 234567.92 | 225289.88
Minneapolis Operations | 17030008 | NWA-HQ Campus-W Bldg Imp | 2017-01-09 | 2018-07-31 | 55000 | 0 | 0 | 1758479 | 1646192.66 | 48 | 526 | 96.39% | 3.612% | 0%
Phoenix Operations | 17040004 | Deer Valley WTP Rehab | 2017-05-01 | 2018-07-31 | 0 | 2378 | 0 | 3476635.54 | 3562675.9 | 2297 | 5381.5 | 88.87% | 11.13% | 0%
Power Delivery Solutions Operations | 17146013 | Opossum Creek Synchro Cond | 2017-10-30 | 2018-07-31 | 0 | 169030 | 195431 | 5655358.4398 | 6148084.5 | 26106.6 | 20294.15 | 77.9% | 22.1% | 0%
Denver Operations | 17060025 | FRA-Bioscience 3 Offsites | 2018-05-21 | 2018-07-27 | 90000 | 4306 | 6812 | 286133.5984 | 268493.97 | 852.97 | 1153.5 | 83.09% | 16.91% | 0%
FCG Operations | 17110022 | USACE FANX 2 Sidewalk Improv | 2018-04-23 | 2018-07-11 | 500 | 0 | 0 | 112323 | 113191.03
Milwaukee Operations | 17080012 | AHC-ED Remodel Kenosha | 2017-10-23 | 2018-07-06 | 2779 | 18652 | 32 | 1257497.7 | 1175250.6 | 2533.9 | 2794 | 89.96% | 9.789% | 0.2505%
Minneapolis Operations | 17030016 | Scouting - N Star Coun Ld Cen | 2017-05-01 | 2018-07-02 | 42000 | 255522.61 | 270918 | 8271368.075 | 8680897.73 | 17421.1 | 19421.32 | 97.6% | 2.397% | 0%
Denver Operations | 17060030 | Park Creek-Filing 55 | 2017-08-25 | 2018-06-30 | 0 | 0 | 0 | 199651 | 189148.97 | 60 | 127.5 | 96.86% | 3.137% | 0%
Phoenix Operations | 17040013 | Gilbert Rd Water Rehab | 2017-09-15 | 2018-06-30 | 0 | 1837 | 0 | 2167697 | 2405792.25 | 2029 | 3457 | 83.22% | 16.78% | 0%
Solar and Emerging Renewables Operations | 17145011 | Terning CSG - MONTSUN LLC | 2017-06-05 | 2018-06-30 | 7081425 | 208860 | 205188 | 9664442.76 | 9142075.88 | 27903 | 25284 | 80.9% | 13.99% | 5.108%
Solar and Emerging Renewables Operations | 17145010 | Murphy CSG - WAVESUN LLC | 2017-05-30 | 2018-06-30 | 7379775 | 254951 | 231028 | 9789051.82 | 10252761.72 | 29352 | 27673 | 80.3% | 15.47% | 4.233%
Portland Operations | 17050010 | Kaiser SMC QR Heads Install | 2017-12-26 | 2018-06-18 | 0 | 23047 | 2658 | 787369.07 | 578702.43 | 3320 | 1625 | 92.74% | 0% | 7.262%
Civil Group Operations | 17148004 | Beaver Creek Civil | 2017-05-05 | 2018-06-01 | 0 | 311279 | 308174 | 7818748.4666 | 7791228.25 | 33704 | 27730 | 76.53% | 23.05% | 0.4219%
Denver Operations | 17060026 | Lendlease Horizon LLC-Horizon | 2017-10-01 | 2018-06-01 | 0 | 58 | 0 | 11655.89 | 1506.83
Minneapolis Operations | 17030044 | Int Paper-Roof Repalcement | 2017-10-16 | 2018-06-01 | 9000 | 19 | 0 | 2076805.84 | 2032027.9 | 1035 | 4104.5 | 94.54% | 4.921% | 0.536%
Solar and Emerging Renewables Operations | 17145007 | Upton County 2 Solar-ConEdison | 2017-03-27 | 2018-06-01 | 233985760 | 15039320.4 | 14756842 | 118865693.7669 | 107914341.73 | 530443.12 | 499113.56 | 87.45% | 12.55% | 0%
Chicago Operations | 17090003 | Lurie Children's Inpatient Exp | 2017-07-01 | 2018-05-31 | 60000 | 51191 | 35754 | 27277150.6249 | 25548485.96 | 28381.5 | 30751.59 | 82.84% | 12.97% | 4.193%
Denver Operations | 17060043 | SCL-LMC IR Equipment Rep | 2018-01-03 | 2018-05-31 | 0 | 1415 | 1395 | 429157.57 | 435117.87 | 1295 | 1398.5 | 92.53% | 7.472% | 0%
FCG Operations | 17110021 | FANX 1 Sidewalk Improv & Rpr | 2018-04-23 | 2018-05-31 | 200 | 0 | 0 | 76964 | 77991.45
Minneapolis Operations | 17030026 | Northern Stacks VI | 2017-08-15 | 2018-05-31 | 120600 | 341124 | 0 | 8634316.87 | 6990954.09 | 14634 | 7843.06 | 92.43% | 7.567% | 0%
Milwaukee Operations | 17080010 | AHC-MRI South Shore @S.L. | 2018-01-02 | 2018-05-15 | 1642 | 13976.5 | 1762 | 793960.14 | 747115.26 | 1253 | 321 | 74.3% | 20.72% | 4.984%
Milwaukee Operations | 17080016 | AHC-IR South Shore @S.L. | 2018-01-02 | 2018-05-09 | 1150 | 8705.51 | 1822 | 777546.71 | 760430.07 | 549.2 | 1272.5 | 90.77% | 9.234% | 0%
Phoenix Operations | 17040001 | MDI-Hampton Inn FF&E | 2017-02-06 | 2018-05-09 | 0 | 0 | 0 | 3396481.91 | 2941843.15
Denver Operations | 17060028 | CCD-Glenbrook Detention Basin | 2017-10-01 | 2018-05-04 | 0 | 292021 | 41578 | 3515173.11 | 4004416.3 | 7295 | 13327 | 85.12% | 14.88% | 0%
Denver Operations | 17060002 | City & County of Denver-Mt H | 2017-03-01 | 2018-05-01 | 0 | 38947.5 | 25101 | 1356034.17 | 1694826.44 | 4334 | 7509.5 | 84.77% | 15.23% | 0%
Denver Operations | 17060005 | City & Cty of Denver-Mt Mass | 2017-05-01 | 2018-05-01 | 0 | 52698 | 28088 | 3413327.1 | 3506399.11 | 9465 | 12317.5 | 85.34% | 14.66% | 0%
Denver Operations | 17060039 | Ardent Hills-Colton CA PV | 2017-11-29 | 2018-05-01 | 0 | 0 | 0 | 19675 | 18187.67
Denver Operations | 17060040 | SCL-LMC MOB II | 2018-01-03 | 2018-05-01 | 0 | 0 | 0 | 0.01 | 2602.59
Denver Operations | 17060042 | SCL-NJH Ctr of Outpatient | 2017-12-01 | 2018-05-01 | 0 | 0 | 0 | 83581 | 61105.78
Minneapolis Operations | 17030032 | HCMC-AOSC Connectors | 2017-08-01 | 2018-04-30 | 22300 | 37408 | 4572 | 1735854.67 | 1674300.2 | 3660.5 | 3804 | 92.03% | 7.965% | 0%
Phoenix Operations | 17040019 | SRP PAB 2018 Cap Improve | 2017-09-01 | 2018-04-30 | 80000 | 0 | 0 | 28617.38 | 28426.27
Power Delivery Solutions Operations | 17146020 | East Valley BESS | 2018-01-08 | 2018-04-30 | 0 | 18928 | 1464 | 3866155.2 | 4782840.15 | 3640 | 5300 | 83.12% | 16.88% | 0%
Phoenix Operations | 17040002 | 24th St WT Res No. 3 Rehab | 2017-03-13 | 2018-04-06 | 155000 | 0 | 42 | 3090170.05 | 3503185.72 | 4786 | 4610 | 83.86% | 16.14% | 0%
Mortenson Energy Services-Operations | 17141027 | Auwahi Turbine 4 Rebuild | 2017-11-27 | 2018-04-02 | 0 | 2191561 | 0 | 5211524 | 5518573.47 | 3040 | 6739 | 66.79% | 27.16% | 6.047%
Denver Operations | 17060015 | Co Rockies-Coors Field 2017 | 2017-10-01 | 2018-04-01 | 5000 | 99029 | 18875 | 8805198.39 | 8665635.04 | 16054.97 | 21893.5 | 85.71% | 14.29% | 0%
Power Delivery Solutions Operations | 17146026 | Eleven Mile Substation HVT | 2017-12-18 | 2018-04-01 | 0 | 65417 | 66765 | 2053254.27 | 2230976.97 | 13454 | 11266 | 76.92% | 23.08% | 0%
Power Delivery Solutions Operations | 17146029 | Maxwell Stabilization | 2018-01-08 | 2018-03-31 | 0 | 60 | 0 | 311817.55 | 283966.68 | 1168 | 607 | 98.85% | 1.153% | 0%
Minneapolis Operations | 17030045 | Twins-Target Field 2018 Impr | 2017-10-16 | 2018-03-30 | 2500 | 311413.32 | 0 | 9658188.66 | 9411237.91 | 18216.2 | 18310.5 | 79.84% | 17.73% | 2.43%
Seattle Operations | 17050020 | UW WCUP TSO | 2017-07-01 | 2018-03-30 | 0 | 0 | 0 | 140264.98 | 138830.13
Seattle Operations | 17050001 | Alternate Utility Facility | 2017-07-24 | 2018-03-28 | 0 | 44164 | 35652 | 25591819.42 | 26304413.1 | 2130 | 4267.14 | 96.86% | 3.14% | 0%
Minneapolis Operations | 17030034 | UMN-CMRR Suite, Lab & CCRB | 2017-08-21 | 2018-03-09 | 3362 | 7060 | 350 | 750331.6 | 687431.66 | 774 | 353.43 | 98.59% | 1.415% | 0%
Chicago Operations | 17090011 | Mercyhealth Hospital & Clinic | 2017-09-01 | 2018-03-01 | 149200 | 608 | 0 | 632863 | 649803.75 | 40 | 15.04 | 100% | 0% | 0%
Denver Operations | 17060003 | Par Equities-Aurora Crossing | 2017-03-01 | 2018-03-01 | 0 | 163444 | 6701 | 2331461.9 | 2507170.48 | 6808 | 7819.5 | 85.3% | 14.7% | 0%
Denver Operations | 17060027 | SCL-LMC Hail Damage | 2017-07-10 | 2018-03-01 | 18000 | 2769 | 4472 | 9852749.97 | 9405410.79 | 6981 | 7434 | 87.15% | 12.85% | 0%
Minneapolis Operations | 17030025 | St David's Center at WPC | 2017-06-19 | 2018-03-01 | 5682 | 4417 | 242 | 1338658.3 | 1263157.6 | 1520.7 | 1582.28 | 93.17% | 6.826% | 0%
Wind Energy I Operations | 17141003 | Milligan 3 Wind | 2017-08-01 | 2018-03-01 | 0 | 40 | 0 | 5170240.5 | 5143794.66
Wind Energy I Operations | 17141030 | Century 3 Repower Wind | 2018-01-02 | 2018-02-26 | 0 | 599 | 503 | 2010911.34 | 1968628.08 | 7774 | 7833.5 | 60.52% | 23.02% | 16.46%
Seattle Operations | 17050013 | Prov Med Ctr Evrt - AWing | 2017-07-19 | 2018-02-15 | 0 | 4223.2 | 1417 | 352411.54 | 346977.54 | 847 | 613.76 | 97.39% | 2.607% | 0%
Solar and Emerging Renewables Operations | 17145015 | Alamo 4 Retrofit Mockup - CED | 2017-09-25 | 2018-02-09 | 0 | 203 | 196 | 23227 | 29086.31 | 194 | 105.5 | 98.58% | 1.422% | 0%
Phoenix Operations | 17040015 | CBR 1st Baseline Shade | 2017-11-17 | 2018-02-02 | 10150 | 800 | 0 | 734371.76 | 709437.88 | 71 | 0 | 0% | 0% | 0%
Chicago Operations | 17090006 | Allstate Ireland Consulting | 2017-02-03 | 2018-02-01 | 0 | 0 | 0 | 182129 | 213128.79
Denver Operations | 17060038 | SCL-LMC Fire Main Repair | 2017-12-04 | 2018-02-01 | 0 | 0 | 0 | 218879 | 220519.76
Power Delivery Solutions Operations | 17146003 | Jasper Solar I HVT | 2017-04-01 | 2018-01-31 | 0 | 15345 | 15105 | 4255850.61 | 3989816.9 | 8147.86 | 2973.5 | 94.05% | 5.946% | 0%
Phoenix Operations | 17040016 | Rockies Ceiling Replacement | 2017-12-18 | 2018-01-29 | 0 | 0 | 0 | 88313.98 | 84091.23
Minneapolis Operations | 17030035 | HSRE-West Health MOB-Reno | 2017-09-18 | 2018-01-21 | 1500 | 0 | 0 | 616278.71 | 574943.33 | 1870 | 2082.66 | 98.99% | 1.008% | 0%
Phoenix Operations | 17040017 | Industrious-Scottsdale Lincoln | 2018-02-02 | 2018-01-19 | 20062 | 0 | 0 | 2058322.57 | 2383570.35 | 0 | 526 | 97.34% | 2.662% | 0%
Phoenix Operations | 17040014 | Rio de Flag-Emergency Aeration | 2017-11-13 | 2018-01-18 | 0 | 1361 | 0 | 254522 | 244096.26 | 964 | 393 | 96.82% | 3.181% | 0%
FCG Operations | 17110006 | UDC HVAC Large | 2017-08-02 | 2018-01-17 | 2500 | 0 | 0 | 649034.24 | 538470.08
FCG Operations | 17110005 | ECB-1 INCR Inst RF Window | 2017-06-26 | 2018-01-16 | 150000 | 0 | 0 | 1052065.83 | 995051.83 | 0 | 140.23 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 17145017 | Alamo 5 Module Replacement CED | 2017-10-23 | 2018-01-14 | 0 | 33182 | 32334 | 930847 | 815545.92 | 15156 | 10175.5 | 92.04% | 7.96% | 0%
Denver Operations | 17060023 | Children's Hosp-18th & Marion | 2017-09-20 | 2018-01-12 | 0 | 146 | 0 | 113778 | 100812.97 | 0 | 8.5 | 94.12% | 5.882% | 0%
Minneapolis Operations | 17030046 | Swervo-Brickhouse Link | 2017-10-02 | 2018-01-02 | 8000 | 0 | 0 | 467061.39 | 506388.43 | 4492 | 5189.46 | 91.99% | 8.006% | 0%
Civil Group Operations | 17148016 | Intrepid Foundations Civil | 2017-09-01 | 2017-12-31 | 0 | 431 | 424 | 1231687.02 | 1179806.66 | 7516 | 7484 | 66.76% | 31.45% | 1.79%
Civil Group Operations | 17148017 | Century Fdn Upg Civil | 2017-09-01 | 2017-12-31 | 0 | 409 | 135 | 1051656.8638 | 1051171.21 | 7011 | 7360 | 67.47% | 32.07% | 0.462%
Denver Operations | 17060044 | Mort Dev-Cottrell Redevelop | 2017-01-01 | 2017-12-31 | 0 | 0 | 0 | 0.01 | 58942.32
Milwaukee Operations | 17080011 | Marquette - Misc. Projects | 2017-07-17 | 2017-12-31 | 0 | 0 | 0 | 131004 | 105510.4 | 80 | 123 | 97.56% | 2.439% | 0%
Minneapolis Operations | 17030002 | Allina-Annual Contract 2017 | 2017-01-01 | 2017-12-31 | 0 | 0 | 0 | 8369804.12 | 8369645.2 | 0 | 39071.34 | 83.59% | 15.3% | 1.107%
Minneapolis Operations | 17030037 | Basilica of St Mary-2017 | 2017-08-28 | 2017-12-31 | 0 | 2 | 0 | 175625.16 | 188814.5 | 826 | 1004.5 | 99.35% | 0.6471% | 0%
Minneapolis Operations | 17030004 | AccessAbililty-Hoover Street | 2017-04-01 | 2017-12-31 | 9244 | 33270.82 | 0 | 1570806.76 | 1631445.49 | 3043.9 | 3210.5 | 99.3% | 0.7008% | 0%
Minneapolis Operations | 17030019 | Mayo Clinic Square Phase 2 | 2017-04-27 | 2017-12-31 | 18880 | 46704 | 21313 | 3201903.95 | 3076052.17 | 5969 | 6372.5 | 95.97% | 3.288% | 0.7375%
Mortenson Energy Services-Operations | 17141001 | MSA 2017 Wind | 2017-01-01 | 2017-12-31 | 0 | 64775 | 0 | 12789482.5303 | 12789482.53 | 393279 | 170418 | 74.77% | 25.04% | 0.1878%
Mortenson Energy Services-Operations | 17141007 | GE Gen Aligns 2017 | 2017-04-26 | 2017-12-31 | 0 | 8614 | 0 | 2498397.585 | 3581367.63 | 68017 | 59086.25 | 75.79% | 23.89% | 0.3241%
Phoenix Operations | 17040005 | Mortenson Office-Rebuild |  | 2017-12-31 | 0 | 0 | 0 | 0 | 54.59
Power Delivery Solutions Operations | 17146001 | Firewheel Transmission OK HVT | 2017-03-01 | 2017-12-31 | 0 | 18 | 0 | 595408 | 472771.67
Power Delivery Solutions Operations | 17146002 | Firewheel Transmission TX HVT | 2017-03-01 | 2017-12-31 | 0 | 8 | 0 | 35910 | 23856.02
Power Delivery Solutions Operations | 17146023 | Broadview Energy JN - T01 | 2017-12-11 | 2017-12-31 | 0 | 3504 | 0 | 21447.98 | 18470.26 | 97 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 17146024 | Broadview Energy KW - T01 | 2017-12-11 | 2017-12-31 | 0 | 3202 | 0 | 18270.5 | 14995.47 | 103 | 0 | 0% | 0% | 0%
Seattle Operations | 17050018 | Surface Water Intake Gen | 2017-10-31 | 2017-12-31 | 0 | 9 | 4 | 41675.46 | 41756.89 | 136 | 134 | 85.07% | 14.93% | 0%
Solar and Emerging Renewables Operations | 17145009 | SAT Slew Drive Replacement | 2017-05-15 | 2017-12-31 | 0 | 2 | 0 | 18591 | 6708.63 | 90 | 34.5 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 17145006 | Quincy II CSG - SunShare | 2017-07-17 | 2017-12-31 | 2000000 | 0 | 0 | 2200 | 1124.25
Wind Energy I Operations | 17141005 | Moventas MSA 2017 | 2017-02-20 | 2017-12-31 | 0 | 55 | 0 | 255994.7105 | 164851.3 | 4799 | 2383.49 | 67.67% | 32.33% | 0%
Chicago Operations | 17090002 | Lurie Children's Hosp Bridge | 2017-06-01 | 2017-12-29 | 3200 | 12732 | 3783 | 4867732 | 4798247.36 | 5430 | 6966.74 | 72.26% | 17.15% | 10.59%
Milwaukee Operations | 17080004 | EUA - WEC Energy Precon Servcs | 2016-11-18 | 2017-12-29 | 0 | 0 | 0 | 5608 | 6403.48
Milwaukee Operations | 17080006 | AHC-Summit Data Center Expansn | 2017-06-13 | 2017-12-29 | 5000 | 26293.45 | 6181 | 7774982.49 | 7558018.92 | 1481.6 | 874.75 | 98.74% | 1.258% | 0%
Minneapolis Operations | 17030006 | UMN-PWB 8th Fl-Health Info | 2017-10-16 | 2017-12-29 | 8500 | 34377 | 25426 | 1368584 | 1335392.14 | 1879 | 2055.67 | 99.81% | 0.1946% | 0%
Minneapolis Operations | 17030012 | Vibra LTAC Hospital of Fargo | 2017-02-06 | 2017-12-29 | 27605 | 6697 | 4905 | 7795922.3458 | 7488659.85 | 10299 | 6210 | 96.09% | 3.913% | 0%
Mortenson Energy Services-Operations | 17141031 | Taconite Ridge | 2017-12-04 | 2017-12-18 | 0 | 0 | 0 | 34137 | 38376.54 | 40 | 250.5 | 99.8% | 0.1996% | 0%
Wind Energy I Operations | 17141008 | Intrepid Repower Wind | 2017-08-01 | 2017-12-15 | 0 | 4204 | 3058 | 17107134.704 | 16832383.57 | 52852 | 64773 | 47.08% | 43.33% | 9.592%
Wind Energy I Operations | 17141009 | Century Repower Wind | 2017-07-15 | 2017-12-15 | 0 | 3670 | 2435 | 19839711.12 | 19556942.57 | 48942 | 78415.53 | 58.73% | 17.59% | 23.67%
Wind Energy I Operations | 17141010 | Victory Repower Wind | 2017-08-01 | 2017-12-15 | 0 | 5045 | 4903 | 14583988.79 | 15486697.22 | 48200 | 62179.5 | 51.3% | 38.89% | 9.81%
Wind Energy I Operations | 17141011 | Fenton Repower Wind | 2017-08-01 | 2017-12-15 | 0 | 143 | 37 | 92457.07 | 86070.15 | 0 | 268 | 92.16% | 7.836% | 0%
Wind Energy I Operations | 17141014 | Intrepid Wind Fnd Upgrades | 2017-08-14 | 2017-12-15 | 0 | 1663 | 1555 | 12352771.7 | 11208031.16 | 37070 | 32994.5 | 68.95% | 27.95% | 3.096%
Wind Energy I Operations | 17141015 | Century Wind Fnd Upgrades | 2017-08-14 | 2017-12-15 | 0 | 1620 | 1609 | 12196024.4308 | 11249979.08 | 33649.7 | 34346.25 | 71.82% | 21.52% | 6.662%
FCG Operations | 17110004 | UDC DCM 4 Technical Library | 2017-07-10 | 2017-12-13 | 2500 | 0 | 0 | 595354.65 | 521932.61
Wind Energy I Operations | 17141028 | Palo Alto Substation Pad Wind | 2017-11-27 | 2017-12-13 | 0 | 14 | 0 | 1532577.9 | 1386754.76
Wind Energy I Operations | 17141004 | Beaver Creek Wind | 2017-06-01 | 2017-12-09 | 0 | 7277 | 5391 | 47417413.2216 | 46700711.81 | 88280 | 87065.3 | 57.9% | 29.8% | 12.3%
Seattle Operations | 17050014 | Prov Med Ctr D Wing OR 312 | 2017-07-01 | 2017-12-04 | 0 | 3376.2 | 2615 | 685239.8364 | 640240.57 | 1052.72 | 983.83 | 90.75% | 9.25% | 0%
Mortenson Energy Services-Operations | 17141029 | High Lonesome Mesa Gearbox | 2017-11-27 | 2017-12-02 | 0 | 24530 | 0 | 271963.28 | 350050.03 | 446 | 782 | 76.66% | 23.34% | 0%
Minneapolis Operations | 17030022 | CGA Mpls Office Remodel | 2017-06-01 | 2017-12-01 | 18000 | 2 | 0 | 2688070.44 | 2711832.11 | 1296 | 1610.97 | 98.42% | 1.583% | 0%
Mortenson Energy Services-Operations | 17141019 | Victory Gen. Refurbishment | 2017-09-11 | 2017-12-01 | 0 | 1 | 0 | 323265.64 | 264390.67
Denver Operations | 17060017 | Woodward-2017 Capital Imp | 2017-06-01 | 2017-11-30 | 0 | 5 | 0 | 583597 | 522296.9 | 0 | 749 | 58.48% | 41.52% | 0%
Denver Operations | 17060021 | SCL-LMC Cardia Nuclear Camera | 2017-07-24 | 2017-11-30 | 0 | 415 | 0 | 80358 | 83552.78 | 415 | 25 | 100% | 0% | 0%
Minneapolis Operations | 17030003 | Fridley Land-NS IV | 2017-03-15 | 2017-11-30 | 177600 | 6671 | 13251 | 13702488.7825 | 11063274.13 | 21585 | 8851.97 | 88.87% | 11.02% | 0.113%
Power Delivery Solutions Operations | 17146015 | Maxwell Cut-In HVT | 2017-09-05 | 2017-11-30 | 0 | 73 | 0 | 436224.3199 | 322071.92 | 966 | 1132 | 65.95% | 34.05% | 0%
Power Delivery Solutions Operations | 17146016 | Maxwell Demo HVT | 2017-09-05 | 2017-11-30 | 0 | 8 | 0 | 23903 | 11833.41 | 240 | 0 | 0% | 0% | 0%
Denver Operations | 17060018 | SCL-LMC Outpatient Pharmacy | 2017-07-12 | 2017-11-29 | 0 | 682 | 0 | 329597.85 | 333351.97 | 744 | 723 | 87.34% | 12.66% | 0%
Denver Operations | 17060019 | SCL-LMC TSN Offices | 2017-06-26 | 2017-11-29 | 0 | 2915 | 2410 | 1747162.44 | 1748968.11 | 2936 | 2768.5 | 93.08% | 6.917% | 0%
Power Delivery Solutions Operations | 17146027 | Alliance Pipeline Feisabil HVT | 2017-11-27 | 2017-11-27 | 0 | 0 | 0 | 15170 | 106.88
Denver Operations | 17060037 | SCL-St Joe's Wall of Hope | 2017-11-06 | 2017-11-24 | 0 | 52 | 0 | 10100.64 | 5854.69 | 32 | 40 | 100% | 0% | 0%
Power Delivery Solutions Operations | 17146011 | Stillwater 2 | 2017-08-01 | 2017-11-23 | 0 | 75918 | 65701 | 6351397.106 | 6055482.02 | 10358 | 9177.5 | 70.7% | 29.3% | 0%
Power Delivery Solutions Operations | 17146006 | Beaver Creek HVT | 2017-06-19 | 2017-11-21 | 0 | 369321 | 295812 | 10313594.63 | 10023056.17 | 11431 | 12597 | 84.84% | 15.16% | 0%
Denver Operations | 17060031 | SCL-St Joe's Pharmacy Retail | 2017-08-21 | 2017-11-17 | 0 | 9 | 0 | 371509.62 | 382518.93 | 1008 | 1189 | 93.27% | 6.728% | 0%
Wind Energy I Operations | 17141020 | Flat Ridge II Bolt Tensioning | 2017-09-18 | 2017-11-17 | 0 | 1357 | 0 | 147108.21 | 133858.48 | 1440 | 1519.5 | 89.21% | 10.79% | 0%
Minneapolis Operations | 17030033 | Minnehaha Academy-Reno | 2017-08-16 | 2017-11-15 | 28000 | 0 | 0 | 1126827.85 | 1119691.88 | 2214 | 2212.86 | 56.35% | 30.8% | 12.86%
Minneapolis Operations | 17030018 | CHS Renovations FY2017 | 2017-04-17 | 2017-11-13 | 330000 | 44188 | 11500 | 1974408.18 | 2007369.27 | 2914.7 | 3504.63 | 87.76% | 10.64% | 1.598%
Chicago Operations | 17090007 | Lurie Childrns Resident Lnge | 2017-06-01 | 2017-11-07 | 1020 | 1897 | 2576 | 617838.6051 | 540028.92 | 2776 | 1285.84 | 79.2% | 14.19% | 6.61%
Minneapolis Operations | 17030047 | UMN-Gibson Repairs for NFL Use | 2017-09-11 | 2017-11-06 | 88000 | 0 | 0 | 545613.15 | 536838.85 | 64 | 65 | 98.46% | 1.538% | 0%
Wind Energy I Operations | 17141002 | Firewheel Transmission Texas | 2017-04-15 | 2017-11-03 | 0 | 0 | 0 | 37914 | 38159.03
Milwaukee Operations | 17080003 | AHC-Grafton Nuclear Medicine | 2017-08-01 | 2017-11-02 | 1315 | 6944 | 0 | 371207.98 | 337520.3 | 479 | 124 | 100% | 0% | 0%
Minneapolis Operations | 17030017 | Blake Ice | 2017-03-27 | 2017-11-01 | 44113 | 75779 | 0 | 2590193.92 | 2525646.5 | 7463 | 7181 | 90.62% | 9.156% | 0.2228%
Minneapolis Operations | 17030015 | Allina-Hastings Clinic TI | 2017-02-27 | 2017-11-01 | 50095 | 21484 | 12870 | 5764205.52 | 5756056.09 | 6937 | 6308.62 | 90.51% | 9.257% | 0.2378%
Seattle Operations | 17050015 | Black Butte WWTP upgrades | 2017-08-24 | 2017-10-31 | 0 | 96.9 | 8 | 58773.83 | 49943.19 | 150.3 | 136 | 86.76% | 13.24% | 0%
Wind Energy I Operations | 17141017 | Muscatine Blade Reload | 2017-09-05 | 2017-10-31 | 0 | 1349.5 | 0 | 206994.1405 | 214381.32 | 0 | 1350.5 | 75.86% | 15.85% | 8.293%
Phoenix Operations | 17040007 | SRP PAB AV Systems Ph2 | 2017-04-03 | 2017-10-30 | 0 | 0 | 0 | 737765.67 | 737019.1
Mortenson Energy Services-Operations | 17141021 | King Mtn. M-03 Demolition | 2017-10-06 | 2017-10-20 | 0 | 554 | 0 | 140954 | 152499.51 | 0 | 867.5 | 71.3% | 28.7% | 0%
Power Delivery Solutions Operations | 17146012 | Stuttgart Substation HVT | 2017-07-24 | 2017-10-19 | 0 | 70461 | 68709 | 983232.13 | 782102.62 | 6309 | 4485.49 | 81.96% | 18.04% | 0%
Civil Group Operations | 17148009 | Redstone Arsenal Civil | 2017-07-01 | 2017-10-18 | 0 | 38676.02 | 28663 | 681251.973 | 574225.68 | 2608 | 2067 | 83.12% | 16.88% | 0%
Milwaukee Operations | 17080005 | AHC-Healing Garden Railing @SL | 2017-06-20 | 2017-10-13 | 1056 | 3510.5 | 0 | 716124.55 | 679732.48 | 204.5 | 337 | 96.74% | 3.264% | 0%
Power Delivery Solutions Operations | 17146017 | Alamo 5 & 7 PRC 005 HVT | 2017-09-20 | 2017-10-06 | 0 | 0 | 0 | 8122.18 | 7106.81
Denver Operations | 17060035 | SCL-Good Sam Fire Line Repair | 2017-09-01 | 2017-09-30 | 0 | 0 | 0 | 129011 | 129370.08
Minneapolis Operations | 17030039 | TCO-WH MOB-Level 2 Reno | 2017-07-03 | 2017-09-30 | 1200 | 0 | 0 | 374478.04 | 358477.34 | 1148 | 1185.82 | 93.89% | 6.114% | 0%
Mortenson Energy Services-Operations | 17141018 | Shannon Turbine 3 Demo | 2017-09-06 | 2017-09-18 | 0 | 208360 | 0 | 232105.62 | 194083.89 | 0 | 964.5 | 66.56% | 33.44% | 0%
Milwaukee Operations | 17080002 | Johnson Controls - Pond Renvtn | 2017-04-10 | 2017-09-08 | 0 | 8969.69 | 840 | 554416.18 | 521171.36 | 1982.9 | 1957 | 99.74% | 0.2555% | 0%
Sports + Entertainment Group Operations | 17150007 | PSU - Energy Savings Program | 2017-06-19 | 2017-09-02 | 0 | 688 | 0 | 602981.7 | 583161.3 | 388 | 241.5 | 89.03% | 9.524% | 1.449%
Chicago Operations | 17090004 | Allstate Jcksnvl 2017 Misc. | 2017-02-03 | 2017-09-01 | 0 | 0 | 0 | 1250222.79 | 1207397.71 | 0 | 0 | 0% | 0% | 0%
Chicago Operations | 17090005 | QTS Chicago Phase 2 | 2017-02-03 | 2017-09-01 | 0 | 50104 | 237 | 3658782.77 | 3514129.89 | 3212 | 2656.25 | 90.97% | 8.536% | 0.4894%
Chicago Operations | 17090009 | Halas Hall Consulting | 2017-05-01 | 2017-09-01 | 0 | 0 | 0 | 445945 | 310212.1 | 0 | 53.33 | 100% | 0% | 0%
Denver Operations | 17060004 | Woodward-IS Equipment | 2017-02-22 | 2017-09-01 | 100000 | 0 | 0 | 1807556 | 1586099.72 | 0 | 1357 | 82.65% | 17.35% | 0%
Denver Operations | 17060032 | SCL-St Joe's CT3 Power | 2017-08-21 | 2017-08-31 | 0 | 0 | 0 | 15117.01 | 15064.7 | 0 | 12 | 100% | 0% | 0%
FCG Operations | 17110001 | UDC Silver Galaxy ATD | 2017-05-17 | 2017-08-21 | 12500 | 0 | 0 | 272987 | 287161.73
Seattle Operations | 17050002 | Yahoo! GQ2 Office TI | 2017-02-06 | 2017-08-18 | 21156 | 25 | 0 | 2140362.97 | 2134965.8 | 82 | 0 | 0% | 0% | 0%
Minneapolis Operations | 17030013 | UMN-Frontier Hall HVAC | 2017-05-15 | 2017-08-15 | 175510 | 317203 | 8948 | 6475452.81 | 6561681.67 | 5991.35 | 6534.98 | 88.65% | 10.58% | 0.7651%
Denver Operations | 17060016 | SCL-LMC Parking Lot Security | 2017-07-10 | 2017-08-01 | 0 | 16 | 0 | 15224 | 15363.18 | 16 | 20 | 82.5% | 17.5% | 0%
Milwaukee Operations | 17080008 | Johnson Controls - Bld.4,Flr 1 | 2017-05-12 | 2017-07-31 | 4847 | 6343 | 6245 | 166363 | 159899.78 | 524 | 510 | 98.24% | 1.765% | 0%
Power Delivery Solutions Operations | 17146014 | Clearwater Trans Line HVT | 2017-06-01 | 2017-07-28 | 0 | 0 | 0 | 11718 | 7160.62
Civil Group Operations | 17148008 | Terning CSG Solar - Civil | 2017-06-01 | 2017-07-17 | 0 | 35 | 0 | 555082 | 471386.08 | 960 | 1913 | 80.97% | 19.03% | 0%
Civil Group Operations | 17148002 | Jasper Civil | 2017-02-01 | 2017-07-01 | 0 | 234599 | 147405 | 5226993.46 | 5401867.11 | 16942 | 19761.5 | 80.67% | 19.33% | 0%
Civil Group Operations | 17148006 | Stuttgart Civil | 2017-05-01 | 2017-07-01 | 0 | 68688 | 17001 | 1598236.99 | 1484688.81 | 5130 | 2945 | 75.3% | 24.7% | 0%
Civil Group Operations | 17148007 | Murphy CSG Civil | 2017-05-01 | 2017-07-01 | 0 | 30 | 0 | 493820 | 435546.13 | 960 | 1104.5 | 75.69% | 24.31% | 0%
Denver Operations | 17060009 | Woodward-RMTIC | 2017-04-03 | 2017-07-01 | 0 | 0 | 0 | 468817 | 422704.68 | 0 | 692 | 69.8% | 30.2% | 0%
Denver Operations | 17060012 | Stadium Mgmt-Broncos 2017 | 2017-04-17 | 2017-07-01 | 0 | 20 | 304 | 595466.25 | 753556.83 | 0 | 4055.5 | 87.18% | 12.82% | 0%
Portland Operations | 17050016 | OHSU Vollum Preconstruction | 2017-01-01 | 2017-07-01 | 0 | 127 | 0 | 12466.31 | 79007.45 | 64 | 86 | 100% | 0% | 0%
Civil Group Operations | 17148001 | Ridgeland Civil | 2017-01-09 | 2017-06-30 | 0 | 756963 | 39188 | 1481167.69 | 1410215.1 | 4280 | 4945 | 79.94% | 20.06% | 0%
Denver Operations | 17060010 | SCL-LMC Integration System | 2017-04-01 | 2017-06-30 | 0 | 0 | 0 | 35269 | 35436.71 | 0 | 329 | 60.49% | 39.51% | 0%
Wind Energy I Operations | 17141006 | Ocotillo WTG 126 | 2017-01-23 | 2017-06-30 | 0 | 734418 | 0 | 1288473.986 | 1316111.51 | 5734 | 3278.51 | 82% | 17.13% | 0.8693%
Power Delivery Solutions Operations | 17146007 | Alamo 6 - HVT - MPT FND | 2017-05-15 | 2017-06-15 | 0 | 617 | 0 | 257225.17 | 255375.18 | 867 | 694 | 92.07% | 3.89% | 4.035%
Phoenix Operations | 17040006 | AlaskaUSA-Glendale Financial | 2017-02-20 | 2017-06-12 | 5257 | 0 | 0 | 1308220.42 | 1377272.96 | 0 | 25 | 100% | 0% | 0%
Power Delivery Solutions Operations | 17146005 | AEP Paint Creek | 2017-03-13 | 2017-05-31 | 0 | 104 | 0 | 38478 | 37359.2 | 360 | 320.5 | 74.88% | 25.12% | 0%
Solar and Emerging Renewables Operations | 17145005 | Midway - Hanwha Q Cell | 2017-04-10 | 2017-05-31 | 229100000 | 13 | 0 | 76056.42 | 43879.51 | 0 | 190.5 | 78.35% | 21.65% | 0%
FCG Operations | 17110003 | Westway Suite Renovation | 2017-05-01 | 2017-05-15 | 1750 | 0 | 0 | 81456.33 | 82331.01
Milwaukee Operations | 17080001 | Johnson Controls - Bld.3,Flr 4 | 2017-03-01 | 2017-05-05 | 9950 | 24355 | 22692 | 298648.6 | 284944.27 | 628.5 | 574 | 100% | 0% | 0%
Power Delivery Solutions Operations | 17146004 | AEP -Fermi Metering | 2017-02-10 | 2017-05-01 | 0 | 9316 | 0 | 47966.53 | 35389.06 | 480 | 623.41 | 63.35% | 36.65% | 0%
Power Delivery Solutions Operations | 17146008 | Sweetwater 3 Repower Analysis | 2017-02-27 | 2017-05-01 | 0 | 4 | 0 | 21739 | 17948.96
Power Delivery Solutions Operations | 17146009 | Cedar Creek Repower Analysis | 2017-03-01 | 2017-05-01 | 0 | 5 | 0 | 21739 | 18142.77
Denver Operations | 17060001 | Co Rockies-Coors Fld Concessio | 2017-01-26 | 2017-03-31 | 2800 | 3 | 0 | 763619.33 | 749702.06 | 0 | 1552.5 | 78.26% | 21.74% | 0%
Minneapolis Operations | 17030007 | Twins-Target Field 2017 Imp | 2017-01-23 | 2017-03-17 | 2500 | 8 | 0 | 502925.98 | 490091.26 | 1094 | 693 | 100% | 0% | 0%
Civil Group Operations | 17148003 | Griffin Trail Wind Civil | 2016-12-22 | 2016-12-31 | 0 | 387 | 0 | 94203 | 32203.18 | 692 | 0 | 0% | 0% | 0%
Seattle Operations | 17013 | St of WA-Leg Bldg Rehab & Add | 2006-12-31 | 2004-12-29 | 267000 | 19484 | 39660 | 82983531 | 83033622 | 0 | 79805 | 100% | 0% | 0%
Seattle Operations | 17010 | CH2M HILL-CEDAR TREATMENT FAC | 2004-06-01 | 2004-06-01 | 0 | 16110 | 0 | 1177457 | 1258963 | 0 | 3511 | 100% | 0% | 0%
Seattle Operations | 17016 | AK AIR-HANGAR MAINTN FACILITY | 2004-01-31 | 2004-03-19 | 0 | 20654 | 7192 | 11136325 | 11148445 | 0 | 20095 | 100% | 0% | 0%
Seattle Operations | 17001 | TULALIP TRIBES-NEW TULALIP CA |  | 2003-06-30 | 245000 | 383493 | 569152 | 4596846 | 4650460 | 0 | 47734 | 100% | 0% | 0%
Seattle Operations | 17018 | MICROSOFT-CRITICAL ENVIRONMEN | 2002-12-31 | 2002-12-31 | 0 | 0 | 0 | 0 | 698606 | 0 | 31 | 100% | 0% | 0%
Seattle Operations | 17015 | UC BERKELEY-INSECTRY& GRNHOUS | 2001-10-31 | 2001-12-06 | 8000 | 443 | 0 | 2438794 | 2448940 | 0 | 2428 | 100% | 0% | 0%
Seattle Operations | 17012 | UNIV BOOKSTORE-BOTHELL CAMPUS | 2001-06-25 | 2001-06-25 | 10510 | 109 | 0 | 471049 | 478884 | 0 | 821 | 100% | 0% | 0%
Seattle Operations | 17003 | AK AIR-FLGHT ASI 55IMPROVEMEN | 2001-04-02 | 2001-04-02 | 4038 | 0 | 0 | 279955 | 280461 | 0 | 734 | 100% | 0% | 0%
Seattle Operations | 17004 | AK AIR-FLGHT MISC FINISH IMPR | 2001-04-02 | 2001-04-02 | 4500 | 0 | 0 | 43029 | 42860 | 0 | 65 | 100% | 0% | 0%
Civil Group Operations | 17148010 | Mount Signal 3 - Civil | 2017-08-15 |  | 0 | 502733 | 445098 | 5902497.66 | 6386036.31 | 18424 | 24742.5 | 80.55% | 19.05% | 0.4082%
Civil Group Operations | 17148011 | Intrepid RePowering Civi | 2017-08-14 |  | 0 | 54010 | 144 | 2587332.3734 | 2624003.42 | 9657.12 | 10408.5 | 71.71% | 28.08% | 0.2162%
Civil Group Operations | 17148012 | Century RePowering Civil | 2017-08-14 |  | 0 | 117661 | 126681 | 3689986.9932 | 3425349.66 | 13198.5 | 11978.5 | 72.89% | 26.91% | 0.2004%
Civil Group Operations | 17148013 | Victory RePowering Civil | 2017-08-14 |  | 0 | 13396 | 7113 | 1896627.2971 | 1900596.08 | 6540.24 | 8832.5 | 71.11% | 28.26% | 0.6284%
Civil Group Operations | 17148015 | Pinal Solar - Civil | 2017-10-13 |  | 0 | 16260 | 68144 | 1110128.8 | 1157039.71 | 4736 | 5843 | 81.48% | 18.52% | 0%
Civil Group Operations | 17148018 | Rattlesnake Creek Wind - Civil | 2017-11-06 |  | 0 | 4439850 | 7882813 | 29768503.52 | 29040610.36 | 100562 | 98382.95 | 76.56% | 23.44% | 0%
Civil Group Operations | 17148019 | Palo Alto Substation - Civil | 2017-11-28 |  | 0 | 11 | 0 | 1245174.8 | 1225205.93 | 3470 | 2443.5 | 54.08% | 38.14% | 7.776%
Civil Group Operations | 17148020 | Green River Wind - Civil | 2017-11-28 |  | 0 | 1 | 800 | 517868 | 581461 | 1305 | 1004.5 | 83.92% | 15.93% | 0.1493%
Minneapolis Operations | 17030021 | TCF Bank Stadium Wall Rpr |  |  | 0 | 0 | 0 | 0.01 | 186868.16 | 0 | 604.5 | 86.52% | 13.48% | 0%
Minneapolis Operations | 17030024 | Mortenson Misc |  |  | 0 | 0 | 0 | 0.01 | 9667.82 | 0 | 55 | 100% | 0% | 0%
Minneapolis Operations | 17030049 | MDI-Discovery Square Phase 2 |  |  | 0 | 597235.4 | 110394 | 25703038.2293 | 24111745.03 | 25034.9 | 22052 | 96.21% | 3.752% | 0.03628%
Minneapolis Operations | 17030014 | UMP-Shingle Creek Pkwy TI | 2017-01-25 |  | 2000 | 0 | 0 | 29735.19 | 30542.83 | 102 | 102 | 92.16% | 7.843% | 0%
Phoenix Operations | 17040012 | Phx Rising Precon & Consult | 2017-07-21 |  | 0 | 0 | 0 | 10393 | 12240.53
Portland Operations | 17050004 | Kaiser IDIQ Precon | 2017-06-01 |  | 0 | 46 | 0 | 202677.04 | 232785.87 | 0 | 80 | 100% | 0% | 0%
Portland Operations | 17050003 | Mortenson Portland Office | 2017-02-15 |  | 8107 | 0 | 0 | 551509 | 563224.15 | 184 | 100 | 100% | 0% | 0%
Seattle Operations | 17002 | MICROSOFT-DUSC 2001 | 2001-12-31 |  | 0 | 0 | 0 | 142909 | 257347 | 0 | 0 | 0% | 0% | 0%
Seattle Operations | 17014 | ST OF WA-EMERGENCY REPAIRS | 2001-05-31 |  | 0 | 55 | 0 | 0 | 785443 | 0 | 1477 | 100% | 0% | 0%
Seattle Operations | 17021 | BELLEVUE TECH TOWER | 2001-12-14 |  | 0 | 624 | 0 | 36144 | 36874 | 0 | 252 | 100% | 0% | 0%
Seattle Operations | 17999 | MORTENSON-CLOSED JOBSEATTLE O | 2001-12-31 |  | 0 | 0 | 0 | 0 | 21805
Seattle Operations | 17005 | QUILEUTE TRIBAL SCHOOL-GYMNAS | 2002-01-31 |  | 16476 | 60943 | 27583 | 3665785 | 3692195 | 0 | 9405 | 100% | 0% | 0%
Seattle Operations | 17017 | AK AIR FTC PHASE IV EXPANSION |  |  | 26037 | 0 | 0 | 5043 | 5209
Seattle Operations | 17020 | EVERETT FACILITIES-EVENTS CTR |  |  | 200000 | 0 | 0 | 0 | 7708
Solar and Emerging Renewables Operations | 17145008 | AlamoVII Demo & 1 MW Add - CED | 2017-04-20 |  | 11811366 | 26 | 12 | 31884.91 | 42940.26 | 350 | 331 | 84.59% | 15.41% | 0%
Solar and Emerging Renewables Operations | 17145012 | Redstone Arsenal - SunPower | 2017-06-14 |  | 12528000 | 953224 | 1051926 | 5372105.7717 | 5800616.31 | 44691.76 | 53504.59 | 82.28% | 17.72% | 0%
Solar and Emerging Renewables Operations | 17145013 | Pinal Solar Project | 2017-11-13 |  | 30960000 | 2241585 | 2013138 | 19638993.95 | 18802722.61 | 76291 | 73368 | 87.14% | 12.86% | 0%
Solar and Emerging Renewables Operations | 17145004 | Stuttgart Solar Project | 2017-06-30 |  | 125553090 | 7998711 | 7320181 | 33571940.57 | 35482435.73 | 280083 | 328477.83 | 82.97% | 17.03% | 0%
Sports + Entertainment Group Operations | 17150006 | Raiders Las Vegas Stadium |  |  | 0 | 0 | 0 | 0 | 1678.22
Sports + Entertainment Group Operations | 17150010 | Mobilitie - MN United MLS DAS |  |  | 0 | 91 | 0 | 1857012.49 | 1828959.81 | 90 | 210 | 95.24% | 4.762% | 0%
Total | [5 empty] | 101472770.48 | 103492136.5 | 5633596479.1216 | 5686481510.35 | 5821573.49 | 6798886.12 | 82.63% | 16.06% | 1.314%

## 2016
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Milwaukee Operations | 16080015 | S.C. Johnson-West Side Campus | 2017-03-06 | 2020-09-01 | 150517 | 2634439.85 | 1097477 | 72706913.9812 | 70618759.47 | 89972.41 | 89000.09 | 92.47% | 7.347% | 0.1848%
Denver Operations | 16060001 | Park Creek-Filing M-L MLK | 2018-10-08 | 2020-01-31 | 0 | 0 | 0 | 1476316 | 1855900.54 | 2173 | 3861 | 97.58% | 2.422% | 0%
Denver Operations | 16060023 | MDI-2250 Blake St Hotel | 2018-08-20 | 2020-01-31 | 110000 | 0 | 0 | 250039 | 258024.05
Milwaukee Operations | 16080026 | Froedtert-CFAC Vertical Expans | 2017-05-19 | 2020-01-31 | 166420 | 1196779.05 | 536257 | 75240433.055 | 74851368.74 | 83061.89 | 86720.12 | 89.21% | 10.16% | 0.6336%
Denver Operations | 16060016 | Six Continents Hotel-2250 Bl | 2017-03-01 | 2019-12-31 | 110000 | 0 | 0 | 0.01 | 0
Milwaukee Operations | 16080021 | AHC-Misc. Projects 2016-2017 | 2016-08-22 | 2019-12-31 | 0 | 1246 | 0 | 387503 | 331944.92 | 1372 | 1172.5 | 86.52% | 13.48% | 0%
Denver Operations | 16060033 | Park Creek-Filing PB | 2016-11-15 | 2019-12-30 | 0 | 0 | 0 | 1826462 | 1846967.24 | 2760 | 6720.5 | 99.06% | 0.9449% | 0%
Denver Operations | 16060003 | CoorsTek WTM AMP | 2017-02-20 | 2019-11-30 | 160000 | 12273.8 | 33956 | 61534552.9329 | 62295973.58 | 22937.3 | 57187 | 89.7% | 10.3% | 0%
FCG Operations | 16110003 | GSA-FASTC Contract 02 | 2016-10-06 | 2019-11-29 | 210034 | 5688028.93 | 4519432 | 145573512.6038 | 174830864.43 | 175163.4 | 407973.46 | 78% | 21.96% | 0.04522%
Portland Operations | 16050011 | HE Portland HC LLC Hyatt | 2018-02-19 | 2019-11-26 | 0 | 1616633.9 | 564596 | 48996318.8752 | 50320439.53 | 40404.08 | 52049.66 | 82.23% | 16.99% | 0.7877%
Seattle Operations | 16050010 | citizenM Hotel-Seattle | 2017-03-21 | 2019-10-17 | 96285 | 374550.72 | 333480 | 51418397.2634 | 52748582.05 | 37391.58 | 83540.99 | 81.1% | 17.09% | 1.813%
Denver Operations | 16060031 | Park Creek-Filing 54 | 2017-11-01 | 2019-08-31 | 0 | 4661 | 43 | 5178630.9044 | 5656846.1 | 7439 | 16187.5 | 95.21% | 4.788% | 0%
Wind Energy I Operations | 16141018 | Walnut Ridge Wind | 2017-08-14 | 2019-08-01 | 0 | 24653 | 21934 | 104805158.5076 | 103427753.63 | 106726 | 142205.5 | 67.38% | 28.5% | 4.114%
Milwaukee Operations | 16080027 | Marquette - APRC | 2017-10-01 | 2019-07-01 | 305500 | 0 | 0 | 167868.63 | 54340.42 | 0 | 3 | 0% | 100% | 0%
FCG Operations | 16110004 | DON-Cherry Pt P-194 UAS Fac | 2017-06-06 | 2019-06-28 | 79973 | 946 | 0 | 25326570.7 | 28493768.52 | 2600 | 6707 | 89.6% | 10.18% | 0.2236%
Denver Operations | 16060020 | UCHealth-HR Hospital | 2016-10-01 | 2019-06-01 | 397320 | 5307203.02 | 3762020.33 | 239503448.8864 | 243788120.19 | 287855.59 | 397342.99 | 82.72% | 17.28% | 0%
FCG Operations | 16110001 | DON-P611 Crab Island Secu. Enc | 2016-06-28 | 2019-04-30 | 2180 | 688048 | 486944 | 47489397.34 | 45065788.02 | 127576 | 142849.57 | 85.45% | 14.55% | 0%
Minneapolis Operations | 16030046 | MDI- Discovery Sq | 2017-10-30 | 2019-03-31 | 80000 | 713621.27 | 325261 | 22743842.4 | 21994416.08 | 24487.5 | 18930.36 | 92.37% | 7.625% | 0%
Minneapolis Operations | 16030010 | MN United-MN Soccer Stadium | 2017-06-14 | 2019-02-22 | 350000 | 3299819.69 | 2659885 | 178582065.541 | 177512793.97 | 156265.79 | 178624.82 | 88.2% | 11.34% | 0.461%
Chicago Operations | 16090003 | Rockford Memorial Hospital | 2016-07-01 | 2019-02-01 | 530000 | 602837.85 | 340051 | 316186531.0793 | 310912710.02 | 108559.5 | 95323.07 | 83.64% | 13.02% | 3.343%
Chicago Operations | 16090004 | 110 West Huron | 2017-09-05 | 2019-01-07 | 121722 | 3659 | 1093 | 45532958.9401 | 43952392.6 | 3311.5 | 8870.11 | 86.09% | 10.46% | 3.45%
Denver Operations | 16060025 | Woodward-Drake Renovation | 2017-01-03 | 2018-12-31 | 0 | 133427.33 | 305 | 27717200.65 | 26085463.78 | 9322.7 | 18633 | 92.01% | 7.994% | 0%
Power Delivery Solutions Operations | 16146021 | Rush Creek Wind - HVT | 2016-04-29 | 2018-12-31 | 0 | 835963 | 1096382 | 53200972.6867 | 51913960.16 | 77844 | 88447.99 | 78.31% | 21.69% | 0%
Milwaukee Operations | 16080022 | Froedtert-IPP Phase 2 | 2017-04-01 | 2018-12-01 | 40300 | 341762.76 | 230061 | 23050441.0008 | 22931598.6 | 25363.38 | 29076.25 | 89.66% | 9.407% | 0.9286%
Milwaukee Operations | 16080023 | Froedtert-IPP Central Sterile | 2017-01-09 | 2018-11-21 | 31000 | 492480 | 267094 | 15791605.099 | 15769263.23 | 17589.1 | 21567.25 | 92.5% | 6.37% | 1.131%
Denver Operations | 16060012 | Park Creek-Central Park Bridge | 2017-02-01 | 2018-10-31 | 0 | 0 | 0 | 827980 | 893155.25 | 100 | 9 | 100% | 0% | 0%
Civil Group Operations | 16148021 | Rush Creek Civil | 2017-06-03 | 2018-10-12 | 0 | 1591045 | 1009403 | 26694294.14 | 30584264.05 | 126660 | 148639.55 | 78.13% | 21.87% | 0%
Wind Energy I Operations | 16141016 | Rush Creek Wind | 2016-06-03 | 2018-10-12 | 0 | 88359 | 16124 | 173967484.58 | 169456153.36 | 240639 | 245250.55 | 82.86% | 17.14% | 0%
Milwaukee Operations | 16080028 | Johnson Controls - Misc. Jobs | 2016-12-28 | 2018-10-01 | 0 | 24 | 0 | 56100 | 40366.37 | 383 | 259.37 | 91.13% | 8.868% | 0%
Chicago Operations | 16090009 | Harper College Building M | 2017-03-01 | 2018-08-31 | 132000 | 372.6 | 47 | 34818630.35 | 34781108.81 | 4264 | 4938.98 | 87.64% | 11.39% | 0.9719%
FCG Operations | 16110002 | DOA-Comm Conc Encased DuctBank | 2017-04-22 | 2018-08-06 | 4500 | 0 | 0 | 867733.17 | 899063.25
Milwaukee Operations | 16080003 | Ministry HC - St. Clare's Exp. | 2016-07-05 | 2018-07-27 | 44219 | 508644.5 | 303217 | 18996538.8878 | 18482550.07 | 30209.5 | 32819 | 90.52% | 9.312% | 0.1676%
Milwaukee Operations | 16080012 | Milwaukee Bucks New Arena | 2016-06-01 | 2018-07-24 | 730000 | 3259426.51 | 1896968 | 337490358.9682 | 339038734.98 | 168629.49 | 192033.67 | 86.98% | 12.81% | 0.2106%
Denver Operations | 16060030 | Park Creek-Filing 52 | 2016-12-15 | 2018-06-30 | 0 | 0 | 7 | 780635 | 835305.35 | 312 | 1842 | 97.88% | 2.117% | 0%
Solar and Emerging Renewables Operations | 16145010 | Big Lake Solar Garden - NRG | 2016-10-17 | 2018-06-30 | 6912000 | 420018 | 419110 | 5616591.4316 | 5872798.51 | 33072 | 33581.45 | 85.63% | 10.45% | 3.914%
Denver Operations | 16060029 | Westfield-4120 Infrastructure | 2017-03-01 | 2018-05-31 | 0 | 554 | 1506 | 9832872.47 | 9629111.95 | 1635 | 6166.5 | 94.28% | 5.716% | 0%
Minneapolis Operations | 16030038 | Jack Links-HQ Improvement | 2016-12-15 | 2018-05-31 | 77267 | 284692.71 | 80926 | 22653399.6324 | 22533633.5 | 14953.7 | 15532.12 | 94.96% | 4.822% | 0.2189%
Minneapolis Operations | 16030030 | Block 9 Redevelopment | 2016-10-31 | 2018-05-31 | 273600 | 0 | 0 | 781502.18 | 733023.11 | 0 | 260 | 100% | 0% | 0%
Phoenix Operations | 16040007 | MDI-Downtown Hampton Inn | 2017-02-08 | 2018-05-09 | 123970 | 0 | 0 | 28214146.5753 | 25871948.68 | 7834.7 | 9685 | 90.33% | 9.67% | 0%
Denver Operations | 16060014 | Park Creek-Filing MD | 2016-08-01 | 2018-04-30 | 0 | 500 | 0 | 544409 | 547379.68 | 310 | 2151 | 96.61% | 3.394% | 0%
Civil Group Operations | 16148020 | Big Lake Solar -Civil | 2016-10-26 | 2018-03-31 | 0 | 1808 | 722 | 345409.91 | 182785.62 | 900 | 360.5 | 88.9% | 11.1% | 0%
Minneapolis Operations | 16030035 | Theodore Roosevelt Library |  | 2018-03-31 | 60000 | 0 | 0 | 711691.33 | 703033.52
Minneapolis Operations | 16030023 | Northern Stack V | 2016-08-15 | 2018-03-31 | 118400 | 295 | 58 | 12459968.2763 | 10856227.25 | 15681 | 12054.62 | 92.82% | 7.176% | 0%
Minneapolis Operations | 16030042 | Westminster-Main Kitchen Rmdl | 2016-11-01 | 2018-03-30 | 1232 | 24 | 0 | 406529.97 | 400533.07 | 297 | 398 | 99.5% | 0.5025% | 0%
Denver Operations | 16060021 | UCH-Inverness Health Ctr | 2017-01-01 | 2018-02-01 | 0 | 1308 | 0 | 90391.39 | 160757.2
Phoenix Operations | 16040006 | SRP History Center | 2017-04-03 | 2018-02-01 | 3171 | 0 | 0 | 325903.3 | 318994.8
Minneapolis Operations | 16030034 | Douglas Cty Hos-Surgery Exp | 2016-09-09 | 2018-01-31 | 32121 | 111011 | 20288 | 6908161.83 | 6529652.74 | 13371 | 12900 | 87.28% | 11.79% | 0.9225%
Minneapolis Operations | 16030013 | Westminster-ODOF | 2016-04-18 | 2018-01-19 | 165000 | 1496570 | 945050 | 39555182.6296 | 41077926.77 | 88282.5 | 126131.37 | 91.61% | 8.371% | 0.02299%
Civil Group Operations | 16148019 | Upton I Solar -Civil | 2016-10-10 | 2017-12-31 | 0 | 343688 | 334272 | 4932535.5755 | 4602463.03 | 14878 | 16538.5 | 82.14% | 17.86% | 0%
Denver Operations | 16060013 | Park Creek-Eastridge Dev. | 2016-08-01 | 2017-12-31 | 0 | 0 | 0 | 2336 | 2352.54
Phoenix Operations | 16040009 | SRP-PAB Cap Improve FY17 |  | 2017-12-31 | 80000 | 1 | 0 | 447093.14 | 439278.92 | 0 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 16145003 | Hudson Solar Garden - SunShare | 2016-06-06 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 6385.19
Solar and Emerging Renewables Operations | 16145004 | Quincy Solar Garden - SunShare | 2017-06-01 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 7850.28
Solar and Emerging Renewables Operations | 16145005 | Imboden II Solar - SunShare | 2017-06-01 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 8923.74
Solar and Emerging Renewables Operations | 16145006 | Imboden III Solar - SunShare | 2017-06-01 | 2017-12-31 | 0 | 43 | 0 | 10314.12 | 9440.62
Solar and Emerging Renewables Operations | 16145024 | McHattie CSG - SunShare | 2017-07-04 | 2017-12-31 | 5530000 | 9 | 0 | 170483 | -151900.64
Solar and Emerging Renewables Operations | 16145018 | Jasper Solar I-JasperSlrFrmLLC | 2017-03-08 | 2017-12-31 | 93377830 | 6572286 | 4069496 | 100643640.086 | 97307869.05 | 177920 | 199123.97 | 89.47% | 10.53% | 0%
Wind Energy I Operations | 16141026 | 2016 TX Sales Tax Audit | 2015-01-01 | 2017-12-31 | 0 | 0 | 0 | 0.01 | 956378.56
Minneapolis Operations | 16030045 | UMN-VFW/Masonic Relocation | 2017-02-01 | 2017-12-29 | 39000 | 345391.25 | 71633 | 8697971.27 | 8786377.25 | 11074 | 11457.04 | 93.45% | 6.001% | 0.5499%
Sports + Entertainment Group Operations | 16150002 | B&G - Omni Hotel at SunTrust | 2016-03-02 | 2017-12-28 | 264000 | 0 | 0 | 417149 | 419450.63
Milwaukee Operations | 16080024 | Aurora Kenosha MOB Suite Remdl | 2016-12-01 | 2017-12-22 | 11601 | 85568 | 48280 | 2600068.97 | 2591332.67 | 4285 | 3294.5 | 91.43% | 8.545% | 0.03035%
Milwaukee Operations | 16080007 | Kohler Co. - Inn on Woodlake E | 2016-11-01 | 2017-11-30 | 59000 | 46669 | 40046 | 11495498.22 | 11302855.23 | 6151 | 6265.5 | 95.34% | 4.621% | 0.0399%
Wind Energy I Operations | 16141014 | Rocksprings Akuo Wind | 2016-12-12 | 2017-11-30 | 0 | 29178 | 15968 | 57332461.42 | 55445035.53 | 70996 | 73508 | 84.62% | 15.38% | 0%
Wind Energy I Operations | 16141021 | Firewheel Transmission OK | 2017-04-15 | 2017-11-03 | 0 | 0 | 0 | 632977 | 631573.26
Denver Operations | 16060032 | Town of Castle Rock-Festival | 2016-11-07 | 2017-11-01 | 0 | 13628 | 1198 | 5435805.1018 | 5540790.68 | 8273 | 10436.5 | 77.32% | 22.68% | 0%
Denver Operations | 16060010 | RTD-Civic Center Project | 2016-07-05 | 2017-10-27 | 0 | 1056537 | 435694 | 25527777.27 | 26271805.6 | 36854 | 61831.5 | 84.57% | 15.43% | 0%
Phoenix Operations | 16040010 | Rio de Flag Aeration | 2017-03-01 | 2017-10-27 | 0 | 52 | 0 | 1044655.08 | 1054455 | 697 | 614 | 97.39% | 2.606% | 0%
Minneapolis Operations | 16030031 | City of Mpls-Target Center Ice | 2017-05-15 | 2017-10-13 | 20000 | 0 | 0 | 72951 | 8607.79 | 48 | 62.78 | 88.85% | 11.15% | 0%
Denver Operations | 16060035 | SCL-Par Excellence | 2016-12-12 | 2017-10-06 | 0 | 0 | 0 | 72125 | 50430.63 | 0 | 687 | 97.23% | 2.766% | 0%
Chicago Operations | 16090002 | SAIC HVAC PH2 | 2016-01-25 | 2017-10-01 | 50000 | 3455.9 | 227 | 6765903.5 | 5688334.75 | 8573 | 5354.06 | 86.06% | 13.71% | 0.2335%
Minneapolis Operations | 16030014 | CentraCare - Long Prairie MC | 2016-05-09 | 2017-10-01 | 65000 | 39241 | 202232 | 13295555.43 | 13029898.86 | 17833.5 | 16814.5 | 94.42% | 5.516% | 0.05947%
Chicago Operations | 16090001 | Wheaton College SOM | 2016-09-01 | 2017-09-30 | 51000 | 76316.04 | 38790 | 18431689.8905 | 18179479.37 | 12882 | 14045.2 | 90.89% | 8.031% | 1.082%
Civil Group Operations | 16148018 | Meadow Lake V Civil | 2016-10-17 | 2017-09-30 | 0 | 694736 | 510577 | 9179639.2741 | 8998860.86 | 26888 | 26345.5 | 72.14% | 26.87% | 0.9869%
Solar and Emerging Renewables Operations | 16145016 | Upton County Solar-ConEdison | 2016-11-04 | 2017-09-30 | 212589000 | 13112484 | 12893396 | 116539897.0871 | 106216177.88 | 555607.2 | 521262.75 | 83.78% | 16.22% | 0%
Wind Energy I Operations | 16141015 | Meadow Lake V Wind | 2016-10-21 | 2017-09-27 | 0 | 13622 | 10837 | 33028756.74 | 33818729.15 | 58278 | 75645.5 | 68.36% | 20.94% | 10.7%
Milwaukee Operations | 16080011 | Ministry HC - St. Clare's MOB | 2016-08-01 | 2017-09-25 | 0 | 202612 | 87243 | 6471936.29 | 6394402.55 | 10244 | 11110 | 90.97% | 8.857% | 0.171%
Milwaukee Operations | 16080010 | Ministry HC - Hyperbaric Oxygn | 2016-08-01 | 2017-09-25 | 10400 | 67426 | 21780 | 3062490.215 | 2991715.2 | 5151 | 5298.5 | 85.68% | 13.98% | 0.3397%
Civil Group Operations | 16148017 | Rocksprings Akuo Civil | 2016-11-30 | 2017-09-15 | 0 | 1014795 | 571396 | 8400143.4809 | 7743996.73 | 27380 | 30233 | 80.85% | 19.15% | 0%
Chicago Operations | 16090010 | School of Art Inst. Auditorium | 2016-08-01 | 2017-08-31 | 9760 | 109802.47 | 11954 | 6620797.6938 | 5670611.25 | 7575 | 8666.22 | 81.49% | 17.14% | 1.373%
Chicago Operations | 16090006 | QTS CHI Phase 4 Addition | 2016-06-01 | 2017-08-31 | 248000 | 736924.32 | 527236 | 51972399.9988 | 52407320.19 | 30215.55 | 35859.99 | 90.97% | 7.951% | 1.078%
Milwaukee Operations | 16080025 | AHC-St. Luke's IR#2 | 2017-05-01 | 2017-08-31 | 0 | 21660.46 | 0 | 897243.59 | 850302.57 | 1117.3 | 1175.5 | 88.9% | 11.1% | 0%
Minneapolis Operations | 16030033 | WFPS - Hockey Facility | 2016-09-08 | 2017-08-21 | 67143 | 1065 | 809 | 14194159.18 | 14293755.16 | 5761 | 6627.5 | 85.44% | 14.29% | 0.2716%
Minneapolis Operations | 16030041 | Vibra-Parking Lot-SFMC | 2016-11-14 | 2017-08-20 | 32711 | 0 | 0 | 247389 | 245308.86
Milwaukee Operations | 16080017 | AHC-Oak Creek Clinic | 2016-12-17 | 2017-08-18 | 51683 | 208080.08 | 191583 | 10517273.979 | 10612993.59 | 11644.6 | 10836.5 | 89.79% | 10.09% | 0.12%
Phoenix Operations | 16040008 | Pecos SWTP Rehab Project | 2016-07-11 | 2017-07-28 | 0 | 105295.02 | 104049 | 2445792.3994 | 2507305.65 | 6920 | 7477.5 | 93.41% | 6.593% | 0%
Wind Energy I Operations | 16141010 | Ringer Hill Wind | 2016-05-16 | 2017-07-28 | 0 | 68363 | 64792 | 22644837.47 | 20139349.12 | 29024 | 32103.75 | 64.06% | 30% | 5.941%
Minneapolis Operations | 16030028 | MDI-Allina Hastings PCC | 2016-10-04 | 2017-07-25 | 50000 | 286232 | 253050 | 7536730.12 | 7075629.51 | 13748 | 13194.91 | 94.12% | 5.639% | 0.2425%
Minneapolis Operations | 16030040 | MDI-Hastings Clinic Street | 2017-04-03 | 2017-07-24 | 0 | 1 | 0 | 887968 | 873865.59 | 830 | 897.5 | 83.57% | 16.43% | 0%
Minneapolis Operations | 16030020 | NDSU - Churchill Hall Reno | 2016-05-31 | 2017-07-24 | 44496 | 233049 | 147178 | 9416271.4301 | 8902475.85 | 17527.3 | 12197.39 | 89.16% | 10.84% | 0%
Denver Operations | 16060022 | Columbine Dev-Quality Italian | 2016-09-20 | 2017-07-20 | 0 | 161 | 0 | 1955989 | 1820592.12 | 673 | 1116.5 | 72.15% | 27.85% | 0%
Minneapolis Operations | 16030024 | Westminster Masonry Restor | 2016-07-11 | 2017-07-07 | 7900 | 22783 | 21332 | 880211.16 | 928503.23 | 4813 | 6149 | 90.65% | 9.351% | 0%
Denver Operations | 16060019 | Larimer Humane Society Precon | 2016-04-01 | 2017-07-01 | 38000 | 0 | 0 | 59999 | 58263.8
Minneapolis Operations | 16030037 | UMN-Wilson Library Minitex | 2017-02-01 | 2017-07-01 | 13500 | 6417 | 0 | 1899265.15 | 1901489.34 | 2338 | 2622.83 | 91.38% | 7.473% | 1.144%
Chicago Operations | 16090007 | Northwestern Welsh Ryan Precon | 2016-06-01 | 2017-06-30 | 200000 | 0 | 0 | 233750 | 253070.51 | 0 | 11 | 90.91% | 9.091% | 0%
Civil Group Operations | 16148022 | Vibra Healthcare Parking Lot | 2016-11-16 | 2017-06-30 | 0 | 0 | 0 | 64253 | 37462.03
Solar and Emerging Renewables Operations | 16145026 | Ridgeland Grubbing - Adger | 2017-01-02 | 2017-06-30 | 0 | 2936 | 2936 | 47045 | 43305.1 | 729 | 729 | 98.63% | 1.372% | 0%
Solar and Emerging Renewables Operations | 16145001 | NSA Crane Solar - Duke Energy | 2016-04-21 | 2017-06-30 | 24304800 | 3190267 | 3227395 | 15211282.8289 | 15481159.19 | 80042.42 | 89841.5 | 80.34% | 19.66% | 0%
Solar and Emerging Renewables Operations | 16145021 | Alamo V Fndtn Upgrade Ph II | 2016-10-01 | 2017-06-30 | 120279600 | 256787 | 220426 | 9486369.75 | 9500967.48 | 94962.7 | 95832.5 | 87.78% | 12.22% | 0%
Wind Energy I Operations | 16141008 | Firewheel Phase A1 | 2016-03-07 | 2017-06-30 | 0 | 38 | 0 | 2208726 | 2110505.68
Power Delivery Solutions Operations | 16146018 | Rocksprings Akuo Wind - HVT | 2017-01-02 | 2017-06-29 | 0 | 111250 | 109538 | 18778545.77 | 17650402.5 | 34161.85 | 52206.49 | 82% | 18% | 0%
Sports + Entertainment Group Operations | 16150001 | One Ballpark Ctr Office Bldg | 2015-12-04 | 2017-06-07 | 255278 | 0 | 0 | 288480.0944 | 311342.16
Wind Energy I Operations | 16141011 | MSA Maintenance Wind | 2016-06-06 | 2017-06-06 | 0 | 9 | 0 | 694068.3061 | 554446.96 | 8929 | 7406.5 | 92.38% | 7.622% | 0%
Denver Operations | 16060009 | Hub-Mixed Use Development | 2016-08-01 | 2017-06-05 | 507000 | 0 | 0 | 0.01 | 576833.02 | 0 | 497 | 68.11% | 31.89% | 0%
Civil Group Operations | 16148011 | Sterling Ranch Filing 1 Civil | 2016-06-01 | 2017-06-01 | 0 | 427771 | 188018 | 3593264.6088 | 4568600.52 | 11645.5 | 4676.5 | 74.44% | 25.56% | 0%
Solar and Emerging Renewables Operations | 16145017 | RidgelandSolarI-RdglndSolarLLC | 2016-11-22 | 2017-06-01 | 12240000 | 1596994 | 693002 | 15229815.894 | 14586436.67 | 28152 | 33436.74 | 90.88% | 9.116% | 0%
Wind Energy I Operations | 16141006 | Ida Grove - Wind | 2016-04-01 | 2017-06-01 | 0 | 543218 | 482892 | 95322247.8416 | 95219367.11 | 126182.5 | 117183 | 59.99% | 35.41% | 4.598%
Wind Energy I Operations | 16141007 | O'Brien County - Wind | 2016-04-16 | 2017-06-01 | 0 | 217306 | 174032 | 66091490.1826 | 60678982.74 | 105189.5 | 84195 | 60.98% | 36.48% | 2.545%
Civil Group Operations | 16148003 | Ida Grove - Civil | 2016-04-11 | 2017-05-31 | 0 | 3012503 | 2301029 | 21569928.41 | 19887440.41 | 143672 | 66259.25 | 70.52% | 28.98% | 0.5014%
Civil Group Operations | 16148014 | Bongards Solar -Civil | 2016-08-03 | 2017-05-31 | 0 | 43 | 0 | 576441.45 | 428025.37 | 1360 | 1183 | 80.73% | 19.27% | 0%
Solar and Emerging Renewables Operations | 16145027 | Jasper Grubbing - Adger | 2017-01-24 | 2017-05-31 | 0 | 36043.4 | 36016 | 900450.69 | 1252344.69 | 5278 | 6350.08 | 73.37% | 26.63% | 0%
Seattle Operations | 16050004 | Smokey Pt Behavioral Hospital | 2016-06-01 | 2017-05-29 | 70257 | 311396.25 | 291276 | 18810983.9003 | 18242213.85 | 9998.21 | 8738.03 | 88.58% | 11.24% | 0.1717%
Minneapolis Operations | 16030043 | Trinity Health Medical Center | 2016-11-23 | 2017-05-15 | 840000 | 3 | 0 | 805115.84 | 805115.84 | 370 | 240 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 16145008 | Alamo V Fnd Upgrade | 2016-05-15 | 2017-05-01 | 120279600 | 85883.5 | 83447 | 5120665.15 | 5031238.77 | 49127 | 57721.5 | 93.28% | 6.722% | 0%
Solar and Emerging Renewables Operations | 16145022 | Alamo 5: 1 MW Expansion - CED | 2016-10-01 | 2017-04-30 | 1333800 | 43208 | 2 | 1058501.11 | 1060860.61 | 3331 | 5226 | 91.01% | 8.993% | 0%
Milwaukee Operations | 16080019 | AHC-Grafton MRI #2 / Alcove BO | 2017-01-03 | 2017-04-14 | 687 | 10505 | 17174 | 593187 | 556409.12 | 593 | 900 | 82.33% | 17.67% | 0%
Milwaukee Operations | 16080005 | Froedtert-ISIP | 2016-01-04 | 2017-03-31 | 77595 | 437233 | 249079 | 34630159.0083 | 34282844.6 | 9538.51 | 11279.62 | 82.44% | 13.61% | 3.95%
Power Delivery Solutions Operations | 16146020 | Bronco Battery Storage HVT | 2016-10-25 | 2017-03-31 | 0 | 5566 | 6288 | 173432 | 169616.46 | 745 | 1174 | 91.52% | 8.475% | 0%
Seattle Operations | 16050006 | 2016 PEMC Small Projects | 2016-07-18 | 2017-03-31 | 780 | 1152.63 | 0 | 747923.1051 | 741557.79 | 1391.38 | 1536.14 | 96.65% | 2.376% | 0.9765%
Solar and Emerging Renewables Operations | 16145011 | Wabasha Solar Garden - NRG | 2016-08-22 | 2017-03-31 | 4078080 | 211740 | 209685 | 3426586.46 | 3496380.36 | 32347 | 21418.25 | 81.41% | 18.41% | 0.1809%
Solar and Emerging Renewables Operations | 16145025 | Steinkraus CSG - Sunshare | 2016-10-25 | 2017-03-31 | 4147000 | 11 | 0 | 35239 | 32271.64
Wind Energy I Operations | 16141013 | Tenaska MSA | 2016-07-14 | 2017-03-31 | 0 | 0 | 0 | 48776 | 38098.65
Power Delivery Solutions Operations | 16146010 | Welsh Upgrade HVT | 2016-07-25 | 2017-03-29 | 0 | 283776 | 262812 | 2441530.344 | 2346312.35 | 19263 | 14500 | 88.21% | 11.79% | 0%
Minneapolis Operations | 16030022 | Allina-Unity Mental Health | 2016-05-16 | 2017-03-10 | 0 | 2481 | 0 | 5969131.47 | 6457355.52 | 15975 | 24733.37 | 93.3% | 6.216% | 0.4852%
Minneapolis Operations | 16030016 | RMC Small Projects 2016 | 2016-03-01 | 2017-03-01 | 8500 | 1775.8 | 0 | 66121.88 | 67197.91 | 382 | 266 | 88.35% | 11.65% | 0%
Minneapolis Operations | 16030027 | Fairview Ridges - 2016 Annual | 2016-07-11 | 2017-02-19 | 0 | 5442.1 | 0 | 161158.8 | 167911.51 | 895 | 851.5 | 89.67% | 10.33% | 0%
Civil Group Operations | 16148024 | Firewheel Phase A1 Civil | 2016-12-07 | 2017-02-15 | 0 | 101334 | 0 | 419600 | 386580.99 | 3806 | 1258 | 75.24% | 24.76% | 0%
Phoenix Operations | 16040005 | AlaskaUSA-Scottsdale Branch | 2017-01-03 | 2017-02-03 | 405 | 0 | 0 | 229682 | 222981.28 | 0 | 2 | 100% | 0% | 0%
HVDC Group Operations | 16135002 | SCT Geotech-LA | 2016-11-28 | 2017-01-31 | 0 | 115 | 0 | 97300 | 89966.44 | 80 | 0 | 0% | 0% | 0%
HVDC Group Operations | 16135003 | SCT Geotech-MS | 2016-11-28 | 2017-01-31 | 0 | 30 | 0 | 103545 | 87045.88
HVDC Group Operations | 16135004 | SCT Geotech TX | 2016-11-28 | 2017-01-31 | 0 | 23 | 0 | 24800 | 21118.58 | 10 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 16146003 | Wind - Western Plains HVT | 2016-04-18 | 2017-01-31 | 0 | 212 | 0 | 10589663 | 10207785.16 | 0 | 0 | 0% | 0% | 0%
Wind Energy I Operations | 16141023 | Muscatine Blade Unload - Wind | 2016-12-12 | 2017-01-20 | 0 | 46 | 0 | 373948.66 | 271400.4 | 1820 | 1468.5 | 91.79% | 8.206% | 0%
Mortenson Energy Services-Operations | 16141024 | Siemens Blade Repair MSA Wind | 2016-12-17 | 2017-01-15 | 0 | 80 | 0 | 646118.445 | 724939.81 | 19238 | 9633.75 | 72.99% | 25.79% | 1.22%
Wind Energy I Operations | 16141020 | Ocotillo T126 Turbine Removal | 2016-12-19 | 2017-01-13 | 0 | 150 | 0 | 396256 | 317260.27 | 1507 | 1435.5 | 84.64% | 15.01% | 0.3483%
Minneapolis Operations | 16030036 | SCCR-Office Rmdl & Sterlizer E | 2016-10-07 | 2017-01-06 | 750 | 12 | 0 | 83573.08 | 78758.91 | 0 | 10 | 50% | 50% | 0%
Denver Operations | 16060026 | SCL-Lutheran Med Ctr-CT 6 | 2016-09-15 | 2017-01-01 | 0 | 0 | 0 | 168060 | 168881.81 | 340 | 473 | 95.45% | 4.545% | 0%
Minneapolis Operations | 16030001 | FUMC-Annual Contract 2016 | 2016-01-01 | 2017-01-01 | 0 | 100 | 0 | 3853531.9956 | 3853500.88 | 7062.33 | 10421.5 | 97.33% | 2.346% | 0.3262%
Chicago Operations | 16090008 | Sky Landing Sculpture | 2016-08-01 | 2016-12-31 | 0 | 0 | 0 | 25000 | 142575.98 | 0 | 593.79 | 93.6% | 6.4% | 0%
Chicago Operations | 16090005 | Chicago Office Buildout | 2016-04-01 | 2016-12-31 | 20255 | 0 | 172 | 2674880 | 2986355.57 | 690 | 1591.75 | 88.41% | 10.81% | 0.7853%
Civil Group Operations | 16148001 | Pearl Solar -Civil | 2016-01-01 | 2016-12-31 | 0 | 107964 | 75983 | 1231300 | 946913.55 | 3615 | 2196 | 78.16% | 21.84% | 0%
Civil Group Operations | 16148002 | Wind - Hidalgo Civil | 2016-02-08 | 2016-12-31 | 0 | 2216133 | 2170317 | 10895789.8448 | 8474914.34 | 49441.27 | 38591.5 | 77.9% | 22.1% | 0%
Civil Group Operations | 16148004 | O'Brien County - Civil | 2016-04-04 | 2016-12-31 | 0 | 771343 | 639291 | 12024906.8682 | 11035012.73 | 34382.5 | 35695.5 | 70.8% | 28.93% | 0.2787%
Civil Group Operations | 16148006 | Mariah del Norte Civil | 2016-03-07 | 2016-12-31 | 0 | 1045701 | 1045484 | 6451066.69 | 5227795.43 | 27300 | 26176.5 | 78.13% | 21.87% | 0%
Civil Group Operations | 16148007 | Western Plains Civil | 2016-04-11 | 2016-12-31 | 0 | 1303317 | 1319789 | 13751361.59 | 11642058.6 | 51579 | 37365 | 78.56% | 21.44% | 0%
Civil Group Operations | 16148008 | NSA Crane Civil | 2016-05-16 | 2016-12-31 | 0 | 34332 | 10290 | 1806968.62 | 1585096.75 | 3150 | 1470 | 89.56% | 10.44% | 0%
Civil Group Operations | 16148010 | Ringer Hill - Civil |  | 2016-12-31 | 0 | 3 | 0 | 94483 | 94282.33 | 700 | 0 | 0% | 0% | 0%
Civil Group Operations | 16148015 | Glazier Solar -Civil | 2016-09-06 | 2016-12-31 | 0 | 12 | 0 | 255184 | 206271.85 | 850 | 897.5 | 85.24% | 14.76% | 0%
Civil Group Operations | 16148016 | Wabasha Solar -Civil | 2016-09-26 | 2016-12-31 | 0 | 12 | 0 | 316106 | 293348.38 | 850 | 1189.5 | 84.03% | 15.97% | 0%
Civil Group Operations | 16148023 | Plum Creek Civil PTC Work | 2016-12-05 | 2016-12-31 | 0 | 15101 | 7429 | 269700 | 218858.36 | 2298 | 575.5 | 76.46% | 23.54% | 0%
Civil Group Operations | 16148025 | Foard City 2016 PTC Civil | 2016-12-01 | 2016-12-31 | 0 | 42623 | 35844 | 479793.8 | 392459.6 | 1845 | 1478 | 68.03% | 31.97% | 0%
Denver Operations | 16060024 | NJH-Misc. Projects | 2016-09-26 | 2016-12-31 | 0 | 0 | 0 | 32733.38 | 53366.93 | 0 | 260 | 78.85% | 21.15% | 0%
Denver Operations | 16060027 | HNTB-Sports Auth Field Site | 2016-09-16 | 2016-12-31 | 0 | 0 | 0 | 26431 | -1412
Denver Operations | 16060028 | MDI-Block 173 Hotel | 2016-07-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | 67849.53
Milwaukee Operations | 16080016 | AHC-Summit MRI | 2016-09-27 | 2016-12-31 | 687 | 3996 | 3081 | 593876 | 531248.75 | 675 | 329.5 | 96.81% | 3.187% | 0%
Minneapolis Operations | 16030997 | 2016 Mpls Equip Facility Recog | 2016-01-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | 0
Solar and Emerging Renewables Operations | 16145019 | Pena Station - SunPower | 2016-10-03 | 2016-12-31 | 1678000 | 6516 | 7017 | 710622.61 | 612547.1 | 5214.5 | 3841.5 | 88.3% | 11.7% | 0%
Sports + Entertainment Group Operations | 16150999 | NPG 2016 Closed Projects | 2016-01-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | 0
Wind Energy I Operations | 16141001 | MSA 2016 Wind |  | 2016-12-31 | 0 | 32450 | 0 | 10245305.2479 | 8259778.66 | 98776 | 119983.25 | 74.44% | 25.14% | 0.4176%
Wind Energy I Operations | 16141004 | MES 2016 Misc. Wind | 2016-01-01 | 2016-12-31 | 0 | 506 | 0 | 82123.9991 | 64712.19 | 1058 | 643.5 | 79.49% | 20.51% | 0%
Wind Energy I Operations | 16141005 | Westar Energy-Western Plains W | 2016-04-18 | 2016-12-31 | 0 | 740703.27 | 702365 | 83805299.0135 | 81624439.68 | 97120 | 115917 | 77.06% | 22.94% | 0%
Wind Energy I Operations | 16141017 | A&D PMT Wind | 2016-11-10 | 2016-12-31 | 0 | 211 | 0 | 3178940 | 3316099.01 | 7446 | 9494.5 | 74.3% | 25.7% | 0%
Wind Energy I Operations | 16141019 | Foard City 2016 PTC | 2016-12-07 | 2016-12-31 | 0 | 0 | 0 | 566809.82 | 556686.17
Wind Energy I Operations | 16141022 | Alstom Decom. Wind | 2016-11-10 | 2016-12-31 | 0 | 3 | 0 | 574224.25 | 513762.02 | 3641 | 1376.5 | 84.78% | 15.22% | 0%
Milwaukee Operations | 16080008 | Engberg Anderson-GMIA Skywalk | 2016-09-01 | 2016-12-30 | 10000 | 0 | 0 | 3495 | 822.53
Denver Operations | 16060005 | MillerCoors-Kiln 9 Fan | 2016-02-26 | 2016-12-28 | 21000 | 77652.75 | 32172 | 8025697.885 | 7737192.92 | 8373.95 | 7827.5 | 88.06% | 11.94% | 0%
Denver Operations | 16060034 | Co Rockies-Coors Fld Sales | 2016-11-23 | 2016-12-23 | 0 | 10 | 0 | 216760.13 | 205038.56 | 364 | 1118.5 | 93.56% | 6.437% | 0%
Denver Operations | 16060011 | Park Creek-PA Trunk Open Space | 2016-05-09 | 2016-12-17 | 0 | 293273 | 128605 | 6071858.592 | 6047598.31 | 7640 | 36195 | 93.6% | 6.404% | 0%
Portland Operations | 16050008 | Nike Flight Operations Center | 2016-09-26 | 2016-12-12 | 40000 | 17 | 0 | 633024.02 | 598653.98 | 0 | 0 | 0% | 0% | 0%
Milwaukee Operations | 16080006 | AHC-St. Luke's CT#1 & #3 Renov | 2016-07-25 | 2016-12-09 | 1824 | 2409 | 0 | 1448603.43 | 1258599.11 | 1733 | 976.15 | 93.55% | 6.454% | 0%
Milwaukee Operations | 16080004 | Froedtert-Simulation Learn Ctr | 2016-06-01 | 2016-12-02 | 11330 | 27765 | 51554 | 3084197 | 3064864.54 | 9357 | 9961 | 90.29% | 9.477% | 0.2359%
Power Delivery Solutions Operations | 16146006 | Ida Grove - HVT |  | 2016-12-02 | 0 | 1252188 | 1370 | 27687902.2 | 26741839.29 | 33080 | 31866 | 73.54% | 26.46% | 0%
Power Delivery Solutions Operations | 16146005 | O'Brien County - HVT | 2016-04-04 | 2016-12-01 | 0 | 627748 | 627927 | 16886575.13 | 16525295.01 | 23986 | 28501.75 | 77.69% | 22.31% | 0%
Power Delivery Solutions Operations | 16146013 | Siemens Industry,Inc-Lk Er ECS | 2016-08-01 | 2016-11-30 | 0 | 0 | 0 | 62150 | 58223.02
Power Delivery Solutions Operations | 16146014 | MCC-Lake Erie Con. HCS Geo | 2016-08-15 | 2016-11-30 | 0 | 0 | 0 | 3366 | 3367.36
Power Delivery Solutions Operations | 16146014-110 | Siemens CAD Ltd-Lk Er HCS | 2016-08-15 | 2016-11-30 | 0 | 0 | 0 | 75737 | 71751.44
Milwaukee Operations | 16080009 | Froedtert-Interim Gen. Solutn | 2016-04-18 | 2016-11-22 | 0 | 1782 | 1412 | 6884643 | 6889957.19 | 1397 | 2626.5 | 85.49% | 13.27% | 1.237%
Power Delivery Solutions Operations | 16146019 | NSA Crane HVT | 2016-10-01 | 2016-11-22 | 0 | 41078 | 41108 | 409972.1 | 411796.73 | 1434 | 2349.25 | 88.09% | 11.91% | 0%
Seattle Operations | 16050001 | Arauco NA Flakeboard Plant Imp | 2016-05-02 | 2016-11-18 | 0 | 1025 | 0 | 5536318.96 | 5143952.51 | 16 | 0 | 0% | 0% | 0%
Wind Energy I Operations | 16141012 | MES Western Plains IR Wind | 2016-07-11 | 2016-11-06 | 0 | 983 | 0 | 87220 | 73496.47 | 304 | 200 | 68% | 32% | 0%
Denver Operations | 16060002 | CoorsTek-WTM TI & Remodel | 2016-04-22 | 2016-11-01 | 31625 | 0 | 0 | 2763415.25 | 2731424.32 | 0 | 1443.5 | 89.85% | 10.15% | 0%
Power Delivery Solutions Operations | 16146015 | DO NOT USE RockspringsHVT-Akuo | 2017-01-02 | 2016-11-01 | 0 | 0 | 0 | 10914 | 0
Milwaukee Operations | 16080020 | MRIC - Capital Plan Study | 2016-08-01 | 2016-10-31 | 0 | 0 | 0 | 25000 | 13362.56
Denver Operations | 16060017 | SCL-Lutheran Med Ctr CT | 2016-07-25 | 2016-10-28 | 0 | 280 | 0 | 505698.38 | 504198.62 | 569 | 1836.5 | 91.29% | 8.712% | 0%
Seattle Operations | 16050009 | Loews Regency Seattle Model RM | 2016-09-21 | 2016-10-25 | 823 | 12 | 0 | 58723 | 56955.72
Power Delivery Solutions Operations | 16146017 | MES 2016 Misc. A&D HVT | 2016-10-03 | 2016-10-24 | 0 | 0 | 0 | 17300 | 18273.06
Phoenix Operations | 16040002 | Corona de Tucson Water | 2016-03-21 | 2016-10-21 | 0 | 16297 | 0 | 1292883.03 | 1404865.37 | 3517 | 3720 | 98.25% | 1.747% | 0%
Power Delivery Solutions Operations | 16146012 | IHI-Tuscon Elec. Power 2 HVT | 2016-08-26 | 2016-10-19 | 0 | 403 | 0 | 63764.79 | 61348.41 | 388 | 313.5 | 79.74% | 20.26% | 0%
Wind Energy I Operations | 16141002 | Hidalgo Wind | 2016-02-01 | 2016-10-15 | 0 | 634000 | 628983 | 56257968.06 | 54666744.32 | 122711 | 123061 | 73.57% | 26.42% | 0.005282%
Milwaukee Operations | 16080014 | Kohl's-EFC 5 | 2016-01-01 | 2016-10-03 | 0 | 0 | 0 | 791023 | 759175.14 | 0 | 20.15 | 100% | 0% | 0%
Denver Operations | 16060018 | Woodward-Coy Plaza | 2016-07-15 | 2016-09-30 | 0 | 0 | 0 | 1139979 | 991341.87 | 0 | 1697.5 | 84.27% | 15.73% | 0%
Minneapolis Operations | 16030004 | Blake School-Athletic Triangle | 2016-03-21 | 2016-09-30 | 500 | 349 | 0 | 2030563.86 | 2081252.84 | 2513 | 2113.2 | 99.31% | 0.6862% | 0%
Minneapolis Operations | 16030009 | U of MN-2016 Small Projects | 2016-05-09 | 2016-09-30 | 3500 | 29 | 0 | 440085.95 | 418755.47 | 369 | 314.63 | 89.51% | 10.49% | 0%
Power Delivery Solutions Operations | 16146001 | Pearl Solar -HVT | 2016-04-11 | 2016-09-30 | 0 | 91805 | 91972 | 2590991.64 | 2128439.58 | 4148 | 1829 | 89.91% | 10.09% | 0%
Sports + Entertainment Group Operations | 16150005 | PSU - Lasch Bldg Maintenance |  | 2016-09-29 | 3500 | 0 | 0 | 108167.84 | 108354.48
Milwaukee Operations | 16080013 | Marquette-Wisc Ave Demo Prjcts | 2016-04-26 | 2016-09-16 | 61000 | 1 | 0 | 1224512.93 | 1148436.2 | 0 | 210.5 | 92.87% | 3.8% | 3.325%
Minneapolis Operations | 16030011 | Blake-MPAC Phase 1 Reno | 2016-06-13 | 2016-09-14 | 5627 | 3848 | 0 | 973530.06 | 951277.71 | 1425 | 1300.8 | 99.38% | 0.615% | 0%
Denver Operations | 16060004 | SCL-St Joseph's-NICU | 2016-05-09 | 2016-09-13 | 1414 | 0 | 0 | 643114.32 | 643459.48 | 0 | 1344.5 | 96.36% | 3.644% | 0%
Milwaukee Operations | 16080018 | Johnson Controls - DES Lab | 2016-08-08 | 2016-09-09 | 7583 | 67 | 0 | 288352.82 | 275511.77 | 283 | 389.5 | 99.1% | 0.8986% | 0%
Minneapolis Operations | 16030002 | US Bank - St. Anthony Falls | 2016-04-01 | 2016-09-01 | 3400 | 753 | 0 | 1587277.24 | 1666560.71 | 0 | 1038 | 88.54% | 11.46% | 0%
Minneapolis Operations | 16030007 | IP Stream - Data Hall 3 | 2016-03-07 | 2016-09-01 | 9000 | 37088 | 11169 | 7546618 | 7509412.39 | 6978 | 6830.87 | 88.85% | 10.77% | 0.3733%
Denver Operations | 16060006 | Stadium Mgmt-Denver Broncos | 2016-04-01 | 2016-08-31 | 2304 | 13 | 0 | 2308038.57 | 2292704.34 | 1606.5 | 3262.5 | 87.85% | 12.15% | 0%
Minneapolis Operations | 16030044 | UMN-Jane Sage Cowles | 2016-07-05 | 2016-08-31 | 50000 | 0 | 0 | 1086135.01 | 1089582.87
Solar and Emerging Renewables Operations | 16145012 | Alamo VII Tracker - Nor-Cal | 2016-05-01 | 2016-08-30 | 132300000 | 10351 | 10223 | 427458.0049 | 222643.09 | 6818 | 4246.5 | 91.51% | 8.489% | 0%
Minneapolis Operations | 16030003 | U of M - Mariucci Arena Locker | 2016-04-11 | 2016-08-12 | 0 | 71977 | 43324 | 3699523.19 | 3868690.51 | 4124 | 5785.62 | 90.53% | 9.195% | 0.2765%
Seattle Operations | 16050007 | Loews Regency Fitness Center | 2016-08-01 | 2016-08-12 | 560 | 11 | 0 | 55490 | 54517.27
Civil Group Operations | 16148013 | Rockrimmon Civil | 2016-07-29 | 2016-08-06 | 0 | 1 | 0 | 25263.21 | 20370.53 | 0 | 241.5 | 53.42% | 46.58% | 0%
Phoenix Operations | 16040001 | Pecos Well Equipping | 2016-03-07 | 2016-08-04 | 0 | 9910 | 0 | 692205.833 | 747965.65 | 1087 | 1663 | 94.53% | 5.472% | 0%
Denver Operations | 16060015 | Murray & Stafford-Enterprise | 2016-04-01 | 2016-08-01 | 0 | 0 | 0 | 0.01 | 47422.01
Power Delivery Solutions Operations | 16146007 | Jordan Creek HVT | 2016-04-30 | 2016-08-01 | 0 | 4 | 0 | 8181 | 8026.41 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 16060008 | Dominican Friars-St Dominic's | 2016-03-01 | 2016-07-31 | 0 | 0 | 0 | 10162.5 | 15119.27
Power Delivery Solutions Operations | 16146011 | AEP Panadero | 2016-07-18 | 2016-07-29 | 0 | 10069 | 0 | 41779.8754 | 30776.75 | 341.7 | 364.5 | 89.85% | 10.15% | 0%
Minneapolis Operations | 16030008 | Hudson Hospital Outpatient Reg |  | 2016-07-15 | 500 | 24 | 0 | 85683.01 | 95871.32 | 304 | 618 | 100% | 0% | 0%
Phoenix Operations | 16040003 | AlaskaUSA-Peoria Branch | 2016-06-13 | 2016-07-15 | 438 | 0 | 0 | 223637.92 | 231779.7 | 0 | 12 | 100% | 0% | 0%
Power Delivery Solutions Operations | 16146009 | MSA Maintenance HVT | 2016-06-15 | 2016-07-15 | 0 | 16 | 0 | 35390.45 | 22436.03 | 102 | 104 | 73.08% | 26.92% | 0%
Seattle Operations | 16050002 | Boren Ave Retail | 2016-04-04 | 2016-07-05 | 1700 | 33 | 0 | 158484.02 | 142959.91 | 44 | 0 | 0% | 0% | 0%
Seattle Operations | 16050003 | Metropolitan Cafe and Deli | 2016-04-04 | 2016-07-05 | 1700 | 0 | 0 | 172081.56 | 162023.46
Seattle Operations | 16050005 | The Wild Building | 2016-05-27 | 2016-06-07 | 5000 | 0 | 0 | 12138 | 10422.75 | 118 | 109 | 100% | 0% | 0%
Power Delivery Solutions Operations | 16146002 | Solara AEP Metering | 2016-02-08 | 2016-05-31 | 0 | 4692 | 0 | 15801.41 | 13978.16 | 146 | 150 | 80% | 20% | 0%
Power Delivery Solutions Operations | 16146008 | Pyron WTG 156 HVT | 2016-05-05 | 2016-05-27 | 0 | 63 | 0 | 113864 | 41342.01 | 244 | 0 | 0% | 0% | 0%
Wind Energy I Operations | 16141009 | GE MSA - Pyron WTG 156 Repair | 2016-05-02 | 2016-05-26 | 0 | 260 | 0 | 281060.47 | 218333.55 | 0 | 245.5 | 87.37% | 12.63% | 0%
Phoenix Operations | 16040004 | AlaskaUSA-Avondale Branch | 2016-04-04 | 2016-05-06 | 700 | 0 | 0 | 213934.62 | 216432.71 | 0 | 17 | 100% | 0% | 0%
Milwaukee Operations | 16080001 | Froedtert-CCC 5th Floor Renvtn | 2016-03-28 | 2016-05-03 | 1900 | 960 | 974 | 185686 | 164930.27 | 212 | 180.5 | 94.46% | 5.54% | 0%
Denver Operations | 16060007 | Oakwood Homes-GVR East | 2016-03-01 | 2016-04-15 | 0 | 0 | 0 | 21756 | 10021.18
Milwaukee Operations | 16080002 | Froedtert-OR 17 Renovation | 2016-01-25 | 2016-04-01 | 1000 | 12566 | 7638 | 646826 | 599062.31 | 792 | 1138 | 77.55% | 21.92% | 0.5272%
Wind Energy I Operations | 16141003 | Wind - Sendero MES | 2016-01-25 | 2016-03-31 | 0 | 0 | 0 | 19806 | 10431.69 | 100 | 86 | 93.02% | 6.977% | 0%
Denver Operations | 16037 | AMGEN INC.AMGEN AC 7 | 2003-01-06 | 2003-01-06 | 4500 | 0 | 0 | 2172061 | 2178762 | 0 | 8537 | 100% | 0% | 0%
Civil Group Operations | 16148005 | Wind - Mariah Del Norte Civil | 2016-03-07 |  | 0 | 0 | 0 | 4750 | 0
Civil Group Operations | 16148009 | Ringer Hill Civil | 2016-05-16 |  | 0 | 0 | 0 | 4750 | 0
Denver Operations | 16007 | KROENKE-PEPSI EIFS | 2004-10-31 |  | 0 | 0 | 0 | 1490354 | 1490381 | 0 | 135 | 100% | 0% | 0%
Denver Operations | 16008 | EAST/WEST PARTNERSPARK PLACE | 2001-12-31 |  | 0 | 0 | 0 | 430456 | 450504 | 0 | 6 | 100% | 0% | 0%
Denver Operations | 16009 | EAST/WEST PARTNERSPARK TOWER | 2002-02-01 |  | 0 | 0 | 0 | 0 | 432545
Denver Operations | 16010 | EAST/WEST PARTNERSPROMENADE B | 2002-01-01 |  | 0 | 25 | 0 | 182728 | 187429
Denver Operations | 16013 | COLORADO ROCKIES COORS FIELD | 2002-01-14 |  | 0 | 0 | 0 | 0 | 7639 | 0 | 91 | 100% | 0% | 0%
Denver Operations | 16015 | HASKELL CONSTRUCTORSVAN SKAT | 2001-06-30 |  | 0 | 0 | 0 | 0 | 62843 | 0 | 1026 | 100% | 0% | 0%
Denver Operations | 16017 | AGILENT TECHNOLOGIESMISC FACI | 2001-12-31 |  | 0 | 0 | 0 | 0 | 15071 | 0 | 300 | 100% | 0% | 0%
Denver Operations | 16019 | STATE OF COLORADOARAPAHOE CNT | 2001-12-31 |  | 0 | 0 | 0 | 0 | 22914 | 0 | 97 | 100% | 0% | 0%
Denver Operations | 16024 | CITY & CNTY OF DENDENVER ART | 2006-01-29 |  | 0 | 627203 | 346691 | 0 | 56510848 | 0 | 90552 | 100% | 0% | 0%
Denver Operations | 16025 | MILE HIGH DEVELOPMENCULTURAL |  |  | 0 | 1299744 | 1728924 | 0 | 13561160 | 0 | 36720 | 100% | 0% | 0%
Denver Operations | 16028 | LARIMER CNTY FACILITIES - FAI |  |  | 0 | 0 | 0 | 0 | 307595 | 0 | 166 | 100% | 0% | 0%
Denver Operations | 16029 | CLAYTON STREET ASSOCCHERRY CR | 2004-05-01 |  | 0 | 12178197 | 3502053 | 41732499 | 103954370 | 0 | 377444 | 100% | 0% | 0%
Denver Operations | 16032 | AMGEN INC. - SITEIMPROVEMENTS | 2002-11-30 |  | 0 | 484 | 0 | 3071293 | 2994459 | 0 | 4592 | 100% | 0% | 0%
Denver Operations | 16034 | CLAYTON STREET ASSOCSEARS L/D | 2002-04-20 |  | 0 | 149168 | 18636 | 0 | 1597211 | 0 | 7746 | 100% | 0% | 0%
Denver Operations | 16036 | MAM-SAUNDERS-EXEMPLAHOSPITAL | 2004-11-04 |  | 0 | 1501815 | 1124998 | 20174858 | 18833608 | 0 | 144528 | 100% | 0% | 0%
Denver Operations | 16999 | DENVER-CLOSED JOBS | 2001-12-31 |  | 0 | 0 | 0 | 0 | 97258 | 0 | 183 | 100% | 0% | 0%
Denver Operations | 16022 | EAST/WEST PARTNERS-SALES OFFI | 2001-11-15 |  | 3100 | 1950 | 0 | 0 | 238229 | 0 | 544 | 100% | 0% | 0%
Denver Operations | 16031 | EAST/WEST PARTNERSRIVERFRONT | 2002-01-15 |  | 3100 | 413 | 0 | 0 | 318252 | 0 | 742 | 100% | 0% | 0%
Denver Operations | 16020 | BROADMOOR-BEE HIVE |  |  | 3184 | 8937 | 7753 | 616135 | 617953 | 0 | 2123 | 100% | 0% | 0%
Denver Operations | 16014 | EAST/WEST PARTNERS-MARK SMITH | 2001-12-19 |  | 4100 | 855 | 0 | 656706 | 919469 | 0 | 2809 | 100% | 0% | 0%
Denver Operations | 16023 | FOREST CITYSTAPLETON VISITOR | 2001-11-30 |  | 5144 | 0 | 32178 | 1018802 | 1022270 | 0 | 3641 | 100% | 0% | 0%
Denver Operations | 16035 | AERIE NETWORKS | 2001-12-21 |  | 7400 | 0 | 0 | 0 | 58830 | 0 | 406 | 100% | 0% | 0%
Denver Operations | 16003 | CSG SYSTEMS INCOFFICE ADDITIO | 2001-07-01 |  | 8000 | 317 | 0 | 280866 | 261272 | 0 | 408 | 100% | 0% | 0%
Denver Operations | 16012 | BROADMOOR-NORTHEASTMOOR OFFIC | 2002-07-01 |  | 11000 | 16 | 0 | 387321 | 416658 | 0 | 2844 | 100% | 0% | 0%
Denver Operations | 16016 | KROENKE SPORTS ENTER PEPSI CN | 2002-07-02 |  | 13500 | 0 | 143617 | 4347550 | 4299489 | 4903 | 5804 | 100% | 0% | 0%
Denver Operations | 16011 | KROENKE SPORTS ENTER 917 AURA | 2001-07-01 |  | 15000 | 0 | 0 | 266914 | 269892 | 0 | 480 | 100% | 0% | 0%
Denver Operations | 16018 | PEPSI BOTTLING |  |  | 20000 | 0 | 0 | 0 | 78562 | 0 | 549 | 100% | 0% | 0%
Denver Operations | 16021 | MORTENSON-NEW OFFICETI | 2001-11-01 |  | 22200 | 21 | 0 | 0 | 230684 | 0 | 671 | 100% | 0% | 0%
Denver Operations | 16002 | KROENKE SPORTS ENTERPEPSI CNT | 2002-07-01 |  | 49690 | 346875 | 12600085847 | 9342583 | 9365768 | 0 | 22178 | 100% | 0% | 0%
Denver Operations | 16004 | AMGEN INC. - AC-27AC-27 | 2002-06-30 |  | 90000 | 476765 | 377732 | 17640166 | 17646132 | 0 | 32893 | 100% | 0% | 0%
Denver Operations | 16001 | BROADMOOR-2001 PHASE3 | 2002-05-01 |  | 100000 | 363017 | 412611 | 28098114 | 29266457 | 0 | 167598 | 100% | 0% | 0%
Denver Operations | 16027 | CLAYTON STREET ASSOCCHERRY CR | 2002-10-01 |  | 218230 | 825513 | 727146 | 1 | 14848807 | 0 | 43073 | 100% | 0% | 0%
Denver Operations | 16006 | HP-HARMONY TECHNOLOGY PARK | 2002-08-30 |  | 270000 | 0 | 0 | 0 | 267942 | 0 | 0 | 0% | 0% | 0%
Denver Operations | 16033 | CORUM REAL ESTATE |  |  | 387025 | 5009869 | 1316581 | 31066923 | 31499547 | 0 | 110021 | 100% | 0% | 0%
Denver Operations | 16005 | 2101 MARKET ST LLCP.W. MAC MA | 2002-11-29 |  | 404000 | 0 | 0 | 0 | 62547
HVDC Group Operations | 16135001 | Southern Cross Conv Stations |  |  | 0 | 0 | 0 | 598609 | 367678.17
Minneapolis Operations | 16030005 | Medtronic Monument | 2016-02-29 |  | 0 | 1068 | 0 | 2497877.37 | 2497840.55 | 264 | 200 | 100% | 0% | 0%
Minneapolis Operations | 16030006 | UMP-MRI Removals | 2016-03-06 |  | 0 | 0 | 0 | 74382.85 | 77890.25 | 240 | 464 | 78.88% | 20.69% | 0.431%
Minneapolis Operations | 16030017 | HSRE-WestHealth Sanitary | 2016-05-09 |  | 0 | 0 | 0 | 309966.82 | 243909.8 | 212 | 87 | 100% | 0% | 0%
Minneapolis Operations | 16030018 | Mortenson Cabins - Oheym |  |  | 0 | 0 | 0 | 0 | 350947.79 | 0 | 2225 | 91.33% | 8.674% | 0%
Minneapolis Operations | 16030019 | BCBS Lighting Replacement | 2016-06-01 |  | 0 | 0 | 0 | 1033470.52 | 1056151.92 | 403 | 935 | 91.82% | 8.182% | 0%
Minneapolis Operations | 16030022-900 | Allina-Unity MH-Exempt | 2016-05-16 |  | 0 | 0 | 0 | 3274211.2 | 3274211.2
Minneapolis Operations | 16030025 | Mortenson Cabins - Alepho |  |  | 0 | 0 | 0 | 0 | 97595.22 | 0 | 550 | 92% | 8% | 0%
Minneapolis Operations | 16030029 | Fridley Land-Misc Projects | 2016-07-15 |  | 0 | 0 | 0 | 287057.66 | 319017.93 | 24 | 819 | 84.98% | 15.02% | 0%
Minneapolis Operations | 16030047 | AECOM-Vertical Exp Study |  |  | 0 | 0 | 0 | 2291.92 | 4311.88
Minneapolis Operations | 16030048 | UMP-Mill City Water Damage | 2016-12-20 |  | 0 | 0 | 0 | 23704 | 23652.18 | 0 | 158 | 98.73% | 1.266% | 0%
Minneapolis Operations | 16030999 | MAM - 2016 Closed Projects | 2016-01-01 |  | 0 | 0 | 0 | 0.01 | 18899.29 | 0 | 190 | 100% | 0% | 0%
Minneapolis Operations | 16030021 | MPR - Misc. Projects | 2016-06-15 |  | 300 | 0 | 0 | 18653.13 | 17739.81 | 0 | 8 | 100% | 0% | 0%
Minneapolis Operations | 16030039 | JW Marriott-Locker Room Rpr | 2016-08-24 |  | 2000 | 320 | 0 | 47771.78 | 47143.03 | 240 | 220 | 100% | 0% | 0%
Minneapolis Operations | 16030012 | NS I - Lindenmeyr TI | 2016-04-19 |  | 111000 | 2694 | 0 | 1814810.36 | 1790049.8 | 1476 | 1908 | 84.43% | 15.15% | 0.4193%
Minneapolis Operations | 16030032 | Fridley Land-NS III | 2016-09-15 |  | 118400 | 787 | 21320 | 11032640.58 | 9517627.82 | 16178 | 12967.61 | 93.52% | 6.431% | 0.04627%
Minneapolis Operations | 16030015 | MDI - 800 Washington Ave | 2016-10-01 |  | 134001 | 0 | 0 | 0.01 | 149262.49 | 0 | 0 | 0% | 0% | 0%
Minneapolis Operations | 16030026 | CHS Campus Projects | 2016-07-15 |  | 330000 | 5 | 0 | 276295.6 | 298301.43 | 356 | 125 | 99.2% | 0.8% | 0%
Power Delivery Solutions Operations | 16146004 | Wind - Ida Grove HVT | 2016-04-01 |  | 0 | 0 | 0 | 11884682.4 | 0
Power Delivery Solutions Operations | 16146016 | MES 2016 Misc. HVT | 2016-10-03 |  | 0 | 0 | 0 | 17300 | 0
Power Delivery Solutions Operations | 16146022 | Firewheel Phase A1 HVT | 2016-10-31 |  | 0 | 31 | 0 | 828961.64 | 734786.67
Solar and Emerging Renewables Operations | 16145007 | Gilcrest SolarGarden-SunShare | 2016-06-06 |  | 0 | 43 | 0 | 10314.12 | 7754.47
Solar and Emerging Renewables Operations | 16145015 | MAM Solar Training Yard | 2016-09-05 |  | 0 | 0 | 0 | 0.01 | 0 | 0 | 2067.75 | 99.3% | 0.7012% | 0%
Solar and Emerging Renewables Operations | 16145020 | G&K Service Pilot - Stem | 2016-10-24 |  | 0 | 14 | 14 | 10435 | 17681.6 | 56 | 97 | 75.26% | 24.74% | 0%
Solar and Emerging Renewables Operations | 16145023 | Oasis 3.0 Mini-Build-SunPower | 2016-10-10 |  | 15000 | 5932 | 730 | 23325 | 22111.6 | 208 | 160 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 16145014 | RadiatorSpringsRacer-SunPower | 2016-08-02 |  | 470880 | 10806 | 10806 | 307640.86 | 278096.78 | 2128 | 2612 | 92.15% | 7.848% | 0%
Solar and Emerging Renewables Operations | 16145013 | Stanford Multi-Site-SunPower | 2016-07-06 |  | 1365552 | 361333 | 356645 | 3319742.68 | 5122921.51 | 18102.5 | 33967.5 | 88.72% | 10.67% | 0.6079%
Solar and Emerging Renewables Operations | 16145002 | Target Helix 10 - SunPower | 2016-04-04 |  | 5838890 | 164141 | 162599 | 4324263.453 | 5541173 | 25781.6 | 34687.25 | 93.28% | 5.191% | 1.531%
Total | [5 empty] | 101043924.73 | 12668272166.33 | 3719037861.9115 | 3836078539.47 | 4869861.48 | 6610283.84 | 85.13% | 14.31% | 0.5567%

## 2015
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
FCG Operations | 15110003-159 | McCarthy/Mortenson JV-NBAF 3 | 2015-05-28 | 2021-10-31 | 0 | 0 | 0 | 740779583 | 0
FCG Operations | 15110008-159 | McC/Mort JV NBAF 3 Site Log | 2015-05-28 | 2021-10-31 | 0 | 0 | 0 | 13020699 | 0
FCG Operations | 15110003 | McCarthy/Mortenson NBAF 3 | 2015-05-28 | 2021-10-31 | 707000 | 0 | 0 | 33149706.6 | 37745807.93 | 0 | 187731 | 83.5% | 16.49% | 0.007457%
FCG Operations | 15110006 | McC/M NBAF Cup O&M | 2015-11-09 | 2020-12-08 | 0 | 0 | 0 | 101600 | 133927.83
FCG Operations | 15110006-159 | McC/M JV NBAF CUP O&M | 2015-11-09 | 2020-12-08 | 0 | 0 | 0 | 18168338 | 0
Denver Operations | 15060046 | Denver Water-OCR WP#6 | 2017-11-01 | 2020-03-31 | 385893 | 1688836.69 | 1420078 | 75260387.2774 | 74193000.8 | 129379.75 | 163559.5 | 89.91% | 10.09% | 0%
Denver Operations | 15060041 | Denver Water-OCR WP#1 | 2015-11-01 | 2020-03-31 | 1481040 | 994089.5 | 737024 | 40568083.0639 | 41677507.58 | 94919 | 101669.05 | 87.35% | 12.65% | 0%
Denver Operations | 15060026 | Park Creek-Stapleton Maint | 2015-08-01 | 2019-12-31 | 0 | 10474.2 | 28 | 7059715.2 | 7208953.28 | 15774.3 | 39457 | 94.49% | 5.514% | 0%
Seattle Operations | 15050003 | Northgate Station-(N160)Precon |  | 2019-09-30 | 0 | 289 | 0 | 1411225 | 1661995.62 | 125 | 155.5 | 97.75% | 2.251% | 0%
Minneapolis Operations | 15030055 | Cornell - Russell Science Ctr | 2017-04-04 | 2019-08-02 | 96000 | 866958.23 | 553745 | 27499372.37 | 25723848.91 | 29385.4 | 27109.71 | 87.62% | 12.33% | 0.0498%
Minneapolis Operations | 15030048 | Mort Dev - 333 Hennepin | 2017-11-15 | 2019-08-01 | 414000 | 3717330.1 | 1285621 | 78220221.47 | 77212796.51 | 112107.21 | 114891.44 | 90.12% | 9.782% | 0.09531%
Mortenson Infrastructure Milw Operations | 15080020-063 | WI DOT-Zoo I Change Phase 2 PC | 2016-01-01 | 2019-06-30 | 0 | 1 | 0 | 1857664 | 1783744.19
Portland Operations | 15050008 | OCC Hotel Parking Garage | 2018-03-01 | 2019-06-25 | 302000 | 16758.14 | 29757 | 27328257.9 | 29220571.93 | 3159.93 | 8829 | 92.32% | 7.64% | 0.04531%
FCG Operations | 15110005 | DON-Dahlgren P287MissileSptFac | 2016-02-25 | 2019-06-01 | 63269 | 1638 | 0 | 28612520.64 | 28471217.62 | 0 | 463.5 | 97.3% | 2.697% | 0%
Denver Operations | 15060028 | UAL-Pilot Training | 2016-02-01 | 2019-05-31 | 0 | 65586 | 84813 | 129969808.115 | 128031238.15 | 89439 | 155455.5 | 89.72% | 10.28% | 0%
Solar and Emerging Renewables Operations | 15145026 | Bongards CSG - Sunshare | 2015-10-30 | 2019-05-31 | 6855030 | 379223 | 378177 | 10537206.09 | 11692645.9 | 32044 | 32370 | 79.93% | 13.26% | 6.802%
Milwaukee Operations | 15080020 | WI DOT-Zoo I Change Phase 2 PC | 2016-01-01 | 2018-12-31 | 0 | 0 | 0 | 0.01 | -0.01
Seattle Operations | 15050005 | The Dalles Wastewater Plant | 2017-05-01 | 2018-12-21 | 0 | 123542 | 68088 | 13440489.662 | 13813539.49 | 20868 | 21393.56 | 94.14% | 5.796% | 0.06077%
Seattle Operations | 15050016 | UW Computer Science Eng II | 2016-12-26 | 2018-12-17 | 130000 | 798255.1 | 704033 | 78567291.0207 | 79875911.32 | 66496.25 | 69453.03 | 92.96% | 6.764% | 0.2728%
Denver Operations | 15060014-162 | ACCH - Gaylord Rockies Resort | 2015-06-22 | 2018-12-14 | 0 | 212048 | 0 | 541963907.59 | 541146657.73 | 187120.5 | 303887.89 | 91.26% | 8.74% | 0%
Denver Operations | 15060014 | MAM/Welbro-Gaylord Rockies Hot | 2015-04-20 | 2018-12-14 | 1900000 | 1422234.2 | 1534288 | 64242516.8133 | 66447466.15 | 292018.61 | 441675.88 | 89.89% | 10.11% | 0%
FCG Operations | 15110002-151 | DOA-ECB Marine Corps | 2016-01-01 | 2018-11-15 | 158106 | 0 | 0 | 88447803.897 | 96752656.66
Chicago Operations | 15090011 | Univ of Chicago Keller Center | 2015-05-01 | 2018-11-05 | 125000 | 290917.5 | 89640 | 57600046.379 | 56861634.62 | 32713.7 | 32013.93 | 91.64% | 6.653% | 1.706%
Portland Operations | 15050010 | Nike IHM Expansion | 2016-04-25 | 2018-08-30 | 200000 | 23015 | 43148 | 59184515.22 | 59087861.45 | 12808 | 16885.09 | 91.39% | 8.584% | 0.02369%
Denver Operations | 15060032-162 | Aurora CCH-Gaylord Offsite | 2015-11-01 | 2018-08-18 | 0 | 0 | 0 | 23168718.44 | 23492823.84 | 2080 | 1729.02 | 99.68% | 0.3181% | 0%
Denver Operations | 15060032 | MAM/Welbro-Gaylord Offsite | 2015-11-01 | 2018-08-16 | 0 | 241257.75 | 263049 | 10827564.7154 | 11714685.68 | 47856.55 | 61341 | 86.47% | 13.53% | 0%
Denver Operations | 15060009 | Park Creek-District IV Outfall | 2015-04-15 | 2018-07-31 | 0 | 0 | 0 | 791075 | 846500.25 | 0 | 955 | 94.55% | 5.445% | 0%
Phoenix Operations | 15040011 | SRP-PAB Capital Improvements | 2015-09-30 | 2018-07-31 | 431000 | 0 | 0 | 900968.29 | 908796.13
Phoenix Operations | 15040012 | SRP-PAB Exp Repair Improve | 2015-09-30 | 2018-07-31 | 431000 | 0 | 0 | 68219.38 | 66408.74
Denver Operations | 15060020 | Park Creek-Filing 49 | 2015-10-15 | 2018-06-30 | 0 | 0 | 47 | 5541985 | 6078662.05 | 1600 | 12527 | 97.77% | 2.227% | 0%
Portland Operations | 15050011 | 12th and Market Apartments | 2016-11-22 | 2018-06-30 | 89480 | 792923 | 673928 | 30253384.5637 | 36635553.75 | 21741 | 39088.39 | 77.56% | 21.63% | 0.8097%
Solar and Emerging Renewables Operations | 15145008 | Glazier CSG-SunShare | 2015-08-01 | 2018-06-30 | 4037040 | 332730 | 328567 | 6376636.4936 | 6769043.63 | 16743 | 19177 | 80.64% | 14.09% | 5.264%
Denver Operations | 15060002 | Exempla-St Joe's Facility Agrt | 2015-06-01 | 2018-06-29 | 0 | 2013.17 | 0 | 741235.4 | 729903.99 | 959.5 | 5459.5 | 91.26% | 8.737% | 0%
Denver Operations | 15060005 | MDI-Sterling Ranch Civic Ctr | 2017-07-28 | 2018-06-04 | 30787 | 336607 | 238207 | 8338253.01 | 7553087.89 | 16556 | 13617 | 92.3% | 7.704% | 0%
Denver Operations | 15060024 | Park Creek-Forest CIty | 2015-08-01 | 2018-04-30 | 0 | 0 | 0 | 2525949.61 | 2388906.11 | 0 | 3583 | 89.05% | 10.95% | 0%
Milwaukee Operations | 15080006 | St.Camillus-Phase 1 Campus Exp | 2015-03-09 | 2018-01-16 | 195000 | 1772702.6 | 1054606 | 47252867.17 | 45730092.36 | 46939.5 | 44274.6 | 95.11% | 4.867% | 0.02033%
Minneapolis Operations | 15030021 | UMN-Athletes Village | 2016-02-15 | 2018-01-08 | 339000 | 529807.78 | 459874 | 87326032.767 | 87054781.16 | 82434.7 | 95920.18 | 92.54% | 7.367% | 0.09279%
Milwaukee Operations | 15080021 | HellermannTyton-Misc. Alteratn | 2015-12-18 | 2017-12-31 | 500 | 28 | 0 | 37508 | 36746.89 | 128 | 299.5 | 99.17% | 0.8347% | 0%
Power Delivery Solutions Operations | 15146008 | Grande Prairie Wind - HVT | 2015-08-17 | 2017-12-31 | 0 | 752438 | 757427 | 36224647.4863 | 33776665.57 | 108779 | 51258 | 79.61% | 20.39% | 0%
Solar and Emerging Renewables Operations | 15145023 | Theis CSG - Sunshare | 2015-10-30 | 2017-12-31 | 6441120 | 25 | 0 | 283118.84 | 289231.43
Solar and Emerging Renewables Operations | 15145009 | Becker CSG-SunShare | 2017-08-01 | 2017-12-31 | 6581250 | 77 | 0 | 276678.25 | 367137.28
Solar and Emerging Renewables Operations | 15145024 | Kane CSG - Sunshare | 2015-10-30 | 2017-12-31 | 6640200 | 460 | 0 | 169797 | 82609.94
Solar and Emerging Renewables Operations | 15145007 | Bartlett CSG-SunShare | 2015-05-01 | 2017-12-31 | 7059150 | 12 | 0 | 261796.84 | 246064.71 | 0 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 15145027 | Gregor CSG - Sunshare | 2015-10-30 | 2017-12-31 | 7142850 | 100 | 0 | 233683 | 241816.76
Solar and Emerging Renewables Operations | 15145006 | Murphy CSG-SunShare | 2015-05-01 | 2017-12-31 | 7379775 | 0 | 0 | 243462.84 | 270760.07 | 0 | 0 | 0% | 0% | 0%
FCG Operations | 15110002 | DOA-ECB Marine Corps JV-Int | 2016-01-01 | 2017-11-30 | 158106 | 0 | 0 | 2470470 | 5970530.74 | 0 | 16729.5 | 74.44% | 25.32% | 0.2391%
Seattle Operations | 15050014 | AMLI/MDI Residential Tower | 2015-10-02 | 2017-11-16 | 424994 | 1958079.37 | 1479535 | 112996953.4075 | 112560314.66 | 96452.09 | 99949.17 | 81.72% | 15.92% | 2.358%
Chicago Operations | 15090014 | College of Lake County GMP2 | 2015-11-01 | 2017-10-31 | 190000 | 175965.2 | 168521 | 29253836.6357 | 28455478.63 | 15175.5 | 14673.21 | 95.52% | 3.857% | 0.6202%
Denver Operations | 15060045 | Denver Water-OCR WP#5 | 2017-05-01 | 2017-10-31 | 103442 | 0 | 0 | 0.01 | 0
Solar and Emerging Renewables Operations | 15145028 | Pearl Solar Project - OCI | 2016-03-22 | 2017-10-31 | 66339000 | 5530356 | 4830684 | 30878316.0466 | 31145780.16 | 274223 | 291200.25 | 94.36% | 5.639% | 0%
FCG Operations | 15110004 | DON-Kings Bay Land Water Inter | 2015-11-23 | 2017-10-22 | 0 | 116266.25 | 123005 | 16284510.984 | 13705272.04 | 68368 | 35379.75 | 87.88% | 12.12% | 0%
Civil Group Operations | 15148007 | I-70 Havana Civil | 2015-06-13 | 2017-09-30 | 0 | 36846 | 17260 | 283774.2136 | 229742.69 | 1123 | 1255 | 87.05% | 12.95% | 0%
Denver Operations | 15060013 | Park Creek-Aurora Filing 1 & 2 | 2015-11-01 | 2017-09-30 | 0 | 1 | 0 | 1427511 | 1539511.1 | 600 | 1286 | 92.46% | 7.543% | 0%
Portland Operations | 15050020 | Marriott Portland City Ctnr |  | 2017-09-30 | 0 | 0 | 0 | 38840 | 51421.52
Seattle Operations | 15050021 | Marriott Residence Inn Seattle | 2016-03-01 | 2017-09-22 | 245375 | 1636350.55 | 1561021 | 58554466.81 | 61764713.08 | 64874 | 81111.96 | 86.3% | 12.86% | 0.8359%
Chicago Operations | 15090001 | SAIC HVAC Improvements | 2015-05-01 | 2017-08-31 | 3500 | 18461 | 0 | 3347909.61 | 2961160.92 | 2247 | 3336.08 | 97.96% | 2.038% | 0%
Sports + Entertainment Group Operations | 15150003 | PSU-IM Bldg-Phase 3 Exp | 2016-05-23 | 2017-08-31 | 60676 | 0 | 0 | 22475764.633 | 22122083.74 | 0 | 946 | 82.51% | 15.38% | 2.114%
Chicago Operations | 15090013 | Advocate GS Life Safety | 2015-08-01 | 2017-08-30 | 25000 | 27257 | 5662 | 2909361.69 | 2852826.89 | 16828 | 4223.26 | 88.42% | 10.04% | 1.539%
Denver Operations | 15060025 | MAM/Welbro - Gaylord Concrete | 2017-02-15 | 2017-08-15 | 1164217 | 10713481.1 | 6305087 | 50372795.2618 | 45035323.82 | 333350 | 312432.47 | 87.48% | 12.52% | 0%
Denver Operations | 15060044 | Denver Water-OCR WP#4 | 2016-05-01 | 2017-08-01 | 129744 | 859521.09 | 883127 | 44082938.9074 | 43472482.1 | 64592 | 67784.5 | 90.58% | 9.423% | 0%
Seattle Operations | 15050012 | Salmon Bay - Lot R | 2016-06-01 | 2017-07-31 | 125000 | -1 | 0 | 357534.14 | 354998.16 | 48 | 413.97 | 100% | 0% | 0%
Denver Operations | 15060004 | Exempla-Lutheran Med Ctr. | 2015-01-26 | 2017-07-28 | 0 | 13329.5 | 20 | 8520566.573 | 8584916.49 | 17322 | 14237.5 | 91.78% | 8.225% | 0%
Denver Operations | 15060047 | Larimer Humane Society | 2016-04-01 | 2017-07-01 | 38000 | 12991 | 0 | 14232064.7717 | 14633211.97 | 746 | 5256 | 97.88% | 2.121% | 0%
Denver Operations | 15060039 | SCL - St. Francis Hosp. Renov | 2015-11-15 | 2017-06-30 | 0 | 0 | 0 | 12946672.37 | 13030229.42
Denver Operations | 15060018 | MCV Capital-Boulder Commons | 2015-12-11 | 2017-06-30 | 105000 | 609898 | 70234 | 23060983.72 | 24816233.86 | 26798 | 38478.5 | 90.27% | 9.731% | 0%
Solar and Emerging Renewables Operations | 15145029 | Byron CSG - Sunshare | 2015-01-01 | 2017-06-30 | 0 | 113 | 0 | 37107 | 30465.34
Wind Energy I Operations | 15141007 | Sunflower Wind | 2015-07-27 | 2017-06-30 | 0 | 245441 | 243735 | 37405744.61 | 37170835.47 | 60104 | 58130.25 | 69.46% | 28.53% | 2.014%
Milwaukee Operations | 15080005 | Kohler Co. - Lodge Kohler | 2016-04-04 | 2017-06-20 | 111228 | 646142 | 473107 | 40478342.43 | 39113702.74 | 27324 | 26252 | 92.98% | 7.024% | 0%
Minneapolis Operations | 15030034 | Dickinson Pub Schl - Mid Schl | 2015-07-01 | 2017-05-31 | 212000 | 11588 | 4633 | 55908124.9438 | 50559168.56 | 11051 | 9350.84 | 87.51% | 12.46% | 0.02139%
Power Delivery Solutions Operations | 15146003 | Alamo 7 Solar -HVT | 2015-10-12 | 2017-05-26 | 0 | 105214 | 104853 | 3994818.27 | 3567963.53 | 8157.18 | 6366.25 | 91.53% | 8.47% | 0%
Seattle Operations | 15050004 | Tilt49 Podium | 2015-03-23 | 2017-05-25 | 212615 | 726099.5 | 553190 | 26097715.9645 | 26265950.55 | 44266.5 | 46273 | 86.76% | 12.68% | 0.5619%
Milwaukee Operations | 15080019 | Guardian IG-Feasibility Study |  | 2017-04-30 | 0 | 0 | 0 | 47548 | 37638.24
Wind Energy I Operations | 15141004 | Grande Prairie Wind | 2015-08-01 | 2017-04-30 | 0 | 1228610 | 1025366 | 115399840.146 | 107296719 | 205334 | 168863.5 | 76.14% | 23.86% | 0%
Milwaukee Operations | 15080017 | Froedtert-West Clinic Vert Exp | 2016-03-15 | 2017-03-31 | 33116 | 168407 | 105013 | 10702657.22 | 10574302.55 | 9047.5 | 9420 | 91.72% | 7.415% | 0.8652%
Mortenson Direct Operations | 15080015-064 | Froedtert-Direct MR LinAc | 2015-10-05 | 2017-03-31 | 1910 | 0 | 0 | 15601 | 15601
Power Delivery Solutions Operations | 15146012 | Broadview-Energy JN Substation | 2016-01-04 | 2017-03-31 | 0 | 464613 | 463442 | 13718744.0325 | 15246553.59 | 22963 | 27237.25 | 71.67% | 28.33% | 0%
Power Delivery Solutions Operations | 15146013 | Broadview Energy KW Substation | 2016-01-04 | 2017-03-31 | 0 | 121077 | 120396 | 4943196.68 | 4741585.58 | 7631 | 7372 | 77.75% | 22.25% | 0%
Portland Operations | 15050002 | AC Hotel Portland | 2015-09-01 | 2017-02-01 | 119790 | 933650.76 | 933137 | 37740392.1058 | 41683714.41 | 25775 | 24745.15 | 83.29% | 16.03% | 0.687%
Portland Operations | 15050019 | United Way Hotel-Portland |  | 2017-01-31 | 0 | 0 | 0 | 53417.06 | 55033.14
Solar and Emerging Renewables Operations | 15145022 | Terning CSG - Sunshare | 2015-10-30 | 2017-01-31 | 7081425 | 65 | 0 | 233108.84 | 231583.93
Sports + Entertainment Group Operations | 15150001 | PSU-Lasch Bldg-Phase 2 | 2016-01-04 | 2017-01-31 | 12380 | 0 | 0 | 10612573.87 | 10595060.75
Milwaukee Operations | 15080015 | Froedtert-MR LinAc | 2015-10-01 | 2017-01-27 | 1910 | 18364 | 6459 | 2004110.54 | 1918186.03 | 2655 | 3821 | 88.5% | 9.474% | 2.028%
Chicago Operations | 15090992 | Chicago Laser Scanning | 2015-01-01 | 2016-12-31 | 0 | 0 | 0 | 0.01 | -154263.56 | 0 | 1767 | 82.29% | 11.74% | 5.971%
Chicago Operations | 15090006 | Lucas Museum of Narrative Art | 2015-01-01 | 2016-12-31 | 512000 | 844.69 | 0 | 1331562 | 1010039.02 | 14 | 1093.32 | 80.38% | 15.18% | 4.436%
Civil Group Operations | 15148008 | Solar-Alamo VII Civil | 2015-06-15 | 2016-12-31 | 0 | 259299 | 259255 | 2596856.25 | 2063790.17 | 8772 | 7519 | 89% | 11% | 0%
Denver Operations | 15060023 | CoorsTek-WTM Highway | 2015-10-01 | 2016-12-31 | 0 | 276 | 0 | 16922761.3 | 16666939.23 | 997 | 9256 | 93.32% | 6.682% | 0%
Minneapolis Operations | 15030043 | UHG - NT Data Coil Failure War | 2015-06-30 | 2016-12-31 | 0 | 0 | 0 | 0 | 71873.89
Minneapolis Operations | 15030031 | Brd of Regnts IA - Schindler | 2015-08-17 | 2016-12-31 | 143812 | 852 | 0 | 28260897.77 | 27754469.42 | 3530 | 5461 | 88.77% | 11.23% | 0%
Power Delivery Solutions Operations | 15146015 | Rocksprings HVT | 2015-11-16 | 2016-12-31 | 0 | 123 | 0 | 5269935 | 5035246.62 | 0 | 1101 | 77.75% | 22.25% | 0%
Power Delivery Solutions Operations | 15146016 | Mariah Del Norte HVT |  | 2016-12-31 | 0 | 265203 | 254484 | 6313551.22 | 6123386.77 | 9965 | 7355 | 73.29% | 26.71% | 0%
Power Delivery Solutions Operations | 15146014 | Broadview-Western Interconnect | 2016-01-04 | 2016-12-30 | 0 | 5867.92 | 5528 | 21380287.8784 | 22586444.69 | 60535 | 63371 | 74.69% | 25.31% | 0%
Solar and Emerging Renewables Operations | 15145030 | Target 8 | 2015-12-01 | 2016-12-30 | 0 | 195812 | 195637 | 3580687.9915 | 5245426.24 | 18989.85 | 27847.75 | 95.54% | 4.113% | 0.3501%
Civil Group Operations | 15148014 | South Plains II Civil | 2015-07-06 | 2016-12-17 | 0 | 832101.91 | 654137 | 7492984.2911 | 7241548.1 | 88388.4 | 31317 | 84.1% | 15.9% | 0%
Minneapolis Operations | 15030018 | MN Sculpture Garden | 2015-10-01 | 2016-12-01 | 0 | 2023 | 0 | 436992 | 425591.72 | 1520 | 2335.5 | 99.61% | 0.3854% | 0%
Denver Operations | 15060017 | PESCO-Operations & Tech Ctr | 2015-10-15 | 2016-11-30 | 112500 | 815313.65 | 498313 | 13044088.2435 | 13013704.12 | 18135.78 | 16435.5 | 85.98% | 14.02% | 0%
Minneapolis Operations | 15030039 | Walker - Vineland Entry | 2015-08-03 | 2016-11-11 | 6292 | 319164.8 | 168865 | 12370086.9088 | 12118482.9 | 22524 | 24970.96 | 94.21% | 5.613% | 0.1762%
Solar and Emerging Renewables Operations | 15145004 | Alamo VI - OCI SP LLC | 2015-04-01 | 2016-11-01 | 140313600 | 12369036 | 12306980 | 78610967.479 | 70326560.99 | 704916.35 | 702114.34 | 89.9% | 10.1% | 0.002421%
Chicago Operations | 15090016 | Allstate Jacksonville PH5 | 2016-02-01 | 2016-10-31 | 30000 | 0 | 0 | 6035069.07 | 5915120.74 | 854 | 712 | 100% | 0% | 0%
Civil Group Operations | 15148005 | Solar-Henrietta Civil | 2015-05-26 | 2016-10-31 | 0 | 170643 | 170492 | 3427321.055 | 2592040.92 | 11702 | 9308 | 79.86% | 20.12% | 0.02686%
Civil Group Operations | 15148019 | Sunflower Civil | 2015-09-08 | 2016-10-31 | 0 | 600485 | 600451 | 7492780.85 | 7224498.76 | 21121 | 23670 | 76.81% | 22.7% | 0.4901%
Denver Operations | 15060035 | DHHA-Pavilion I Renovate | 2015-10-08 | 2016-10-31 | 8300 | 30 | 0 | 3793657.74 | 3681990.37 | 0 | 8829.25 | 90.14% | 9.862% | 0%
Solar and Emerging Renewables Operations | 15145010 | Alamo VII-OCI | 2015-07-01 | 2016-10-31 | 132300000 | 12981805 | 12715372 | 79722860.9454 | 66660655.16 | 707310.26 | 688722.07 | 85.24% | 14.75% | 0.0009438%
Phoenix Operations | 15040016 | AlaskaUSA-Arcadia Branch | 2016-09-12 | 2016-10-20 | 500 | 0 | 0 | 194800.82 | 214580.23 | 0 | 18 | 100% | 0% | 0%
Denver Operations | 15060038 | MillerCoors-East Gate Mod | 2015-10-01 | 2016-10-13 | 0 | 22831 | 117692 | 1482393.6 | 1514389.3 | 2706 | 6032 | 87.18% | 12.82% | 0%
Denver Operations | 15060006 | PVH-NICU Renovation | 2015-03-23 | 2016-10-13 | 24080 | 10.5 | 0 | 9064220.92 | 8997642.64 | 4243.5 | 8523.5 | 92.78% | 7.221% | 0%
Denver Operations | 15060019 | Park Creek-Filing 48 | 2015-09-01 | 2016-09-30 | 0 | 100 | 0 | 89843 | 109597.49 | 60 | 270 | 92.22% | 7.778% | 0%
Minneapolis Operations | 15030023 | NS II-Northern Stacks II | 2016-03-14 | 2016-09-30 | 135000 | 359322 | 0 | 11134923.69 | 9656275.5 | 12338 | 10417.46 | 89.53% | 10.47% | 0%
Minneapolis Operations | 15030054 | UIA-Kinnick Stadium-Renovate | 2016-12-01 | 2016-09-30 | 156678 | 2480 | 0 | 174783.01 | 111109.02
Solar and Emerging Renewables Operations | 15145017 | Granite Mtn E Solar-Sun Edison | 2015-08-03 | 2016-09-30 | 100012200 | 6730922 | 6726311 | 37100086.625 | 35468376.16 | 246750 | 228532.45 | 81.32% | 18.67% | 0.006126%
Phoenix Operations | 15040014 | Project Tilden | 2015-12-11 | 2016-09-16 | 1300000 | 50024 | 0 | 174011883.18 | 172822962.77 | 8883 | 18687.5 | 76.73% | 21.29% | 1.977%
Minneapolis Operations | 15030041 | CH Robinson - Data Center | 2015-09-24 | 2016-09-14 | 25000 | 995.61 | 31206 | 17879305.41 | 17684765.84 | 16163 | 18513.6 | 94.88% | 4.848% | 0.2755%
Solar and Emerging Renewables Operations | 15145018 | Granite Mtn W Solar-Sun Edison | 2015-08-03 | 2016-09-09 | 62521440 | 3833137 | 3813439 | 21814267.727 | 18641392.38 | 138271 | 115812.81 | 85.48% | 14.51% | 0.01209%
Solar and Emerging Renewables Operations | 15145019 | Iron Springs Solar-Sun Edison | 2015-08-03 | 2016-09-09 | 100012200 | 5662194 | 5661743 | 30398366.7454 | 26886156.96 | 253794 | 226617.3 | 82.3% | 17.7% | 0%
Minneapolis Operations | 15030058 | RMC Surgery Remodel Proj | 2016-01-11 | 2016-09-03 | 7727 | 10441 | 25511 | 1828737.86 | 1814696.92 | 4919 | 6916 | 92.45% | 7.418% | 0.1301%
Civil Group Operations | 15148002 | REG I-South Plains I Civil | 2015-02-23 | 2016-09-01 | 0 | 806831.01 | 737823 | 6438732.1225 | 5892269.66 | 88500 | 30348 | 80.59% | 19.41% | 0%
Minneapolis Operations | 15030047 | Temple Israel-Edu & Lobby Exp. | 2015-09-01 | 2016-09-01 | 34800 | 279065 | 248506 | 10229665.33 | 9493672.09 | 26617 | 31384.31 | 94.79% | 4.478% | 0.7329%
Civil Group Operations | 15148010 | Solar-Enterprise Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1838377.39 | 1836874.94
Civil Group Operations | 15148011 | Solar-Escalante I Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1899629.9 | 1904241.18
Civil Group Operations | 15148012 | Solar-Escalante II Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1676584.3 | 1675196.16
Civil Group Operations | 15148013 | Solar-Escalante III Civil | 2015-06-15 | 2016-08-31 | 0 | 0 | 0 | 1987630.53 | 1984145.94
Civil Group Operations | 15148015 | Solar-Iron Springs Civil | 2015-08-03 | 2016-08-31 | 0 | 0 | 0 | 4119673.87 | 4116681.24
Civil Group Operations | 15148016 | Solar Granite Mtn East Civil | 2015-08-03 | 2016-08-31 | 0 | 0 | 0 | 6936740.02 | 6936932.71
Civil Group Operations | 15148017 | Solar Granite Mtn West Civil | 2015-08-03 | 2016-08-31 | 0 | 0 | 0 | 3564025.56 | 3541533.52
Power Delivery Solutions Operations | 15146005 | Solar-Enterprise HVT | 2015-09-01 | 2016-08-31 | 0 | 0 | 0 | 5108162.86 | 5110237.21
Power Delivery Solutions Operations | 15146006 | Solar-Escalante II HVT | 2015-09-01 | 2016-08-31 | 0 | 0 | 0 | 11283024.99 | 11277938.87
Power Delivery Solutions Operations | 15146010 | Solar Escalante I HVT | 2015-12-01 | 2016-08-31 | 0 | 0 | 0 | 1121378 | 1120372.63
Power Delivery Solutions Operations | 15146011 | Solar - Escalante III HVT | 2015-12-01 | 2016-08-31 | 0 | 0 | 0 | 810916 | 809843.43
Solar and Emerging Renewables Operations | 15145012 | Enterprise Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104889120 | 6732794 | 6731343 | 37537724.5694 | 34388770.82 | 257363 | 237108.12 | 84.19% | 15.49% | 0.3239%
Solar and Emerging Renewables Operations | 15145013 | Escalante 1 Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104889120 | 6304312 | 5982240 | 29040537.5367 | 26229989.53 | 248887.5 | 184195.27 | 85.31% | 14.69% | 0%
Solar and Emerging Renewables Operations | 15145014 | Escalante 2 Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104889120 | 6257551 | 6180253 | 41603658.075 | 38152896.43 | 237009 | 212717.5 | 83.02% | 16.98% | 0.005641%
Solar and Emerging Renewables Operations | 15145015 | Escalante 3 Solar-SunEdison | 2015-07-01 | 2016-08-31 | 104896360 | 7241418 | 7169047 | 31090428.9693 | 27705033.94 | 258258.55 | 273616.5 | 83.39% | 16.61% | 0%
Wind Energy I Operations | 15141005 | Rocksprings Wind | 2015-09-01 | 2016-08-31 | 0 | 1631 | 168 | 20759426 | 20807148.5 | 13393 | 5560.25 | 78.33% | 21.67% | 0%
Phoenix Operations | 15040013 | SRP-PAB MRI AV Systems | 2016-02-01 | 2016-08-30 | 0 | 0 | 0 | 244229.45 | 243843.42
Milwaukee Operations | 15080002 | Uline - Conference Center | 2015-06-01 | 2016-08-12 | 18700 | 465991 | 291474 | 12503791 | 12685245.73 | 18774 | 23565 | 89.79% | 9.62% | 0.5941%
Minneapolis Operations | 15030049 | UofMN-Mech Eng Lab Renovation |  | 2016-08-01 | 31600 | 17065 | 11729 | 3727348.93 | 3608301.12 | 3902.5 | 4344.84 | 96.23% | 3.775% | 0%
Civil Group Operations | 15148023 | Rocksprings Civil | 2015-11-09 | 2016-07-31 | 0 | 342228 | 444225 | 4690149 | 4647148.82 | 4923 | 12701.25 | 80.55% | 19.45% | 0%
Sports + Entertainment Group Operations | 15150004-155 | KSU - NorthEast Connector | 2016-01-05 | 2016-07-30 | 17000 | 2873 | 0 | 13484912.9 | 12312362.75 | 5444 | 2518.5 | 87.35% | 12.65% | 0%
Milwaukee Operations | 15080007 | Kohl's-Data Center Renov & Add | 2015-10-19 | 2016-07-07 | 70000 | 0 | 0 | 4615563 | 4215315.13 | 103 | 592.5 | 99.83% | 0.1688% | 0%
Civil Group Operations | 15148022 | First Creek Restoration Civil | 2015-10-26 | 2016-07-01 | 0 | 335389 | 345249 | 1185604.7504 | 1034870.69 | 4158 | 5888.25 | 82.78% | 17.22% | 0%
Minneapolis Operations | 15030012 | PNHS - Meth E Tower Vert Exp | 2015-05-01 | 2016-07-01 | 38334 | 294398 | 117936 | 14235788.76 | 14150037 | 28775 | 30980 | 93.35% | 6.583% | 0.07101%
Chicago Operations | 15090009 | Silver Cross Master Plan | 2015-01-31 | 2016-06-30 | 22800 | 15730 | 0 | 544366 | 564078.17 | 1591 | 1830.73 | 99.95% | 0.05462% | 0%
Denver Operations | 15060043 | Denver Water-OCR WP#3 | 2016-01-01 | 2016-06-30 | 160814 | 5444 | 6709 | 1420596.74 | 1410378.68 | 1122 | 1210 | 85.12% | 14.88% | 0%
Minneapolis Operations | 15030008 | RPB - Vertical Expansion | 2015-05-15 | 2016-06-15 | 41600 | 234541 | 249112 | 8026043.6 | 8472899.03 | 12870 | 15404.21 | 92.32% | 7.306% | 0.3765%
Denver Operations | 15060036 | SCL-Data Center | 2015-08-10 | 2016-06-01 | 0 | 0 | 0 | 81706.09 | 82362.77
Chicago Operations | 15090017 | Faegre Baker Daniels 45th FL | 2016-01-04 | 2016-05-31 | 0 | 0 | 0 | 950058 | 969173.94 | 546 | 614 | 98.05% | 1.954% | 0%
Chicago Operations | 15090015 | Allstate Largo FL | 2015-10-01 | 2016-05-31 | 140000 | 0 | 0 | 10904487.06 | 10814707.07 | 0 | 674 | 100% | 0% | 0%
Milwaukee Operations | 15080004 | Froedtert-7 & 8 Inpatient BO's | 2015-09-21 | 2016-05-31 | 66808 | 194133 | 210018 | 12548203.4 | 11869930.31 | 13937 | 15169.5 | 93.71% | 6.269% | 0.01978%
Mortenson Direct Operations | 15080004-064 | Froedtert-Direct Levels 7&8 BO | 2015-10-01 | 2016-05-31 | 0 | 0 | 0 | 3889347.44 | 3889347.63
Minneapolis Operations | 15030032 | Stream - DH2 Fitup (1200kw) | 2015-07-01 | 2016-05-16 | 3000 | 3 | 0 | 7087922.37 | 7028194.33 | 1656 | 1351.01 | 96.54% | 3.46% | 0%
Power Delivery Solutions Operations | 15146004 | REG I-Marshall HVT |  | 2016-05-13 | 0 | 258090 | 255247 | 4051230.19 | 3734991.51 | 4618 | 4828 | 84.55% | 15.45% | 0%
Seattle Operations | 15050001 | Swedish Cherry Hill Projects | 2015-02-01 | 2016-04-30 | 19575 | 51415.0903 | 0 | 12725713.2396 | 12643140.03 | 12042 | 13831.94 | 92.55% | 6.499% | 0.9507%
Milwaukee Operations | 15080014 | WEC Energy Group-Facility Asmt |  | 2016-04-29 | 0 | 0 | 0 | 213790 | 169568.2
Seattle Operations | 15050022 | 1111 Third Ave Plaza Reno | 2016-01-04 | 2016-04-15 | 8143 | 0 | 0 | 0 | 114186.6
Chicago Operations | 15090004 | Loyola Univ MC Misc. Projects | 2015-02-01 | 2016-03-31 | 0 | 0 | 0 | 0 | 891.35
Civil Group Operations | 15148004 | REG I - Sendero Civil | 2015-05-18 | 2016-03-31 | 0 | 433394 | 412769 | 4486700.01 | 3803669.23 | 18499 | 17758 | 75.33% | 24.67% | 0%
Civil Group Operations | 15148018 | Wind-Marshall Civil | 2015-08-31 | 2016-03-31 | 0 | 371661 | 354395 | 3791825.8611 | 3153890.16 | 13922.48 | 9855 | 79.07% | 20.93% | 0%
Denver Operations | 15060012 | SCL-Exempla Luth-EP Lab Precon | 2015-11-30 | 2016-03-31 | 0 | 1385 | 0 | 515532.04 | 516786.06 | 2481 | 1786.5 | 92.86% | 7.137% | 0%
Minneapolis Operations | 15030052 | MN Twins - 2016 Improvements | 2015-10-28 | 2016-03-31 | 9000 | 45654 | 0 | 4499965.94 | 4291872.51 | 5917 | 8183.71 | 95.28% | 4.717% | 0%
Power Delivery Solutions Operations | 15146007 | Alamo VI Solar -HVT | 2015-11-09 | 2016-03-31 | 0 | 86847 | 87648 | 3026575.194 | 2629838.26 | 5245 | 3892.5 | 90.15% | 9.852% | 0%
Seattle Operations | 15050017 | City of Bend WWTF Exp | 2015-09-15 | 2016-03-31 | 0 | 0 | 0 | 733243.92 | 1162814.59 | 380 | 691 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 15145005 | Henrietta Solar-SunPower | 2015-06-09 | 2016-03-18 | 127785600 | 834756.53 | 819212 | 12152451.4648 | 9673435.14 | 68994.5 | 55735.5 | 98.03% | 1.969% | 0.002691%
Minneapolis Operations | 15030057 | U of MN - Siebert Field | 2015-12-11 | 2016-03-16 | 4695 | 26691 | 29591 | 1044779.13 | 1082414.5 | 4360 | 4201.65 | 99.69% | 0.3094% | 0%
Minneapolis Operations | 15030044 | MOA - Group Sales Banquet Hall | 2015-08-01 | 2016-03-04 | 8321 | 37891.35 | 0 | 2843347.8782 | 2679475.84 | 5804 | 4123.5 | 76.2% | 23.41% | 0.388%
Civil Group Operations | 15148003 | Alamo VI Solar -Civil | 2015-03-30 | 2016-03-01 | 0 | 261960 | 241300 | 2079343.09 | 1953440.82 | 5146 | 4839.5 | 76.24% | 23.76% | 0%
Milwaukee Operations | 15080016 | Froedtert-MRI 4 E.R.R. | 2015-11-01 | 2016-03-01 | 2850 | 36674 | 4804 | 1032808 | 952192.57 | 901 | 1326.5 | 75.12% | 16.77% | 8.104%
Milwaukee Operations | 15080018 | Froedtert-MRI 5 MRgFUS | 2015-11-01 | 2016-03-01 | 2850 | 0 | 120 | 40775 | 35602.43 | 0 | 4 | 100% | 0% | 0%
Mortenson Direct Operations | 15080016-064 | Froedtert-Direct MRI 4 E.R.R. | 2015-11-01 | 2016-03-01 | 0 | 0 | 0 | 24970 | 24970
Phoenix Operations | 15040009 | CU Boulder-Solar Array | 2015-08-24 | 2016-03-01 | 0 | 0 | 0 | 873780.79 | 1307401.75
Denver Operations | 15060029 | Vestas-Windsor Phase X | 2015-08-24 | 2016-02-29 | 35000 | 291956 | 100569 | 7696194.99 | 8058902.09 | 12180 | 19223 | 82.31% | 17.69% | 0%
Minneapolis Operations | 15030016 | FlyOver America | 2015-03-23 | 2016-02-29 | 14584 | 9220.8 | 4 | 6100970.464 | 6072672.02 | 8129.4 | 7760.5 | 76.67% | 22.27% | 1.057%
Chicago Operations | 15090012 | United ORD T1 Club Renovations | 2015-08-01 | 2016-02-28 | 8368 | 30194.23 | 19901 | 4015501.355 | 3878322 | 2935.5 | 3865.17 | 91.54% | 6.352% | 2.109%
Denver Operations | 15060040 | SCL-EONS Level 4 Package | 2016-01-01 | 2016-02-26 | 225 | 98 | 0 | 77195.02 | 76458.61 | 28 | 383.5 | 98.83% | 1.173% | 0%
Seattle Operations | 15050013 | 2015 Providence Everett Small | 2015-08-03 | 2016-02-19 | 1347 | 3507 | 0 | 674049.68 | 723182.8 | 799.5 | 2230.89 | 85.36% | 13.18% | 1.457%
Phoenix Operations | 15040015 | AlaskaUSA-Tempe Bank Branch | 2016-09-06 | 2016-02-08 | 500 | 0 | 0 | 175714.83 | 198862.63 | 0 | 3 | 100% | 0% | 0%
Denver Operations | 15060034 | Co Rockies-Coors Field Winter | 2015-10-01 | 2016-02-01 | 0 | 5646 | 8 | 1013717 | 1022168.48 | 1527 | 2067 | 95.79% | 4.209% | 0%
Milwaukee Operations | 15080008 | Marquette-N.Campus Bldg. Demo | 2015-06-01 | 2016-02-01 | 0 | 0 | 0 | 2004673 | 1968218.02 | 0 | 97 | 96.91% | 3.093% | 0%
Denver Operations | 15060033 | CU-VAC-Replace Faulty Humid | 2015-11-15 | 2016-01-31 | 9800 | 0 | 0 | 88593 | 119888.02
Phoenix Operations | 15040010 | Globe-PRV Replacement | 2015-11-01 | 2016-01-31 | 0 | 0 | 0 | 605826.6 | 586997.87
Denver Operations | 15060042 | Denver Water-Materials Lab | 2015-11-16 | 2016-01-29 | 2694 | 2721 | 0 | 273555.5 | 243015.29 | 1180 | 506.5 | 97.04% | 2.962% | 0%
Solar and Emerging Renewables Operations | 15145011 | Blue Lake-SunEdison | 2015-06-08 | 2016-01-22 | 1567800 | 158513.08 | 157082 | 1932901.97 | 1886941.86 | 9924 | 11609.75 | 83.52% | 16.48% | 0%
Seattle Operations | 15050018 | Swedish Ballard Small Projects | 2015-11-02 | 2016-01-15 | 1347 | 513 | 2 | 782390.77 | 799381.69 | 664 | 1082.15 | 93.95% | 6.053% | 0%
Milwaukee Operations | 15080009 | Columbia St.Mary's-Oz.3rd Flr. | 2015-07-31 | 2016-01-11 | 2786 | 17012 | 3682 | 401899.15 | 363856.41 | 1785.5 | 1566.5 | 86.12% | 13.88% | 0%
Minneapolis Operations | 15030001 | FUMC-Annual Contract 2015 | 2015-01-01 | 2016-01-01 | 0 | 75994.589 | 0 | 4586721.64 | 4535466.89 | 9222.5 | 11145.36 | 98.15% | 1.763% | 0.08524%
Solar and Emerging Renewables Operations | 15145016 | CU Boulder Solar Array | 2015-08-24 | 2016-01-01 | 0 | 0 | 0 | 0.01 | 0
Chicago Operations | 15090008 | Kliment-Neubauer Collegium | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 26520 | 2075.44
Chicago Operations | 15090991 | Chicago Prefab Shop | 2015-01-01 | 2015-12-31 | 0 | 187159 | 96390 | 0 | -59011.56 | 5716.25 | 10212.9 | 98.43% | 1.464% | 0.1028%
Chicago Operations | 15090997 | Chicago Equip Facility 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -1998874.12
Chicago Operations | 15090999 | Chicago Closed Projects 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 5000.01 | 8545.84 | 0 | 70.88 | 100% | 0% | 0%
Civil Group Operations | 15148997 | Civil-Equipment Facility '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -1463123.08
Civil Group Operations | 15148999 | Civil-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -19577.67
Denver Operations | 15060015 | CU-Athletics Branding Impl. | 2015-06-01 | 2015-12-31 | 200000 | 1462 | 0 | 1739594 | 1680716.8
FCG Operations | 15110997 | FCG 2015 Equipment Facility | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0 | -16161.5
FCG Operations | 15110999 | FCG 2015 Closed Projects | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0 | -150836.91
Milwaukee Operations | 15080999 | Milwaukee Closed Job Costs '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 14524.9 | 0 | 55 | 96.36% | 3.636% | 0%
Milwaukee Operations | 15080003 | Acuity Ins-Lvl 1 Flrg Warranty | 2015-03-04 | 2015-12-31 | 38052 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 15030015 | MOA-Small Projects 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 88168 | 84048.9 | 0 | 1090 | 69.08% | 30.92% | 0%
Minneapolis Operations | 15030028 | U of MN - 2015 Small Projects | 2015-05-18 | 2015-12-31 | 0 | 512 | 0 | 567509.89 | 496792.97 | 741 | 566.5 | 93.56% | 6.443% | 0%
Minneapolis Operations | 15030997 | 2015 Mpls Equip Facility Recog | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -4728635
Minneapolis Operations | 15030999 | MAM - 2015 Closed Projects | 2013-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -125838.08 | 0 | 222 | 100% | 0% | 0%
Minneapolis Operations | 15030014 | UMN ASVM 3rd Floor Renovation |  | 2015-12-31 | 3000 | 2551 | 0 | 717908.32 | 718245.01 | 1116 | 993.5 | 99.4% | 0.6039% | 0%
Minneapolis Operations | 15030045 | 4150 LLC - 3rd Fl Corridor | 2015-08-05 | 2015-12-31 | 3087 | 12277 | 0 | 1083507.172 | 1027032.58 | 1524 | 1559.5 | 97.31% | 2.693% | 0%
Minneapolis Operations | 15030056 | 4150 LLC. - NW Assoc. Cons. | 2015-11-18 | 2015-12-31 | 3150 | 9010 | 0 | 197672.13 | 172590.73 | 233 | 200 | 98% | 2% | 0%
Minneapolis Operations | 15030053 | 4150 LLC-LifeScience Alley | 2015-10-19 | 2015-12-31 | 26000 | 9259 | 0 | 274952.5 | 225995.83 | 640 | 478.5 | 98.12% | 1.881% | 0%
Phoenix Operations | 15040003 | Mortenson-Phx Office 2015 TI | 2015-09-01 | 2015-12-31 | 0 | 0 | 0 | 180000 | -134.29 | 0 | 16.5 | 96.97% | 3.03% | 0%
Power Delivery Solutions Operations | 15146001 | Slate Creek HVT | 2015-03-30 | 2015-12-31 | 0 | 748131 | 747909 | 9286049 | 8920778.41 | 15434 | 21066.5 | 77.72% | 22.28% | 0%
Power Delivery Solutions Operations | 15146002 | REG I-Amazon HVT | 2015-05-15 | 2015-12-31 | 0 | 141 | 0 | 3961175 | 3911326.41
Power Delivery Solutions Operations | 15146997 | HVT-Equipment Facility '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -112854.89
Power Delivery Solutions Operations | 15146999 | HVT-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -81128.47
Seattle Operations | 15050997 | 2015 Seattle Equip Facility | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -1315981.5
Seattle Operations | 15050999 | 2015 Seattle Closed Projects | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 14818.1 | 0 | 16 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 15145999 | Solar-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 59689.94
Wind Energy I Operations | 15141001 | Fowler Ridge IV LLC-Amazon | 2015-05-04 | 2015-12-31 | 0 | 7768 | 7457 | 45492782.0635 | 44537488.92 | 67838 | 60931.75 | 67.42% | 23.74% | 8.838%
Wind Energy I Operations | 15141002 | Sendero Wind Energy LLC-Sender | 2015-06-01 | 2015-12-31 | 0 | 3164 | 2084 | 17759387.55 | 18147771.67 | 31995 | 46677.25 | 74.11% | 25.89% | 0%
Wind Energy I Operations | 15141008 | SunEdison Antelope Hills Wind | 2015-07-27 | 2015-12-31 | 0 | 0 | 0 | 561720.5 | 565082.3
Wind Energy I Operations | 15141997 | Wind Equipment Facility '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | -6197627.41
Wind Energy I Operations | 15141999 | Wind-Closed Projects 2015 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 361360.57 | 0 | 1927.14 | 94.5% | 5.5% | 0%
Wind Energy I Operations | 15141999-110 | Wind-Closed Projects '15 | 2015-01-01 | 2015-12-31 | 0 | 0 | 0 | 0.01 | 11133.39
Denver Operations | 15060027 | Kroenke-Pepsi Ctr Ext Lighting | 2015-08-03 | 2015-12-21 | 10000 | -1 | 0 | 1738599.7 | 1705878.78 | 2389 | 1876 | 93.47% | 6.53% | 0%
Milwaukee Operations | 15080013 | Columbia St.Mary's-Oz.MRI Repl | 2015-09-18 | 2015-12-18 | 1870 | 14747 | 0 | 588822.48 | 582882.81 | 1820 | 1780 | 97.58% | 2.416% | 0%
Power Delivery Solutions Operations | 15146009 | AEP-Uvalde Substation HVT | 2015-08-17 | 2015-12-18 | 0 | 23551 | 23550 | 249056 | 218948.18 | 1829 | 2022 | 92.73% | 7.27% | 0%
Solar and Emerging Renewables Operations | 15145020 | OCI-AlamoV SCADA Retrofit | 2015-09-28 | 2015-12-18 | 120279600 | 35263 | 35235 | 432047.49 | 295537.34 | 4966 | 5238.75 | 89.37% | 10.63% | 0%
Minneapolis Operations | 15030051 | MOA - Crayola Demolition | 2015-09-15 | 2015-12-11 | 8321 | 22 | 0 | 146857 | 120408.79 | 1896 | 1357 | 79.96% | 20.04% | 0%
Denver Operations | 15060003 | Charles Schwab-Train Station | 2015-06-01 | 2015-12-01 | 5200 | 0 | 0 | 85352 | 89707.66 | 0 | 15.01 | 100% | 0% | 0%
Minneapolis Operations | 15030036 | TC United Way - 1st Floor | 2015-06-22 | 2015-12-01 | 13898 | 10 | 0 | 403378.5 | 408495.59 | 340 | 657 | 96.5% | 3.501% | 0%
Minneapolis Operations | 15030006 | Basilica Renovation and HVAC | 2015-03-15 | 2015-12-01 | 22000 | 38229 | 41055 | 1382228.08 | 1331666.66 | 2689 | 4177.91 | 97.16% | 2.836% | 0%
Seattle Operations | 15050007 | Providence Everett Hospice | 2015-06-01 | 2015-12-01 | 14330 | 15256.8263 | 0 | 3479928.04 | 3643962.69 | 2408 | 6104.68 | 90.14% | 7.642% | 2.22%
Minneapolis Operations | 15030050 | Basilica Annual Contract Work | 2015-09-08 | 2015-11-30 | 0 | 0 | 0 | 198753.76 | 198104.6 | 1302 | 1228.51 | 87.99% | 12.01% | 0%
Civil Group Operations | 15148006 | REG I-Alexander Civil | 2015-06-03 | 2015-11-27 | 0 | 155494 | 152435 | 2771108.79 | 2272562.42 | 11803 | 8518 | 71.61% | 27.32% | 1.068%
Denver Operations | 15060007 | CCP/MS-US Bank Tower | 2015-03-02 | 2015-11-27 | 13500 | 3 | 208 | 1325133.05 | 1377531.17 | 0 | 4202.5 | 86.86% | 13.14% | 0%
Civil Group Operations | 15148001 | REG I-Amazon Civil | 2015-05-04 | 2015-11-16 | 0 | 541707 | 518102 | 8147753.2504 | 7992158.22 | 29744.67 | 30429.5 | 67.7% | 30.11% | 2.189%
Minneapolis Operations | 15030022 | HCMC-Helistop and Elevator | 2015-07-01 | 2015-11-16 | 9900 | 11018 | 0 | 2226398.69 | 1999036.38 | 3475 | 4646.5 | 93.34% | 6.317% | 0.3443%
Milwaukee Operations | 15080001 | Guardian IG-Sun Prairie Remodl | 2015-04-06 | 2015-11-02 | 226106 | 0 | 0 | 3672060.02 | 3624753.24 | 901 | 849.5 | 99.06% | 0.9417% | 0%
Minneapolis Operations | 15030011 | PNHS - MSE Core & Shell | 2015-04-20 | 2015-11-01 | 22944 | 119470 | 90487 | 3654453.06 | 3654442.2 | 11739 | 12516.75 | 94.46% | 5.537% | 0%
Chicago Operations | 15090010 | Allstate Jcksnvl Restack IV | 2015-03-31 | 2015-10-31 | 19138 | 0 | 0 | 1705777.69 | 1691925.63 | 252 | 920 | 100% | 0% | 0%
Milwaukee Operations | 15080010 | AHC-SLMC Starbucks | 2015-08-26 | 2015-10-30 | 2547 | 7804 | 0 | 406715.82 | 356574.74 | 1114 | 1281 | 82.16% | 17.84% | 0%
Minneapolis Operations | 15030033 | 4150 LLC - Best Vendors 2nd Fl | 2015-05-04 | 2015-10-30 | 26000 | 101636 | 0 | 1076107.36 | 978892.57 | 912 | 1199 | 95.54% | 4.462% | 0%
Minneapolis Operations | 15030038 | RMC - Cherry St. Parking Lot | 2015-05-15 | 2015-10-30 | 70000 | 0 | 0 | 736263 | 753624.05 | 320 | 446.5 | 97.31% | 2.688% | 0%
Denver Operations | 15060011 | Sterling Ranch-Roxbrough | 2015-07-01 | 2015-10-15 | 0 | 0 | 0 | 0.01 | 0
Denver Operations | 15060021 | Vestas-Windsor Phase IX | 2015-06-22 | 2015-10-12 | 63000 | 298606 | 2967 | 4045272.35 | 3825824.11 | 9888 | 8550.5 | 86.8% | 13.2% | 0%
Denver Operations | 15060031 | CCP-US Bank Phase 2 | 2015-08-11 | 2015-10-11 | 0 | 0 | 0 | 364652 | 369282.31 | 0 | 16 | 100% | 0% | 0%
Seattle Operations | 15050015 | Jars Juice Retail TI | 2015-08-17 | 2015-10-01 | 1055 | 0 | 0 | 192839.12 | 193595.38 | 0 | 2.5 | 80% | 20% | 0%
Solar and Emerging Renewables Operations | 15145003 | UC Davis - SunPower | 2015-02-18 | 2015-10-01 | 16286400 | 43051 | 35843 | 1798685.28 | 1561869.54 | 9482.82 | 7532 | 84.63% | 15.37% | 0%
Chicago Operations | 15090007 | Northwestern Athletic Field | 2015-03-01 | 2015-09-30 | 0 | 3509 | 0 | 2753770.16 | 2644246.17 | 1227 | 1090.4 | 78.86% | 16.97% | 4.173%
Denver Operations | 15060010 | Univ. Of Co-Athletic Audio/V | 2015-04-01 | 2015-08-31 | 0 | 320 | 0 | 0 | 0
Seattle Operations | 15050006 | Freshy's Tenant Improvement | 2015-03-16 | 2015-08-31 | 1301 | 2 | 8 | 142613.87 | 142763.72 | 68 | 32 | 100% | 0% | 0%
Minneapolis Operations | 15030027 | U of MN - Weaver Dens 2nd Flr | 2015-05-18 | 2015-08-21 | 5500 | 18148 | 0 | 515801 | 506296.1 | 983 | 1115 | 98.92% | 1.076% | 0%
Minneapolis Operations | 15030013 | UMN Scholars Walk Canopy | 2015-05-18 | 2015-08-14 | 9000 | 2332.2 | 0 | 1660557.4 | 1557745.52 | 2548 | 2494 | 95.31% | 4.491% | 0.2005%
Minneapolis Operations | 15030020 | Cornell-Dows & Tarr Hall Reno | 2015-03-14 | 2015-08-14 | 38208 | 2055 | 0 | 3934287.89 | 3865657.17 | 3331 | 2256 | 85.42% | 14.58% | 0%
Seattle Operations | 15050009 | Elemental Pizza | 2015-05-04 | 2015-08-14 | 4740 | 1142.15 | 4607 | 608186.37 | 579035.01 | 1309 | 1219.5 | 94.3% | 5.699% | 0%
Denver Operations | 15060001 | CSU-PERC New Facility | 2015-03-01 | 2015-08-01 | 27608 | 0 | 0 | 0.01 | 0
Chicago Operations | 15090003 | Chicago Theater Bathroom Ren. | 2014-12-01 | 2015-07-31 | 220 | 0 | 0 | 76101 | 52046.53 | 475 | 134 | 100% | 0% | 0%
Chicago Operations | 15090005 | 111 S Wacker Column Retro | 2015-01-28 | 2015-07-31 | 8125 | 4896 | 0 | 5861817.98 | 5026432.95 | 3649 | 4155.9 | 66.87% | 23.44% | 9.697%
Denver Operations | 15060022 | Ft Collins DDA-Old Towne Sq | 2015-01-01 | 2015-07-31 | 0 | 0 | 0 | 34343 | 37406.8
Phoenix Operations | 15040005 | AlaskaUSA-Mesa Bank Branch | 2015-06-10 | 2015-07-22 | 1490 | 871.4565 | 0 | 235351.49 | 233910.61
Minneapolis Operations | 15030024 | Deer District-Bucks Precon |  | 2015-07-15 | 694000 | 0 | 0 | 0.01 | 0
Sports + Entertainment Group Operations | 15150002 | Deer District- Bucks Precon |  | 2015-07-15 | 694000 | 0 | 0 | 99213.45 | 115464.28
Minneapolis Operations | 15030030 | Stream - MNPDC DH1 Office | 2015-05-11 | 2015-07-09 | 3000 | 55.22 | 0 | 215977.22 | 234452.82 | 151 | 462.5 | 100% | 0% | 0%
Phoenix Operations | 15040006 | AlaskaUSA-Phoenix Branch | 2015-06-08 | 2015-07-04 | 1490 | 881.5661 | 0 | 227957.56 | 233333.69
Chicago Operations | 15090002 | Advocate GS Cooling Tower Upg. | 2015-02-01 | 2015-06-30 | 0 | 0 | 0 | 1017732.5 | 1017155.94 | 0 | 288.69 | 100% | 0% | 0%
Discontinued Groups | 15120001 | Yahoo! BF2 Day 1 Phase 2 | 2014-12-31 | 2015-06-30 | 30000 | 22 | 0 | 14303752 | 13911537.6 | 0 | 7 | 100% | 0% | 0%
Minneapolis Operations | 15030025 | HCMC - Mock-Ups | 2015-05-04 | 2015-06-30 | 12000 | 0 | 0 | 121267 | 116506.67 | 754 | 733.92 | 93.53% | 6.472% | 0%
Minneapolis Operations | 15030019 | Northern Stacks-Kaufman TI | 2015-04-01 | 2015-06-20 | 48207 | 523 | 0 | 726745 | 733889.11 | 1078 | 751 | 87.62% | 12.38% | 0%
Minneapolis Operations | 15030017 | MOA-SE Court Duct Relocation | 2015-04-06 | 2015-06-17 | 0 | 7 | 0 | 446197.99 | 421381.69 | 406 | 284 | 80.28% | 19.72% | 0%
Phoenix Operations | 15040002 | SunPower Corp Systems-Stanford | 2015-09-10 | 2015-05-30 | 0 | 0 | 0 | 129411.5 | 71391.98
Minneapolis Operations | 15030002 | UMMC-Fairview - Repro/MMC | 2014-12-17 | 2015-05-01 | 12000 | 26 | 0 | 1359521.38 | 1117046.94 | 2334 | 1105 | 93.39% | 5.701% | 0.905%
Denver Operations | 15060008 | Denver Water-Conduit | 2015-04-01 | 2015-04-30 | 0 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 15030007 | BAE Systems Data Center | 2015-02-02 | 2015-04-01 | 1500 | 3357 | 0 | 501973 | 432006.87 | 622 | 303.99 | 98.68% | 1.316% | 0%
Minneapolis Operations | 15030004 | RMC - Wound Care Clinic | 2015-01-05 | 2015-03-31 | 3200 | 3529.2 | 0 | 738382.19 | 716634.85 | 2137 | 2603 | 96.64% | 3.362% | 0%
Minneapolis Operations | 15030005 | UMN Physics Nano Lab 353 | 2015-02-16 | 2015-03-15 | 1400 | 410 | 0 | 354605 | 342361.35 | 280 | 224 | 100% | 0% | 0%
Phoenix Operations | 15040001 | PCH-Rosenburg Sterilizer | 2015-02-11 | 2015-03-11 | 289 | 378 | 0 | 106193 | 113593.66
Milwaukee Operations | 15080997 | Milwaukee - Equip Facility '15 | 2015-01-01 | 2015-01-31 | 0 | 0 | 0 | -739966 | -1381419.87
Minneapolis Operations | 15030003 | 4150, LLC - ZIVIX | 2014-12-22 | 2015-01-30 | 6750 | 85.59 | 0 | 197325.36 | 195273.78 | 247 | 255 | 99.22% | 0.7843% | 0%
Phoenix Operations | 15040997 | Phoenix-Equipment Facility '15 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 85691.18
Phoenix Operations | 15040999 | Phoenix-Closed Projects 2015 | 2013-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -8414.84
Solar and Emerging Renewables Operations | 15145997 | Solar-Equipment Facility '15 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -2308021.62
Denver Operations | 15060997 | Denver-EF 2015 | 2013-01-01 | 2013-12-31 | 0 | 0 | 0 | 0.01 | -2457024.28
Denver Operations | 15060999 | Denver-Closed Project 2015 | 2012-01-01 | 2012-12-31 | 0 | 2 | 0 | 0.01 | -466.91 | 0 | 9.5 | 84.21% | 15.79% | 0%
Civil Group Operations | 15148009 | Solar - Blue Lake Center Civil | 2015-05-26 |  | 0 | 5918 | 5916 | 177132 | 156308.76 | 866 | 788 | 74.24% | 25.76% | 0%
Data Center Operations | 15120999 | MCG 2015 Closed Project | 2015-01-01 |  | 0 | 0 | 0 | 0 | 2135.41
Discontinued Groups | 15400999 | Discontinued-15 Closed |  |  | 0 | 0 | 0 | 0 | 98084.67
FCG Operations | 15110007-159 | McC/Mort JV NBAF 3 Concrete | 2015-05-28 |  | 0 | 0 | 0 | 47618831 | 0
FCG Operations | 15110001 | JBLM Entertainment Center |  |  | 74000 | 0 | 0 | 784711.03 | 782682.54
FCG Operations | 15001 | DON-AIRCRAFT MAINT.HANGAR P-5 | 2002-11-23 |  | 123000 | 69284 | 0 | 20749086 | 20750359 | 0 | 5621 | 100% | 0% | 0%
Minneapolis Operations | 15030009 | RMC - 2015 Annual Contract | 2015-01-01 |  | 0 | 9597 | 8 | 211213.36 | 199760.62 | 1385 | 924 | 96.65% | 3.355% | 0%
Minneapolis Operations | 15030026 | ANW Facilities Contract - 2015 | 2015-01-01 |  | 0 | 0 | 0 | 0.01 | 3984926.2 | 0 | 33824.3 | 90.94% | 7.69% | 1.373%
Minneapolis Operations | 15030029 | UHG - NTC2 Coil Replacement | 2015-07-01 |  | 0 | 0 | 0 | 2633880.95 | 2387003.54 | 797 | 1223.57 | 66.35% | 33.65% | 0%
Minneapolis Operations | 15030040 | Do not use |  |  | 0 | 0 | 0 | 0.01 | 0
Minneapolis Operations | 15030042 | MN Twins - MMA Warranty | 2015-06-30 |  | 0 | 0 | 0 | 0 | 442572.19 | 0 | 698 | 71.63% | 28.37% | 0%
Minneapolis Operations | 15030035 | Landry's - Rainforest Cafe | 2015-06-01 |  | 10913 | 29714 | 0 | 2156761.09 | 2119485.48 | 2103 | 1453.5 | 83.8% | 14% | 2.202%
Minneapolis Operations | 15030046 | MAM - Campus Office Space Reno | 2015-08-24 |  | 40120 | 0 | 0 | 4857701 | 3587238.78 | 3109 | 3698 | 97.89% | 2.109% | 0%
Minneapolis Operations | 15030037 | Northern Stacks I - OnTrac TI | 2015-06-15 |  | 52724 | 4981 | 0 | 1218320 | 1033680.25 | 1614 | 1230 | 87.85% | 10.85% | 1.301%
Minneapolis Operations | 15030010 | Mort Dev-Museum of Art | 2016-06-01 |  | 60000 | 1 | 0 | 2088931 | 1897920.1
Phoenix Operations | 15040007 | SRP PAB Balance of Reno |  |  | 431000 | 0 | 0 | 0.01 | 0
Solar and Emerging Renewables Operations | 15145001 | MN Solar Gardens - SunShare |  |  | 0 | 0 | 0 | 0.01 | 661090.41 | 0 | 18.5 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 15145021 | Traxler CSG - Sunshare | 2015-10-31 |  | 0 | 63 | 0 | 18739 | 22125.78
Solar and Emerging Renewables Operations | 15145025 | Kroll CSG - Sunshare |  |  | 0 | 98 | 0 | 18938 | 25494.95
Sports + Entertainment Group Operations | 15150004 | KSU - NorthEast Connector | 2016-01-05 |  | 17000 | 2812 | 0 | 1171316.63 | 1170794.85 | 5444 | 2518.5 | 87.35% | 12.65% | 0%
Wind Energy I Operations | 15141003 | Minnesota Power-Taconite Ridge | 2015-06-08 |  | 0 | 380749 | 0 | 459310.5404 | 489319.43 | 1360 | 1451 | 60.92% | 24.47% | 14.61%
Wind Energy I Operations | 15141006 | Siemens-Ocotillo Turbine 110 | 2015-08-03 |  | 0 | 1017307 | 0 | 1197557 | 1013487.49 | 2474 | 2075.5 | 72.18% | 21.97% | 5.854%
Total | [5 empty] | 123765469.2482 | 107363475 | 4441494721.5976 | 3550496226.6 | 6928406.48 | 7327351.1 | 86.57% | 13.16% | 0.2693%

## 2014
Operating Group | Project Number | Project Name | Construction Start Date | Substantial Completion Date | GSF | Estimated Units | Actual Units | Estimated Cost | Actual Cost | Est Craft Labor Hours | Act Craft Labor Hours | Act Craft NT % | Act Craft OT % | Act Craft DT %
Denver Operations | 14060010 | Denver Water-Campus | 2014-04-28 | 2020-03-01 | 325000 | 0 | 0 | 532951 | 496849.89 | 0 | 15 | 100% | 0% | 0%
Portland Operations | 14050005 | Hyatt Regency Hotel (OCC) | 2017-08-09 | 2019-11-04 | 634000 | 1962295.55 | 1576116 | 174850901.1072 | 175728472.35 | 78390.2 | 94370.89 | 85.48% | 14.4% | 0.1197%
Sports + Entertainment Group Operations | 14150006 | Mortenson Clark - Golden State | 2017-01-09 | 2019-08-01 | 0 | 0 | 0 | 29134095 | 29426155.55 | 1992 | 1454 | 100% | 0% | 0%
Seattle Operations | 14050001 | Coos Bay Wastewater Treatment | 2016-09-01 | 2019-07-22 | 4800 | 324516 | 329454 | 20581708.33 | 22610150.74 | 27093 | 36060.5 | 95.81% | 4.072% | 0.1165%
FCG Operations | 14110001 | DHS-Rpr Rbld USCG Academy | 2015-04-06 | 2018-12-31 | 0 | 2421 | 0 | 23715115.26 | 24236022.1
Minneapolis Operations | 14030033 | City of Mpls-Target Center Ren | 2016-05-06 | 2018-09-07 | 0 | 1102439.46 | 760040 | 115862113.7914 | 114968520.37 | 95564.53 | 77651.48 | 88.87% | 10.43% | 0.7057%
Minneapolis Operations | 14030054 | HCMC - AOSC | 2015-11-02 | 2018-09-04 | 320000 | 3459675 | 2432594 | 107026144.0185 | 100531025.81 | 217683.1 | 152716.22 | 90.96% | 8.941% | 0.09495%
Denver Operations | 14060023 | RTD-Central Park Station | 2014-08-14 | 2018-07-01 | 0 | 32789 | 13363 | 10701134.13 | 11056173.64 | 7389 | 15741 | 93.09% | 6.906% | 0%
HVDC Group Operations | 14135001 | MCC-Bipole III Converter HVDC | 2015-11-01 | 2018-06-30 | 248000 | 0 | 0 | 34220629 | 34220628.88 | 0 | -140765.96 | 102.1% | -1.583% | -0.4792%
HVDC Group Operations | 14135001-110 | Manitoba Hydro-Bipole III | 2015-11-01 | 2018-06-30 | 248000 | 185290.74 | 104874 | 438371573.2709 | 459645057.76 | 94719.5 | 37157.65 | -112.1% | 116.4% | 95.69%
Denver Operations | 14060015 | Sterling Ranch-Development | 2014-06-01 | 2018-06-29 | 0 | 184172.5 | 365079 | 84033394.92 | 89304254.52 | 25862.14 | 97079.68 | 87.08% | 12.92% | 0%
Minneapolis Operations | 14030054-900 | HCMC - AOSC Tax Exempt | 2015-11-02 | 2018-02-16 | 320000 | 4 | 0 | 42449253.28 | 42453385.88
Chicago Operations | 14090001 | College of Lake County A&B | 2013-10-01 | 2017-12-31 | 475000 | 151342.5 | 132527 | 19967389.7552 | 19672885.96 | 14791 | 15301.89 | 91.14% | 8.473% | 0.3856%
Milwaukee Operations | 14080007 | Harley-Davidson-Misc.Projects | 2014-05-22 | 2017-12-31 | 0 | 2 | 0 | 182059 | 157733.88 | 582 | 577 | 96.45% | 3.553% | 0%
Phoenix Operations | 14040005 | SRP-Full Renovation, Expansion | 2014-09-02 | 2017-12-31 | 431000 | 490.72 | 0 | 80027668.2387 | 79801586.92 | 26226.77 | 32210 | 86.48% | 13.52% | 0%
Denver Operations | 14060006 | Park Creek-P-10 | 2015-06-01 | 2017-12-04 | 0 | 757 | 0 | 1751415 | 1801957.39 | 1230 | 6850 | 96.23% | 3.766% | 0%
Seattle Operations | 14050006 | Tilt49 Office | 2015-02-02 | 2017-09-30 | 530000 | 1468654 | 1535590 | 50870539.9097 | 50470832.9 | 69436 | 71825.3 | 84.77% | 13.94% | 1.29%
Denver Operations | 14060011 | Exempla-St Joseph-Campus | 2014-12-13 | 2017-09-07 | 12000 | 133704.05 | 65672 | 24986657.9226 | 25296024.25 | 27943.85 | 64224.5 | 91.22% | 8.782% | 0%
Denver Operations | 14060009 | Park Creek-Westerly Creek Ph3 | 2015-01-07 | 2017-06-01 | 0 | 743 | 0 | 1245565 | 1232569.59 | 1036 | 7429.5 | 95.65% | 4.348% | 0%
Seattle Operations | 14050012 | UWT-Urban Solutions Center | 2014-12-01 | 2017-05-18 | 40000 | 306391.5 | 213317 | 18694153.2515 | 18044259.8 | 20557.5 | 17681.43 | 96.32% | 3.603% | 0.07352%
FCG Operations | 14110002 | DHS-USCG Recapitalize Fac NJ | 2014-09-05 | 2017-05-04 | 35000 | -3 | 0 | 26292883.77 | 28663615.84 | 4000 | 4232 | 100% | 0% | 0%
FCG Operations | 14110003 | DOJ-Bldg 7 Washingtn Dorm Reno | 2015-04-06 | 2017-04-14 | 81723 | 355362 | 0 | 31107486.802 | 31737579.7 | 0 | 3867.5 | 98.85% | 1.151% | 0%
Denver Operations | 14060027 | Park Creek-Section 10 | 2015-03-14 | 2017-03-31 | 0 | 100 | 0 | 468553 | 491718.11 | 380 | 154 | 77.92% | 22.08% | 0%
Milwaukee Operations | 14080003 | Acuity Ins-Corporate HQ Expnsn | 2014-03-15 | 2017-02-10 | 873000 | 11215391.36 | 2416842 | 171798194.9892 | 174500254.73 | 217323.21 | 272124 | 85.85% | 13.89% | 0.2604%
Minneapolis Operations | 14030045 | SW Healthcare Serv. - Hospital | 2015-03-01 | 2017-02-06 | 75095 | 227472 | 169515 | 27905214.331 | 25960744.96 | 12526.44 | 11988.5 | 66.58% | 29.44% | 3.975%
Chicago Operations | 14090003 | Advocate Dreyer Clinic | 2013-10-01 | 2016-12-31 | 60000 | 0 | 0 | 33833.86 | 39631.21
Denver Operations | 14060005 | Park Creek-P-9 | 2014-05-01 | 2016-12-31 | 0 | 686 | 0 | 194843.01 | 194900.34 | 5 | 83 | 98.19% | 1.807% | 0%
Minneapolis Operations | 14030002 | Thrivent Lutheran-Annual Cont | 2014-01-01 | 2016-12-31 | 0 | 0 | 0 | 504204.92 | 504007.8 | 1583.5 | 1922.5 | 98.47% | 1.534% | 0%
Phoenix Operations | 14040009 | SunPower Target 49 | 2015-03-02 | 2016-12-31 | 0 | 1355184 | 652914 | 12322266.2675 | 17331690.58 | 56587.21 | 114109.25 | 95.73% | 3.896% | 0.3762%
Power Delivery Solutions Operations | 14146006 | REG I-Shannon HVT | 2015-02-01 | 2016-12-31 | 0 | 181380 | 197549 | 15186884.37 | 14832501.27 | 28997 | 32736.25 | 84.26% | 15.69% | 0.0504%
Milwaukee Operations | 14080012 | Columbia St.Mary's-Misc2014-16 | 2014-01-01 | 2016-12-30 | 0 | 4462.26 | 0 | 238653.26 | 241801.15 | 686 | 786 | 83.08% | 16.92% | 0%
Denver Operations | 14060028 | Park Creek-Filing 47 | 2014-11-05 | 2016-12-16 | 0 | 100 | 0 | 1530678 | 1694726.14 | 1355 | 2751 | 97.2% | 2.799% | 0%
Denver Operations | 14060017 | Dominion Water-Water/Waste | 2015-11-01 | 2016-11-30 | 0 | 0 | 0 | 0.01 | 0
Seattle Operations | 14050008 | UW West Campus Utility Plant | 2015-08-05 | 2016-11-30 | 20000 | 138901.65 | 99862 | 34622485.4418 | 34992924.42 | 15910.5 | 14827.31 | 90.71% | 9.155% | 0.1315%
Chicago Operations | 14090015 | Five Star ORD Baggage Handling | 2015-04-07 | 2016-10-27 | 8102 | 16833.53 | 3490 | 2573817.6408 | 2525159.76 | 2052.12 | 3737.44 | 88.8% | 8.495% | 2.702%
Minneapolis Operations | 14030047 | AC Marriott - 4th & Hennepin | 2015-04-01 | 2016-10-14 | 131039 | 1204930 | 718558 | 39303768.5716 | 37517067.95 | 39525 | 46939.5 | 92.5% | 7.502% | 0%
Wind Energy I Operations | 14140020 | Mariah del Norte Wind | 2014-12-16 | 2016-09-30 | 0 | 571595 | 572144 | 53196896.0826 | 52296993.5 | 74316 | 80956.5 | 82.51% | 17.49% | 0%
Milwaukee Operations | 14080004 | AHC-St.Luke's Main Lobby Renov | 2015-07-10 | 2016-09-01 | 7675 | 125958 | 92117 | 3875608.44 | 3475400.47 | 7997.5 | 7947.78 | 91.98% | 7.908% | 0.1132%
Minneapolis Operations | 14030046 | City of Mankato-Civic Ctr Exp | 2015-04-01 | 2016-07-20 | 112000 | 380084 | 295430 | 28593981.61 | 26469012.17 | 28703.5 | 30819 | 94.89% | 4.864% | 0.2434%
Minneapolis Operations | 14030023 | Iowa State - Marston Hall Ren. | 2014-07-07 | 2016-07-15 | 64534 | 14799.7365 | 0 | 1641215.604 | 2002780.01 | 2706 | 2917 | 81.28% | 18.51% | 0.2057%
Chicago Operations | 14090014 | QTS Chicago Data Center | 2016-12-23 | 2016-06-30 | 80000 | 795780 | 602113 | 76192992.47 | 75573181.03 | 23011 | 18939.51 | 94.23% | 5.401% | 0.3722%
Civil Group Operations | 14148021 | Slate Creek Civil | 2015-03-30 | 2016-06-30 | 0 | 460911 | 461851 | 5725521.6097 | 5218679.61 | 24401.19 | 23759 | 80.75% | 19.25% | 0%
Wind Energy I Operations | 14140015 | South Plains II Wind | 2015-03-23 | 2016-06-30 | 0 | 17268 | 10536 | 72077363.8203 | 71914299.07 | 185355 | 188738 | 83.17% | 16.83% | 0%
Denver Operations | 14060022 | BMC Investments-245 Columbine | 2015-01-26 | 2016-06-17 | 0 | 426862 | 362465 | 40952456.74 | 41969495.15 | 33797 | 65599.5 | 92.78% | 7.222% | 0%
Milwaukee Operations | 14080011 | Uline - Distribution Center W2 | 2014-09-11 | 2016-06-17 | 1128150 | 2333785.3 | 235783 | 85118914.28 | 84417290.61 | 21282 | 30962.5 | 89.81% | 10.15% | 0.03876%
Milwaukee Operations | 14080017 | Froedtert-ISIP Make Ready | 2016-01-04 | 2016-06-15 | 150000 | 887531 | 1080795 | 3536193.32 | 3515905.68 | 14488 | 15294.38 | 91.79% | 7.741% | 0.4675%
Wind Energy I Operations | 14140024 | Slate Creek Wind | 2015-03-30 | 2016-06-01 | 0 | 5291 | 5267 | 36950914.8 | 37241113.19 | 75492.5 | 98770.5 | 75.13% | 24.87% | 0%
Seattle Operations | 14050004 | Pacific Tower Improvements | 2014-05-15 | 2016-05-31 | 205368 | 43633.07 | 9423 | 11415903.4229 | 10376482.4 | 16305.25 | 13132.63 | 96.68% | 2.947% | 0.3769%
Chicago Operations | 14090010 | AGSH AHU Refurbishment | 2015-06-01 | 2016-05-01 | 1000 | 7 | 0 | 3055595.27 | 3051169.82 | 420 | 1014 | 90.93% | 8.531% | 0.5424%
Chicago Operations | 14090017 | Harper College Direct | 2014-12-01 | 2016-05-01 | 3000 | 97969 | 0 | 3898963.68 | 3667092.59 | 2307 | 2354.25 | 88.68% | 10.13% | 1.189%
Denver Operations | 14060013 | City of Aurora-Iliff Station | 2015-03-15 | 2016-04-30 | 206000 | 1865980.9 | 1233265 | 9872095.6637 | 10565115.94 | 21430 | 48232 | 89.99% | 10.01% | 0%
FCG Operations | 14110004 | DHS-USCG Training Ctr Pier 4 | 2015-03-06 | 2016-04-08 | 10652 | 18 | 0 | 15937763.36 | 16621138.07 | 0 | 756.5 | 81.89% | 18.11% | 0%
Minneapolis Operations | 14030009 | Westminster Church - Open Door | 2014-01-29 | 2016-03-17 | 0 | 372 | 0 | 78225.7 | 139584.12 | 8 | 383 | 96.74% | 3.264% | 0%
Portland Operations | 14050009 | Nike TV Highway Warehouse | 2015-11-02 | 2016-03-04 | 210000 | 569 | 0 | 1950357 | 1767233.36 | 31 | 344.73 | 100% | 0% | 0%
Denver Operations | 14060029 | Ft Collins DDA-Old Town | 2015-03-26 | 2016-02-29 | 0 | 168689.07 | 97836 | 2730418.2183 | 3553654.43 | 9625.87 | 21406.05 | 82.75% | 17.25% | 0%
Seattle Operations | 14050013 | UWT McDonald Renovations | 2014-11-10 | 2016-02-28 | 53773 | 84789 | 54501 | 8877598.555 | 7417648.03 | 12663.5 | 11143.99 | 89.87% | 10% | 0.1256%
Solar and Emerging Renewables Operations | 14145004 | OCI-Alamo Solar V | 2014-08-11 | 2016-02-27 | 120279600 | 47031316.95 | 22012894 | 76015715.9754 | 75086381.88 | 675943.91 | 717246.14 | 87.18% | 12.82% | 0.001046%
Civil Group Operations | 14148007 | REG I-Shannon Civil | 2014-09-01 | 2016-01-31 | 0 | 668895 | 611106 | 8553587.261 | 7437448.95 | 37402 | 23568.5 | 83.25% | 16.75% | 0%
Denver Operations | 14060025 | CU-Folsom Parking Garage | 2014-10-01 | 2016-01-29 | 210000 | 1344065 | 793825 | 21449173 | 21236483.74 | 56250.24 | 53613 | 81.43% | 18.55% | 0.01492%
Minneapolis Operations | 14030048 | MOA - North Garden Renovation | 2015-01-01 | 2016-01-15 | 111835 | 81384.0041 | 0 | 13950491.26 | 13502534.68 | 14821 | 14004.5 | 80.53% | 19.38% | 0.08569%
Denver Operations | 14060024 | Woodward-Headquarters | 2014-11-06 | 2016-01-14 | 60000 | 6692232 | 120003 | 20346127.95 | 19023429.7 | 11339 | 26567 | 91.55% | 8.447% | 0%
Civil Group Operations | 14148001 | Sanford Medical (Mpls) - Civil | 2014-03-10 | 2015-12-31 | 0 | 1132671 | 1132034 | 11024511.04 | 11142179.68 | 31740 | 48241.5 | 71.46% | 27.92% | 0.6193%
Civil Group Operations | 14148006 | Solar-Alamo V Civil | 2014-09-01 | 2015-12-31 | 0 | 161069 | 160952 | 2975017.83 | 2874952.79 | 10299.5 | 7306.5 | 82.77% | 17.23% | 0%
Denver Operations | 14060018 | Dominion Water-Sanitation | 2014-11-30 | 2015-12-31 | 0 | 22 | 0 | 0 | 0
Milwaukee Operations | 14080018 | AHC-Aurora Summit Data Center | 2015-06-11 | 2015-12-31 | 17915 | 269537 | 104649 | 9397426.151 | 8523966.49 | 7012 | 5429 | 94.57% | 4.9% | 0.5342%
Power Delivery Solutions Operations | 14146003 | MCC-Clarington HVT | 2014-05-01 | 2015-12-31 | 0 | 0 | 0 | 9640 | 9640.66
Power Delivery Solutions Operations | 14146003-110 | REG Canada-Clarington HVT | 2014-05-01 | 2015-12-31 | 0 | 8 | 0 | 77355 | 67162.17
Power Delivery Solutions Operations | 14146004 | MCC-Majestic & Meyer HVT | 2014-06-01 | 2015-12-31 | 0 | 0 | 0 | 5640 | 5640.43
Power Delivery Solutions Operations | 14146004-110 | REG Canada-Majestic HVT | 2014-06-01 | 2015-12-31 | 0 | 8 | 0 | 70861 | 53003.72
Power Delivery Solutions Operations | 14146005 | MCC-Trout Creek HVT | 2014-06-01 | 2015-12-31 | 0 | 0 | 0 | 3902 | 3902.11
Power Delivery Solutions Operations | 14146005-110 | REG Canada-Trout Creek HVT | 2014-06-01 | 2015-12-31 | 0 | 8 | 0 | 68161 | 48524.49
Seattle Operations | 14050002 | Providence-Small Projects | 2014-04-03 | 2015-12-31 | 1347 | 47115.8 | 0 | 5116514.51 | 4985761.65 | 6302 | 8267.34 | 90.8% | 8.667% | 0.5322%
Seattle Operations | 14050010 | UWT Tioga & MDS Bldg Renovatio | 2015-08-30 | 2015-12-31 | 55000 | 11 | 0 | 163699.16 | 156102.99
Wind Energy I Operations | 14140010 | Relight-Meridien Wind | 2015-03-15 | 2015-12-31 | 0 | 2 | 0 | 12154 | 34586.45
Wind Energy I Operations | 14140012 | GE Power & Water-GE Wind | 2014-10-08 | 2015-12-31 | 0 | 801 | 193 | 3381492 | 2946513.76 | 163935 | 40054.5 | 82.39% | 17.56% | 0.04993%
Milwaukee Operations | 14080001 | MDI - Hotel Commonwealth Exp. | 2014-07-21 | 2015-12-15 | 152082 | 2 | 0 | 49608546.81 | 50156415.61 | 0 | 4069.84 | 92.81% | 7.089% | 0.09828%
Wind Energy I Operations | 14140016 | Sunwind Energy - Doyle Wind | 2015-04-01 | 2015-12-01 | 0 | 0 | 0 | 20660 | 22919.08
Minneapolis Operations | 14030042 | North Pad Office - MOA Office | 2014-10-30 | 2015-11-30 | 181831 | 6 | 584567 | 24240248.84 | 23787912.72 | 21540 | 22114.14 | 81.13% | 18.43% | 0.4432%
Wind Energy I Operations | 14147004-110 | Grand Valley LTD-Grand Valley | 2014-06-27 | 2015-11-30 | 0 | 0 | 0 | 13766 | 1206.97
Minneapolis Operations | 14030018 | Agribank FCB - Tenant Improve | 2014-03-17 | 2015-11-20 | 7400 | 16993 | 0 | 878562.8116 | 719504.38 | 1969 | 1590.5 | 92.8% | 7.199% | 0%
Sports + Entertainment Group Operations | 14150008 | PSU-Lasch Bldg-Phase I | 2015-03-01 | 2015-11-12 | 6300 | 0 | 0 | 2419307.7 | 2360474
Denver Operations | 14060001 | Charles Schwab-Denver Campus | 2014-01-09 | 2015-11-05 | 670685 | 1830920.82 | 687059 | 78381470.81 | 75609518.15 | 110742.67 | 111081.99 | 86.21% | 13.79% | 0%
Wind Energy I Operations | 14140007 | South Plains Wind | 2015-04-01 | 2015-11-01 | 0 | 10971 | 7895 | 55185356.37 | 54058585.87 | 105339 | 102009.25 | 75.33% | 24.67% | 0%
Chicago Operations | 14090016 | Advocate GS Firemain Repl. | 2014-09-15 | 2015-10-31 | 0 | 0 | 0 | 402894 | 403086.33
Wind Energy I Operations | 14140013 | NJR-Alexander Wind | 2015-06-01 | 2015-10-31 | 0 | 1613 | 1231 | 17636914 | 17750774.43 | 23835 | 25296 | 63.65% | 28.36% | 7.989%
Denver Operations | 14060014 | Mortenson-Denv Office Remodel | 2015-02-16 | 2015-10-09 | 25052 | 391.03 | 0 | 3270199.08 | 32386.8 | 1866 | 1084 | 95.94% | 4.059% | 0%
Discontinued Groups | 14120003 | Hayward Data Center LBA Realty | 2014-11-05 | 2015-10-09 | 147000 | 3 | 0 | 17755226.3 | 16667306.01
Sports + Entertainment Group Operations | 14150007 | Tampa Bay Lightning - Amalie | 2015-06-15 | 2015-10-08 | 73495 | 1573 | 0 | 17478044.2744 | 17520071.53 | 0 | 4328.5 | 67.17% | 26.44% | 6.388%
Phoenix Operations | 14040011 | DFS-Carpet Replacement | 2014-11-01 | 2015-10-01 | 0 | 0 | 0 | 1049055.79 | 1047980.81
Sports + Entertainment Group Operations | 14150002 | Mort/GE J - Stadium N End Zone | 2014-12-01 | 2015-09-30 | 0 | 0 | 0 | 3487890 | 3551673.49 | 0 | 8979.55 | 78.15% | 21.4% | 0.4455%
Sports + Entertainment Group Operations | 14150002-155 | KSU - North End Zone | 2014-05-01 | 2015-09-30 | 0 | 22459 | 0 | 55897335.68 | 53142179.97 | 26240 | 10628.11 | 77.74% | 22.26% | 0%
Wind Energy I Operations | 14147003 | MCC-Trout Creek Wind PSC | 2014-01-14 | 2015-09-30 | 0 | 0 | 0 | 28321 | 28321.07
Wind Energy I Operations | 14147003-110 | Leader Resources-Trout Creek | 2014-01-14 | 2015-09-30 | 0 | 1 | 0 | 175743 | 164168.72
Data Center Operations | 14120002 | PTC UPS Rplcmt & Elec Upgr | 2014-09-15 | 2015-09-25 | 0 | 32931 | 0 | 15098948.29 | 14213825.27 | 7292.07 | 6037.49 | 97.83% | 2.17% | 0%
Minneapolis Operations | 14030029 | BCBS -DC Stabilization Phase 2 | 2014-06-09 | 2015-09-11 | 6300 | 1494 | 0 | 3518068.54 | 3391267.86 | 2680 | 2649.8 | 94.4% | 4.963% | 0.6416%
Power Delivery Solutions Operations | 14146007 | Solar-Alamo V HVT | 2015-02-14 | 2015-08-21 | 0 | 205392 | 33987 | 3019372.55 | 2712718.8 | 7946 | 5174.5 | 87.18% | 12.82% | 0%
Minneapolis Operations | 14030052 | MCTC - Workforce Prog Renovat | 2015-05-11 | 2015-08-14 | 0 | 37587 | 32898 | 2687423.72 | 2433258.61 | 6251 | 4868.18 | 97.68% | 1.982% | 0.3389%
Minneapolis Operations | 14030051 | U of MN - Centennial Hall HVAC | 2015-01-15 | 2015-08-14 | 235525 | 236268 | 0 | 9557549.57 | 9602781.27 | 13923 | 10727.45 | 88.02% | 11.98% | 0%
Denver Operations | 14060004 | CU-Boulder Athletics Complex | 2014-05-01 | 2015-08-01 | 0 | 4590269.82 | 902045 | 145444737.15 | 161385313.74 | 216768.74 | 393937.25 | 81.21% | 18.79% | 0%
Power Delivery Solutions Operations | 14146002-110 | REG Canada-St. Columban HVT | 2014-01-10 | 2015-07-31 | 0 | 212097 | 0 | 15797292 | 16487613.56
Wind Energy I Operations | 14140001 | Balko Wind LLC- Balko Wind | 2014-10-01 | 2015-07-31 | 0 | 11034.85 | 8501 | 45992204.8588 | 45040394.78 | 103787 | 114018 | 82.39% | 17.61% | 0%
Wind Energy I Operations | 14140005 | EDF-Pilot Hill Wind | 2014-07-01 | 2015-07-03 | 0 | 7887 | 5128 | 77129390.78 | 87618710.89 | 83836 | 115109.98 | 65.52% | 21.85% | 12.63%
Civil Group Operations | 14148003 | REG I-Balko Civil | 2014-08-15 | 2015-07-01 | 0 | 1254760 | 961981 | 9339893.4449 | 7404607.2 | 43088.35 | 39067.5 | 77.02% | 22.98% | 0%
Milwaukee Operations | 14080014 | Froedtert-1st Floor Pharmacy | 2015-01-19 | 2015-07-01 | 1000 | 32949 | 0 | 1252211 | 1235910.12 | 1967 | 1686 | 93.77% | 5.931% | 0.2966%
Milwaukee Operations | 14080015 | Froedtert-3rd Cath Lab 1&2 Ren | 2015-01-19 | 2015-07-01 | 1000 | 6045 | 0 | 237759 | 239268.34 | 503 | 338.5 | 70.75% | 29.25% | 0%
Mortenson Direct Operations | 14080014-064 | Froedtert-Direct 1st Flr Phrmc | 2015-01-19 | 2015-07-01 | 0 | 0 | 0 | 87016.35 | 87016.35
Mortenson Direct Operations | 14080015-064 | Froedtert-Direct 3rd Cath Lab | 2015-01-19 | 2015-07-01 | 1000 | 0 | 0 | 7236 | 7236
Chicago Operations | 14090005 | Lakefront Athletic Complex | 2013-10-01 | 2015-06-30 | 553000 | 0 | 0 | 278453 | 256549.54
Denver Operations | 14060016 | Park Creek-Filing 44 | 2014-07-28 | 2015-06-30 | 0 | 545 | 0 | 55059 | 56021.94 | 175 | 187.5 | 98.93% | 1.067% | 0%
Minneapolis Operations | 14030043 | Allina Health-2014 Annual Cont | 2014-01-01 | 2015-06-30 | 0 | 0 | 0 | 0.01 | 29257404.55 | 0 | 127551.54 | 88.76% | 10.09% | 1.151%
Solar and Emerging Renewables Operations | 14145006 | Sunpower-Quinto Solar | 2014-07-25 | 2015-06-09 | 135590400 | 544354.12 | 271265 | 21525316.005 | 21328272.18 | 125455.13 | 139011 | 89.87% | 9.696% | 0.4356%
Civil Group Operations | 14148010 | REG I-Macksburg Civil Add'l 3 | 2014-10-01 | 2015-06-01 | 0 | 12 | 12 | 760158.27 | 801039.3 | 721 | 1703 | 68.09% | 30.5% | 1.409%
Milwaukee Operations | 14080013 | S.C.Johnson-Courtyrd Restoratn | 2014-09-02 | 2015-06-01 | 41358 | 73073.0875 | 0 | 1632135.6375 | 1609306.05 | 2458 | 3551.5 | 88.69% | 11.08% | 0.2253%
Wind Energy I Operations | 14140014 | MidAmerican-Macksburg Add'l 3 | 2013-10-21 | 2015-06-01 | 0 | 211969 | 0 | 4097047.19 | 3592241.34 | 0 | 4109.5 | 63.2% | 26.04% | 10.77%
Seattle Operations | 14050003 | Yahoo GQ Pond and Lift Station | 2014-07-10 | 2015-05-31 | 2100 | 561.47 | 0 | 3720998.4396 | 3711947.44 | 1330.47 | 1328.04 | 100% | 0% | 0%
Minneapolis Operations | 14030016 | Mayo Clinic Square-Base Build | 2014-03-07 | 2015-05-29 | 146519 | 341111.9 | 253478 | 22250346.23 | 21966534.48 | 39423.5 | 39313.07 | 96.44% | 3.332% | 0.2264%
Minneapolis Operations | 14030036 | Allina -ANW East Tower Upgrade | 2014-11-19 | 2015-05-15 | 17215 | 18123 | 0 | 3559698.84 | 3597117.94 | 10041 | 10794.6 | 92.84% | 6.624% | 0.5373%
Minneapolis Operations | 14030049 | Park Nicollet - Methodist Hosp | 2015-04-01 | 2015-05-08 | 55000 | 0 | 0 | 90701 | 92464.66 | 0 | 24 | 100% | 0% | 0%
Mortenson Direct Operations | 14080019-064 | Froedtert-Direct 1st Fl WC EVS | 2015-01-15 | 2015-05-08 | 1000 | 0 | 0 | 13088 | 13088
Solar and Emerging Renewables Operations | 14145014 | SunPower-Hooper Solar | 2014-12-01 | 2015-04-30 | 58046400 | 148469.1361 | 100956 | 2678804.9691 | 2120392.34 | 13718.8 | 10643.5 | 86.24% | 13.76% | 0%
Minneapolis Operations | 14030055 | Twins Ballpark - 2015 Improve | 2014-12-15 | 2015-04-10 | 4500 | 31581 | 0 | 1739078 | 1701226.8 | 3022 | 4091.5 | 92.66% | 7.344% | 0%
Milwaukee Operations | 14080019 | Froedtert-1st Flr. W.C. EVS Rm | 2015-01-15 | 2015-04-01 | 1000 | 8965 | 0 | 196288 | 189644.4 | 638 | 559 | 92.58% | 7.424% | 0%
Chicago Operations | 14090004 | Residential/Life Safety | 2014-05-12 | 2015-03-31 | 0 | 144262.34 | 24978 | 5190573.37 | 4377438.56 | 10325.5 | 8431.86 | 98.91% | 0.9666% | 0.1186%
Chicago Operations | 14090006 | Hudson ATS Replacement | 2014-03-01 | 2015-03-31 | 20000 | 16 | 0 | 989973 | 905451.25
Denver Operations | 14060026 | Leprino-Food Hangar | 2014-10-06 | 2015-03-31 | 34525 | 408443 | 18746 | 4509248.35 | 4519427.74 | 11009.1 | 12807 | 82.84% | 17.16% | 0%
Milwaukee Operations | 14080006 | AHC-St. Luke's IR BiPlane Rm 1 | 2015-01-05 | 2015-03-27 | 862 | 2079.27 | 0 | 632186.27 | 582744.18 | 764 | 775 | 89.1% | 10.9% | 0%
Minneapolis Operations | 14030039 | TRIA ASC Renovation | 2014-09-10 | 2015-03-15 | 8400 | 1154.34 | 0 | 1739058.14 | 1674264.72 | 2163 | 2097 | 92.89% | 5.961% | 1.144%
Civil Group Operations | 14148009 | REG I-Route 66 Civil | 2014-08-15 | 2015-02-28 | 0 | 834292 | 710523 | 5355935.9152 | 4689174.19 | 25177.3 | 25582.5 | 79.11% | 20.89% | 0%
Minneapolis Operations | 14030022 | U of MN - Dwan Imaging Center | 2014-06-16 | 2015-02-28 | 7000 | 8722.36 | 0 | 2213713.79 | 2264764.52 | 2426 | 3195.5 | 99.77% | 0.2347% | 0%
Solar and Emerging Renewables Operations | 14145011 | Fulton Mill Solar Farm, LLC-Fu | 2014-10-27 | 2015-02-28 | 2996460 | 9862 | 0 | 4758195 | 4817923.41
Seattle Operations | 14050007 | Apple Inc-Castle Rock | 2014-06-06 | 2015-02-26 | 129200 | 20 | 0 | 56855870.24 | 56184031.96 | 0 | 527.5 | 72.04% | 27.39% | 0.5687%
Solar and Emerging Renewables Operations | 14145001 | OCI-Alamo Solar III | 2014-01-27 | 2015-02-07 | 6747300 | 830161.26 | 1029926 | 6349063 | 6459588.96 | 42955 | 53357.25 | 92.09% | 7.899% | 0.01499%
Minneapolis Operations | 14030050 | UMN - Physics Lab 481 Comp | 2014-12-01 | 2015-02-06 | 1400 | 249 | 0 | 205963 | 196998.28 | 213 | 181.5 | 100% | 0% | 0%
Phoenix Operations | 14040012 | SRP-CUB Roof Replacement | 2014-10-31 | 2015-01-31 | 20000 | 0 | 0 | 169280.32 | 164699.55
Phoenix Operations | 14040013 | SRP-CUB Mechanical Improve. | 2014-11-07 | 2015-01-31 | 20000 | 4 | 0 | 769491.89 | 764710.3 | 32 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 14145010 | Dooley Solar Farm LLC, Dooley | 2014-09-16 | 2015-01-31 | 998820 | 3400 | 0 | 1749371 | 1794380.73
Solar and Emerging Renewables Operations | 14145012 | Plum Solar Farm, LLC-Plum Sola | 2014-10-21 | 2015-01-28 | 1997640 | 6591 | 0 | 3193547 | 3259634.01
Solar and Emerging Renewables Operations | 14145013 | Stillmore Solar Farm, LLC-Stil | 2014-10-21 | 2015-01-27 | 998820 | 3379 | 0 | 1679915 | 1753617.32
Milwaukee Operations | 14080020 | WHEDA - Door Installation | 2014-12-29 | 2015-01-08 | 40 | 0 | 0 | 3490 | 2601.25 | 0 | 21 | 100% | 0% | 0%
Minneapolis Operations | 14030032 | Fridley Land - Northern Stacks | 2014-07-14 | 2015-01-02 | 213000 | 823397 | 311899 | 10825927.23 | 10658924.79 | 13210 | 15752.7 | 88.71% | 11.14% | 0.1524%
Chicago Operations | 14090007 | Blue Sky Professional Services | 2014-03-01 | 2014-12-31 | 0 | 0 | 0 | 19250 | 17536.86
Chicago Operations | 14090008 | Guestroom Renovation PH2 | 2014-03-01 | 2014-12-31 | 0 | 200 | 0 | 73170 | 64614.18 | 0 | 115 | 93.91% | 5.652% | 0.4348%
Chicago Operations | 14090009 | SAIC Interior Renovation | 2013-10-01 | 2014-12-31 | 0 | 18975 | 1880 | 1056665 | 1091220.98 | 492 | 1493.79 | 92.94% | 6.795% | 0.2678%
Chicago Operations | 14090997 | Chicago Equip Facility 2014 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -991469.06
Chicago Operations | 14090999 | Chicago Closed Projects 2014 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -1830.7 | 0 | 166 | 100% | 0% | 0%
Chicago Operations | 14090013 | Advocate Collaboration Space | 2014-07-01 | 2014-12-31 | 5000 | 0 | 0 | 89784 | 74194.55 | 274 | 273.74 | 93.42% | 4.749% | 1.827%
Civil Group Operations | 14148002 | REG I-Windthorst II Civil | 2014-04-01 | 2014-12-31 | 0 | 271542.15 | 176834 | 2119876.443 | 2453695.94 | 11905.5 | 10638.5 | 90.09% | 9.912% | 0%
Civil Group Operations | 14148011 | Solar-Hooper Civil (Close) |  | 2014-12-31 | 0 | 38877 | 32051 | 506191 | 0 | 3190 | 0 | 0% | 0% | 0%
Civil Group Operations | 14148014 | REG I-Mariah Del Norte 2 | 2014-12-19 | 2014-12-31 | 0 | 13 | 4 | 35758 | 37362.85 | 120 | 87.5 | 100% | 0% | 0%
Civil Group Operations | 14148015 | REG I-Mariah South 3 Civil | 2014-12-01 | 2014-12-31 | 0 | 12 | 4 | 38400 | 52068.25 | 120 | 100 | 100% | 0% | 0%
Civil Group Operations | 14148019 | Solar-Hooper Civil |  | 2014-12-31 | 0 | 38881 | 6800 | 517250.74 | 257594.37 | 3222 | 840 | 76.9% | 22.38% | 0.7143%
Civil Group Operations | 14148020 | REG I-Mariah NW Phase 1 Civil | 2014-12-18 | 2014-12-31 | 0 | 13 | 4 | 36480 | 46597.91 | 120 | 165 | 100% | 0% | 0%
Civil Group Operations | 14148997 | Civil-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -509053.82
Civil Group Operations | 14148999 | Civil-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 8471.04
Denver Operations | 14060002 | Sterling Ranch Dev-Consulting | 2014-01-13 | 2014-12-31 | 0 | 0 | 0 | 347024 | 338194.27 | 28 | 21.5 | 65.12% | 34.88% | 0%
FCG Operations | 14110997 | FCG 2014 Equipment Facility | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0 | -30018.99
FCG Operations | 14110999 | FCG 2014 Closed Projects | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0 | -452756.88
Milwaukee Operations | 14080010 | AHC-Data Center Assessmnt (PS) | 2014-04-01 | 2014-12-31 | 0 | 0 | 0 | 63283.64 | 63283.64
Milwaukee Operations | 14080997 | Milwaukee - Equip Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | -433968 | -526112
Milwaukee Operations | 14080999 | Milwaukee Closed Job Costs '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -110108.4 | 0 | 137.5 | 95.27% | 4.727% | 0%
Milwaukee Operations | 14080016 | Guardian IG-New Facility Precn |  | 2014-12-31 | 240000 | 0 | 0 | 38000 | 43416.44
Minneapolis Operations | 14030001 | FUMC-Annual Contract 2014 |  | 2014-12-31 | 0 | 35645.86 | 0 | 1857782.61 | 1841238.89 | 8880 | 10100 | 95.98% | 2.733% | 1.292%
Minneapolis Operations | 14030035 | MOA-West Parking Ramp Repairs | 2014-06-03 | 2014-12-31 | 0 | 63 | 0 | 216725 | 230249.3 | 1877 | 901 | 73.58% | 26.42% | 0%
Minneapolis Operations | 14030997 | 2014 Mpls Equip Facility Recog | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -2279740.5
Minneapolis Operations | 14030999 | MAM - 2014 Closed Projects | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 26496.22 | 0 | 2617 | 93.73% | 6.267% | 0%
Minneapolis Operations | 14030044 | HCMC Generator Addition | 2014-11-03 | 2014-12-31 | 400 | 6279.17 | 0 | 735678.57 | 711527.87 | 1863 | 1795.5 | 98.33% | 1.671% | 0%
Minneapolis Operations | 14030020 | RMC - Nuclear Medicine Equip. | 2014-03-17 | 2014-12-31 | 800 | 370 | 0 | 120471.94 | 121670.3 | 394 | 448 | 96.99% | 3.013% | 0%
Minneapolis Operations | 14030008 | Mortenson HQ Projects | 2014-01-22 | 2014-12-31 | 2400 | 513.65 | 0 | 1954997.4 | 0.42 | 1996 | 2291 | 77.28% | 21.8% | 0.9166%
Minneapolis Operations | 14030015 | Mall of America - West Market | 2014-02-23 | 2014-12-31 | 107215 | 360034.572 | 0 | 10208750 | 9801370.77 | 9756.14 | 9084.5 | 82.11% | 17.89% | 0%
Phoenix Operations | 14040008 | PCH at MGMC Discharge Canopy |  | 2014-12-31 | 0 | 0 | 0 | 0.01 | 0 | 0 | -800 | 100% | 0% | 0%
Phoenix Operations | 14040997 | Phoenix-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 30220.23
Phoenix Operations | 14040999 | Phoenix-Closed Projects 2014 | 2013-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 177.56
Portland Operations | 14050011 | Nike Small Projects | 2014-12-01 | 2014-12-31 | 0 | 1 | 0 | 15630 | 17268.93 | 27 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 14146001 | REG I-Windthorst II HVT | 2014-04-14 | 2014-12-31 | 0 | 1516582 | 221293 | 5451800.3 | 5933595.82 | 7615 | 22211.5 | 78.09% | 21.91% | 0%
Power Delivery Solutions Operations | 14146997 | HVT-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -1027453.41
Power Delivery Solutions Operations | 14146999 | HVT-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 47761.54 | 0 | 88.5 | 93.79% | 6.215% | 0%
Seattle Operations | 14050997 | Seattle Equip Facility 2014 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -2391119.27
Seattle Operations | 14050999 | Seattle 2014 Closed Projects | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -6098.86
Solar and Emerging Renewables Operations | 14145997 | Solar-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -284987.62
Solar and Emerging Renewables Operations | 14145999 | Solar-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 8277.52 | 0 | 1786.74 | 100% | 0% | 0%
Solar and Emerging Renewables Operations | 14145007 | Granby Road Solar LLC-Granby | 2014-08-18 | 2014-12-31 | 1015560 | 202 | 0 | 4147182 | 4285136.62 | 0 | 15.5 | 96.77% | 3.226% | 0%
Wind Energy I Operations | 14140017 | Pattern Panhandle 3-Panhandle | 2014-12-12 | 2014-12-31 | 0 | 18 | 3 | 257671 | 238666.3 | 36 | 19.5 | 0% | 100% | 0%
Wind Energy I Operations | 14140997 | US Wind-Equipment Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | -3142190.97
Wind Energy I Operations | 14140999 | US Wind-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 144852.24
Wind Energy I Operations | 14147001 | MCC-Clarington Wind PSC | 2014-01-14 | 2014-12-31 | 0 | 0 | 0 | 32909 | 32909.43
Wind Energy I Operations | 14147001-110 | Leader Resources-Clarington | 2014-01-14 | 2014-12-31 | 0 | 1 | 0 | 230282 | 231362.03
Wind Energy I Operations | 14147002 | MCC-Majestic & Meyer Wind PSC | 2014-01-14 | 2014-12-31 | 0 | 0 | 0 | 13827 | 13826.74
Wind Energy I Operations | 14147002-110 | Leader Resources-Majestic | 2014-01-14 | 2014-12-31 | 0 | 1 | 0 | 193887 | 187878.49
Wind Energy I Operations | 14147997 | REG Canada-Equip Facility '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 0
Wind Energy I Operations | 14147999 | Wind I Can-Closed Proj '14 US | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0 | -75.45
Wind Energy I Operations | 14147999-110 | REG Canada-Closed Projects '14 | 2014-01-01 | 2014-12-31 | 0 | 0 | 0 | 0.01 | 437098.79
Minneapolis Operations | 14030026 | Fairview Ridges - Master Agree | 2014-04-01 | 2014-12-30 | 0 | 2120.14 | 0 | 480673.23 | 461781.3 | 1079 | 1250.64 | 96% | 3.998% | 0%
Minneapolis Operations | 14030038 | Hudson MRI Replacement | 2014-08-04 | 2014-12-26 | 512 | 228.2 | 0 | 173186.2 | 158497.6 | 290 | 311 | 96.95% | 3.055% | 0%
Solar and Emerging Renewables Operations | 14145008 | Twiss Street Solar, LLC-Twiss | 2014-08-18 | 2014-12-15 | 1953000 | 202 | 0 | 4072941 | 4272243.45 | 0 | 245.5 | 80.04% | 19.55% | 0.4073%
Civil Group Operations | 14148004 | FCG-Galena Park Civil |  | 2014-12-10 | 0 | 2102 | 9 | 436057 | 313232.02 | 1716 | 836 | 76.5% | 23.5% | 0%
Wind Energy I Operations | 14140008 | Sherbino Mesa II-Sherbino Foun | 2014-07-07 | 2014-11-30 | 0 | 1545 | 1112 | 768439 | 617102.78 | 2058 | 1591 | 84.99% | 15.01% | 0%
Phoenix Operations | 14040007 | SRP Board Conference Room | 2014-10-06 | 2014-11-26 | 431000 | 7171.54 | 0 | 428606.4 | 423236.57 | 0 | 0 | 0% | 0% | 0%
Power Delivery Solutions Operations | 14146002 | MCC-St. Columban HVT | 2014-01-10 | 2014-11-10 | 0 | 0 | 0 | 765552 | 765552.68
Wind Energy I Operations | 14140003 | Broadview Energy KW-Broadview | 2014-11-01 | 2014-11-01 | 0 | 0 | 0 | 15250 | 15233.02
Denver Operations | 14060021 | City of Boulder-Airport | 2014-08-04 | 2014-10-31 | 0 | 1780 | 0 | 1132451.03 | 1020246.82 | 1138 | 821.5 | 75.35% | 24.65% | 0%
Minneapolis Operations | 14030013 | Mayo Sports Clinic | 2014-04-07 | 2014-10-31 | 20000 | -823.43 | 4188 | 2995389 | 2931318.74 | 6411 | 5822.33 | 89.82% | 10.18% | 0%
Solar and Emerging Renewables Operations | 14145017 | SunPower-Antelope Valley 2 | 2013-02-08 | 2014-10-31 | 0 | 69475.7021 | 22994 | 1264203.0109 | 1021839.76 | 17916.8 | 19876.25 | 89.54% | 8.599% | 1.864%
Wind Energy I Operations | 14140006 | Trinity Hills Wind LLC-Trinity | 2014-07-07 | 2014-10-31 | 0 | 5839 | 3641 | 1804555.81 | 1949760.74 | 6438 | 7660 | 80.91% | 19.09% | 0%
Phoenix Operations | 14040010 | AlaskaUSA-Branch Bank TI | 2014-10-01 | 2014-10-25 | 910 | 112 | 0 | 151229 | 141892.97
Minneapolis Operations | 14030040 | Ridgeview Med Ctr-Hospice Rep. | 2014-09-08 | 2014-10-20 | 0 | 4 | 0 | 121226 | 120937.28 | 336 | 312 | 87.82% | 12.18% | 0%
Sports + Entertainment Group Operations | 14150001 | Rushmore Plaza Civic Center | 2014-02-01 | 2014-10-20 | 0 | 0 | 0 | 78690 | 70688.08
Minneapolis Operations | 14030021 | U of MN - Williams Arena Roof | 2014-06-05 | 2014-10-16 | 134388 | 6055.15 | 0 | 6325678.76 | 6318759.26 | 4155 | 3873.46 | 83.5% | 16.5% | 0%
Data Center Operations | 14120001 | Eden Prairie Data Ctr Ph 3 & | 2014-01-14 | 2014-10-01 | 18885 | 28475.82 | 0 | 1868784 | 1795772.14 | 4035 | 3696.5 | 98.5% | 1.501% | 0%
Denver Operations | 14060003 | UCCS-Stanton Round About | 2014-04-28 | 2014-10-01 | 0 | 49517 | 9525 | 905308 | 1136603.92 | 3384 | 7499 | 79.58% | 20.42% | 0%
Chicago Operations | 14090012 | United Customer Service Center | 2014-07-15 | 2014-09-30 | 3000 | 216 | 0 | 1167544.43 | 1157540.43 | 867 | 1087.35 | 94.16% | 5.38% | 0.4598%
Milwaukee Operations | 14080002 | ATC-Project Badger:Phase 0 | 2014-03-15 | 2014-09-30 | 500 | 36659 | 25832 | 4672991.71 | 4862204.23 | 3239 | 3454 | 93.82% | 6.181% | 0%
Minneapolis Operations | 14030031 | CHC - Woodbury Clinic TI | 2014-05-22 | 2014-09-17 | 17661 | 39799.33 | 0 | 783344.25 | 795923.74 | 2784 | 2475 | 93.27% | 6.727% | 0%
Solar and Emerging Renewables Operations | 14145005 | SunPower-Castaic Lake Solar | 2014-06-23 | 2014-09-15 | 4384800 | 85253.4702 | 80256 | 2472661.0002 | 2587785.18 | 12378 | 8117 | 99.66% | 0.3388% | 0%
Phoenix Operations | 14040006 | PCH-East Valley Lab Remodel | 2014-08-25 | 2014-09-09 | 0 | 949 | 0 | 54117 | 51415.47
Chicago Operations | 14090002 | Allstate Jacksonvl Restack 3 | 2013-10-01 | 2014-08-31 | 25000 | 10 | 0 | 3529426 | 3540577.01 | 1440 | 2259 | 73.75% | 26.25% | 0%
Phoenix Operations | 14040002 | PCH-Mercy Gilbert Med Ctr | 2014-06-22 | 2014-08-31 | 809 | 4612.6 | 0 | 355140.92 | 352906.35 | 0 | 832 | 100% | 0% | 0%
Milwaukee Operations | 14080009 | Historic Courteen Seed - Vault | 2014-07-02 | 2014-08-29 | 105 | 1 | 0 | 54813 | 47591.47 | 0 | 239 | 93.93% | 6.067% | 0%
Wind Energy I Operations | 14140009 | General Electric-Schenectady | 2014-07-21 | 2014-08-25 | 0 | 98 | 78 | 581473.74 | 516170.51 | 2552 | 2789.5 | 72.88% | 27.12% | 0%
Minneapolis Operations | 14030010 | Fairview Ridges-Ambulatory Sur | 2014-03-31 | 2014-08-15 | 14250 | 7999 | 0 | 3339471.29 | 3274408.71 | 3129 | 2698.36 | 95.11% | 4.892% | 0%
Phoenix Operations | 14040003 | PCH-Signage Improvements | 2015-01-12 | 2014-08-15 | 0 | -300.44 | 0 | 38859.56 | 37180.73
Minneapolis Operations | 14030007 | U of MN - Akerman Hall Impr | 2014-02-03 | 2014-07-31 | 120000 | 1082.33 | 0 | 1114412 | 1067357.14 | 1799 | 1807 | 98.67% | 1.328% | 0%
Wind Energy I Operations | 14140011 | PPM Technical-Penescal Blade | 2014-07-22 | 2014-07-26 | 0 | 2 | 1 | 26756 | 23738.63 | 16 | 30 | 0% | 100% | 0%
Minneapolis Operations | 14030014 | Cornell College-Residence Hall | 2014-05-14 | 2014-07-22 | 80561 | 51 | 0 | 4770945.14 | 4752109.78 | 2438 | 3507.6 | 95.62% | 4.376% | 0%
Minneapolis Operations | 14030017 | AT&T - DAS Head-End Room - TCF | 2014-03-17 | 2014-06-30 | 850 | 2066 | 0 | 909466 | 865637.05 | 361 | 217 | 88.94% | 11.06% | 0%
Solar and Emerging Renewables Operations | 14145003 | SunPower-China Secondment | 2014-04-10 | 2014-06-30 | 0 | 207 | 0 | 60278.66 | 33495.09 | 88 | 440 | 65.45% | 20.68% | 13.86%
Denver Operations | 14060008 | Town of Lyons-Meadow Park | 2014-04-21 | 2014-06-17 | 0 | 12578 | 0 | 671013.28 | 742881.68 | 8 | 1433 | 80.46% | 19.54% | 0%
Milwaukee Operations | 14080005 | Levy R&H LP-Chrome Tent @H-D | 2014-04-23 | 2014-05-30 | 15000 | 2305.09 | 0 | 93221 | 78662.22 | 250 | 195.5 | 90.79% | 9.207% | 0%
Minneapolis Operations | 14030005 | U of MN - Hasselmo Hall | 2014-01-13 | 2014-05-30 | 5150 | 1153.05 | 0 | 543068 | 530849.89 | 752 | 864.56 | 99.07% | 0.9253% | 0%
Denver Operations | 14060007 | Shawmut-MLBAM Instant Replay | 2014-04-11 | 2014-05-23 | 308 | 32 | 0 | 228824 | 204396.38 | 16 | 666 | 87.46% | 12.54% | 0%
Minneapolis Operations | 14030012 | U of MN - Hasselmo - Robotics | 2014-03-03 | 2014-05-23 | 4300 | 5828.45 | 0 | 507966 | 505986.91 | 845 | 881.8 | 99.77% | 0.2268% | 0%
Wind Energy I Operations | 14140002 | Milw-Acuity Flagpole Erection | 2014-04-24 | 2014-05-20 | 0 | 1 | 0 | 353171 | 482478.35 | 0 | 105.5 | 54.5% | 25.59% | 19.91%
Denver Operations | 14060012 | Town of Lyons-NRCS | 2014-04-28 | 2014-05-14 | 0 | 0 | 0 | 61440 | 65206.44 | 0 | 84.5 | 73.37% | 26.63% | 0%
Minneapolis Operations | 14030019 | Fairview Ridges - NICU Refresh | 2014-03-13 | 2014-05-13 | 4000 | 120.63 | 0 | 194879.38 | 191242.14 | 275 | 468.5 | 99.79% | 0.2134% | 0%
Minneapolis Operations | 14030027 | Silliker Lab Remodel | 2014-02-27 | 2014-05-01 | 4900 | 190.29 | 0 | 128647 | 104556.5 | 424 | 123 | 100% | 0% | 0%
Wind Energy I Operations | 14140004 | Iberdrola Renewables-Locust | 2014-04-17 | 2014-04-28 | 0 | 7 | 0 | 447930 | 396159.61 | 300 | 508.5 | 75.02% | 24.98% | 0%
Minneapolis Operations | 14030004 | RMC TTMC 1st Fl Clinic 3rd Fl | 2014-01-06 | 2014-04-01 | 16338 | 5098.2 | 0 | 863056.44 | 864560.95 | 1867 | 1394.5 | 97.71% | 2.295% | 0%
Phoenix Operations | 14040001 | Banner-Telemetry Monitoring | 2014-03-31 | 2014-03-25 | 350 | 0 | 0 | 38088 | 30180.97
Solar and Emerging Renewables Operations | 14145002 | SunPower-Churchill Reno Solar | 2014-02-05 | 2014-03-05 | 0 | 160.58 | 0 | 187808.99 | 187967.2 | 802 | 872.5 | 86.88% | 13.12% | 0%
Minneapolis Operations | 14030006 | UMPhysicians Park Plaza 4th | 2014-01-24 | 2014-01-29 | 1000 | -9.64 | 0 | 22247 | 20860.42 | 98.5 | 99.5 | 72.36% | 19.1% | 8.543%
Minneapolis Operations | 14030003 | U of MN-Physicians Lower Lev | 2014-01-02 | 2014-01-24 | 3200 | 249.06 | 0 | 39182 | 39440.93 | 129.5 | 133.01 | 100% | 0% | 0%
Denver Operations | 14060997 | Denver-EF-2014 | 2013-01-01 | 2013-12-31 | 0 | 0 | 0 | 0.01 | -2899870.78
Denver Operations | 14060999 | Denver-Closed Projects 2014 | 2012-01-01 | 2012-12-31 | 0 | 0 | 0 | 0.01 | 110900.99 | 0 | 103.5 | 88.89% | 11.11% | 0%
Civil Group Operations | 14148005 | Solar-Alamo III Civil | 2014-07-11 |  | 0 | 288416 | 158983 | 377520 | 291749.71 | 1977 | 1421 | 84.41% | 15.59% | 0%
Civil Group Operations | 14148008 | Solar-Quinto Civil |  |  | 0 | 0 | 0 | 6662612 | 6664410.7
Civil Group Operations | 14148012 | REG I-Panhandle 3 Civil | 2014-12-13 |  | 0 | 32488 | 18341 | 186000 | 111097.99 | 650 | 313.5 | 54.7% | 45.3% | 0%
Civil Group Operations | 14148013 | REG I-Panhandle 4 Civil | 2014-12-15 |  | 0 | 32490 | 17422 | 135232 | 87030.27 | 580 | 277 | 61.73% | 38.27% | 0%
Civil Group Operations | 14148017 | REG I-Route 66 II Civil | 2014-12-17 |  | 0 | 13 | 5 | 41760 | 22075.26 | 500 | 186.5 | 68.9% | 31.1% | 0%
Civil Group Operations | 14148018 | REG I-Castro County Civil | 2014-12-17 |  | 0 | 14 | 8 | 31520 | 23298.4 | 200 | 70 | 7.143% | 92.86% | 0%
Discontinued Groups | 14400999 | Discontinued-14 Closed |  |  | 0 | 0 | 0 | 0 | 2417990.83 | 0 | 20 | 40% | 60% | 0%
Minneapolis Operations | 14030024 | Timberwolves/MCS - GC's | 2014-03-07 |  | 0 | 0 | 0 | 0.01 | -0.07 | 0 | 8530 | 89.7% | 10.19% | 0.1172%
Minneapolis Operations | 14030025 | Abbott Hospital-Facilites Supp | 2014-04-03 |  | 0 | 0 | 0 | 70802 | 73591.79
Minneapolis Operations | 14030034 | MOAC LLC - Small Projects 2014 | 2014-05-19 |  | 0 | 0 | 0 | 75720 | 74361.46 | 0 | 378.5 | 90.22% | 9.775% | 0%
Minneapolis Operations | 14030011 | Betacom - AT&T Head End Room | 2014-02-25 |  | 700 | 16 | 0 | 573522 | 390754.9 | 962 | 666 | 91.74% | 8.258% | 0%
Minneapolis Operations | 14030041 | TC United Way - Restroom Rem | 2014-10-13 |  | 958 | 9 | 0 | 336744.39 | 353638 | 1212 | 1127.5 | 94.46% | 5.543% | 0%
Minneapolis Operations | 14030037 | MOA - SE Court Slab Infill | 2014-07-13 |  | 5000 | 20888.61 | 0 | 1251482.38 | 1181878.33 | 1115 | 737 | 79.78% | 20.22% | 0%
Minneapolis Operations | 14030028 | Allina Health - West Health | 2014-03-10 |  | 10000 | 34 | 0 | 962410 | 985866.6 | 2542 | 2682.09 | 88.29% | 11.71% | 0%
Minneapolis Operations | 14030030 | Kilbourne Group - Block 9 | 2014-03-01 |  | 445682 | 0 | 0 | 11574 | 17679.67
Minneapolis Operations | 14030053 | Fridley Land-North. Stacks BAE | 2015-01-26 |  | 479000 | 143339 | 36627 | 12737225.38 | 12104260.5 | 6988 | 12616.18 | 95.78% | 4.134% | 0.08719%
Phoenix Operations | 14040004 | Concourse-UofA Boingo Phase II |  |  | 0 | 0 | 0 | 0.01 | 0
Solar and Emerging Renewables Operations | 14145016 | Northwirth-Mortenson HQ RooftC |  |  | 0 | 1713 | 0 | 111158 | 0 | 246 | 0 | 0% | 0% | 0%
Solar and Emerging Renewables Operations | 14145018 | Northwirth-Mortenson HQ Roofto |  |  | 0 | 0 | 0 | 111158 | 0
Solar and Emerging Renewables Operations | 14145009 | Chicopee River Solar, LLC-Chic |  |  | 2611080 | 202 | 0 | 5358475 | 5429033.24 | 0 | 113.5 | 81.94% | 15.86% | 2.203%
Sports + Entertainment Group Operations | 14150005 | Boingo Wireless - KSU DAS | 2014-07-07 |  | 7500 | 0 | 0 | 0.01 | 78965.21
Sports + Entertainment Group Operations | 14150004 | American Builders - Atl Braves | 2014-09-16 |  | 1100000 | 3 | 0 | 11667010.01 | 12940093.92 | 0 | 4261 | 76.41% | 21.3% | 2.288%
Sports + Entertainment Group Operations | 14150004-141 | Cobb County - Atlanta Braves | 2014-09-16 |  | 1100000 | 0 | 0 | 600600984 | 0
Wind Energy I Operations | 14140018 | Pattern Panhandle 4-Panhandle | 2014-12-12 |  | 0 | 16 | 3 | 190162 | 185795.55 | 36 | 10 | 0% | 100% | 0%
Wind Energy I Operations | 14140019 | Orion Wind Resources-Castro | 2015-04-01 |  | 0 | 0 | 0 | 54300 | 53860.33
Wind Energy I Operations | 14140021 | Mariah South LLC-Mariah South | 2014-12-18 |  | 0 | 0 | 0 | 63100 | 62400.79
Wind Energy I Operations | 14140022 | Mariah North West LLC-Mariah 1 | 2014-12-18 |  | 0 | 0 | 0 | 63250 | 60274.16
Wind Energy I Operations | 14140023 | Route 66 Wind II-Route 66 Wind | 2014-12-17 |  | 0 | 0 | 0 | 58628 | 58848.42
Total | [5 empty] | 105884059.5885 | 48601511 | 3832252869.3237 | 3274985371.91 | 3900382.6 | 4345689.12 | 83.32% | 15.27% | 1.406%